## CHANGE REQUEST COVER SHEET

## Change Request Number: 06-13

## Date Received: 1/23/06 Revised: 06/6/06

Title: AMS  Test and Evaluation Guidelines

# Name: Mike Virga/T & E Gold Standard Working Group

Routing Symbol:  ATO-W/AJW-1110

Phone: 609-485-8877

Policy OR Guidance: Guidance

Section/Text Location Affected: Each In-Service Management Section and Diagram

Summary of Change: Current Test & Evaluation (T&E) Process Guidelines based on the current Test and Evaluation Gold Standard (TEGS), Version 2.0.

Reason for Change: To provide AMS T&E Process Guidelines consistent the latest TEGS Version 2.0.  Version 2.0 of the TEGS was published in October 2004.  It was updated to include information for Safety Risk Management and National Key Site.  The TEGS language in related AMS documents is also updated for consistency.

Target Audience: Users of FAST and AMS Documentation.

Potential Links within FAST for the Change: T&E Policy and Guidance

#### Attachments: Language of Change

### Development, Review, and/or Concurrence: (1) Technical Operations, Safety & Operations Support Office; (2) Safety, Independent Operational Test & Evaluation Office; (3) Integrated Engineering Services, Air Traffic Management Automation; (4) Integrated Engineering Services, Communication & Navigation Division.

### ASAG Briefing Conducted:	4/4/06 and 6/6/06

ASAG Decision: Endorsed

Acquisition Management System

Test and Evaluation Process

Guidelines

June 2006

Table of Contents

1.0	Purpose	1

2.0	Test and Evaluation Guiding Principles	1

3.0	Test and Evaluation During the Acquisition Management Phases – Overview	2

3.1	Investment Analysis Test and Evaluation	6

3.1.1	Initial Investment Analysis	6

3.1.2	Final Investment Analysis	6

3.2	SI and ISM Test and Evaluation	7

3.2.1	Needs and Requirements	9

3.2.1.1	SI Needs and Requirements	9

3.2.1.2	ISM Needs and Requirements (TEGS Phase 1: “Define It”)	10

3.2.2	Design and Development	11

3.2.2.1	SI Design and Development	12

3.2.2.2	ISM Design and Development (TEGS Phase 2: “Design It”)	12

3.2.3	Development Test	13

3.2.3.1	SI Development Test	14

3.2.3.2	ISM Development Test (TEGS Phase 3: “Build It”)	14

3.2.4	SI Operational Test and ISM System Test	14

3.2.4.1	SI Operational Test	14

3.2.4.2	ISM System Test (TEGS Phase 4: “Test It”)	15

3.2.5	Site Tests	17

3.2.5.1	SI Site Tests	18

3.2.5.2	ISM Key Site Test (TEGS Phase 5: “Key Site/National Deployment”)	18

3.2.6	Independent Operational Test and Evaluation	19

3.2.7	Field Acceptance and Field Familiarization Tests	20

3.2.7.1	SI Field Familiarization Tests	21

3.2.7.2	ISM Field Acceptance Test and Field Familiarization	21

3.2.8	SI to ISM Transition	22

3.3	Test and Evaluation for Pre-Planned Product Improvements	23

4.0	Research and Development Prototype Test Activities	24

5.0	Key Test and Evaluation Organizations	25

5.1	Service Organization	25

5.2	Office of Independent Operational Test and Evaluation	25

5.3	Site Test Organization	25

5.4	The William J. Hughes Technical Center	25

5.5	Second-level Support	25

5.6	Technical Operations	26

6.0	Test and Evaluation Documentation	27

6.1	OMB Exhibit 300	27

6.1.1	Attachment 1: Program Requirements Document	27

6.1.2	Attachment 3: Implementation Strategy and Planning	27

6.2	SI Test Documentation	28

6.2.1	Development Test Plan	28

6.2.2	Operational Test Plan	28

6.2.3	Production Acceptance Test Plan	28

6.2.4	Site Acceptance Test Plan	28

6.2.5	Field Familiarization Test Plan	28

6.2.6	Test Procedures	28

6.2.7	Quick-Look Test Reports	29

6.2.8	Test Reports	29

6.3	ISM Documentation	29

6.3.1	Description of Modification	29

6.3.2	System/Project Development Plan	30

6.3.3	Test Tool and Test Environment Specification	30

6.3.4	Development Test Activities Planned and Documented	30

6.3.5	Failure/Discrepancy Reports	31

6.3.6	Development Test Report	31

6.3.7	System/Project Test Plan	31

6.3.8	Baseline Established/Development Documentation	31

6.3.9	Develop Key Site Test Plan	32

6.3.10	Baseline Performance/Functional Verification	32

6.3.11	System/Project Release Documents	32

6.3.12	System/Project Test Report	33

6.3.13	Key Site Package (if applicable)	33

6.3.14	Finalize Field Familiarization Plan and Generic Upgrade Schedule	33

6.3.15	Key Site Test Report	34

6.3.16	Discrepancies/Issues/Actions Documented	34

7.0	Recommended Test and Evaluation Processes	35

7.1	SI System Test Planning Process	35

7.1.1	Development Test, PAT, and SAT Planning	36

7.1.2	OT Planning	36

7.1.3	Development Test and OT for System Modifications and P3Is	36

7.2	SI Method for Verifying Operational Requirements	37

7.2.1	Relationship of Operational Requirements, COIs, and CPPs	37

7.2.2	Identifying Candidates for COIs	38

7.2.3	Verification of Operational Requirements via COI Decomposition	39

7.3	Key Site Selection Process	40

7.4	User Prioritization Process	41

List of Figures

Figure 3.0-1: Tests and Test Activities Associated with NAS Acquisition Programs	2

Figure 3.0-2: Test and Evaluation Process	4

Figure 3.2-3: SI/ISM Needs and Requirements Checklist	10

Figure 3.2-4: Design and Development Checklist	11

Figure 3.2-5: SI/ISM Development Test Checklist	13

Figure 3.2-6: SI Operational Test and ISM System Test Checklist	16

Figure 3.2-7: SI/ISM Site Test Checklist	17

Figure 3.2-8: IOT&E Checklist	20

Figure 3.2-9: SI/ISM Field Familiarization Checklist	20

Figure 3.2-10: New System Implementation	21

Figure 3.2-11: Air Traffic Automation Operational Suitability Requirement Checklist	22

Figure 7.2-1: COI Decomposition	39

Figure 7.2-3: Actual COIs, MOEs, and MOPs	40

List of Tables

Table 3.2-1: SI Test Objectives	8

Table 3-2.2: ISM Test Objectives	9

Table 7.2-1: Where COIs and CPPs are Defined, and Who Defines Them	38

Table 7.2-2: COI, CPP, MOE, MOS, and MOP Definitions	39

Table 7.2-4: Overall Responsibility of COI Decomposition Process	40

APPENDIX A	BEST PRACTICES

APPENDIX B	SI Lessons Learned

APPENDIX C	Format and Content Guidance for T&E Documents

Appendix D	ASR-11 COI Example

aPPENDIX E	iot&e dETAILS

Appendix F	Acronyms and Definitions

Background

On April 1, 1996, the Federal Aviation Administration adopted an Acquisition Management System (AMS) that relies on teamwork and team competency to manage the development and acquisition of systems and other products for the National Airspace System (NAS).  The AMS minimizes policy and relies on the prudent application of guidance, best practices, and lessons learned from previous and ongoing  investment programs.

The AMS empowers service organizations to decide how NAS systems will be acquired and how requirements will be verified or tested.  These decisions are subject to minimal oversight outside service organization management structures.  The service organizations fully integrate the acquiring and user organizations into a singular partnership structure that can make both corporate and program decisions.  Its purpose is to build quality and achieve consensus using cross-functional teams supported by proven guidance, structured templates, and best practices as learned from the most successful  investment programs.

This guidance document provides a sound foundation for planning and executing Test and Evaluation activities appropriate to each individual investment program.

# Purpose

This document provides Test and Evaluation (T&E) guidance in support of the Federal Aviation Administration (FAA) Acquisition Management System (AMS).  This document will be updated throughout its lifetime, as better practices are identified and new lessons are learned.  Document users are encouraged to submit comments, lessons learned, and any data that may improve this document to the Acquisition Planning and PolicyDivision.  The latest version of this document, and all referenced AMS documents, are available in the FAA Acquisition System Toolset (FAST).  FAST can be found on the internet at <http://FAST.faa.gov.>

# Test and Evaluation Guiding Principles

- T&E programs should be structured to:

- Provide essential information to support decision-making

- Provide essential information for assessing technical and acquisition risk

- Verify the attainment of technical performance specifications and objectives

- Verify that systems are operationally effective and suitable for intended use

- Test objectives for each AMS lifecycle phase should be designed to mitigate potential operational risks and to demonstrate system performance appropriate to that phase.  Quantitative criteria should provide substantive evidence for analysis of Hardware (HW), Software (SW), and system maturity and readiness to proceed through the acquisition management process.

- Each T&E phase should have specific milestones (entrance and exit criteria) that should be satisfied prior to entering the next T&E phase.  This applies to both the Solution Implementation (SI) phase and the In-Service Management (ISM) phase during the lifecycle.

- Independent Operational Test and Evaluation (IOT&E) is an essential part of the T&E process for designated programs, and it provides decision-makers with an independent assessment of operational readiness.

- Parallel testing is encouraged when it is more efficient than, and at least as effective as, serial testing.

- The Test and Evaluation Gold Standard and Implementation Guide defines the activities to be performed in the ISM phase.  The Test and Evaluation Gold Standard and Implementation Guide details five phases that must be addressed by the ISM Team for all National Airspace System modifications.  They are the “Define It,” “Design It,” “Build It,” “Test It,” and “Key Site/National Deployment” phases.  The details can be found at:

<http://intranet.aos.faa.gov/aos20/aos22/pi/t&e/Documents/IG_v2.0.>

# Test and Evaluation During the Acquisition Management Phases – Overview

The T&E processes for acquisition management have been developed to ensure consistency in testing approaches throughout the lifecycle of the program.  Figure 3.0-1 illustrates the relationship of test activities to the different phases of a typical acquisition.  This section describes the relationship between these test activities and explains how and when requirements are verified.  In addition, it describes how an assessment of operational readiness is made.

Figure 3.0-1: Tests and Test Activities Associated with NAS Investment Programs

The acquisition process begins with the research and systems analysis and the mission analysis phases.  Research and systems analysis is tightly coupled with, and supportive of, other AMS lifecycle management processes.  It is especially important during the early stages of lifecycle management, when activities such as simulation, rapid prototyping, and Computer-Human Interface development are conducted to define requirements, develop operational concepts, and reduce risk before entering Investment Analysis.

During mission analysis, a service-level Mission Need Statement (SLMNS) is developed, along with a set of initial requirements, to help determine what investment alternatives will be evaluated in the next phase.  The Chief Operating Officer (COO) of the Air Traffic Organization or the Associate Administrator (non-Air Traffic Organization) of the line of business approves the SLMNS.  Test activities conducted during the mission analysis phase include concept feasibility demonstrations, which are conducted to determine the viability of a concept or new capability and to assess of the testability of the initial requirements.  A favorable outcome results in the creation of an approved set of initial requirements and candidate alternatives.

The two-part Investment Analysis phase includes initial and final investment analyses.  It also assesses the testability of the refined requirements and generates an estimation of the cost needed to conduct test activities.  These, in turn, serve as inputs to the Office of Management and Budget (OMB) Exhibit 300 and its attachments.  When appropriate, candidate solutions may be analyzed and demonstrated to support the development and validation of the Program Requirements (PR), attachment to Exhibit 300 Program Baseline.  Another attachment, the Implementation Strategy and Planning (ISP) document, also supplements information in the Exhibit 300 Program Baseline.  Part 1 of the ISP defines the lifecycle management strategy for the overall investment program.  Part 2 is a network of actions and activities to execute the phase of the program approved for implementation by the Joint Resources Council (JRC).

The Investment Analysis phase usually concludes with the authorization for the program to proceed to the JRC for a final investment decision.  The JRC authorizes movement of the program to the SI phase.

Figure 3.0-2 identifies the six major elements of the T&E processes implemented during the Investment Analysis, SI, and ISM phases of the AMS.  These processes also identify test process documentation, test tools, and test environments that support the test objectives.  The T&E processes can be used to plan high-level T&E activities as they relate to the phases of the AMS.

Figure 3.0-2: Test and Evaluation Process

The SI phase typically begins with refinement and expansion of the ISP, leading to a full-scale development, Commercial-Off-The-Shelf (COTS)/Non-Developmental Item (NDI) procurement or operational prototype.  SI System Test (which includes Development Test, Operational Test (OT), Production Acceptance Test (PAT), Site Acceptance Test (SAT)), IOT&E, and Field Familiarization, are performed by various FAA organizations to verify that requirements have been met and that the system is ready for operational use.

The implementing service organization is responsible for System Test; the Office of IOT&E is responsible for performing IOT&E on designated programs, and site and regional Air Traffic and Technical Operations personnel perform Field Familiarization for new systems.  Early in the SI phase, prototype testing may be conducted to validate requirements and verify risk reduction plans associated with Investment Analysis assumptions.  In some cases, the JRC may authorize the program to proceed through prototype testing.  However, it may not advance to full-scale development until prototype test results are known and the JRC approves an updated Exhibit 300 Program Baseline.

System Test is designed to accomplish two objectives during the SI phase.  First, it verifies the satisfaction of all requirements associated with the acquisition of a system.  Second, it answers the Critical Operational Issues (COIs) contained in the PR Attachment.  When it is successfully completed, the service organization determines if the system is ready either for an In-Service Decision (ISD) (when IOT&E is not required) or IOT&E.  Following SAT, Field Familiarization is performed to verify that the site is ready to transition to the new system.  IOT&E is performed on designated programs, as directed by the Vice President of Safety Services.  It is designed to evaluate the operational readiness of the system in its intended operational environment.  An IOT&E report provides an operational readiness assessment to the Vice President of Safety Services and the ISD authority.

The ISM phase typically starts after system deployment.  NAS modifications identified during the ISM phase generally originate while the system is sustained in an operational state.  Changes to the baseline are handled via the NAS Change Proposal (NCP)/case file process.  All HW/SW modifications performed during the ISM phase of the acquisition management process must follow a structured and disciplined T&E process.  The process is defined in the Test and Evaluation Gold Standard and Implementation Guide and is accomplished through a five-phase approach:

- Needs and Requirements Defined (“Define It”)

- Design and Development (“Design It”)

- Development Test (“Build It”)

- System Test (“Test It”)

- Field Acceptance and Field Familiarization Test (“Key Site/National Deployment”)

(Refer to http://intranet.aos.faa.gov/aos20/aos22/pi/t&e/Documents/IG_v2.0.)

ISM System Test (defined in paragraph 3.2.4.2 and not to be confused with SI System Test), Key Site Test, and Field Familiarization.  T&E is conducted to ensure that modified components, functionality, or enhancements operate properly and do not degrade system effectiveness or suitability.  All activities are conducted with appropriate user/stakeholder involvement to ensure that the modifications are ready for deployment.

To make programs more efficient, it is sometimes necessary to tailor the standard acquisition/modification approach (e.g., spiral development, technical refresh, prototyping, emergency HW/SW releases, etc.).  Each ISM Team must evaluate the need or requirement and determine how the Test and Evaluation Gold Standard Matrix will be addressed and/or tailored, for a specific program or NAS modification.  Test standards detailed in the Test and Evaluation Gold Standard and Implementation Guide should be used as a basis to develop a tailored test approach.

FAA T&E processes rely on the development and use of T&E documents, test tools, and test environments.  These are utilized to confirm operational readiness by measuring specific system performance and simulating operational environments.  Test documentation, test tools, and test environments are initially developed and used during SI T&E and are then modified and/or supplemented during ISM T&E based on changes or upgrades to the system.

## Investment Analysis Test and Evaluation

Investment Analysis generates information the JRC needs to make an investment decision, which signifies the start of an investment program.  Because programs do not start until the investment decision is made, testing usually does not take place during the Investment Analysis phase, although test-related activities do contribute to the development of the PR Attachment and ISP, which are attachments to the  Exhibit 300 Program Baseline.

### Initial Investment Analysis

The initial PRD establishes the operational framework and performance requirements for satisfying a mission need.  During the development of the PRD, each requirement is assessed for testability.  Requirements found not to be testable are often further refined or decomposed into testable requirements, and the results are provided to the service organization.  Test professionals also review COIs and Critical Performance Parameters (CPPs) to ensure they are complete, testable, and traceable to system or operational requirements.  COIs are key operational effectiveness or suitability issues expressed as questions about system concerns, such as capabilities, practicability, and environmental effects.  COIs are examined in tests during the SI phase to determine a product’s capability to perform its mission.  CPPs are top-level system performance parameters that are expressed as specific, quantified values.

The Exhibit 300 Program Baseline establishes the performance, cost, schedule, and benefits boundaries for implementing the solution.  The PR Attachment contains the appropriate CPPs and COIs.  Test professionals develop a high-level test strategy and estimate test costs for each candidate solution for inclusion in the Business Case Analysis Report.  They also review vendor performance data and demonstrations of COTS/NDI products that may satisfy the mission need.

Feasibility analyses and demonstrations address the refinement of the PR Attachment and assess human factors and the evaluation of procedural impacts.  The evaluation of a specific technology can reduce risk and collect data necessary to support investment decisions.

### Final Investment Analysis

Final Investment Analysis focuses on detailed planning for the selected solution for implementation.  A tailored test strategy is developed and included in Part 1 of the ISP.  Implementing the test strategy is described in Part 2 of the ISP.  An Operational Capability Test (OCT) or Operational Capability Demonstration (OCD) may be conducted to verify requirements or select a particular COTS/NDI product.  An OCT/OCD should address maintainability and human factors requirements; the information obtained may allow a reduction in the required testing.  Vendor data may be used to reduce FAA test efforts for commercial products.  (Plans to use vendor test data in place of FAA tests and the rationale for doing so should be identified in the ISP.)

## SI and ISM Test and Evaluation

The most significant T&E activities associated with the acquisition and delivery of new NAS systems are conducted during the SI phase.  During this phase, the test strategy is implemented through a series of tests that includes Development Test, OT, PAT, SAT, Field Familiarization, and IOT&E (for designated programs).  Objectives for this series of tests are developed to verify that requirements have been met.  Detailed guidelines are provided for Development Test, OT, PAT, and SAT in the William J. Hughes Technical Center (WJHTC) System Test and Evaluation Process Document.  Detailed guidelines are provided for IOT&E in the IOT&E Operations Manual.  Table 3.2-1 lists the high-level objectives of each of the SI test phases.

All NAS modifications should be developed and implemented following the Test and Evaluation Gold Standard and Implementation Guide.  Service teams responsible for the development and implementation of NAS modifications to the field must comply with the Test and Evaluation Gold Standard (TEGS).  In addition, major upgrades or sustainment efforts for operational NAS systems may also be designated for IOT&E.  These programs must adhere to an IOT&E process that is equivalent to the process followed for new acquisitions.

| SI Test Objectives | DT | OT | PAT | SAT | FF | IOT&E |
| --- | --- | --- | --- | --- | --- | --- |
| Verify contractor compliance to contracted functional and performance requirements | ( |  |  |  |  |  |
| Verify the engineering design, development, and maintenance process | ( |  |  |  |  |  |
| Verify system compliance to electromagnetic interference requirements | ( |  |  |  |  |  |
| Identify deficiencies in system design and documentation, the NAS, HW, SW, human performance factors, and operational concepts | ( | ( |  | ( |  | ( |
| Verify that human factors implementation meets user needs |  | ( |  |  | ( | ( |
| Resolve COIs |  | ( |  |  |  | ( |
| Assess operational effectiveness, supportability, and suitability, including the human component | ( | ( |  | ( | ( | ( |
| Verify the system meets Reliability, Maintainability, and Availability requirements | ( | ( |  |  |  | ( |
| Evaluate the compatibility and interoperability with existing or planned systems or equipment | ( | ( |  | ( | ( | ( |
| Assess system operations in a degraded mode | ( | ( |  | ( | ( |  |
| Verify the system is safe, secure, and survivable | ( | ( |  | ( | ( | ( |
| Assess the site adaptability of the system | ( | ( |  | ( | ( | ( |
| Assess the transition switch-over capability/plan | ( | ( |  | ( | ( | ( |
| Verify the adequacy of manuals, handbooks, supporting plans, and other documentation for operations, maintenance, and training | ( | ( |  | ( | ( | ( |
| Assess the degree to which the system can be monitored, operated, and maintained by users in an operational environment |  | ( |  |  | ( | ( |
| Verify system operations under stress and NAS loading | ( | ( |  | ( |  |  |
| Assess NAS end-to-end performance with the system installed to ensure pre-existing NAS functionality is not degraded by new system insertion/integration |  | ( |  | ( | ( | ( |
| Ensure production units are of consistent quality and are equivalent to the first article |  |  | ( | ( |  |  |
| Verify production units are free from manufacturing defects |  |  | ( | ( |  |  |
| Verify Installation and Integration of fielded systems is consistent with approved SAT plans |  |  |  | ( |  |  |

Table 3.2-1: SI Test Objectives

After deployment, NAS systems may require modifications during their in-service lifetimes.  The T&E process is designed to standardize the manner in which HW/SW modifications are tested and evaluated in support of deployment to the field.

During ISM, the test strategy is implemented through a series of tests that includes Development Test, System Test, Key Site Test, Field Acceptance Test, and Field Familiarization.

Objectives for tests during SI and ISM phases are developed to verify that requirements have been met.  Using different environment and test tools, the series of tests may verify the same requirement more than once.  There are program-specific guidelines regarding the amount of parallel testing, repeat testing in different test environments, and regression testing necessary to produce a comprehensive, cost-effective test program.  These considerations should be addressed during test strategy and test plan development.

Table 3.2-2 lists the high-level objectives of each of the test phases of ISM:

| ISM Test Objectives | Development Test | System Test | Key Site Test | Field Familiarization |
| --- | --- | --- | --- | --- |
| Verify compliance to functional and performance requirements | ( |  |  |  |
| Verify the engineering design, development, and maintenance process | ( |  |  |  |
| Verify system compliance to interference requirements | ( |  |  |  |
| Identify deficiencies in system design and documentation, the NAS, HW, SW, human performance factors, and operational concepts | ( | ( | ( | ( |
| Identify and demonstrate mitigation of risks | ( | ( | ( | ( |
| Assess operational effectiveness, supportability, and suitability, including the human component | ( | ( | ( | ( |
| Verify the system meets Reliability, Maintainability, and Availability requirements | ( | ( | ( | ( |
| Evaluate the compatibility and interoperability with existing or planned systems or equipment | ( | ( | ( | ( |
| Assess system operations in a degraded mode | ( | ( | ( | ( |
| Verify the system is safe, secure, and survivable | ( | ( | ( | ( |
| Assess the site adaptability of the system |  | ( | ( | ( |
| Verify the adequacy of manuals, handbooks, supporting plans, and other documentation for operations, maintenance, and training |  | ( | ( | ( |
| Assess the degree to which the system can be monitored, operated, and maintained by users in an operational environment |  | ( | ( | ( |
| Verify system operations under stress and NAS loading |  | ( | ( | ( |
| Assess NAS end-to-end performance with the system installed to ensure pre-existing NAS functionality is not degraded by new system insertion/integration |  | ( | ( | ( |
| Verify operational procedures |  | ( | ( | ( |
| Verify functional certification procedures |  | ( | ( | ( |
| Verify system is compliant with physical and information security requirements | ( | ( | ( |  |
| Verify the Safety Risk Management Requirements have been met | ( | ( | ( |  |
| Verify HW and SW installation instructions |  |  | ( | ( |

Table 3-2.2: ISM Test Objectives

### Needs and Requirements

Figure 3-2.3 identifies processes and criteria for the needs and requirements activities within the SI and ISM phases of AMS.  The processes and checklist criteria can be used to plan high-level T&E activities and support the development of entry and exit criteria.

#### SI Needs and Requirements

Early SI phase test activities focus on the definition of test-related program needs and requirements.  This definition provides the basis for developing the schedule, resources, and scope of all testing activities throughout the acquisition management lifecycle.  The key documents and elements that require inputs from the test activity are the Exhibit 300 Program Baseline, COIs/CPPs, Statement of Work, and specification.  These test activities address requirements testability, definition of test requirements and strategies, definition of test tools, assessment of feasibility of candidate solutions, and support of contract award.

Figure 3.2-3: SI/ISM Needs and Requirements Checklist

#### ISM Needs and Requirements (TEGS Phase 1: “Define It”)

Needs identified during the ISM phase of a system’s lifecycle originate from the operational environment while the system is sustained in an operational state.  Case files (or new needs) can also be initiated by the operational support activity.  These needs are subjected to various levels of screening and validation at the local level and throughout the FAA.  Needs that cannot be satisfied at the local level are validated and entered into the national requirements process.

Due to the complex nature of the NAS, operators and maintainers may encounter system problems that require a change to the system, the baseline, or an adaptable parameter.  This is identified via a Program Trouble Report (PTR), Hardware Discrepancy Report (HDR), or an equivalent.  The PTR documents the need for the change, and the identified problem is researched to determine if the system is actually operating within its established baseline.  Changes to the baseline are normally handled via the NCP/case file.  The NCP process can be initiated at any level and may address changes of any magnitude.  If the system were determined to be operating within its baseline, the PTR would be closed, and the originator would be advised that a system baseline change would be necessary to address the identified need.

When an NCP is approved, the implementing service organization receives a Configuration Control Decision (CCD).  A functional description is written to describe how the CCD will be implemented.  The functional description includes, at a minimum, a statement of the problem, expected outcomes, description of interfaces, and subsystem performance parameters.   Unique test criteria/scenarios will be identified and applied later in the ISM test process.  The creation of a specific method of testing a requirement may be deferred until the design (Preliminary Design Review (PDR)/Critical Design Review (CDR) and Peer Review) is formulated.  It is the responsibility of service organizations to ensure the functional description is structured so that requirements are verifiable.

The Test and Evaluation Gold Standard and Implementation Guide defines those activities to be addressed during ISM Needs and Requirements (TEGS Phase 1: “Define It”).  A system development plan is developed to plan and track the system throughout its lifecycle.  It defines the purpose, scope, organizational roles and responsibilities, estimates, resources, schedules, known risks, test environment, and test tools.

System requirements are evaluated through the System Requirements Review.  This review will ensure that the requirements are clearly understood.  It will also identify any deviations from the specifications, which are documented and addressed in the Baseline Performance Specification.  Prior to moving into the Design and Development phase, the test tool and test environment specification documentation is complete, thereby ensuring that necessary tools and configurations are available to test effectively.  Key site (back-up and primary) selection activities will be initiated based on requirements to be tested, HW/SW configuration, and/or availability of the system in the operational environment.

All proposed changes to the NAS should be evaluated to ensure they do not adversely affect the safety or security of the system.

### Design and Development

Figure 3.2-4 identifies associated processes and criteria for the Design and Development activities within the SI and ISM phases of the AMS.  The processes and checklist criteria can be used to plan high-level T&E activities and support the development of entry and exit criteria.

Figure 3.2-4: Design and Development Checklist

#### SI Design and Development

Most large acquisitions are designed and developed by a prime contractor and monitored by the FAA.  The contractor conducts the PDR and CDR.  At both reviews, the contractor presents the planned test strategy to the FAA.  The contractor will then develop test documentation for approval by the FAA.  It will consist of the test plans and procedures that will be used by the contractor during the conduct of Development Test.  FAA test personnel carefully review these documents and all other pertinent documents to ensure preparations for Development Test are being addressed properly.  As the design phase continues, other test activities associated with Development Test are also conducted by the contractor and approved by the FAA.  They include development of test tools, establishment of the test environment, simulation of external interfaces, development of the Verification Requirements Traceability Matrix (VRTM), and issuance of initial failure reports and final test reports.

#### ISM Design and Development (TEGS Phase 2: “Design It”)

The primary test-related activities that occur during the Design and Development phase are detailed test planning, PDR, and CDR.  These reviews are used to finalize design, ensure initial user agreement, and present proposed test strategies.  The service organization coordinates the appropriate user and stakeholder involvement in PDR/CDR activities based on the complexity and impact of the functional changes.

Detailed test planning includes the development of test plans and creation of any needed test tools and test environments.  The thoroughness of these test tools directly affects the level of verification that can be accomplished in a reasonable timeframe.  The test tools and test environment should allow for maximum verification of the system prior to operational use.

The Test and Evaluation Gold Standard and Implementation Guide defines the activities addressed during ISM Design and Development (TEGS Phase 2: “Design It”).

### Development Test

Figure 3.2-5 identifies associated processes and criteria for Development Test activities within the SI and ISM phases of the AMS.  The processes and checklist criteria can be used to plan high-level T&E activities and support the development of entry and exit criteria.

Figure 3.2-5: SI/ISM Development Test Checklist

#### SI Development Test

The primary objective of SI Development Test is to demonstrate that all technical and performance requirements specified in the contract have been met.  Development Test is normally performed by the contractor and witnessed by the service organization at the factory and/or WJHTC.  It typically begins with a series of HW and SW tests.  HW tests begin at the board level or component level and proceed to the system level.  SW testing begins by verifying the most detailed requirements at the unit level.  It then proceeds to verify higher-level integrated requirements at the segment level and verify requirements at the Computer Software Configuration Item level.  Development Test at the vendor facility also includes a design qualification test that demonstrates the system’s ability to satisfy the system specification.  Development Test verifies the system meets contract requirements.

#### ISM Development Test (TEGS Phase 3: “Build It”)

ISM Development Test is performed to verify the modification meets specified requirements and interrelated functions are not adversely affected.  These test activities include functional unit tests and/or first-article tests that ensure the modification works as designed and is in compliance with the specification requirement.  The service organization, users, and stakeholders determine if demonstrations are required to ensure the design meets user needs.  At the completion of Development Test, a build baseline is established.  The development of functional certification procedures for the packaged system will commence and be finalized in later test phases.  The Test and Evaluation Gold Standard and Implementation Guide defines the activities to be addressed during ISM Development Test (TEGS Phase 3: “Build It”).

### SI Operational Test and ISM System Test

Figure 3.2-6 identifies processes and criteria for the SI Operational Test and ISM System Test activities.  The processes and checklist criteria can be used to plan high-level T&E activities and support the development of entry and exit criteria.

#### SI Operational Test

The primary objective of OT is to demonstrate that a new system is operationally effective and operationally suitable for use in the NAS and that the NAS infrastructure is ready to accept the system.  These tests focus on demonstrating that operational requirements have been met and all COIs and CPPs have been satisfied.  OT is conducted at WJHTC or a field site using field personnel.

The major components of OT are integration tests, performance tests, effectiveness tests, and suitability tests.  Integration testing performed during OT verifies that the system interfaces with existing elements of the NAS and the NAS can operate with the new subsystem at the required performance levels.  Interface testing with future NAS elements may be provided through the use of simulators, where warranted.

Effectiveness testing performed during OT evaluates the degree to which a product accomplishes its mission when used by representative personnel in the expected operational environment.  This testing includes capacity and NAS loading, degraded mode operations, safety, security, and transition switchover.  Field personnel often operate the equipment for some of these tests because they are the most representative operators; it also helps them become familiar with the system.  This approach reduces the learning curve and minimizes disruption during system installation in the field.  Effectiveness and suitability T&E may continue at the key site (or key sites) if a complete assessment cannot be accomplished at WJHTC.  OT effectiveness testing also assesses COIs.

OT suitability testing evaluates the degree to which a product intended for field use satisfies its availability, compatibility, interoperability, reliability, maintainability, safety, and human factors requirements.  In addition, logistics supportability, documentation, certification criteria, system installation, and operating procedures, and transition and training requirements, are validated.  OT suitability testing also includes an assessment of the COIs.

For designated programs, after the successful conclusion of OT, the Vice President of the implementing service organization declares the system ready for IOT&E via the IOT&E Readiness Declaration (IOTRD).  The IOTRD addresses the IOT&E prerequisites/requirements as detailed in the T&E section of the ISP.  (See Appendix C-11 for a sample IOTRD template.)

#### ISM System Test (TEGS Phase 4: “Test It”)

ISM System Test is conducted to ensure the modification is ready for use in the NAS.  The major components of the ISM System Test are integration tests, operational effectiveness tests, and operational suitability tests.  System Test is performed independent of the developer, under conditions that simulate the operational environment as closely as possible.  The user community will participate in operational suitability test activities during this phase as required.  Features/performance that cannot be fully verified during this phase of T&E are deferred to the Key Site Test.  Test procedures to be used during the Key Site Test and Field Familiarization are refined during this phase of testing.

ISM integration test includes baseline performance and validation of new functionality and existing system functionality.  It also verifies that the modified system interfaces with the existing elements of the NAS as specified by the Interface Control Document.  Performance measurements are taken to verify the system is operating in accordance with established baselines.

The ISM operational effectiveness testing evaluates the degree to which the modified system accomplishes its mission.  This testing includes capacity and loading, degraded mode operations, safety, security, and system and support system regression.  Field personnel often operate the equipment for some of these tests because they are the most representative operators; it also helps them become familiar with the system.

Figure 3.2-6: SI Operational Test and ISM System Test Checklist

ISM operational suitability testing evaluates the degree to which the new modification satisfies its availability, compatibility, interoperability, reliability, maintainability, safety, and human factors requirements.  In addition, logistics supportability, documentation, certification criteria, and training requirements are validated.  The service organization often conducts ISM suitability tests with support from the stakeholders.

When abnormalities are identified during ISM System Test, a determination is made by the service organization, users, and stakeholders to either fix the anomaly prior to release or defer it to a future release.  These decisions are documented in the System Test report.  The results of the ISM System Test activities, including test limitations, are documented in Appendix 1 of the System Support Modification (SSM).  Effectiveness and suitability T&E may be continued at the key site(s) if a complete assessment cannot be accomplished at WJHTC.

Coordination with management and national union leadership regarding impact and implementation issues related to the modification should be finalized during this phase.

The Test and Evaluation Gold Standard and Implementation Guide defines those activities to be addressed during ISM System Test (TEGS Phase 4: “Test It”).

### Site Tests

Figure 3.2-7 identifies associated processes and criteria for the site test activities within the SI and ISM phases of the AMS.  The processes and checklist criteria can be used to plan high-level T&E activities and support the development of entry and exit criteria.

Figure 3.2-7: SI/ISM Site Test Checklist

#### SI Site Tests

During some acquisitions, PAT is conducted by the vendor on each system it produces before the system leaves the factory.  Production tests usually consist of quality control tests plus a subset of Development Test.  These tests verify the assembly line is producing units with the same quality and performance as the first article.

Following delivery to the site, each system undergoes installation and check-out and SAT.  These tests are conducted by the vendor to ensure the system is installed and functioning properly in preparation for site acceptance.

#### ISM Key Site Test (TEGS Phase 5: “Key Site/National Deployment”)

The ISM Key Site Test is conducted at an operational NAS facility to verify the modification meets user needs.  These test activities also allow for verification of requirements that could not be fully evaluated during the ISM System Test.  The operating service organization and regional office make the key site selection that is documented in a joint memorandum.  The selection is based on the facility that has the equipment and interfaces to fully test and implement the modification.  Delivery documentation is verified to ensure it can be followed at subsequent sites without assistance.

Each site has unique parameters for equipment, interfaces, and airspace that should be configured or adapted before tests can be performed.  Site personnel are responsible for site adaptation updates and changes for the modification being released.  Key Site Test activities begin with a Key Site Test Readiness Review, which includes test overview, review of operational and support SW, test procedure information, and the review of any known problems or concerns that may affect the test.  Key Site Test anomalies are noted and documented for improvement.

Key Site Test results are documented in the Key Site Test report.  When abnormalities are identified during ISM Key Site Test, the service organization, users, and stakeholders will determine whether to fix the anomaly prior to release or defer it to a future release.  Any problems will be noted and documented in Appendix 1 of the SSM prior to national release.  Test procedures to be used by downstream sites to conduct Field Acceptance Test and Field Familiarization are finalized during this phase of testing.  At the conclusion of all scheduled activities, a national telephone conference will be held to brief key site events that have occurred.  If applicable, a joint memorandum for national release is formulated and forwarded to responsible parties.  Successful completion of Key Site Test allows national delivery of the modification.

The Test and Evaluation Gold Standard and Implementation Guide defines the activities to be addressed during ISM Key Site Test (TEGS Phase 5: “Key Site/National Deployment”).

### Independent Operational Test and Evaluation

Figure 3.2-8 identifies associated processes and criteria for the IOT&E activities within the SI or ISM phase of the AMS.  The processes and checklist criteria can be used to plan high-level T&E activities and to define initial entry and exit criteria.  IOT&E is a full system-level evaluation conducted in an operational environment to confirm the operational readiness of a system to be part of the NAS.  Therefore, IOT&E is performed on systems that have achieved Initial Operating Capability (IOC) at an operational field facility (the key site).  Data collection for IOT&E may begin prior to IOC if there are concerns about:

- HW/SW installation

- Transition between the system under evaluation and any legacy systems

Data collected prior to IOC supplements formal data collection during IOT&E.  After IOC, the system undergoing IOT&E is an operational component of the NAS and must be operated and maintained by its intended users as designed for actual NAS operations.  The results of IOT&E are used to support the ISD or other decisions regarding the operational use and deployment of systems.

The COO, through the Vice President of Safety Services, designates programs for IOT&E.  Factors considered in designating programs include complexity, operational criticality, lifecycle cost, interoperability, and risk.  An IOT&E is conducted by an IOT&E Team that includes members from Air Traffic and Technical Operations and is led by a Program Manager from the Office of IOT&E.  The strategy, resources, and schedule for IOT&E are documented in the T&E section of Exhibit 300 Program Baseline, Attachment 3: Implementation Strategy and Planning.  The Office of IOT&E co-approves the T&E Section of the ISP for designated programs.

After formation, IOT&E Teams are involved in monitoring key test events conducted earlier in the SI or ISM phases to identify areas of operational risk.  Identified risks are communicated to the service organization and may affect the scope of IOT&E.  At the conclusion of System Test activities, the Vice President of the implementing service organization declares the system ready for IOT&E via delivery of the IOTRD to the Vice President of Safety Services.  Upon receipt of the IOTRD, and at the discretion of the Vice President of Safety Services, the IOT&E Team commences IOT&E at the key site(s).  At the conclusion of the IOT&E, the IOT&E Team makes a determination of the system’s operational readiness based on the operational risk associated with any identified issues.  IOT&E results are briefed to the key site managers, the service organization, and Air Traffic Organization stakeholders at the Directorate and Vice President levels.

Figure 3.2-8: IOT&E Checklist

### Field Acceptance and Field Familiarization Tests

Figure 3.2-9 identifies associated processes and criteria for the Field Acceptance Test and Field Familiarization activities within the SI and ISM phases of the AMS.  The processes and checklist criteria can be used to plan high-level T&E activities and support the development of entry and exit criteria.  After the SSM has been delivered, the site will perform site adaptation and testing (if applicable) prior to implementation into the NAS.  (Refer to 3.2.5.2 (TEGS Phase 5: Key Site/National Deployment))

Figure 3.2-9: SI/ISM Field Familiarization Checklist

#### SI Field Familiarization Tests

Field Familiarization is conducted by Air Traffic and Technical Operations field personnel at each site to which the new system is delivered.  New system implementation is depicted in Figure 3.2-10.  Field Familiarization is performed after OT has been completed.  Its primary objective is to verify the site is ready to switch to the new system.  This includes ensuring:

- The new system has been properly installed

- The new system interfaces with the existing NAS

- Operational procedures and system documentation are in place

- Proper logistics and support are available

- Site personnel are trained and ready to use the new system

Prior to conduct, the Field Familiarization test approach  is be documented by the key site and subsequent sites to facilitate test conduct.  Lessons learned are documented and shared with waterfall sites.  As shown in Figure 3.2-10, Field Familiarization testing is conducted at each site after the system has successfully completed installation, check-out testing, and SAT.  Field Familiarization follows Contract Acceptance Inspection and leads to the declaration of IOC.  IOC is declared by site personnel when the system is ready for conditional operational use in the NAS.  At the key site, Field Familiarization is followed (or performed in parallel) with IOT&E (for designated programs).  The key site should be the only site at which IOC is declared prior to the ISD.  (More than one site may be designated a key site.)  Field Familiarization culminates with the declaration by site personnel that the system is ready for conditional operational use.  SI test activities conclude after successful completion of Field Familiarization, the declaration of IOC, IOT&E, and the ISD.

Figure 3.2-10: New System Implementation

#### ISM Field Acceptance Test and Field Familiarization

The ISM Field Acceptance Test and Field Familiarization are performed at all downstream sites to validate performance prior to operational use.  Field Acceptance Test is conducted by Air Traffic and Technical Operations field personnel at each site to which the system or modification is delivered.  The installed system or modification is certified as the first step toward operational integration.  If the modified system passes certification, Air Traffic begins operational suitability testing.  (The Air Traffic Automation Operational Suitability Requirement Checklist can be found in Figure 3.2-11.)  Test activities are performed after successful Key Site Test has been completed.  Its primary objective is to verify the site is ready to integrate the system or modification into the NAS.  This ensures the new system is properly installed and interfaces with the existing NAS, system documentation is in place, and proper logistics and support are available.  Prior to conduct, the Field Acceptance Test approach should be documented by the key site and subsequent sites.  Lessons learned should be documented and shared with subsequent sites.

Field Familiarization follows Field Acceptance Test and leads to a declaration of full operational integration.  Field Familiarization ensures operational procedures and system documentation are in place and site personnel are trained and ready to use the upgraded system.  After a system achieves the declaration of IOC, site personnel may use the new system operationally, usually in conjunction with the legacy system.  During this period of joint use, which is called Operational Suitability Demonstration (OSD), Air Traffic and Technical Operations personnel become familiar with the system, and additional personnel are trained until all personnel who will operate the modified system are qualified to do so.  Site personnel declare full operational integration, which signifies the system has been modified and is ready for conditional operational use in the NAS.  When modifications are completed at all eligible sites, action will be taken to close out the implementation of the modification via the Maintenance Management System process.

Figure 3.2-11: Air Traffic Automation Operational Suitability Requirement Checklist

### SI to ISM Transition

The Operational Readiness Date (ORD) signifies the end of OSD, at which time, switchover to the new system is complete.  Following OSD, the system is formally accepted by the site via the Joint Acceptance Inspection process.  This leads to the commissioning of the new system, decommissioning of the legacy system, and transition to the ISM phase of the lifecycle. ORD/commissioning should not occur at any site until after the ISD.

## Test and Evaluation for Pre-Planned Product Improvements

Most NAS systems are modified during their in-service lifetimes.  Sometimes, modifications are pre-planned as part of the acquisition strategy and are called Pre-Planned Product Improvements (P3Is).  Other modifications are made to correct problems discovered during operational use or to adapt the system to a changing operational environment.  Major modifications and P3I projects follow the same System Test, Field Familiarization, and IOT&E test sequence described in sections 3.1 and 3.2, suitably tailored to match the smaller scope typical of these projects.

When an operational system is modified, a generic version of the product is usually tested by the service organization in a series of tests designed to verify requirements compliance and operational readiness.  HW/SW unit tests are conducted on individual, modified, or new SW and HW items.  The generic system is then tested in a series of system verification tests.  These tests validate new functionality and measure system performance and capacity.  They also identify any problems with system documentation.  Baseline regression tests are also conducted to verify the integrity of existing functionality.  The generic system is delivered to the key site via a draft System Support Directive (SSD).

Service organization personnel travel to the key site to help install and test a locally adapted version of the system.  Key Site Test ensures the system is installed correctly and interfaces to other systems are operating properly.  Key Site Test also tests all modified and new SW items at the unit, module, and system levels.  Successful completion of Key Site Test is required before a final SSD is issued to deploy the system nationally.  When all operational and support SW has been tested successfully, Field Familiarization begins.

# Research and Development Prototype Test Activities

Research and Development (R&D) programs provide the management process with valuable input.  Empirical information from modeling, simulations, tests of R&D prototypes, and manufacturer tests of COTS equipment may validate new operational concepts, clarify requirements trade-offs, or verify the benefit of inserting new technology into the NAS.  As this information becomes available, it contributes to, and often triggers, Mission Analysis and Investment Analysis.  R&D prototype development and test adheres to the same fundamental paradigms as a full-scale system acquisition: early user involvement, proper planning, sound engineering, rigorous testing, and comprehensive analysis.

# Key Test and Evaluation Organizations

This section identifies organizations that are key contributors to test activities throughout the project lifecycle.

## Service Organization

The service organization plans, directs, and implements all SI test activities and coordinates inputs on schedule and resources from IOT&E and Field Familiarization for use in overall planning.  Service organizations are responsible for requirements management, determining the need for user involvement, and the coordination of user teams throughout the test process.  It is the responsibility of the service organization to ensure operational needs at the national and field level are adequately represented and considered.

## Office of Independent Operational Test and Evaluation

The Office of IOT&E is responsible for planning and conducting IOT&E on designated programs.  The Office of IOT&E develops IOT&E sections for inclusion in the T&E section of Exhibit 300 Program Baseline, Attachment 3: Implementation Strategy and Planning.  The Office of IOT&E co-approves the ISP T&E section on programs designated for IOT&E.  The IOT&E Team develops IOT&E plans and procedures.  The Office of IOT&E also provides assistance in the development of COIs for inclusion in the program’s Exhibit 300 Program Baseline, Attachment 1: Program Requirements.

## Site Test Organization

Air Traffic and Technical Operations facility managers typically appoint site test directors.  This is initiated by a service organization request and coordinated with the appropriate service area representative.  Site test director activities include overseeing the site testing of new or modified NAS systems.  Test directors also plan, manage, and report the results of site tests conducted by site Air Traffic and Technical Operations personnel.

## The William J. Hughes Technical Center

WJHTC Integrated Engineering Services is the organization responsible for providing test leadership and technical expertise to service organizations in planning and conducting System Test activities.  It is responsible for the preparation of required test documentation, coordination, and conduct of System Test and reporting the results.  This is defined and outlined in the approved service organization plan.  WJHTC also plans and conducts test activities for some ISM systems.

## Second-level Support

National Second-level Support provides centralized technical and engineering services in support of operational NAS systems.  These services include field support and restoration activities, problem identification and resolution, and system engineering and enhancement.  National Second-level Support organizations plan and conduct all phases of test activities for ISM systems and provide operational and technical expertise to the service organizations in support of System Test activities.

## Technical Operations

The headquarters organization with national oversight of field Technical Operations programs (e.g., certification, maintenance, trend analysis) has the responsibility to ensure service area and technical field needs are adequately represented and considered at the national level.  Technical Operations may also be responsible for the coordination of some Key Site Test activities.

# Test and Evaluation Documentation

This section contains an overview of T&E documentation and references the instructions for developing and preparing these documents.

## Exhibit 300 Program baseline

The Exhibit 300 Program Baseline establishes the performance baseline and operational framework for the investment program.  CPPs that will be used by the JRC to monitor the program are recorded in OMB Exhibit 300.  This document is developed as part of Investment Analysis and is approved as part of the Investment Decision.  The COO of the Air Traffic Organization or the Associate Administrator of the line of business with the need (non-Air Traffic Organization) approves the Exhibit 300 Program Baseline along with the Acquisition Executive, the Chief Financial Officer, and the Air Traffic Organization Senior Vice President of Finance.  The operational requirements and COIs, which must be resolved as a basis for the ISD, are also identified in the Exhibit 300 Program Baseline.  FAST provides detailed information on the  T&E content of the PR (Attachment 1) and the ISP (Attachment 3).

### Attachment 1: Program Requirements

The PR (Exhibit 300 Program Baseline: Attachment 1) establishes the performance baseline and operational framework required by the sponsoring line of business.  Air Traffic Organization Vice Presidents (or non-Air Traffic Organization Directors of organizations with the mission need) and the operating service organization(s) approve the PR Attachment and all changes to it.  The PR Attachment identifies the operational requirements and COIs that must be resolved as a basis for the ISD.  The FAST template for the PR Attachment provides detailed information on the document’s T&E content.

### Attachment 3: Implementation Strategy and Planning

The ISP attachment supplements information in the Exhibit 300 Program Baseline.  It defines the overall lifecycle management strategy for an investment program and contains a network of detailed actions and activities the service organization will undertake to implement the phase of the program approved by the JRC.  Planning in the attachment encompasses and integrates all aspects of program implementation.  These may include the acquisition of systems and equipment, construction or modification of facilities and physical infrastructure, functional integration within the FAA enterprise architecture, and procurement of services.  The attachment also integrates activity in diverse functional disciplines supporting the program, such as systems engineering, contracting, system safety management, logistics support, T&E, security, Configuration Management, human integration, and Quality Assurance.

Part 1 of the ISP defines the lifecycle management strategy for the overall investment program.  Part 2 is a network of actions and activities that will be undertaken to execute the phase of the program approved for implementation by the JRC.  For IOT&E-designated programs, the Office of IOT&E co-approves the ISP T&E sections.

## SI Test Documentation

### Development Test Plan

The Contractor Master Test Plan (CMTP) is the highest-level Development Test plan.  It describes all tests that will be conducted to demonstrate that specified technical and performance requirements have been met.  The CMTP is developed in accordance with the guidance described in Appendix C-12.  It identifies lower-level Development Test plans that will be prepared to describe tests required in the specification, such as electromagnetic tests, SW tests, first article tests, or capacity tests.  In addition to test descriptions, Development Test plans describe the contractor’s strategy for conducting tests, test resource requirements (i.e., equipment and personnel), test location, and test data reduction and analysis plans.  Appendix C-5 provides detailed guidance on the content and format of Development Test plans.  Appendix C-13 provides an alternate Development Test template for use on modifications and P3Is during the In-Service phase.

### Operational Test Plan

The OT plan forms the basis for the OT program.  The OT plan describes all tests the service organization will conduct to determine whether Exhibit 300 Program Baseline requirements have been met, whether COIs have been resolved, and whether the new system is suitable for use in the NAS.  Two major test series usually are described in an OT plan: the NAS integration test series and the suitability/effectiveness test series.  The OT plan also describes the various planning and preparation activities required prior to OT, the OT strategy/approach, test resource requirements, and test entry conditions.  The OT plan contains an OT schedule and an FAA VRTM.  Appendix C-1 provides detailed guidance on the content and format of OT plans.

### Production Acceptance Test Plan

The PAT plan typically describes two distinct series of tests: manufacturing tests (to ensure the manufacturing process is producing quality units) and Factory Acceptance Test (to ensure each unit is defect-free and meets requirements before shipment).  The PAT plan uses the same format as the Development Test plan, but extensive tailoring is recommended.  Appendix C-5 provides content and format guidance for PAT plans.

### Site Acceptance Test Plan

The SAT plan describes tests that are conducted at each site to demonstrate the installed unit is integrated with other site equipment and is operating properly.  SAT is usually a subset of Development Test.  The SAT plan uses the same format as the PAT plan.  (See Appendix C-5)

### Field Familiarization Test Plan

The Field Familiarization test plan is initially developed by the key site and utilized or tailored as required by subsequent sites.  It describes the various planning and preparation activities required prior to testing.  The plan describes the test activities in sufficient detail to guide the development of test procedures.  (See Appendix C- 8)

### Test Procedures

The individual test procedures decompose the test plan into a step-by-step procedure to conduct the test.  The content of the procedures should include test cases that are traceable to specific requirements defined in project or FAA VRTMs.  Appendices C-2 and C-6 provide content and format guidance for OT procedures and Development Test/PAT procedures, respectively.

### Quick-Look Test Reports

Quick-look test reports are abbreviated test reports that provide preliminary test results and conclusions to decision-makers within approximately 15 days of completing a test.  The primary purpose of quick-look reports is to allow the program to proceed or the decision authority to render a preliminary decision without delay if preliminary test results reveal no significant problems.  Appendix C-4 describes the format for quick-look test reports.  An OT quick-look report may be acceptable documentation for the decision to declare IOC at a key site, but a final (not draft) OT Report must be completed and available as input to the In-Service Review process to support an In-Service Decision.

### Test Reports

Test reports document the results of a test and usually recommend a course of action based on those results.  The test report addresses test results, including test conduct, data collected, the data reduction and analysis process, and conclusions to be drawn from the test data.  Content and format guidance for OT reports, Development Test/PAT reports, Field Familiarization test reports, and operational system functional verification reports are contained in Appendices C-3, C-7, and C-9.  A format also is provided in Appendix C-10 for reporting the results of tests that compare the performance of systems.

## ISM Documentation

### Description of Modification

A Description of Modification describes the requested change to the system/project baseline.  The description establishes a foundation used to verify requirements during development and system testing.  The specific method of verifying a requirement may be deferred or changed until the design is formulated.

While documenting the description of the change and expected outcomes, consideration should be given to specific testing criteria/scenarios to be applied later in formal testing.  Stakeholders (e.g., development and test) should be involved to ensure the description is structured so that requirements are verifiable.

Consideration should be given to the following items when developing a Description of Modification:

- Identification of the change (CCD number, case file number, PTR/HDR number, etc.)

- Statement of the problem or issue being addressed

- Description of the change and expected outcomes to be generated

- Listing of equipment and human interfaces

- Any system performance parameters affected (expected results/impact)

### System/Project Development Plan

To plan and track progress throughout the lifecycle of the intended modification, a system/project development plan, or equivalent, should be documented and baselined in this phase.

Consideration should be given to the following items when developing a system/project development plan:

- Purpose and scope

- Description of Modification

- Task definition

- Lifecycle approach used to develop or maintain the system/project

- Organization roles and responsibilities

- Estimates and basis of estimates

- Schedule for the system/project (start date, milestones, review points, finish date)

- Critical computer resources

- Facilities and tools to support the project

- Risk management (assessment of risk)

- Status reporting

### Test Tool and Test Environment Specification

The tools and configurations required to test effectively are documented in the test tool and test environment specification documents.  This specification also identifies any tools that should be upgraded to support the test effort.  It is important to identify the test tools early to properly support the tests in future phases.  In addition, the test environment (including specific requirements to simulate the field environment), and lab requirements should be defined and documented.

### Development Test Activities Planned and Documented

Development Test activities planned and documented identifies test activities, resource requirements, schedules/milestones, and describes the technical and performance requirements evaluated during the “Build It” phase.  The developer is responsible for ensuring a Development Test plan is completed prior to entering the “Build It” phase of the modification.  This plan may be a stand-alone document or included as part of the system/project test plan.

Consideration should be given to the following items when planning and documenting Development Test activities:

- Task definition and scope (including Development Test plan, goals, and objectives, as well as a description of the tests to be conducted)

- Organization roles and responsibilities

- Schedule and resource needs (document in detail the rationale that validates resources needed)

- Testing tasks describing how the testing will take place and evaluation criteria (e.g., how is it determined the test is successful?) risks and contingencies

- Test deliverables (e.g., test documents and test data/results of the test)

### Failure/Discrepancy Reports

Reports are issued for all problems discovered during the “Build It” phase.  These reports can be in the form of failure reports, discrepancy reports, or the equivalent, and should include identified problems and the associated resolution.  Failures or discrepancies are tracked until dispositions are documented for each.  Any failures or discrepancies in test tool development should also be noted.  Stakeholders may be involved to determine the priority of any deferred failures or discrepancies.

Consideration should be given to the following items when developing a failure/discrepancy report:

- Project or system identification

- Requirement impacted

- Description of failure/discrepancy and associated resolution

- Severity of the problem

- Impact of the problem

### Development Test Report

At the conclusion of test activities, a Development Test report, or the equivalent, is created.  This report documents the tests performed and the results and data collected, as well as data reduction and analysis.  Any conclusions or recommendations drawn from the test data are also included in the report.  A Project/Team Lead or Manager should review the Development Test report.

Consideration should be given to the following items when creating a Development Test report:

- Modification and release identification

- Description of test conducted

- Schedule, location, and participants

- Data collection and analysis method

- Test results, conclusions, and recommendations

### System/Project Test Plan

A system/project test plan, or equivalent, contains information such as test strategies and resource requirements, as well as a description of the tests to be performed during System Test.

Consideration should be given to the following items when developing a system/project test plan:

- Task definition and scope (including system/project test goals and objectives, as well as a description of the tests to be conducted)

- Organization roles and responsibilities for test

- Schedule and staffing needs

- Testing tasks and evaluation criteria (e.g., requirements under test)

- Risks and contingencies

- Test deliverables (e.g., test documents and test data/results of the test)

### Baseline Established/Development Documentation

A baseline for the modification that incorporates changes is established at the end of the “Build It” phase.  All changes to the baseline should follow the Configuration Management practices of the respective organization.  In addition, development documentation is completed before performing System Test.  This documentation includes system documentation, such as specifications, National Airspace System Maintenance Documents, design data, plans, and any additional documentation required for the system/project.

### Develop Key Site Test Plan

If applicable, a key site test plan should be developed using defined capability criteria.  Appropriate personnel should coordinate with the appropriate organization to determine the level of testing required at the key site.  Planned activities should be documented and may include the following:

- Modification and release information

- Organization roles and responsibilities

- Schedule of activities

- An overview of modification installation procedures

- Description of tests to be conducted

- Data collection and analysis methods

### Baseline Performance/Functional Verification

The integration tests conducted in this phase include baseline performance and functional verification.  The revalidation of a system is extensive and may include the following testing:

- Performance measurements

- Computer-Human Interface/Command and Control testing

- Interface tests

- Degraded operations testing

- System stability testing

- Support system regression testing

- Verify information systems security requirements have been met

- Verify Safety Management System requirements have been met

### System/Project Release Documents

Releases that change a system/project baseline are delivered via the SSM, which should be validated prior to delivery to field sites to ensure that procedures are accurate.  The SSM template includes specifications that describe its contents and format.  The SSM template includes Appendix 1, which contains information including purpose, scope, results, and test limitations.  If Key Site Test will be performed, an SSM should be developed and re-validated at the key site prior to finalizing the SSM for national delivery.

It is recommended the following information be included (if applicable), in Appendix 1, if it is not included in the content of the SSM:

- The sequence in which to connect hardware and install software in order for the release to work properly

- Known discrepancies that are defined as problems discovered against the release and not fixed prior to delivery

- Identification of the system(s) and/or version(s) that this release was tested during System Test (e.g., DSR BCC22, DARC DVP04, CARTS R32, ARSR4, RMM XCD1046)

- Identification of the key site facility and of system(s) and/or version(s) that this release was tested during Key Site Test

- Key site lessons learned

### System/Project Test Report

At the conclusion of test activities, a system/project test report is created.  This report documents the tests performed and the results and data collected, as well as data reduction and analysis methodology.

Consideration should be given to the following items when developing a system/project test report:

- System/project and release identification

- Description of test conducted

- Schedule, location, and participants

- Data collection and analysis method

- Test results, conclusions, and recommendations

- Test limitations

### Key Site Package (if applicable)

Portions of the operational suitability test are both national and local in scope.  The appropriate organization will prepare the key site operational suitability test procedures, which should include a comprehensive, plain language description of all components of the delivery.  It should also include a description of potential operational impact derived from a review of applicable orders, directives and key site-specific procedures.  Site participation is limited to providing expertise on site procedures and directives.  The procedures could be developed independent of site personnel.

The appropriate organization should coordinate the:

- Generation and/or modification of required test plans

- Preparation and inspection of site deliverables

- Performance of a key site dry run on the key site executable deliverables

- Modification of documentation that will be coordinated and forwarded to selected key site and regional personnel (Redlined documents are forwarded if documents have not been finalized.)

- Development of a checklist of the items needed at the key site for the testing and troubleshooting of software and hardware

- Items, if not available at the key site, to be shipped prior to, or carried to, the key site facility

### Finalize Field Familiarization Plan and Generic Upgrade Schedule

The installation schedule (including test timetable, facility training requirements, necessary on-site support and IOC successes and lessons learned) from the key site is reviewed when planning for downstream implementation of the modification.

### Key Site Test Report

The development/test organization will modify its delivery documentation to include information in the fallback section of the SSM to communicate the results of all test activities.  This should include information regarding test limitations, anomalies, known degradations to ATC and maintenance, and procedures for regression to the previous operational baseline.  The development/test organization should ensure the delivery package is complete prior to release.  Ensure outstanding discrepancies/issues relative to Key Site Test are captured.  Any action items should be documented and assigned for disposition.

### Discrepancies/Issues/Actions Documented

Ensure outstanding discrepancies/issues/actions relative to the modification/release are captured.  Any action items should be documented and assigned for disposition.  All activities with status codes of yellow, red, or blue require annotation in the respective remarks column on the Gold Standard Matrix.

# Recommended Test and Evaluation Processes

This section describes recommended processes (a series of actions or operations) for performing the tests and test activities described in Sections 2.0 through 4.0.  The recommended processes should be tailored to each program and used when appropriate.

## SI System Test Planning Process

Initial System Test planning is completed in the initial Investment Analysis phase by the service organization.  This T&E planning information is documented in the ISP.  An initial VRTM also is developed at this time.  System Test planning is then developed to greater levels of detail and documented in the Development Test, OT, PAT, and SAT plans.  A recommended process for planning System Test follows:

- First, review the SLMNS, PR Attachment, Program Baseline, investment analysis documentation, and any other pertinent information relevant to the solution under consideration.

The service organization test lead, along with IOT&E (for designated programs), verifies that a set of COIs exists for the system and establishes a set of Measures of Effectiveness (MOEs) and Measures of Suitability (MOSs).  Normally, a set of six to ten COIs in the form of broad questions about the usability of the system are included by the users in the PR Attachment.  If COIs are not contained in the PR Attachment, the service organization with the mission need is contacted to provide the information and an updated PR Attachment.  The MOEs and MOSs become agreed-upon measures that, if successfully answered, formulate the basis for a positive assessment of the associated COI.  Typically, five to ten MOEs and/or MOSs are associated with each COI.  The Measures of Performance (MOPs) are thresholds associated with an MOE or MOS and are used as a measure of success.  If the MOS/MOE process is not completed in time for the initial ISP, it should be added when available and included for reference in the OT plan.

2.	A preliminary VRTM is developed during this step.  The VRTM is used to help guide high-level planning by listing all known requirements for the system and mapping them to a test that will verify each requirement.  In the process of mapping, the tester is forced to group requirements into one of the available test categories and think about how the testing can be accomplished either at a specific location and time or through certain resource constraints.  Initially, the VRTM should include all NAS requirements, including Interface Requirements Documents and Interface Control Documents, requirements from the PR Attachment (or program baseline, if applicable), MOEs/MOSs; and other OT items.  If the equipment specification is available, it may be made a part of the VRTM, or a separate specification VRTM may be referenced.  Normally, the equipment specification VRTM is verified completely during Development Test under the prime equipment contract.  The intent of the VRTM is to capture and trace the verification of all system requirements.  As more detailed requirements become known, they should be added to the VRTM.  The list of other OT items that may be included in the VRTM is gleaned from the description of the types of testing contained in an OT program as described in Section 4.0 of this guidance document.  If not already listed in the VRTM, any of the following types of items may be included:

- NAS system integration items

- Reliability

- Maintainability

- Availability

- Degraded-mode operations

- Stress and NAS loading

- Human factors evaluations

- Safety

- Site adaptation

- Security

- Transition switch-over

- Supportability

### Development Test, PAT, and SAT Planning

During the SI phase, as the program matures, a procurement package, including a statement of work and specification, is developed.  The test lead, working as part of the service organization, should coordinate the preparation of test sections for both the statement of work and the specification.  The statement of work should contain a description of contractor test activities needed to support Development Test, PAT, and SAT.  Requirements for these test activities are listed in the specification.  All items listed in the VRTM to be accomplished during Development Test, PAT, or SAT should be included in the statement of work and specification so the developer can demonstrate compliance.

### OT Planning

Requirements and OT items assigned in the VRTM to operational testing may be grouped by the test lead into manageable segments for accomplishment.  A single OT plan or multiple plans may be prepared.  The strategy should be consistent with the ISP.  Planning is tailored to each system. Test location, facilities, and resources required are program-dependent.  Early operational testing (when possible) is encouraged.  Testing in the factory or at the WJHTC should be a priority. When necessary, operational testing may be conducted at the first field site. Because the scope of operational testing includes integration testing, as well as effectiveness and suitability testing, it may be convenient to prepare the integration test plan and the effectiveness and suitability test plan separately.  Second-level maintenance, Air Traffic, and Technical Operations personnel play an important role in operational testing.  Through their involvement with and representation on the service organization, these personnel should assist and work with the test lead to plan and participate in operational tests and evaluations.

### Development Test and OT for System Modifications and P3Is

System modifications and P3Is are subject to the same kinds of testing as newly developed systems.  Because the modifications may be developed by an FAA maintenance organization and the changes may be limited in scope or contain only SW modifications, the extent of the testing and who performs the tests may be different than those for newly developed systems.  Significant modifications and P3I testing should be planned in coordination with the service organization, the test lead, and the maintenance organization.  Development Test and OT plans are recommended.  When the maintenance organization develops the modification, it is responsible for planning and implementing an appropriate test program.  P3I OT is planned by the test lead for the service organization.  This allows the service organization to assess the P3Is before it is deployed to the key site.

## SI Method for Verifying Operational Requirements

AMS policy requires that the T&E process provide for the final verification of operational readiness.  Operational readiness is the combined consideration of operational effectiveness and operational suitability.  Operational effectiveness is the degree of mission accomplishment achieved by a system when used by representative personnel in the environment reflective of its intended operational use.  Operational suitability is the degree to which a system can be used satisfactorily in the field with consideration given to availability, maintainability, safety, human factors, logistics, supportability, documentation, and training.

The goal of the FAA’s test activities is to ensure new or modified systems meet user operational needs (i.e., operational capabilities).  The two key elements of success in this process are:

- Ensuring user requirements for the new system’s operational capabilities are clearly and accurately expressed in the PR Attachment and Exhibit 300 Program Baseline.

- Ensuring these operational requirements approved by the JRC in the Exhibit 300 Program Baseline are understood, confirmed to be testable, and subsequently verified by the tester through a structured test program.

One method used by testers to verify operational requirements is the resolution of COIs.  COIs are key operational effectiveness and operational suitability issues that must be examined during operational testing to determine the system’s capability to perform its mission.  They address essential capabilities, risks, or uncertainties that must be evaluated. COIs are developed by the service organization with the mission need from mission-critical requirements and are identified in the PR Attachment.  The T&E section of the PR Attachment and Exhibit 300 Program Baseline indicates that COIs must be resolved successfully as a basis for the ISD.

### Relationship of Operational Requirements, COIs, and CPPs

COIs and CPPs are developed by the service organization with the mission need from mission-critical requirements and are documented in the PR Attachment.  Table 7.2-1 shows where COIs and CPPs are defined and the responsible organizations.

While a COI focuses on a high-level question that needs to be answered during the T&E of a system, CPPs are measurable performance parameters.  In addition to defining COIs, the service organization with the mission need also defines important quantifiable requirements in the PR Attachment as CPPs.  The T&E section of the ISP should provide a strategy for evaluating the system that will ensure the COIs are answered and all CPPs are evaluated, thereby ensuring that operational readiness will be verified.

|  | Documented In: | Author | Approval | Role of Testers |
| --- | --- | --- | --- | --- |
| COIs/CPPs | PRAttachment Exhibit 300 Program Baseline | Service organization with the mission need | Service organization with the mission need and operating service organization | Review and provide input to ensure COIs are testable |

Table 7.2-1: Where COIs and CPPs are Defined, and Who Defines Them

### Identifying Candidates for COIs

The service organization with the mission need is responsible for identifying a complete set of COIs.  All mission-critical requirements must trace to the set of COIs that is developed.  Not all COIs, however, are testable because of schedule or location conflicts.  COI development and operational requirements definition are done as part of the same process.  COIs are developed with the help of the user and test organizations to ensure the COIs are comprehensive.  The tester has a critical role in ensuring the COIs are verifiable and testable.  For most systems, the high-level requirements can be addressed by the development of six to ten COIs.  Typically, the service organization with the mission need uses the following two-step process to develop COIs:

1. 	Based upon the SLMNS, the service organization with the mission need develops questions that if answered will determine whether the system can be used within the NAS.  These COIs then are documented in the PR Attachment.  Examples of COIs include:

- Does the performance of the _________ system support existing Air Traffic Control operations?

- Can the _________ system be interfaced and used effectively with existing NAS systems?

- Does the _________ system provide an Air Traffic and Technical Operations user interface that is acceptable, fully supports existing/planned operations and maintenance, and minimizes personnel skill requirements and training?

- Is the Reliability, Maintainability, and Availability of the ____________ system suitable for incorporation into the NAS when used in an operational environment with the available resources, logistics plan, maintenance procedures, etc.?

2.	After completing an initial list of COIs, the service organization with the mission need consults with other experts to ensure the list is complete and testable.  Experts who can provide valuable input include:

- Current operational users

- Testers (to ensure the COIs are testable)

- People who have had experience procuring, testing, and fielding similar systems in the past (can provide lessons learned information)

### Verification of Operational Requirements via COI Decomposition

Resolution of a COI usually cannot be accomplished by a single test measurement. Instead, individual measurements provide answers to various sub-questions, and the resulting answers must be combined for full resolution of a COI.  Each COI, therefore, must be broken down into a set of quantifiable measures.

The tester provides an outline of his or her test program by decomposing the COIs from  the Exhibit 300 Program Baseline, first into MOEs and MOSs, and then into MOPs.  For each COI, there will be multiple MOEs/MOSs, and for each MOE/MOS there are typically multiple MOPs.  The tester’s completed COI decomposition is confirmed by the user during the test planning stage. Figure 7.2-1 illustrates the decomposition process.  MOPs that correspond to each CPP listed in the Exhibit 300 Program Baseline must also be developed.  Table 7.2-2 provides definitions of COIs, CPPs, MOEs, MOSs, and MOPs.

Figure 7.2-1: COI Decomposition

|  | Definition |
| --- | --- |
| COI | Key operational effectiveness or operational suitability issue that must be examined in operational testing to determine a product’s capability to perform its mission. |
| CPP | Performance parameters that are top-level critical requirements come directly from the Exhibit 300 Program Baseline. For each parameter a threshold and objective are stated as well. |
| MOE | First-level decomposition of an effectiveness component associated with a COI. Operational effectiveness addresses the degree to which a product accomplishes its mission when used by representative personnel in the expected operational environment. |
| MOS | First-level decomposition of a suitability component associated with a COI. Operational suitability addresses the degree to which a product intended for field use satisfies its availability, compatibility, transportability, interoperability, reliability, maintainability, safety, human factors, logistics supportability documentation, personnel, and training requirements. |
| MOP | Quantitative/qualitative values that characterize the MOEs/MOSs. These values are measurable by a test process. |

Table 7.2-2: COI, CPP, MOE, MOS, and MOP Definitions

COI decomposition is accomplished early in the planning of operational testing.  A radar system example is provided below (see Figure 7.2-3) to illustrate the COI decomposition process.  The tester’s job is to develop the MOEs, MOSs, and MOPs.  The tester works with users to reach agreement on the COI decomposition.  Figure 7.2-3 illustrates actual COIs, CPPs, MOEs, and MOPs.

Figure 7.2-3: Actual COIs, MOEs, and MOPs

Figure 7.2-3 depicts overall responsibility of the COI decomposition process.  Appendix D contains a full example of the COI decomposition for the ASR-11 program.

|  | Documented In: | Author | Agreement | Role of Service Organization |
| --- | --- | --- | --- | --- |
| MOEs MOSs MOPs | Test Plans Test Plans Test Plans | Testers Testers Testers | Users Users Users | Ensure that COI decomposition accurately reflects operational needs, via agreement with test plans |

Table 7.2-4: Overall Responsibility of COI Decomposition Process

The development and use of COIs is essential to the operational evaluation of new systems. Complete and testable COIs benefit sponsors, users, and testers.  While sponsors are responsible for COI development, tester involvement ensures COIs are testable and user involvement ensures user requirements are reflected properly.  The joint efforts of the sponsor, user, and test organizations are necessary to verify overall operational readiness.

## Key Site Selection Process

The service organization is responsible for coordinating key site selection activities.  WJHTC Integrated Engineering Services, Technical Operations, and Air Traffic will provide the service organization a description of any special capabilities needed at the key site.  Consideration will be given to other activities scheduled at the various sites to avoid conflicting resource requirements or excessive workloads.  Final selection of primary and back-up key site candidates will be communicated to all affected organizations as early as possible.  Information will be fully and freely shared with FAA staff, bargaining unit employees, and management personnel.  Selection of key site is performed in parallel with development and test, and must be completed with sufficient time to allow for preparation for key site activities.

## User Prioritization Process

Using the prioritized list and estimated timeframes and costs, a determination will be made as to which need will be packaged in the next system release and its proposed release date.  Service organizations are responsible for coordinating with appropriate users and stakeholders to weigh operational priorities in light of deployment opportunities and other agency considerations.  The result should be a complete system baseline package or project definition before proceeding to the design and development stage.  The implementing service organization identifies opportunities to deliver the changes to the operational environment.  This may result in an implementation package that contains only one change or several components, or it may entail a complete HW and SW system release.  Following the packaging process, a preliminary notification of planned changes to affected organizations will be delivered.

APPENDIX A

Best practices are fundamental principles that foster sound T&E programs.

A.1 Early Involvement of the Expanded T&E Team. Involve IOT&E and site personnel when defining the test strategy and increase coordination as development proceeds. IOT&E should be involved in all aspects of test planning and test strategy development that affect IOT&E. Field sector and air traffic managers should concur with the key site selection and with the demands that testing will place on the key site. The expanded test team should be apprised of program and schedule changes that might affect site testing, IOT&E, and Field Familiarization.

A.2 Use the WJHTC for Testing. The WJHTC has superb test and simulation facilities, experienced test personnel, and a corporate memory of FAA testing. Test at WJHTC instead of at the developer’s facilities when realistic operational environments are critical to the test. Beginning OT at WJHTC will minimize test disruptions to site operations.

A.3 Early Testing. The earlier in the acquisition management process problems are discovered the easier they are to correct, the lower the cost to correct, and the smaller the schedule impact. Transfer testing forward from the operational site to WJHTC to the developer’s facility when feasible. Increase resources for early testing until the marginal cost of additional testing equals the expected savings associated with finding problems earlier rather than later.

A.4 Coordination. Test programs for major acquisitions are extremely complex. Test program success is dependent on team coordination, even when test documents are perfectly prepared.

A.5 Contractor/FAA Relationships. The relationship between FAA and contractor personnel should be cooperative and goal-oriented rather than adversarial. Testing is adversely affected if FAA goals and contractor goals are significantly different or if organization loyalties are more important than cooperating to get the job done.

A.6 Use Software Inspections and Automated Tools to Reduce Testing Costs. It is reported that 60 to 90 percent of software defects are found through software inspection. In addition to eliminating some repetitive manual tasks, tools can promote effective dynamic analysis by guiding the selection of test data and monitoring test execution.

A.7 Testing COTS/NDI. COTS/NDI systems, like developmental systems, must satisfy NAS operational performance and suitability requirements. The greatest differences between COTS/NDI system testing and developmental system testing occur in lower-level tests where the user does not have access to COTS/NDI code, board designs, etc. Consider conducting OCDs/OCTs to stress COTS/NDI components and to demonstrate that the COTS/NDI equipment will function as expected in the NAS operational environment.

A.8 Joint Test Programs. For joint test programs to be successful, planning must start early in the acquisitionmanagement process. Mitigate differences through coordination, define roles and responsibilities, ensure that requirements are broad enough to cover all participant’s needs, and develop and use similar test strategies.

A.9 Dry Runs. All test programs significantly benefit from the performance of “dry runs” of tests/procedures prior to formal conduct.

APPENDIX B

SI Lessons Learned

B.1 Introduction

In implementing the Acquisition Management System, it is imperative the FAA build on its successes and learn from its failures. To help disseminate the FAA’s T&E experience, this appendix presents lessons learned in T&E from several FAA programs and experiences. The information is from several sources, including project reports, organizational recommendations, and recommendations from experienced personnel.  The material is grouped according to functional area.  The project, on which the experience was gained is identified at the end of the lesson, when applicable.

Experience in test and evaluation indicate the following:

B.2 General

Early testing is crucial. This best practice is reiterated as a lesson learned. It is easier and cheaper to find errors earlier than later.

Test schedules are success-oriented and do not usually include time for re-testing and regression testing. Errors will be found. Create a correction process and schedule time to deal with problems.

Don’t allow developers to perform system tests on their own system. The test team should be independent of the development team.

A system is not truly tested until it is used by its target audience in an operational setting.

Establish entry and exit criteria. Solid entry and exit criteria should be established for each phase of testing, from dry runs to test readiness review (TRR), to developmental testing, to operational testing.

Ensure thorough FAA review of all developed and commercial documentation. All documentation reviewed by the FAA should be assigned to the appropriate organization for review. For example, all documentation intended for field use should not be approved by the FAA until the end-users of the target system have thoroughly validated the contents of the documentation. This also applies to commercial documentation. (Peripheral Adapter Module Replacement Item (PAMRI))

Define a streamlined hand-off process between FAA organizations. At the end of each test phase, a formal process for the transition of the system under test to other FAA organizations must be defined. The total status of the system and its components must be accurately conveyed. This transition process must include at a minimum: system configuration, hardware and software; problem status (description, fixes in progress, fixes installed and regression tested); and documentation status. Implementation of this lesson could be in the form of a memorandum of understanding. A coordination meeting should be held between the transitioning parties one month prior to system turnover.  (PAMRI)

B.3 Human Factors

Performance measuring. Measurements of the speed and accuracy of operators and maintainers performing critical tasks on a system have proven to be a good indicator of human-system capability. This information can reduce program schedule and cost risks.

Integrating performance measures. Efficiency in testing and analysis can be achieved by integrating measures of human performance and measures of human-system effectiveness with other system performance data collection and analysis activities.

B.4 Independent Operational Test and Evaluation (IOT&E)

Use the Independent Operational Test Readiness Declaration (IOTRD). Establishing a high-level decision point for the start of IOT&E requires the developing organization to make a corporate-level decision on system readiness.

Use of the IOT&E Team and actual operators/users is critical. Using the IOT&E Team and actual operators and users in the planning, conducting, reporting, and assessment of IOT&E is critical to ensuring that operational assessments are realistic. It also facilitates a joint Technical Operations and Air Traffic decision on operational readiness.

Conduct IOT&E in an operational environment. Testing in an operational environment will verify NAS interoperability and identify specific operational deficiencies for correction by the acquisition/lifecycle maintenance organization.

Conducting IOT&E at the first operational site may not be sufficient to resolve all critical operational issues (COIs). In those cases, testing at subsequent sites or special test facilities may be required.

End-state maintenance/logistics plans need to be considered during IOT&E.

B.5 Operational Test

Involve FAA T&E organization in operational site testing prior to contract award. This involvement achieves their buy-in and ensures more successful site tests and in-service review and decision (ISRD).  (Digital Voice Recording System (DVRS))

Include vendor representative(s) in government testing. Allow a vendor representative to remain on site during government testing to provide additional training or clarification regarding the product.  (DVRS)

Classify users to aid data analysis. Consider classifying your users into the following classes: (1) Those who have worked with the program through many iterations; (2) those who have just had a “deliverable” level of training; and (3) those who have had no experience whatsoever. Interpretation of user responses to questionnaire data may need to be segregated. Maximize class 2 for legitimacy of findings.  (Voice Switching Communication System (VSCS))

Minimize test interference. Minimize parallel testing to avoid data corruption. Parallel testing is used to reduce the time required for operational testing, but it can cloud the issue of how representative of field experience the testing is. For example, VSCS tracked and reported on unplanned maintenance actions, but because fault insertion test shifts were interleaved throughout the period, VSCS was criticized for having inappropriate data points in our sample.  (VSCS)

Train the testers. For the evaluation, a high percentage of the testers should have received the most recent training package.  (VSCS)

Baseline the current field workload situation. Baseline the workload associated with the current field situation to facilitate categorizing the new system as an increase or decrease.  (VSCS)

Ensure that the test environment duplicates the operational environment. Do everything possible to have the test environment duplicate the operational environment. Do not allow extensive debug operations during the Operational Test timeframe. Declare the shift conditions (time of day, light versus heavy traffic, etc.) and make sure that decisions made by the operations personnel reflect those conditions.  (VSCS)

Schedule personnel in advance. The test schedule constantly changed, making it impossible to reliably schedule field personnel. Because the field personnel schedule needed to be established first, WJHTC personnel could not be scheduled until a day or two prior to testing.  (VSCS)

Establish and adequately train a pool of problem documenters to ensure consistency and accuracy of program trouble report (PTR) documentation. Assign at least one person from this pool to every shift to act as that shift’s lead documenter. Documenters should have strong overall knowledge of the system to facilitate communication.  (VSCS)

Vary tester responsibilities to maintain interest. Periodically change personnel responsibilities to facilitate the development of WJHTC personnel.  (VSCS)

Air Traffic and Technical Operations test teams need to communicate. Communication and coordination between Air Traffic and Technical Operations personnel is crucial to ensuring the most efficient use of personnel. At times, personnel reported for work but received no guidance or were not needed. Prior to each shift’s testing, all personnel need to be briefed on the test goals and the expected plan of action.  (VSCS)

Schedule the number of testers by need, not interest. Carefully schedule personnel, particularly during functionality testing, to match the requirements of the test. Too many or too few testers may cause distractions and inefficient use of personnel, thereby adversely affecting test completion.  (VSCS)

Avoid collocation of multiple test teams to avoid confusion. During functionality testing, multiple teams of testers occupied the same testing area but were performing different tasks. This led to confusion.  (VSCS)

Coordinate leaves of absence with testing schedule. Granting leave or returning test personnel to their facilities without coordinating with the Tech Center leads to staffing shortages. A suggested correction is for the Operational Test and Evaluation (OT&E) test lead to select a member of the OT&E test team to coordinate with the WJHTC concerning any schedule alterations.  (VSCS)

Familiarize testers with the system before writing test procedures. Hands-on familiarity with features under test facilitates test procedure preparation and test coordination. Often, WJHTC personnel must prepare testing procedures and coordinate tests (specifically functionality tests) by reading documentation explaining the feature under test. This is a difficult task, erroneous at times, which can precipitate a failure to adequately test all facets of the new feature. Developer demonstration of new features to WJHTC personnel prior to test procedure development would allow for more thorough understanding, leading to better test procedures. Formal training for test personnel should be considered.  (VSCS)

Use a laboratory reading binder. Establish a laboratory reading binder to facilitate Test Coordinator shift switchover. The oncoming Test Coordinator reviews the current status of testing prior to beginning each shift and is responsible for ensuring that all shift participants know their responsibilities. The binder might include a copy of the information delivered during the pre-test briefing as well as all approved changes and PTRs. Any amendments or additions to directives included in the binder should be signed by a designated approving authority.  (VSCS)

Involve field site personnel early in the test and development program. Early involvement of the site personnel has several major advantages:

1.	It allows earlier technical input from the system’s user community (design and operations).

2.	It provides the WJHTC personnel (development test and evaluation (DT&E) and OT&E) with the perspective of the site personnel and provides additional familiarization with using the system in the field.

3.	It allows site personnel earlier insight into system documentation.  (PAMRI)

Properly implement the problem management system. The problem management system is intended to manage the reporting, categorization, and resolution of problems identified and documented in the PTRs. Some of the lessons learned during PAMRI were:

1.	Establish and enforce problem reporting procedures. Specifically, identify all types of incidents that should be reported and explicitly specify the data to be collected and reported.

2.	Categorize and prioritize problems in a timely manner.  (PAMRI)

Schedule enough time to complete tests. The effectiveness of the display channel complex rehost (DCCR) OT&E suffered somewhat as a consequence of trying to maintain an extremely aggressive schedule. The test schedule was created so that development test and evaluation (DT&E), OT&E, and Site Acceptance Test (SAT) at the Chicago Air Route Traffic Control Center (ARTCC), and site I&I at the Fort Worth; Washington, DC; and Cleveland ARTCCs were all performed concurrently. The concurrent test activities resulted in contention for personnel and lab resources.  (DCCR)

Use an integrated test team approach. The PAMRI test team members had expertise in all major areas: hardware, software, systems engineering, human factors engineering, NAS operational procedures, maintenance procedures, and testing. Personnel were drawn from the WJHTC, the field sites, and support contractors. Using an integrated test team resulted in a comprehensive testing program with sufficient field and operational representation to instill confidence that the system met the requirements and that operational concerns were addressed and resolved prior to deployment to the first field site. This approach placed additional requirements, however, on test management. Using varied resources required additional familiarization with and training in the system, the requirements, the WJHTC laboratory, and the operational environment prior to the start of testing. Additionally, the team should be formed as early as possible and should be kept intact until all test activities are completed.  (PAMRI)

Establish a procedure for resolving critical operational issues. Operational issues became apparent during early phases as operational field personnel began to participate, but these issues were more or less ignored in order to emphasize meeting contract requirements at that time. A procedure should be established to ensure that any issues that arise are resolved by the appropriate group. Failure to do so may result in such issues becoming show-stoppers later.  (PAMRI)

Separate tapes and printouts. A problem with the PTR process was experienced during OT&E. At the beginning of OT&E testing, the PTR-related tapes and printouts were labeled and stored in the same box at the end of each day. This resulted in devoting several days to system analysis and recording (SAR) tapes to the printouts, which delayed PTR resolution.  The problem was eliminated by slotting the SAR/Core tapes in the library where they are maintained. In this manner, the software team (contractor) can access the SAR/Core tape data in order to fix the PTRs. Additionally, the problems were recorded accurately and thoroughly into a PTR database. The information indicated in the database included: the time, date, SAR and Core tape numbers, the defined problem and, the line printer listing (if available). These modifications to the PTR process proved to be extremely effective and increased productivity.  (DCCR)

B.6 Development Test (DT)

Use Comparative “Smart” Testing Between Vendors Prior to Selection.  (Digital Voice Recording System (DVRS)

Use an experienced data reduction and analysis (DR&A) team. An experienced data DR&A test team enabled better understanding of DR&A reports. This team worked several tests, which required huge amounts of data, and was able to extract important information for the test lead.  (Initial Sector Suite System (ISSS))

Emphasize test procedure success criteria. The FAA’s emphasis on test procedure success criteria for a limited number of tests resulted in thorough testing of requirements. Requirements were interpreted and agreements were made with developer counterparts on the best way to test the requirements, regardless of the verification method listed.  (ISSS)

List requirements in the test plan. Listing requirements in the test plan was very beneficial for tracking and allocating all requirements. Designating a location for testing  requirements and not allowing the location to be changed after a certain date made the requirement-tracking task manageable.  (ISSS)

Ensure FAA familiarity with the PTR database. FAA familiarity with the PTR database reduced dependence on the contractor for PTR information. It also provided insight into some of the problems with the system.  (ISSS)

Encourage and facilitate communication and interaction between the FAA and the developers. Close interaction between the contractor and FAA counterparts greatly enhanced the overall test effort. The e-mail facility among contractor personnel and housing contractor and their FAA counterparts facilitated communication.  (ISSS)

Ensure system engineering support of test. FAA test personnel often were called upon to make system engineering decisions, leading to prolonged disagreements with contractor system engineering personnel. System engineering decisions needed to be made in a more expedient fashion.  (ISSS)

Validate Log Analysis Monitor Program (LAMP) user routines in a timely manner. Late LAMP user routines (LUR) validation led to confusion during test run analysis. Some LURs were validated after use for fault detection, isolation, and recovery (FDIR) runs, while some were validated during test runs. Others did not work for FDIR. Since the LURs were validated so late, there was no time to correct them for FDIR.  (ISSS)

Useful DR&A tools are needed. There was a general lack of useful DR&A tools. The LURs were canned reports and did not provide the flexibility needed for data analysis. In some cases, huge amounts of data could not be reduced using LAMP, which limited FAA effectiveness during data analysis.  (ISSS)

List requirements text in the test procedures. This would have saved a lot of time during inspection preparation. The lack of requirements text in the test procedures required keeping the test plan on hand at all times.  (ISSS)

Avoid last minute test procedure changes. Continuous last minute test procedure script updates led to confusion during test runs. Many times, the contractor provided the procedures at the start of laboratory time, without giving the FAA counterpart enough time to review updates.  (ISSS)

Be selective in deciding which debug sessions to attend. Constant monitoring of debug runs caused FAA burnout. The FAA was requested to attend all laboratory times at all hours to monitor test progress. Often, little was accomplished, or the laboratory time was spent collecting data for PTR resolution. FAA attendance at all laboratory times may have been unnecessary.  (ISSS)

Ensure timely delivery of documents on electronic media. Long delays of document deliveries via electronic media made document review tedious, particularly requirements tracking. Confusion was created when the electronic version was delivered late and with changes that made it inconsistent with the hard copy delivered earlier.  (ISSS)

Test requirements to only the level at which they are specified. Interchanging system specifications and low-level hardware and software requirements led to confusion during requirements allocation tracking and testing.  The requirements had an improper level of detail in some cases.  (ISSS)

Follow system acquisition standards and guidelines. It is imperative to follow system acquisition standards and guidelines. In the past, the test organization wrote documents that should have been written at the beginning of the acquisition phase.  (System Support Computer Complex (SSCC-1/SSCC-3))

Identify the test bed for system support early. From the onset of system procurement, the FAA must be sure of exactly the kind of test bed needed for system support. This test bed includes facility management for monitoring test bed use and configuring it for use. It also includes the simulation architecture needed to run the test bed as a stand-alone system. As operational requirements mature, efforts must be made to derive support requirements, based on an already-published operational concept, from them.  (SSCC-1/SSCC-3)

Do not diminish the importance of installation and integration testing (I&I). I&I test procedures must be considered as important as DT&E and OT&E testing. I&I testing was lacking on this program, not only because of the reuse of possibly ineffective procedures but also because of a nebulous requirement set that applied to equipment throughout the system. All other testing will benefit from more attention to I&I testing and development of more effective I&I procedures.  (SSCC-1/SSCC-3)

Monitor deferred functionality closely. The FAA should be careful when allowing functionality to slip to further segments or partitions in the test program, because this may lead to failure to either produce the functionality or test the functionality.  (SSCC-1/SSCC-3)

Develop a transition plan. When new support systems evolve, the FAA should develop a plan for transitioning from the current system to the new system. If functionality is different, the FAA should ensure that users understand how and why.  (SSCC-1/SSCC-3)

Adequately train all test personnel on the system. The test organization needs as much or more training than the user community on whatever system is accepted, especially upfront. The system should be made accessible as early as possible, even if the software is not robust or the system is not in its end state. The test organization needs to be familiar with the system before it can be tested.  (SSCC-1/SSCC-3)

Facilitate a team effort. A DCCR Joint Test Working Group (DJTWG) was formed to facilitate a team effort. This group was composed of FAA personnel and support and prime contractor test personnel. The group held weekly meetings and all test issues, including laboratory resources, were discussed and resolved. The availability of laboratory resources needed by the DCCR program was highly constrained. En route laboratory was time-shared for testing the DCCR and the display system replacements (DSRs), and the DCCR schedule itself involved system resources time-sharing for DT&E testing and OT&E testing and training functions. During the DJTWG meetings, the conflicting requirements for laboratory resources needed by each team member were quickly resolved, accomplishments were discussed, and problems encountered during the testing were resolved. The formation of this group was very beneficial to the DCCR program.  (DCCR)

B.7 System Acceptance Testing

Use the WJHTC as the factory location.  The decision to use the WJHTC as the location to conduct factory system testing was one of the most beneficial decisions on the PAMRI test program. The benefits of this decision were earlier deployment and test in a more realistic operational environment; earlier FAA exposure to and use of the system; and elimination of one previously planned move and installation of the equipment.  (PAMRI)

Isolate test systems from operational systems.  When testing the new equipment in an operational environment, extreme care must be taken to ensure that the system under test is isolated from the operational system. During the DCCR testing at the Fort Worth ARTCC, the direct access radar channel (DARC) interface was inadvertently left connected to the Host system while DARC was being used to control air traffic. When a test scenario to test the DCCR system was run, the targets generated by the scenario were displayed not only on the DCCR plan view displays (PVDs), but also on the DARC PVDs that were being used by the air traffic controllers. When they realized that some of the targets displayed on their PVDs were not real targets, the entire system was declared non-operational. To ensure that this type of situation does not happen again, the following corrective steps were added to the DCCR site system acceptance test procedures:

1.	Connect/disconnect operational system by hardware logic.  The R-console interface module (RIM) jumpers were physically pulled to connect the available PVDs to the DCCR system. During removal of any equipment, site personnel should be present and in agreement with the procedure to be performed.

2.	Use software commands to disconnect operational system interfaces.  The Host-DARC interface was disabled at both ends.  The network management interface contractor (NMIC) disabled the DARC side of this interface, while the DCCR test team disabled the Host side of the interface.

3.	Perform a visual check of the status of all interfaces of the operational system. A printout of the status of Host interfaces was obtained and reviewed to verify that all Host interfaces, including DARC and radar, were disabled. Additionally, the use of any initialization checks should be verified between site personnel and contractors before complete system bring-up.  This will ensure that site personnel are satisfied that all critical device assignments are consistent with what is required.  (PAMRI and DCCR)

APPENDIX C

Format and Content Guidance for T&E Documents

Appendices C-1 through C-19 provide content and format guidance (templates) for 20 T&E documents that are prepared or used by the FAA.

Appendix C-1

Content and Format of FAA Operational

Test (OT) Plans

Note: The Operational Test (OT) plan forms the basis for the OT program. It describes the various planning and preparation activities required prior to the OT, the testing to be accomplished, how test procedures will be executed, and how test results will be reported. The OT plan describes the OT program to a general audience and also provides sufficient detail to guide the development of test procedures.

Title Page: The title page contains the official title of the system, the title of the test plan (e.g., “Operational Test Plan”), the signature(s) of the approving authority(ies), dates, titles, and organizations represented.

Table of Contents: The table of contents contains paragraph titles and page numbers. Illustrations, tables, and figures are listed separately.

1.0  Introduction: This section contains the following paragraphs to provide the reader with the basis for the test plan, including the system, the test program, and an overview of the plan.

1.1  Background: This paragraph presents an overview of the system/program and the overall test program.

1.2  Purpose of the Test Plan: This paragraph defines the specific purpose of the plan (for example, to describe the test program and provide a basis for development of test procedures).

1.3  Scope of the Test Plan: This paragraph identifies the segment of the test program the test plan will address.

2.0  Reference Documents: This section contains a list of the documents referenced in the test plan that direct the test program and the documents needed to implement the test program.

3.0  System Description: This section describes the system to be tested. It contains the following paragraphs.

3.1  System Overview: This paragraph contains a general system description. A block diagram of the hardware and/or software is included. The system description also summarizes the operational environment into which the unit under test will be placed. This summary includes operations concept, maintenance concept, and operational training requirements as necessary. The system description also includes operational positions affected by the unit under test.

3.2  Interfaces Overview: This paragraph provides a functional description of the system test interfaces. A list and/or block diagram of the system interfaces should be placed in this section.

4.0  Test Program Description: This section contains the following paragraphs, which describe the test program planned and the tests to be conducted.

4.1  Approach and Concept: This paragraph describes the overall approach to testing that is being applied to the specific test program. It addresses both testing and evaluation aspects of the test program.

4.1.1  Evaluation Approach: This paragraph describes the specific areas to be evaluated, the general data collection methods, and evaluation techniques. Additional details related to the evaluations will be included in paragraph 4.4.

4.1.2  Critical Operational Issues (COIs)/Test Requirement Summary: This paragraph lists COIs, with a brief discussion. COIs are the aspects of system functionality and operations that are critical to evaluation of the system's operational suitability and effectiveness. Briefly discuss the COIs and include a list of specific evaluation criteria or MOEs/MOSs. A graphic/matrix or narrative description of the relationship of COIs to MOEs and MOSs should also be included.

4.1.3  Performance Thresholds: This paragraph lists values for a particular parameter required to provide a system capability that will satisfy the validated mission need (performance threshold).

4.1.4  Activities Leading to Test: This paragraph identifies program activities that must  be accomplished prior to beginning testing addressed by the plan, including previous testing (e.g., operational capability demonstration, operational evaluations).

4.2  Test Environment: This paragraph describes the test facilities where the testing will be conducted, and the number of systems that will be tested. The descriptions should include the test locations and environmental conditions (e.g., weather, terrain) as appropriate. For example, some systems may require testing at several test locations that represent the range of environmental and operational conditions in which the system will be used.

4.2.1  Test Location(s): This paragraph describes where testing will occur. If the plan covers various test phases or different test locations, each should be described.

4.3  Test and Analysis Tools: This paragraph lists and describes the test, data reduction, and analysis tools that will be used to support the testing. These tools may include hardware tools (e.g., instrumentation, prototypes/mockups) and/or software tools (e.g., simulators, software programs).

4.4  Test and Evaluation Descriptions: This paragraph describes each test and evaluation to be conducted. Each test and evaluation description contains sufficient information to plan and develop test procedures and schedule the test activities described. The following outline describes the information to be included in each test description.

4.4.1  Test or Evaluation Title: The test description specifies the title of and a number designation for the test or evaluation.

4.4.1.1  Test or Evaluation Objectives: The test description states the OT objectives, requirements, MOEs, and MOSs that the test will verify.

4.4.1.2  Test or Evaluation Criteria: The test description defines the success criteria for each OT objective, requirement, MOE, and MOS.

4.4.1.3. Test or Evaluation Approach: The test description states the methods used to meet the test objectives and to resolve COIs. This description can include a list of the types of tasks or activities that will occur, the specific test conditions, and specific test scenarios and special operational situations that may occur in the test. The test approach should also specify estimates of the type and number of personnel, any special test equipment, and data collection methods.

4.4.1.4 Data Analysis Methods: The test description states the methods and analysis tools used to accomplish data reduction.

5.0 Test Management: This section contains the following paragraphs.

5.1 Test Management Organization. This paragraph describes the structure and composition of the test organizations and personnel responsible for carrying out the testing. This paragraph addresses the following areas:

5.1.1. Roles and Responsibilities: Identifies the various organizations and personnel that will conduct and support the testing.

5.1.2 Other Participating Organizations: Describes specific roles and responsibilities (for example, the use of operational user teams as test subjects or test observers).

5.1.3 OT Working Group: This paragraph describes the OT Working Group (if it has been formed) and its role, and identifies its members by number of personnel and organization.

5.1.4 Test Conduct Team(s): This paragraph describes the positions and duties of test team(s) that will conduct the tests. The organizations represented on the test team should be defined (for example, Test Manager will be an active field representative).

5.2 Training: This paragraph describes the range and level of training and familiarization needed to develop test procedures and execute tests. This paragraph addresses the following training areas.

5.2.1 Test Developer Training: This paragraph describes the type of knowledge (system and operational) that the test developers need, and where and when they obtain it.

5.2.2 Test Participant Training: This paragraph describes the type of knowledge (system and operational) that the test participants need according to their various roles (e.g., test subject, observer, DR&A). For example, test subjects for operational testing should receive training that represents the training operators will receive to perform their jobs with the new system.

5.2.3 Special Training Requirements: This paragraph describes any special knowledge needed by the test team(s) (e.g., familiarization with the test program and the test facility, use of special test tool(s)).

5.3 System Configuration Management: This paragraph describes the methods for ensuring the system under test is consistent (e.g., configuration audits). This paragraph identifies how changes to the baseline system (audited system) will be controlled.

5.3.1 Testbed Configuration: This paragraph describes the configuration of the testbed, if a testbed is used in place of an operational site. The paragraph describes the extent of the testbed configuration audit (hardware line replacement unit (LRU) by part number/serial number, revision level, software by version, and build date) and when the audit will be conducted in relation to test schedule. This paragraph describes how closely the testbed represents the actual, intended operational environment. For example, some testing may be performed using simulators and other drivers, and may not include actual interfaces and external equipment.

5.4 OT Entry Criteria: This paragraph describes a list of the items and conditions, such as planned project milestones, that must be met before testing can begin. This description should include the limitations on the effectiveness of the testing if these conditions are not met. (Note: A test procedure should include more specific test readiness criteria.)

5.5 Test Execution: This paragraph describes the process for conducting a test session. It should include a description of the pre-test and post-test briefings and when they will occur relative to the test. Also, the specific criteria for proceeding with a test (e.g., test procedures dry run and red-lined, required training completed) and the procedures for conducting individual tests should be included, as well as general criteria which warrant a re-test.

5.6 OT Exit Criteria: This paragraph describes the measures/metrics or other conditions that must be met before a series of tests are complete and/or a test program is complete and has met its objectives. The completion criteria may include factors beyond the control of the testing organization (e.g., schedule deadlines). (Note: A test procedure should include more specific completion criteria (e.g., success criteria).)

5.7 OT Reports: This section identifies the type of test report, its contents, when it will be published, to whom it will be distributed.

5.8 System/Operational Deficiency Reports: This paragraph describes the process of recording, tracking, and correcting deficiencies experienced during OT.

5.9 OT Schedule: This paragraph contains a testing schedule, to the detail known at the time of test plan development. The test schedule is presented as a GANTT chart, and includes other development/acquisition activities and milestones as appropriate to indicate interdependencies.

5.10 Personnel Resource Requirements: This paragraph describes the personnel needed for each phase of testing. The description includes operational positions required and the skills associated with each position, the role of individual test personnel; the organizations supplying the personnel; and the time periods that personnel will be requested for. This information should be presented in a table.

5.11 Planning Considerations and Limitations: This paragraph describes factors that may affect full achievement of the testing concepts and goals. Any known limitations to achieving complete resolution of test requirements (e.g., lack of true realism due to simulation rather than live operations) should be described. This paragraph defines the planned work-arounds and resolution to known limitations. This paragraph also discusses critical interface issues and/or interfaces that will not be available/tested.

6.0  Acronyms and Glossary: This section lists acronyms and definitions peculiar to the test plan/program.

Appendices: Appendices may be added to the test plan, as appropriate, to provide detailed information. The appendices will be identified sequentially, starting with the letter A.

VRTM: This appendix includes the COI OT requirements and NAS-SS-1000 requirements. The VRTM will indicate the specific tests (at the level described in the test plan) where each requirement is being addressed.

Appendix C-2

Content and Format of Operational Test (OT) Procedures

Title Page: The title page contains the official name of the system, the title of the test to be accomplished and the words “OT Procedures.” The title page contains the signature of the approving authority, date, title, and organization represented.

Table of Contents: The table of contents contains paragraph titles and page numbers. Illustrations, tables, and figures are listed separately.

1.0  Introduction: This section provides an overview and brief description of testing to be accomplished.

2.0  Reference Documents: This section contains all reference documents used in the development of the Test Procedure.

3.0  Test Description: This section describes the unit under test and how it will be placed in its operational environment. (This section is based on the system description presented in the OT plan.)  Any known variations from the system to be fielded shall be noted. This section contains the following paragraphs.

3.1  Test Overview: This paragraph contains a general system description. A block diagram of the hardware and/or software will be included. The system description also summarizes the operational environment into which the unit under test will be placed. This summary includes operations concept, maintenance concept, and operational training requirements as necessary. The system description also includes operational positions affected by the unit under test.

3.2  Interfaces: This paragraph describes how the interfaces of the unit under test are to physically and functionally perform.

4.0  Test Program Description: This section is a summary of the Test Program as presented in the OT plan.

5.0  Test Management: This section contains the following paragraphs.

5.1  Test Director: This paragraph defines the test director's roles and responsibilities in conducting the test.

5.2  Coordination: This paragraph describes the coordination required prior to, during, and after testing.

5.3  Deviations: This paragraph defines any deviations from the OT plan. This paragraph addresses what effect the deviations will have in meeting the test objectives/requirements.

5.4  Data Elements: This paragraph provides a summary and definition of all data elements to be collected during the test. (Note: The data elements must support the validation of the OT objectives/requirements listed in the test description of the OT plan.)

5.5  Data Base Design and Structure: This paragraph provides a description of the architectural structure of the database containing the electronically recorded test data that will be used to evaluate the system.

Appendix: This Appendix is labeled Test Procedures and contains the detailed individual test procedures. Each individual test procedure is a self-contained information packet that provides all the information necessary for the tester to set up, conduct, and collect data from the test.

Individual test procedures are written in small logical units of work to facilitate resumption of testing after scheduled or unscheduled interruptions with a minimum of reconfiguration.

The minimum requirements for the contents of individual test procedures include:

a.	Title. A unique test procedure identification, which is preferably based on a numbering convention used in the Test Plan. Identification may be based upon test (or requirement) series, category, subcategory, or other alpha-numeric designation.

b.	Test Objectives. Detailed objectives of this particular test procedure. Reference the OT objective(s)/requirement(s) being evaluated by this test procedures.

c.	Initial Set up/Configuration. State the initial conditions that must be present prior to the start of the test. Examples include: operational software and/or hardware levels, hardware configuration, environmental conditions, and normal or degraded conditions. This section may be in the form of a checklist, if desired.

d. 	Test Personnel Requirements. List types, number, and skill levels of test participants required to execute the test, include any demographics as applicable. State the type, number, and skill levels of test monitors and test support personnel required.

e. 	Test Support Hardware, Software, and Documentation. List the test support hardware, software, and documentation required to execute the test. In addition, list any operational, procedural, or reference manuals required by the test participants (i.e., maintainers, operators, controllers, etc.) during conduct of this test procedure.

f.	Evaluation Criteria. Identify the standards used to judge the achievement of operational effectiveness and suitability as they relate to a level of performance against which system characteristics are compared. Identify the data required to satisfy the requirement: for example, two false detections per hour of test scenario.

g.	Procedures. The test procedures will be written in detailed step-by-step instructions. Step-by-step procedures for conducting the test will be provided. These procedures include all test actions, sequences of actions, and the proper responses to the actions. Test events will be described in the order in which they are planned to occur, with dependency of any one event on another indicated. Test responses/outputs with specified allowable tolerances will be indicated.

Test procedures shall contain the following information:

1.	Each step will have an action step with the expected response to the action.

2.	Exceptions to action steps will be instructions to the tester, which will be defined as such.

3.	Test procedure steps that validate requirements will list the criteria and all requirements verified by the procedure.

4.	Test procedures will be written in logical units of work to facilitate resumption of testing after scheduled or unscheduled interruptions of testing.

5.	Each action with an expected response will contain an initial block for the test director and/or his or her representative.

6.	Each test and/or sub-test contains a sign-off sheet for the test director.

h.	Data Collection, Recording, and Reduction. Describe how data will be collected recorded, and reduced for processing. Identify the forms, formats, equipment, procedures, and resources to be used in gathering test data. For example, data collection personnel will record false detections on a data collection form and will attach these data collection forms to the test procedures. Completed forms will be collected at the end of the day and keyed into the central database during the second shift so they will be available for review and analysis the following day.

i.	Analysis Methods. Describe how the data will be displayed and analyzed to lead to evaluation of the MOPs/MOEs and COIs. For example, the mean false detections per hour will be displayed in a diagram, figure, etc., used to support data and/or results.

Appendix C-3

Content and Format of Operational Test (OT) Reports

Title Page: The title page contains the official name of the system, the name of the document, the signature of the approving authority, date, title, and organization represented.

Executive Summary: This section briefly summarizes the OT Report, and explains the OT and significant results for a management audience. The Executive Summary includes background information on the system under test, test type, purpose, location and date, highlights of the results, significant conclusions, and significant recommendations.

Table of Contents: The table of contents contains paragraph titles and page numbers. Illustrations, table and figures are listed separately.

1.0 Introduction: This section contains the following paragraphs and provides the background information necessary for understanding the OT Report.

1.1 Purpose of Report: This paragraph states the purpose of the OT Report.

1.2 Scope of Report: This paragraph briefly summarizes the contents and arrangement of the report.

2.0 Reference Documents: This section contains all reference documents used in the development of the Test Report.

3.0 System Description: This section contains the following paragraphs.

3.1 Mission Review: This paragraph briefly summarizes the system mission and functions and their relationship to the NAS.

3.2 Test System Configuration: This paragraph includes a description of the NAS subsystem, including hardware and software, that was tested, as opposed to the expected operational system. A full description of any software and hardware changes made during testing will be presented. All of the descriptions included in this paragraph will be detailed enough so that anyone with the proper technical background, but without previous knowledge of the system, will have a complete understanding of how the system operates and any constraints under which it was tested.

3.3 Interfaces: This paragraph describes all NAS interfaces applicable to the tested system. Describe the status of each interface in reference to the test (i.e., actual interface used, simulated by, deferred, not available, etc.).

4.0 Test & Evaluation Description: This section contains the following paragraphs, which provide details of how the test was conducted for each test (Test Number One .... Test N).

4.1 Test Number One:

4.1.1 Test Objectives/Criteria: This paragraph describes the test objectives/criteria validated (as described in the test descriptions contained in the test plan) and follow-through to the test results and conclusions sections.

4.1.2 Testing Descriptions/Schedules and Locations/Participants: This paragraph identifies the Test Descriptions (as outlined in the test plan) and or sub-tests completed. This paragraph gives the reader a picture of how the test was structured. Within each test description “critical test” issues are addressed. This paragraph contains all dates and locations pertinent to the test. This paragraph lists all participants and the functions they performed.

4.1.3 Data Collection and Analysis Method: This paragraph explains how the test data were obtained and what methods of analysis were used to obtain the results. The explanation of the analyses methods will be in sufficient detail so that a person with adequate technical background can use the raw data to produce the same results.

4.1.4 Results/Discussion: This section documents the data collected during the test and the analyses that were performed to yield the final results. (If the volume of results is too large to include in the report it will be referenced.)  Trouble reports that were generated and how the problems were resolved are discussed. COIs, MOEs, MOSs and RD/NAS requirements and their resolution will be discussed in the results. Sufficient summary tables of actual collected or analyzed information will be included in the report to provide full backup for the report’s conclusions and recommendations. As the results are presented they will be discussed relative to test requirements and test objectives presented in the test plan. Any testing that had to be deferred will be addressed along with the reason for the deferral.

4.1.5 Conclusions: This section states facts and conclusions that logically flow from, and can be supported by, the specific results. Highlight the significant conclusion supported by the specific results. Highlight the significant capabilities, advantages, and shortcomings of the system. Note which COIs have been addressed by this test and if the COI has been adequately addressed and resolved. Indicate if regression testing will be necessary, the requirements to be re-tested, the impact on the test program, and where the regression testing will take place.

4.2 Test Number Two .........Test Number N:

4.2.1 Test Objective/Criteria:

4.2.2 Testing Description:

4.2.3 Data Collection and Analysis Method:

4.2.4 Results/Discussion:

4.2.5 Conclusions:

5.0 Summary of Conclusions: This section summarizes the conclusions for each of the individual tests as detailed in paragraph 4.0.

6.0 Recommendations: This section states recommendations in the same order they are discussed in paragraph 4.2.6, Conclusions. Make sure that recommendations logically follow from the results and conclusions. Discuss details or risks/benefits.

Appendix C-4

Content and Format of Quick Look Reports

Quick Look Reports: Quick look reports are provided to the Service Team within 10 to 15 calendar days following completion of the test. It is recognized that data analysis will not be complete and a full test report can not be provided because of the short turnaround. The quick look report provides management with a brief background on the test; a summary of test activities, including the test article configuration; the significant test results that are known at the time; and a preliminary test result synopsis or conclusions. At a minimum, the following sections from an OT Report format will be included:

1.0 Introduction:

2.0 Test and Evaluation Description:

3.0 Results and Discussion:

4.0 Synopsis/Conclusions:

5.0 Recommendations:

A matrix containing the following information may be used to summarize test results:

OT ISSUES MATRIX

| Sequence Number | Criticality | Description of Issues | Proposed Solution |
| --- | --- | --- | --- |

CRITICALITY: 	Low–Minimum risk or impact that can be fixed in a routine manner

Medium–Significant risk but can be worked around on a temporary basis

High–Mission critical risk, must be fixed prior to deployment

Appendix C-5

Content and Format of

Development Test (DT) and

Production Acceptance Test (PAT) Plans

Note: The DT plan format will be tailored to the type of test and/or phase of testing required by contract (production acceptance, site acceptance, factory acceptance, software, system, etc.).

Title Page: The title page contains the name of the program and the type of test plan (software test plan, site acceptance test plan). The title page contains the signatures of the program manager, the test program manager, and the quality assurance manager. The title page is signed by all managers before the test plan is submitted for review.

Executive Summary: The Executive Summary starts on a new page. The Executive Summary contains an overview of the test plan, which includes: the test plan's relationship to the overall test program, the relationship of the test plan to contract requirements, and significant system or program information considered important to completing the tests outlined in the test plan.

Table of Contents: The table of contents contains paragraph titles and page numbers. It lists each test description. Illustrations, tables, and figures are listed separately.

1.0 Introduction: This section is divided into the following paragraphs.

1.1 Purpose: The following statement, in its entirety, will be included in the introduction: "The purpose of this test plan is to validate requirements assigned to this phase of testing required by ________________________ (enter contract system specification number) for the _________________(enter official system title and contract number). This test plan documents _______________(enter contractor's company name) test strategy in order to meet the requirements of the contract."

1.2 Scope: This paragraph provides an overview of the strategy for validating requirements assigned to the phase of testing covered by the test plan. The paragraph generally describes the tests to be accomplished, location of testing, the systematic arrangement of testing, and includes all subcontractor testing, when applicable.

2.0 Reference Documents: This section contains all reference documents used in the development of the test plan, including all requirements documents listed or referenced in the system specification and contract.

3.0 System Description: This section will be divided into the following paragraphs.

3.1 System: This paragraph describes the systems/subsystems to be tested and their major functions. The paragraph also contains a functional block diagram of the system and subsystems.

3.2 Interfaces: This paragraph contains a simplified block diagram with a functional description of each interface. The paragraph includes facility interfaces, remote maintenance monitoring interface, voice communications interface, operator interface, and any interface required to validate the system specification requirements.

4.0 Test Program Management: This section will be divided into the following paragraphs.

4.1 Management: This paragraph describes the contractor's management responsibilities for the testing phase by test plan. This paragraph includes an organizational chart with names of individuals responsible for each department and/or subcontractor participating in the test program.

4.2 Schedule: This paragraph includes a test schedule integrated with program milestones. The schedule identifies all tests to be accomplished.

5.0 Test Configuration Management: This section identifies the specific configuration management process for each unit under test.

6.0 Discrepancy Reporting and Corrective Action. This section describes the Discrepancy Reporting and Corrective Action program that supports the test program. The Discrepancy Reporting and Corrective Action forms and instructions for completing those forms are included in this section.

Test Descriptions: This section contains test descriptions for each test to be conducted under this test plan. The test descriptions are attached as Appendix A of this plan.

The test descriptions contain sufficient information to allow the preparation of the test procedures for the test described. The following outline describes the minimum information to be included in each test description:

a.	Test or Evaluation Title: Specify the title of the test/evaluation and a number designation.

b.	Test or Evaluation Objectives: List the objectives/requirements the test will validate and test success criteria.

c.	Test or Evaluation Approach: State the methods to be used to meet the test objectives.

d.	Execution Time: Estimate the total time it will take to execute the test(s) described, including multiple runs of a test procedure.

e.	Location: Identify the testing location.

f.	Tasks/Activities: List tasks or activities that will occur during the test.

g.	Personnel: Identify number and type of personnel required to accomplish the test.

h.	Test Equipment: Identify all test equipment (hardware and software) required to accomplish the test. Define any analysis tools that will be used to support the test.

i.	Data Reduction/Analysis: Describe the test data reduction method, in relation to the Test Equipment identified in item h that will support the test. Identify any data analysis that will be associated with the test. The contractor describes the data expected, when and how the data will be processed, and how the data supports verification of the requirement.

j.	Special Conditions: Describe any special test conditions, test scenarios, or special operating conditions required to accomplish the test.

Appendix C-6

Content and Format of Development Test (DT) and Performance Acceptance Test (PAT) Procedures

Note: The DT/PAT Test Procedure format is tailored to the type of test, and/or phase of testing required by contract (production acceptance, site acceptance, factory acceptance, software, system, etc.).

Title Page: The title page contains the name of the program and the words “Test Procedure for ___________________ (enter the specific test name and test identifier).”  The title page contains the signature of the program manager, the test manager, and the quality assurance manager. The title page must be signed prior to submission for review.

Table of Contents: The table of contents contains each test and/or subtest and its test identifier with associated paragraph titles and page numbers. Illustrations, tables, and figures are listed separately.

1.0 Introduction: This section is divided into the following paragraphs.

1.1 Purpose: This paragraph includes the following statement in its entirety: "The purpose of this test procedure is to validate the requirements of _________________ (enter contract system specification number) assigned to this test procedure, for the __________________ (enter official system title and contract number). This test procedures documents ____________________ (enter contractor's company name) test strategy in order to verify the requirements of the contract."

1.2 Scope: This paragraph provides an overview/brief description of the test to be accomplished. This paragraph describes in general terms the type of test to be accomplished by this procedure and how the test relates to the overall test program.

2.0 Reference Documents: This section contains all requirements documents used in the development of the test procedure.

3.0 Test Description: This section will be divided into the following paragraphs.

3.1 System Under Test: This paragraph describes the systems/subsystems under test and includes a functional block diagram of the system and subsystems.

3.2 Interface Under Test: This paragraph contains a simplified block diagram with a functional description for each interface under test.

3.3 Test Setup: This paragraph contains a detailed block diagram of the test interfaces and setup. The diagram and text include all connection points, test points, and controls. All test equipment will be identified on the diagram with connection points.

3.4 Test Equipment: This paragraph contains a list of all test equipment required in the procedure, by manufacturer and part number; and includes an area to record serial number and calibration date. All test equipment functions will be defined.

3.5 Personnel: This paragraph identifies the personnel required to run the test (i.e., engineers, technicians, quality assurance personnel, test director, etc.).

3.6 Location: This paragraph identifies the location(s) where each test event related to the test procedure will occur.

Schedule: Schedule information is presented in relation to other program events. The schedule identifies a Test Readiness Review, test duration, and test debriefing time.

4.0 Test Conduct: This section is divided into the following paragraphs.

4.1 Safety Considerations: This paragraph provides a compilation of unique hazards anticipated. This paragraph includes any safety procedures to be followed, personal limits, protective equipment to be used, and authorities to be notified for each test. It also identifies a responsible test team member (safety officer) with authority to terminate testing.

4.2 Requirements Under Test: This paragraph lists all requirements under test by document name, paragraph number, and test.

4.3 Procedures: (Note: This section may be attached as an Appendix, if numerous procedures are required.)  The test procedures will be written as detailed step-by-step instructions. Test procedures contain the following information:

a.	Each step has an action step with the expected response to the action.

b.	An exception to action steps is instructions to the tester, which will be defined as such.

c.	Test procedure steps that validate requirements list the criteria and all requirements verified by the procedure.

d.	Test procedures are written in logical units of work to facilitate resumption of testing after scheduled or unscheduled interruptions of testing.

e.	Each action with an expected response contains an initial block for the government test director and/or government witness.

f.	Each test and/or sub-test contains a sign-off sheet for the government test director and the contractor's test director.

4.4 Test Data Reduction and Analysis: The requirements and procedures for the reduction and analysis of test data are provided in this paragraph. Data to be recorded during the test, manually or automatically, are specified. Requirements for data recording and reduction are specified in a manner and detail such that the resulting information will clearly indicate whether or not the requirements have been met.

Appendix C-7

Content and Format of Development Test (DT) and Performance Acceptance Test (PAT) Reports

Note: The DT/PAT Test Report format is tailored to the type of test, and/or phase of testing required by contract (production acceptance site acceptance, factory acceptance, software, system, etc.).

Title Page: The title page contains the official name of the system, and the words "Test Report for_______________________" (enter the specific test and test identifier)” The title page contains the signature of the program manager and signatures of those responsible (e.g., Program Manager, Test Manager, and Quality Assurance Manager). The title page must be signed by all responsible prior to submittal for government review.

Test Summary: The Test Summary starts on a new page. The Test Summary contains a brief description of the test and the status of each requirement tested. The Test Summary describes any testing deferred and provides justification for deferral.

Table of Contents: The table of contents contains all major section headings.

1.1 Test Conduct: This paragraph contains a summary of test procedure changes that occurred during the test. Changes to procedures that will be used in future tests are incorporated prior to the next scheduled test. This paragraph defines the schedule and method of incorporating identified changes. It identifies test set-up changes or system configuration changes that occurred during the test and presents the rationale for the changes.

1.2 Participants: This paragraph contains the names of all participants and the functions they performed.

1.3 Data Collection and Analysis: This section explains how test data were collected and method of analysis used to obtain results.

2.0 Test Log: This section contains a copy of the actual test log developed during the test. Any discrepancy reports filed during the test and supporting data and documents developed during the test are attached to the test log.

3.0 Test Procedures: This section contains a copy of the test procedures used during the test. Each test procedure is signed by the government representative who witnessed the test.

Appendix C-8

Content and Format of Field Familiarization

Test Plans

Note: The Field Familiarization test plan is initially developed by the key site and utilized or tailored as required by subsequent sites. It describes the various planning and preparation activities required prior to testing. The plan describes the test activities and sufficient detail to guide the development of test procedures.

Title Page: The title page contains the official title of the system, the title of the test plan, the key site identification and the signature(s) of the approving authority(ies), dates, titles, and organizations represented.

Table of Contents: The table of contents contains paragraph titles and page numbers.  Illustrations, tables, and figures are listed separately.

1.0 Introduction: This section contains the following paragraphs to provide the reader with the basis for the test plan, including the system, the test program, and an overview of the plan.

1.1 Background: This paragraph presents an overview of the system/program and the overall program.

1.2 Purpose of the Test Plan: This paragraph defines the specific purpose of the plan (e.g., to describe the test program and provide a basis for development of test procedures).

1.3 Scope of the Test Plan: This paragraph identifies the segment of the test program the test plan will address.

2.0 Reference Documents: This section contains a list of the documents referenced in the test plan that directs or supports test activities and the documents needed to transition to IOC.

3.0 System Description: This section describes the system to be tested.  It contains the following paragraphs.

3.1 System Overview: This paragraph contains a general system description.  A block diagram of the hardware and/or software is included.  The system description also summarizes the operational environment into which the unit under test will be placed.  This summary includes operations concept, maintenance concept, and operational training requirements as necessary.  The system description also includes operational positions affected by the unit under test.

3.2 Interfaces Overview: This paragraph provides a functional description of the system test interfaces.  A list and/or block diagram of the system interfaces should be placed in this section.

4.0 Test Program Description: This section contains the following paragraphs, which describe the test activities planned and the tests to be conducted.

4.1 Approach and Concept: This section describes the overall approach to testing that is being applied to the specific test program.  It addresses both testing and evaluation aspects of the test program.  Test procedure sources and test procedure development plans should be described.

4.2 Entrance Criteria: This section lists and describes the required milestones, environmental requirements, documentation and logistical requirements that are needed prior to starting Field Familiarization at the site.

4.3 Exit Criteria: This section lists and describes the required activities, milestones and test result necessary to transition from Field Familiarization into IOC.

4.3 Test Tools and Environment: This section lists and describes the test, data reduction, and analysis tools that will be used to support the testing.  These tools may include hardware tools (e.g., instrumentation, H/W drivers, analyzers) and/or software tools (e.g., simulators, software programs).  Support software, site adaptation and simulation build required for test and evaluation should be itemized and described.  Various site NAS system configurations required and approve to safely support all site Field Familiarization test activities should be described and detailed.

4.4 Test and Evaluation Descriptions: This paragraph describes each test and evaluation to be conducted.  Each test and evaluation description contains sufficient information to plan and develop test procedures and schedule the activities described.  The following outline describes the information to be included in each test description.

4.4.1 Test or Evaluation Title: The test description specifies the title of and a number designation for the test or evaluation.

4.4.1.1 Test or Evaluation Objectives: The test description states the Field Familiarization objectives, requirements, and site operational conditions or scenarios to be addressed.  Each objective should have associated success criteria described.

4.4.1.3 Test and Evaluation Approach: The test description states the methods used to meet the test objectives.  This description can include a list of the types of tasks or activities that will occur, the specific test conditions, and specific test scenarios and special operational situations that may occur in the test.  The test approach should also specify estimates of the type and number of personnel, the number of test iterations, any special test equipment, and data collection methods.

4.4.1.4 Data Analysis Methods: The test description states the methods and analysis tools used to accomplish data reduction.

5.0 Test Management: This section contains the following paragraphs.

5.1 Test Management Organization. This paragraph describes the structure and composition of the test organizations and personnel responsible for carrying out the testing.  This paragraph addresses the following areas:

5.1.1. Roles and Responsibilities: Identifies the various organizations and personnel that will conduct and support the testing.

5.1.2 Other Participating Organizations: Describes specific roles and responsibilities (e.g., the use of operational user teams as test subjects or test observers).

5.1.3 Test Conduct Team(s): This paragraph describes the positions and duties of test team(s) that will conduct the tests.  The organizations represented on the test team should be defined (for example, Test Manager will be an active field representative).

5.2 Training: This section describes the training plan needed to meet Field Familiarization, IOC and ORD requirements.

5.3 System Configuration Management: This section describes the methods for ensuring the system under test is consistent (e.g., configuration audits).  This paragraph identifies how changes to the baseline system (audited system) will be controlled.

5.4 Test Execution: This paragraph describes the process for conducting a test session. It should include a description of the pre-test and post-test briefings and when they will occur relative to the test.  Also, the specific criteria for proceeding with a test (e.g., test procedures dry run and red-lined, required training completed) and the procedures for conducting individual tests should be included, as well as general criteria which warrant a re-test.

5.5 Field Familiarization Reports: This section identifies the type of test report, its contents, when it will be published, to whom it will be distributed.

5.6 System/Operational Deficiency Reports: This paragraph describes the process of recording, tracking, and correcting deficiencies experienced during Field Familiarization.

5.7 Field Familiarization Schedule: This paragraph contains a testing schedule, to the detailknown at the time of test plan development.  The test schedule is presented as a GANTT chart, and includes other development/acquisition activities and milestones as appropriate to indicate interdependencies.

5.8 Personnel Resource Requirements: This paragraph describes the personnel needed for each phase of testing.  The description includes operational positions required and the skills associated with each position, the role of individual test personnel; the organizations supplying the personnel; and the time periods that personnel will be requested for.  This information should be presented in a table.

5.9 Planning Considerations and Limitations: This paragraph describes factors that may affect full achievement of the testing concepts and goals.  Any known limitations to achieving complete resolution of test requirements (e.g., lack of true realism due to simulation rather than live operations) should be described.  This paragraph defines the planned workarounds and resolution to known limitations.  This paragraph also discusses critical interface issues and/or interfaces that will not be available/tested.

6.0 Acronyms and Glossary: This section lists acronyms and definitions peculiar to the test plan/program.

Appendices: Appendices may be added to the test plan, as appropriate, to provide detailed information.  The appendices will be identified sequentially, starting with the letter A.

Appendix C-9

Format Requirements For

Field Familiarization Test Reports

1.0  Introduction: This section describes the purpose of the report and a brief description of the NAS subsystem under test.

2.0  Summary: This section summarizes the Field Familiarization report.  The summary includes overall test results, including significant PTRs.  The Technical Operations and Air Traffic test directors IOC recommendation is contained in this section.

3.0  Transition Tests: This section briefly describes the transition test results.  Significant PTRs are described, and their current status is noted.

4.0  Maintenance Tests: This section briefly describes the maintenance test results.  Significant PTRs are described, and their current status is noted.

5.0  Certification Tests: This section briefly describes the certification test results.  Significant PTRs are described, and their current status is noted.

6.0  Failure Mode Tests: This section briefly describes the failure mode test results.  Significant PTRs are described, and their current status is noted.

7.0  Operational Tests: This section briefly describes the Operational Test results.  Significant PTRs are described, and their current status is noted.

8.0  PTR Summary: All PTRs opened during Field Familiarization test are summarized, and their current status is noted.

Appendix C-10

Content and Format of

System Performance Analysis Reports

Note: Performance measurement usually involves a comparison between two systems.  Ideally, the same workload scenario is run under the same conditions against the operational baseline system and the updated baseline.  Performance parameters are recorded, analyzed and compared. Significant differences in performance are explained in the report.

Title Page: The title page contains the document title, system name and version, date of report completion, and the title of the organization that developed the report.

Executive Summary: This section briefly summarizes the test report and explains significant results for a management audience.  The Executive Summary includes background information for the system under test, test type, purpose, location and date, highlights of the results, significant conclusions, and significant recommendations.

Table of Contents: The table of contents contains paragraph titles and page numbers. Illustrations, tables, and figures are listed separately.  The contents of this report template were derived from a test report on the Central Computer Complex Host (CCCH) system performance.  The contents of this report should be tailored to the system under test.

1.0 Stress Scenario Description: This section summarizes the simulation scenario used.  The name, duration, and unique features of the scenario(s) should be described.

1.1 Results, Conclusions, and Recommendations: Results, conclusions and recommendations are generally reported in terms of specific performance parameters that may vary depending on the system under test.  This section contains any general information that applies to all parameters. Example paragraphs for this section include the following:

1.1.1 Central Processor Unit Utilization (CPU): This paragraph quantifies the load applied against the system and the performance response of the central processor.  Notable differences between systems are explained.  Supporting data is presented in graphical or tabular form.  For example, in the CCCH, the number of aircraft tracked quantifies the system load. Data Reduction and Analysis tools provide detailed information about CPU utilization.  The total amount of CPU utilization is reported as a percentage (maximum usage = 100 percent).  This total is then broken down to account for application software, the operating system, interrupts, and on-line recording tool overhead.  If possible, differences in CPU utilization should be provided for individual program elements that were added to or changed in the updated system.

1.1.2 Memory Utilization: This paragraph quantifies and compares the utilization of system memory for each system tested.  Notable differences between systems are explained. Supporting data is presented in graphical or tabular form.

1.1.3 Message Response Times: This paragraph quantifies and compares how much time each system takes to respond to user input messages.  The definition of the message response should be provided or referred to.  Notable differences in response times between systems should be explained.  Supporting data is presented in graphical or tabular form.

1.1.4 Direct Access Storage Device Utilization: This paragraph quantifies and compares utilization of storage devices such as direct access storage devices (DASDs), hard drives, etc.  Notable differences between systems should be explained.  Supporting data is presented in graphical or tabular form.

1.1.5 Buffer Space Availability: This paragraph quantifies and compares the amount of free system memory (buffer space).  Notable differences between systems should be explained. Supporting data is presented in graphical or tabular form.

Appendix A System Description: This appendix describes the systems tested.  Version numbers or names are provided, and the test environment is described in terms of enabled functions, disabled functions, and enabled on-line recording tools.

Appendix B Analysis Description: This appendix summarizes the processes used to collect, analyze, and report system performance.

Appendix C Performance Measurement Procedures: This section describes the procedures used to conduct performance measurement testing.  Any deviations from the referenced standard procedures are noted.

Appendix D Applicable Documents: This appendix lists any documents referenced in the report.

Appendix C-11

Sample IOTRD Format

1.0 Test Status:

1.1 Report the status of DT and OT tests: The expected status is that all developmental testing and operational testing has been completed.

1.2 Summarize the results of DT and OT tests: Typically the summary states that tests indicate that the system is ready for approval at the In-Service Decision milestone.

1.3 Provide references to and distribution information about test reports that contain additional information about DT and OT test results: A representative entry might be that DT reports and Quick Look OT reports have been completed and distributed to the FAE, the Office of IOT&E, and all test participants.

2.0 System Status:

2.1 Summary of Open PTRs: Summarize the open PTRs, their significance (type) and their impact on system performance and system effectiveness.  Identify any PTRs, which will not be closed before the beginning of IOT&E.  Identify any limitations that the open PTRs might impose on IOT&E testing.  Attach a PTR closure plan to the IOTRD.

2.2 System Stability Description: Describe the stability of the system in terms of configuration management and baselining. A typical statement might be: “System hardware, software and specifications are baselined and under the configuration control of the _______ CCB.”

3.0 IOT&E Prerequisite Status: Provide the status of each IOT&E prerequisite detailed in the T&E section of the ISP, and the proposed work around if it is not ready/available.

3.1 Equipment Support status for the unit under test: Describe the supply support and availability of manuals for the system under test.  A typical equipment support statement might be: “Spares for all FAA maintained equipment are on site and the logistics center will maintain a two years supply of spares to the LRU. Leased equipment will be maintained by the ________ Company.  Hardware Technical Manuals, and Operator Handbooks have been delivered to the site and verified.”

3.2 Training Status: Describe the training that has been given to the test team.  A representative statement would be: “Personnel who will operate and maintain the system during IOT&E have received training, which is representative of the training that will be given to operational personnel.”

4.0 Test resource requirements: Describe service organization test resource requirements and certify that those resources will be available.

5.0 Recommendation: Clearly state the recommendation and any less than ideal conditions associated with the recommendation.  (e.g., The system is ready for IOT&E and we recommend proceeding with these test before the PTRs identified in 2.1 are closed.)

6.0 Exceptions: Identify and describe any exceptions to the readiness of the system for IOT&E.  Describe the operational impact of the exception(s) and the justification for proceeding with an IOTRD with the exception(s).

Recommendation of Readiness:		Signed, Implementing Service Organization Lead

Declaration of Readiness:			Signed, Service Unit Vice President

Appendix C-12

Content and Format of

Contractor Master Test Plan (CMTP)

Note: The CMTP format will be tailored to the type of test program required by contract.

Title Page: The title page contains the name of the program and the words “Contractor’s Master Test Plan.”  The title page contains the signatures of the program manager, the test program manager, and the quality assurance manager.  The title page is signed by all managers before the test plan is submitted for review.

Table of Contents: The table of contents contains paragraph titles and page numbers.  It lists each test description. Illustrations, tables, and figures are listed separately.

1.0 Introduction: This section is divided into the following paragraphs.

1.1 Purpose: The following statement will be included in the introduction: “The purpose of this test plan is to validate requirements in system specification _____________ (enter contract system specification number) for the _____________(enter official system title and contract number).  This CMTP documents _____________(enter contractor's company name) test program strategy in order to meet the requirements of the contract.”

1.2 Scope: This paragraph describes the amount and type of testing to be performed, any limitations imposed, and indicates the amount of test data from prior testing that is proposed for use in verifying requirements.

2.0 Reference Documents: This section contains all reference documents used in the development of the CMTP, including all requirements documents listed or referenced in the system specification and contract.

3.0 System Description: This section will be divided into the following paragraphs.

3.1 System: This paragraph describes the system(s) to be tested, and included the major functions of subsystems.  The contractor also provides a functional block diagram of the system and subsystems.

3.2 Interfaces: This paragraph contains a simplified system block diagram with a functional description of each interface.  This includes any interface required to validate the system specification requirements (e.g., facility interfaces, remote maintenance monitoring interface, voice communications interface, operator interface).

4.0 Test Program Description: This section will be divided into the following paragraphs.

4.1 Management: This paragraph describes the contractor's management responsibilities for the test program.  This includes an organizational chart with names of individuals responsible for each department and/or subcontractor(s) participating in the test program.

4.2 Test Identification: This paragraph shall list all tests to be accomplished in the contractor’s test program, both specification required and any other contractor tests.  Tests shall be labeled with a unique identifier for ease and consistency of reference throughout the test program.

4.3 Subordinate Test Plans: This paragraph identifies all the appropriate test plan(s)  that will further detail each test referenced in paragraph 4.2 (above).  All critical functionalities and test criteria required to complete each test are itemized.  The contractors identify all subordinate test plans required in order to meet the requirements of the contract.  This includes unit/module level software and hardware test plans, inspection plans (e.g., sub-First Article), subordinate reliability plans (e.g., for screenings, failure analysis, etc., if required by contract).

4.4 Integrated Schedule. This paragraph contains the test program integrated schedule.  The integrated schedule contains major contract milestones and test program milestones that show how the contractor intends to meet the contract schedule.

4.5 Configuration Management (CM) on Unit Under Test: This paragraph describes how the software and hardware configurations of each unit under test will be controlled in the context of each specification, etc. test.  The contractor shall also describe the methods and personnel to be employed for the production, certification, and control of test software that is planned for these tests. (The CM plan may be referenced if applicable.)

4.6 Problem Reporting and Resolution: This paragraph describes the failure/problem identification, reporting, and resolution process.  It also identifies the documentation to be used in this process.  This paragraph also describes the roll of the Quality organization and CM in the resolution process. (The SOW and/or CM plan may be referenced if applicable.)

5.0 Verification Requirements Traceability: A single matrix will be constructed in accordance with the attributes of the VRTM (Appendix C-8), which addresses the broad test methods to be employed for each contract requirement.  The matrix is based upon the System Specification, contract, and other subordinate requirements deemed appropriate for the testing program.  The VRTM shall:

1. Clearly itemize the method of test (I, A, D, or T) for each specification requirement, and,

2. Clearly identify the specification test (e.g., Section 4.0) to which each specification requirement shall be allocated for testing and which DT test plan documents the verification of the particular requirement.

Each specification requirement shall be allocated to at least one, specification defined test category.  Upon Government approval, the VRTM shall be changed only with the approval of the FAA.

Appendix C-13

Content and Format of

Development Test Plan (ISM)

Title Page: The title page contains the official title of the system, the title “Development Test Plan,” the signature(s) of the approving authority or authorities, the version of the document, organization represented and dates.

Table of Contents: The table of contents contains paragraph titles and page numbers.  It lists each test description.  Illustrations, tables, and figures are listed separately.

1.0 Introduction: This section contains the purpose and scope of the Development Test plan.

1.1 Purpose: The following statement, in its entirety, is included in the introduction: “The purpose of this test plan is to validate requirements assigned to this phase of testing for the _________________(enter official system title or contract number).  This test plan documents _______________(enter AOS routing or contractor's company name) test strategy in order to meet the requirements of the customer.”

1.2 Scope and Task Definition: This section documents the parameters or extent of the Development Test plan.  It should include a list of the system(s) to be tested, all tasks and the overall goals and objectives.

2.0 Organization Roles & Responsibilities: This section identifies the participants and their responsibilities.  Identifying all resources necessary to manage, design, prepare, execute, witness, check and resolve all development test objectives.

3.0 Training (Optional): This section describes the range and level of training and familiarization needed to develop test procedures and execute tests.  This paragraph details the type of knowledge the participants need to complete the tasks outlined in their roles and responsibilities.  It also clarifies where and when the training is to take place.

4.0 Schedule and Staffing Needs: This section includes a detailed schedule of all test milestones, an estimation of time and staffing needs required to perform each testing task.

5.0 Entry & Exit Criteria: This section outlines the entry and exit criteria for the Development Test plan.

5.1 Entry Criteria: This paragraph describes a list of items and conditions that must be met before testing can begin.

5.2 Exit Criteria: This paragraph describes the measures/metrics or other conditions that must be met before testing is complete and has met its objectives.

6.0 System Process Description: This section describes the system under test, the test setup, the test equipment, and the test location.

6.1 System Under Test: This paragraph describes the system(s) under test.

6.2 Test Setup: This paragraph contains a detailed diagram of the test configuration, interfaces, and setup.

6.3 Test Equipment: This paragraph contains a list of all test equipment required in the procedure.  All test equipment functions are defined.

6.4 Locations: This paragraph identifies the location(s) where each test event related to the test procedure occurs.

7.0 Testing Tasks & Evaluation Criteria: This section contains those requirements under test, the procedures and testing tasks involved, risks and contingencies, and deliverables.

7.1 Requirements Under Test: This paragraph contains all technical and functional requirements under test.

7.2 Procedures: The test procedures are written as detailed step-by-step instructions or tasks.  Test tasks may vary depending on the type of testing being done.

7.3 Risks and Contingencies: This paragraph identifies the probable risks associated with the System Test plan and a contingency plan for resolution.

7.4 Test Deliverables: This paragraph outlines those deliverables that are expected and how it is determined that the test is successful.

8.0 Acronyms and Glossary: This section lists acronyms and definitions.

Appendices: Appendices may be added to the Development Test plan as appropriate, to provide detail information.  The appendices are identified sequentially, starting with the letter A.

Appendix C-14

Content and Format of

Failure Reports For ISM

Title Page: The title page contains the official name of the system, the title “Failure Report,” the version of the document, organizations represented and date.

Change History: Includes the version, file name, description of change, author of change and date.

Table of Contents: The table of contents contains paragraph titles and page numbers. Illustrations, tables and figures are listed separately.

1.0 Introduction: This section contains the following paragraphs and provides the background information necessary for understanding the Failure Report.

1.1 Purpose of Report: This paragraph states the purpose of the Failure Report.

1.2 Scope of Report: This paragraph briefly summarizes the contents and arrangement of the report.

2.0 Organization Roles & Responsibilities: This paragraph contains the names of all participants and the functions they performed.

3.0 Project or System Identification: This paragraph provides an overview of the project or system under test.

4.0 Severity of the Problem: This paragraph describes the problem and summarizes the level of impact it has on the project or system.  It identifies fatal errors, where the system or component is unable to function and those test results that are fault tolerant.

5.0 Description of Failure: This paragraph defines the failure.  It details the conditions that were present when the failure occurred and a point-by-point description as to what happened.  It provides information describing the physical or functional manifestation of a failure and describes the ratio of the number of failures of a given category to a given unit of measure.

6.0 Resolution and Responsible Organization: This paragraph documents the resolution needed to resolve the failure and the organization responsible for resolving the problem.

7.0 Outstanding Problems: This section outlines the existing problems and the impact they have on the next phase of the life cycle.  It also lists the concerns with the test tools or test environment.

8.0 Acronyms and Glossary: This section lists acronyms and definitions peculiar to the test plan/program.

Appendices: Appendices may be added to the Failure Report, as appropriate, to provide detailed information.  The appendices are identified sequentially, starting with the letter A.

Appendix C-15

Content and Format of

Development Test Report for ISM

Title Page: The title page contains the official name of the system, and the words "Test Report for_______________________" (enter the specific test and test identifier)  The title page contains the signature of the branch manager and signatures of those responsible.  The version of the document and the date must also be noted.

Change History: Includes the version, file name, description of change, author of change and date.

Table of Contents: The table of contents contains paragraph titles and page numbers.  Illustrations, tables and figures are listed separately.

1.0 Introduction: This section contains the following paragraphs and provides the background information necessary for understanding the Development Test Report.

1.1 Purpose of Report: This paragraph states the purpose of the Development Test Report.

1.2 Scope of Report: This paragraph briefly summarizes the contents and arrangement of the report.

2.0 Organization Roles & Responsibilities: This paragraph contains the names of all participants and the functions they performed.

3.0 System Description: This section contains the following paragraphs.

3.1 Mission Review: This paragraph briefly summarizes the system mission and functions and their relationship to the change.

3.2 Test System Configuration: This paragraph includes a description of the subsystem, including hardware and software, that was tested, as opposed to the expected operational system.  A full description of any software and hardware changes made during testing is presented.  All of the descriptions included in this paragraph are detailed enough so that anyone with the proper technical background, but without previous knowledge of the system, has a complete understanding of how the system operates and any constraints under which it was tested.

3.3 Interfaces: This paragraph describes all interfaces applicable to the tested system.  Describe the status of each interface in reference to the test (actual interface used, simulated by, deferred, not available, etc.).

4.0 Test & Evaluation Description: This section contains the following paragraphs, which provide details of how the test was conducted for each test (Test Number One ... Test N).

4.1 Test Number One:

4.1.1 Test Objectives/Criteria: This paragraph describes the test objectives/criteria validated (as described in the test descriptions contained in the test plan) and follow-through to the test results and conclusions sections.

4.1.2 Testing Descriptions/Schedules and Locations/Participants: This paragraph identifies the Test Descriptions (as outlined in the test plan) and or sub-tests completed.  This paragraph gives the reader a picture of how the test was structured.  Within each test description “critical test” issues are addressed.  This paragraph contains all dates and locations pertinent to the test.  This paragraph lists all participants and the functions they performed.

4.1.3 Data Collection and Analysis Method: This paragraph explains how the test data were obtained and what methods of analysis were used to obtain the results.  The explanations of the analysis methods are in sufficient detail so that a person with adequate technical background can use the raw data to produce the same results.

4.1.4 Results/Discussion: This section documents the data collected during the test and the analyses that were performed to yield the final results.  (If the volume of results is too large to include in the report it is referenced.)  Trouble reports that were generated and how the problems were resolved are discussed.  Sufficient summary tables of actual collected or analyzed information is included in the report to provide full backup for the report’s conclusions and recommendations.  As the results are presented they are discussed relative to test requirements and test objectives presented in the test plan.  Any testing that had to be deferred is addressed along with the reason for the deferral.

4.1.5 Conclusions: This section states facts and conclusions that logically flow from, and can be supported by, the specific results.  Highlight the significant conclusion supported by the specific results.  Highlight the significant capabilities, advantages, and shortcomings of the system.  Indicate if regression testing is necessary, the requirements to be re-tested, the impact on the test program, and where the regression testing is taking place.

4.2 Test Number Two ... Test Number N:

4.2.1 Test Objectives/Criteria:

4.2.2 Testing Description:

4.2.3 Data Collection and Analysis Method:

4.2.4 Results/Discussion:

4.2.5 Conclusions:

5.0 Summary of Conclusions: This section summarizes the conclusions for each of the individual tests as detailed in paragraph 4.0.

6.0 Recommendations: This section states recommendations in the same order they are discussed in paragraph 4.1.5, 4.2.5, etc. (Conclusions).  Make sure that recommendations logically follow from the results and conclusions.  Discuss details or risks/benefits.

7.0 Acronyms and Glossary: This section lists acronyms and definitions peculiar to the test plan/program.

Appendices: Appendices may be added to the test report, as appropriate, to provide detailed information.  The appendices are identified sequentially, starting with letter A.

Appendix C-16

Content and Format of

System Test Plan for ISM

Title Page: The title page contains the official title of the system, the title “System Test Plan,” the signature(s) of the approving authority or authorities, the version of the document, organization represented and dates.

Change History: Includes the version, file name, description of change, author of change and date.

Table of Contents: The table of contents contains paragraph titles and page numbers. Illustrations, tables, and figures are listed separately.

1.0 Introduction: This section contains the purpose and scope of the System Test plan.

1.1 Purpose: This paragraph describes the purpose of the System Test plan.  The System Test plan is designed to determine, to the greatest extent possible, the operation of the system in a simulated environment.  It defines/describes the tasks to be accomplished, including background information where applicable.

1.2 Scope and Task Definition: This section documents the parameters or extent of the System Test plan.  It should include a list of the system(s) to be tested, all tasks and the overall goals and objectives.

2.0 Organization Roles & Responsibilities: This section identifies the participants and their responsibilities.  Identifying all resources necessary to manage, design, prepare, execute, witness, check and resolve all system test objectives.

3.0 Training (Optional): This section describes the range and level of training and familiarization needed to develop test procedures and execute tests.  This paragraph details the type of knowledge the participants need to complete the tasks outlined in their roles & responsibilities.  It also clarifies where and when the training is taking place.

4.0 Schedule and Staffing Needs: This section includes a detailed schedule of all test milestones, an estimation of time and staffing needs required to perform each testing task.

5.0 Entry & Exit Criteria: This section outlines the entry and exit criteria for the System Test plan.

5.1 Entry Criteria: This paragraph describes a list of items and conditions that must be met before testing can begin.

5.2 Exit Criteria: This paragraph describes the measures/metrics or other conditions that must be met before system testing is complete and has met its objectives.

6.0 System Process Description: This section describes the system under test, the test setup, the test equipment, and the test location.

6.1 System Under Test: This paragraph describes the system(s) under test.

6.2 Test Setup: This paragraph contains a detailed diagram of the test interfaces and setup.

6.3 Test Equipment: This paragraph contains a list of all test equipment required in the procedure. All test equipment functions are defined.

6.4 Locations: This paragraph identifies the location(s) where each test event related to the test procedure occurs.

7.0 Testing Tasks & Evaluation Criteria: This section contains those requirements under test, the procedures and testing tasks involved, risks and contingencies, and deliverables.

7.1 Requirements Under Test: This paragraph contains all technical and functional requirements under test.

7.2 Procedures: The test procedures are written as detailed step-by-step instructions or tasks. Test tasks may vary depending on the type of testing being done.

7.3 Risks and Contingencies: This paragraph identifies the probable risks associated to the System Test plan and a contingency plan for resolution.

7.4 Test Deliverables: This paragraph outlines those deliverables that are expected and how successful completion is determined.

8.0 Acronyms and Glossary: This section lists acronyms and definitions.

Appendices: Appendices may be added to the System Test plan as appropriate, to provide detail information. The appendices are identified sequentially, starting with the letter A.

Appendix C-17

Content and Format of

System Test Report for ISM

Title Page: The title page contains the official name of the system, and the words "Test Report for_______________________" (enter the specific test and test identifier)” The title page contains the signature of the program manager and signatures of those responsible.  The title page must be signed by all responsible prior to submittal for government review.  The version of the document and the date must also be noted.

Table of Contents: The table of contents contains paragraph titles and page numbers. Illustrations, tables and figures are listed separately.

1.0 Introduction: This section contains the following paragraphs and provides the background information necessary for understanding the System Test Report.

1.1 Purpose of Report: This paragraph states the purpose of the System Test Report.

1.2 Scope of Report: This paragraph briefly summarizes the contents and arrangement of the report.

2.0 Organization Roles & Responsibilities: This paragraph contains the names of all participants and the functions they performed.

3.0 System Description: This section contains the following paragraphs.

3.1 Mission Review: This paragraph briefly summarizes the system mission and functions and their relationship to the change.

3.2 Test System Configuration: This paragraph includes a description of the subsystem, including hardware and software that was tested, as opposed to the expected operational system.  A full description of any software and hardware changes made during testing is being presented.  All of the descriptions included in this paragraph are detailed enough so that anyone with the proper technical background, but without previous knowledge of the system, has a complete understanding of how the system operates and any constraints under which it was tested.

3.3 Interfaces: This paragraph describes all interfaces applicable to the tested system. Describe the status of each interface in reference to the test (actual interface used, simulated by, deferred, not available, etc.).

4.0 Test & Evaluation Description: This section contains the following paragraphs, which provide details of how the test was conducted for each test (Test Number One ... Test N).

4.1 Test Number One:

4.1.1 Test Objectives/Criteria: This paragraph describes the test objectives/criteria validated (as described in the test descriptions contained in the test plan) and follow-through to the test results and conclusions sections.

4.1.2 Testing Descriptions/Schedules and Locations/Participants: This paragraph identifies the Test Descriptions (as outlined in the test plan) and or sub-tests completed.  This paragraph gives the reader a picture of how the test was structured.  Within each test description “critical test” issues are addressed.  This paragraph contains all dates and locations pertinent to the test.  This paragraph lists all participants and the functions they performed.

4.1.3 Data Collection and Analysis Method: This paragraph explains how the test data were obtained and what methods of analysis were used to obtain the results.  The explanation of the analysis methods is in sufficient detail so that a person with adequate technical background can use the raw data to produce the same results.

4.1.4 Results/Discussion: This section documents the data collected during the test and the analyses that were performed to yield the final results.  (If the volume of results is too large to include in the report it is referenced.)  Trouble reports that were generated and how the problems were resolved are discussed.  Sufficient summary tables of actual collected or analyzed information is included in the report to provide full backup for the report’s conclusions and recommendations.  As the results are presented they are discussed relative to test requirements and test objectives presented in the test plan.  Any testing that had to be deferred is addressed along with the reason for the deferral.

4.1.5 Conclusions: This section states facts and conclusions that logically flow from, and can be supported by, the specific results.  Highlight the significant conclusion supported by the specific results.  Highlight the significant capabilities, advantages, and shortcomings of the system. Indicate if regression testing is necessary, the requirements to be re-tested, the impact on the test program, and where the regression testing is taking place.

4.2 Test Number Two ... Test Number N:

4.2.1 Test Objective/Criteria:

4.2.2 Testing Description:

4.2.3 Data Collection and Analysis Method:

4.2.4 Results/Discussion:

4.2.5 Conclusions:

5.0 Summary of Conclusions: This section summarizes the conclusions for each of the individual tests as detailed in paragraph 4.0.

6.0 Recommendations: This section states recommendations in the same order they are discussed in paragraph 4.2.6, Conclusions.  Make sure that recommendations logically follow from the results and conclusions.  Discuss details or risks/benefits.

7.0 Acronyms and Glossary: This section lists acronyms and definitions peculiar to the test plan/program.

Appendices: Appendices may be added to the test report, as appropriate, to provide detailed information.  The appendices are identified sequentially, starting with the letter A.

Appendix C-18

Content and Format of

Key Site Test Plan for ISM

Title Page: The title page contains the official title of the system, the title “Key Site Test Plan,” the signature(s) of the approving authority or authorities, the version of the document, organization represented and dates.

Change History: Includes the version, file name, description of change, author of change and date.

Table of Contents: The table of contents contains paragraph titles and page numbers. Illustrations, tables, and figures are listed separately.

1.0 Introduction: This section includes the purpose and scope of the Key Site Test plan.

1.1 Purpose: This paragraph includes the purpose of the Key Site Test plan. The purpose is to verify that the field releases meet the user needs. It is performed in the actual environment where the equipment is used and all interfaces available. The key site is also used to verify requirements that cannot be fully evaluated during system test.

1.2 Scope and Task Definition: This section documents the parameters or extent of the Key Site Test plan. It should include a list of the system(s) to be tested, all tasks and the overall goals and objectives.

2.0 Organization Roles & Responsibilities: This section identifies the participants and their responsibilities. Identify all resources necessary to manage, design, prepare, execute, witness, check and resolve all Key Site Test objectives.

3.0 Training (Optional): This section describes the range and level of training and familiarization needed to develop test procedures and execute tests. This paragraph details the type of knowledge the participants need to complete the tasks outlined in their roles & responsibilities. It also clarifies where and when the training is taking place.

4.0 Schedule and Staffing Needs: This section includes a detailed schedule of all test milestones, an estimation of time and staffing needs required to perform each testing task.

5.0 Entry & Exit Criteria: This section outlines the entry and exit criteria for the Key Site Test plan.

5.1 Entry Criteria: This paragraph describes a list of items and conditions that must be met before testing can begin.

5.2 Exit Criteria: This paragraph describes the measures/metrics or other conditions that must be met before key site testing is complete and has met its objectives.

6.0 System Process Description: This section describes the system under test, the test setup, the test equipment, and the test location.

6.1 System Under Test: This paragraph describes the system(s) under test.

6.2 Test Setup: This paragraph contains a detail diagram of the test interfaces and setup.

6.3 Test Equipment: This paragraph contains a list of all test equipment required in the procedure. All test equipment functions are defined.

6.4 Locations: This paragraph identifies the location(s) where each test event related to the test procedure occurs.

7.0 Testing Tasks & Evaluation Criteria: This section contains those requirements under test, the procedures and testing tasks involved, risks and contingencies, and deliverables.

7.1 Requirements Under Test: This paragraph contains all technical and functional requirements under test.

7.2 Procedures: The test procedures are written as detailed step-by-step instructions or tasks. Test tasks may vary depending on the type of testing being done.

7.3 Risks and Contingencies: This paragraph identifies the probable risks associated with the Key Site Test plan and a contingency plan for resolution.

7.4 Test Deliverables: This paragraph outlines those deliverables that are expected.

8.0 Acronyms and Glossary: This section lists acronyms and definitions.

Appendices: Appendices may be added to the Key Site Test plan as appropriate, to provide detail information.  The appendices are identified sequentially, starting with the letter A.

Appendix C-19

Content and Format of

Key Site Test Report for ISM

Title Page: The title page contains the official name of the system, and the words “Test Report for_______________________” (enter the specific test and test identifier) The title page contains the signature of the program manager and signatures of those responsible.  The title page must be signed by all responsible prior to submittal for government review.  The version of the document and the date must also be noted.

Change History: Includes the version, file name, description of change, author of change and date.

Table of Contents: The table of contents contains paragraph titles and page numbers. Illustrations, tables and figures are listed separately.

1.0 Introduction: This section contains the following paragraphs and provides the background information necessary for understanding the Key Site Test Report.

1.1 Purpose of Report: This paragraph states the purpose of the Key Site Test Report.

1.2 Scope of Report: This paragraph briefly summarizes the contents and arrangement of the report.

2.0 Organization Roles & Responsibilities: This paragraph contains the names of all participants and the functions they performed.

3.0 System Description: This section contains the following paragraphs.

3.1 Mission Review: This paragraph briefly summarizes the system mission and functions and their relationship to the change.

3.2 Test System Configuration: This paragraph includes a description of the subsystem, including hardware and software that was tested, as opposed to the expected operational system. A full description of any software and hardware changes made during testing is presented.  All of the descriptions included in this paragraph are detailed enough so that anyone with the proper technical background, but without previous knowledge of the system, has a complete understanding of how the system operates and any constraints under which it was tested.

3.3 Interfaces: This paragraph describes all interfaces applicable to the tested system. Describe the status of each interface in reference to the test (actual interface used, simulated by, deferred, not available, etc.).

4.0 Test & Evaluation Description: This section contains the following paragraphs, which provide details of how the test was conducted for each test (Test Number One ... Test N).

4.1 Test Number One:

4.1.1 Test Objectives/Criteria: This paragraph describes the test objectives/criteria validated (as described in the test descriptions contained in the test plan) and follow-through to the test results and conclusions sections.

4.1.2 Testing Descriptions/Schedules and Locations/Participants: This paragraph identifies the Test Descriptions (as outlined in the test plan) and or sub-tests completed.  This paragraph gives the reader a picture of how the test was structured.  Within each test description “critical test” issues are addressed.  This paragraph contains all dates and locations pertinent to the test.  This paragraph lists all participants and the functions they performed.

4.1.3 Data Collection and Analysis Method: This paragraph explains how the test data were obtained and what methods of analysis were used to obtain the results.  The explanation of the analysis methods is in sufficient detail so that a person with adequate technical background can use the raw data to produce the same results.

4.1.4 Results/Discussion: This section documents the data collected during the test and the analyses that were performed to yield the final results.  (If the volume of results is too large to include in the report, it is referenced.)  Trouble reports that were generated and how the problems were resolved are discussed.  Sufficient summary tables of actual collected or analyzed information is included in the report to provide full backup for the report’s conclusions and recommendations.  As the results are presented they are discussed relative to test requirements and test objectives presented in the test plan.  Any testing that had to be deferred is addressed along with the reason for the deferral.

4.1.5 Conclusions: This section states facts and conclusions that logically flow from, and can be supported by, the specific results.  Highlight the significant conclusion supported by the specific results.  Highlight the significant capabilities, advantages, and shortcomings of the system. Indicate if regression testing is necessary, the requirements to be re-tested, the impact on the test program, and where the regression testing is taking place.

4.2 Test Number Two ... Test Number N:

4.2.1 Test Objective/Criteria:

4.2.2 Testing Description:

4.2.3 Data Collection and Analysis Method:

4.2.4 Results/Discussion:

4.2.5 Conclusions:

5.0 Summary of Conclusions: This section summarizes the conclusions for each of the individual tests as detailed in paragraph 4.0.

6.0 Recommendations: This section states recommendations in the same order they are discussed in paragraph 4.1.5, 4.2.5, etc. (Conclusions).  Make sure that recommendations logically follow from the results and conclusions.  Discuss details or risks/benefits.

7.0 Acronyms and Glossary: This section lists acronyms and definitions peculiar to the test plan/program.

Appendices: Appendices may be added to the test report, as appropriate, to provide detailed information.  The appendices are identified sequentially, starting with the letter A.

APPENDIX D

ASR-11 COI Example

COI 1.0 Coverage

Does the DASR/ASR-11 performance and coverage volume support air traffic control operations?

MOE 1.1 Radar Coverage: Does the DASR/ASR-11 radar coverage volume support air traffic control operations?

MOP 1.1.1 Radar Altitude Coverage: 0 to 24,000 ft AGL.

MOP 1.1.2 Radar Azimuth Coverage: 0 to 360 degrees.

MOP 1.1.3 Radar Range Coverage: 0.5 to 55 nm (Cont: 0.5 to 60 nm).

MOP 1.1.4 Radar Elevation Coverage: 0 to 30 degrees.

MOP 1.1.5 Target Speed: 25 to 700 knots.

MOP 1.1.6 Probability of Detection: The ASR-11 will detect 1.0 meter squared RCS Swerling 1 target to a range of 55 nmi (Contract says 60 nmi) in the clear and at the nose of the main beam with a single scan probability of detection of 0.8 at a Probability of false alarm of 10-6: (Contract additionally requires) Pfa of 10-6 over 92% of the radial velocities between -700 to +700 knots.

MOE 1.2 Beacon Coverage: Does the beacon coverage meet the requirements of the air traffic controller?

MOP 1.2.1 Beacon Altitude Coverage: 0 to 60,000 feet.

MOP 1.2.2 Beacon Elevation Angle Coverage: 0.5 to 40 degrees.

MOP 1.2.3 Beacon Azimuth Coverage: 0 to 360 degrees.

MOP 1.2.4 Beacon Range Coverage: 0.5 to 60 nmi or 0.5 to 120 nmi slant range on site selectable basis.

MOP 1.2.4 Beacon Code Validity:

a)	Validated 95% of the time when 4 or more replies are received per mode.

b)	Be correct at least 99% of the time in the presence of FRUIT as specified in 3.2.2.4., and  c) have validation of incorrect codes due to FRUIT or other causes less than 1% of the time.

MOP 1.2.5 Beacon Code Reliability: 0.995 minimum for targets with a round reliability of 0.75 with three-fourths of the modes responding, in a steadystate condition of 10,000 ATCRBS and 200 Mode-S false-replies unsynchronized-in-time (FRUIT) per second, of which 30% are in the main beam.

MOE 1.3 Radar/Beacon Capacity: Is the capacity of the ASR-11 radar and beacon sufficient to support the requirements of the air traffic controller?

MOP 1.3.1: Radar/Beacon Capacity:

a)	700 real aircraft targets in any mix of PSR only, PSR/SSR merge, or SSR only targets, in the presence of an additional 300 false PSR targets and 100 false SSR reports, uniformly or non-uniformly distributed in azimuth for a 360-degree scan, and not be impacted by weather channel processing.

b)	A peak of 250 targets uniformly distributed in a 90-degree sector.

c)	A peak of 100 targets uniformly distributed across two 11.25-degree sectors.

d)	A peak of 16 targets per 1.3-degree wedge lasting for not more than two contiguous wedges.

MOP 1.3.2 Target Overload Processing: When the target load exceeds the capacity defined in paragraph 3.4.1, the ASR-11 shall have a internal processing capable of automatically decreasing the number of reports. In severe overloading cases, the ASR-11 should incrementally reduce processor maximum range on primary targets in order to ensure maintaining the performance requirements on beacon targets. When the overload condition clears, full reporting of all targets out to maximum slant range should be restored.

MOE 1.4 Radar/Beacon Reinforcement: Is the radar reinforcement of beacon targets sufficient to meet the requirements of the air traffic controller?

MOP 1.4.1 Radar Reinforcement Rate:

a)	The ASR-11 will merge SSR (case a and case b) and PSR target reports when the same aircraft target is detected by both radars. The PSR and SSR targets should be successfully merged 98% of the time.

b)	The ASR-11 will provide the following site-selectable sources for range and azimuth position data for merged target reports,

1)	Range and azimuth of the SSR target, and

2)	Range and azimuth of the PSR target.

MOE 1.5 Radar/Beacon Data Timeliness: Is the radar/beacon target data sufficiently timely to meet the requirements of the air traffic controller?

MOP 1.5.1 Radar/Beacon Target Data Timeliness: A data delay of less than 2.0 seconds under all conditions.

COI 2.0 False Alarm Rate

Does the number and distribution of false target reports from the ASR-11 allow reliable aircraft detection, identification, and tracking consistent with the air traffic control mission and airspace requirements?

MOE 2.1 Radar False Alarm Rate: Is the radar false alarm rate sufficiently low to support the requirements of the air traffic controller?

MOP 2.1.1 Radar False Alarm Rate:

a)	No more than one false scan-to-scan correlated search report per scan averaged over fifteen minutes under normal clutter conditions. Normal clutter conditions include thermal noise, terrain, stationery discrete, sea, and distributed rain.

b)	No more than 10 false scan-to-scan correlated search reports per scan averaged over 10 scans when the clutter environment exceeds normal conditions. Excessive clutter conditions include surface vehicles, anomalous propagation, angels, and cellular rain.

MOP 2.1.2 Radar Target Split Rate: No greater than 1% for targets having an SNR greater than or equal to 20 dB.

MOE 2.2 Beacon False Alarm Rate: Is the beacon false alarm rate sufficiently low to support the requirements of the air traffic controller?

MOP 2.2.1 Beacon False Alarm Rate: No more than one false beacon report per scan resulting from steady state FRUIT and no more than one as a result of reflections of the main beam.

MOP 2.2.2 Beacon Target Split Rate: No more than one split beacon target report per scan when averaged over 15 minutes.

COI 3.0 Aircraft Separation

Does the ASR-11 detect closely spaced aircraft with sufficient reliability to allow the controller to maintain separation standards?

MOE 3.1 Radar Accuracy: Is the radar sufficiently accurate in reporting the position of the aircraft to support the air traffic controller?

MOP 3.1.1 Radar Range Accuracy: 275 feet

MOP 3.1.2 Radar Azimuth Accuracy: 0.16 degrees

MOE 3.2 Radar Resolution: Is the radar resolution capability to resolve two closely spaced aircraft sufficient to support air traffic controller requirements?

MOP 3.2.1 Radar Range Resolution: 0.125 nmi.

MOP 3.2.2 Radar Azimuth Resolution: 2.8 degrees (Contract Spec says 2.6 degrees).

MOE 3.3 Beacon Accuracy: Is the beacon sufficiently accurate in reporting the position of the aircraft to support the air traffic controller?

MOP 3.3.1 Beacon Range Accuracy: 190 feet.

MOP 3.3.2 Beacon Azimuth Accuracy: 0.08 degrees RMS.

MOE 3.4 Beacon Resolution: Is the beacon resolution capability to resolve two closely spaced aircraft sufficient to support the air traffic controller?

MOP 3.4.1 Beacon Range Resolution: 95% when identical targets are separated in slant range by 0.05 to 0.5 nmi inclusive (assuming identical transponder reply delays) and 99.9 & when they are separated by more than 0.5 nmi.

MOP 3.4.2 Beacon Azimuth Resolution: 95% for two identical targets, which are 0.05, nmi of each other in slant range and separated by 2.1 degrees (assuming identical transponder delays). Additionally, 99% for the same two targets which are within 0.05 nmi of each other in slant range and have at least one distinguishing characteristic and are separated by 1.5 degrees.

COI 4.0 Reliability, Maintainability, Availability

Is the reliability, maintainability, and availability of the ASR-11 suitable for incorporation into the NAS when used in an operational environment with the available resources, logistics plan, maintenance procedures, and personnel?

MOS 4.1 Availability: Is the ASR-11 sufficiently available to support air traffic control operations.

MOP 4.1.1 Radar Operational Availability: 0.99984.

MOP 4.1.2 Beacon Operational Availability: 0.99998.

MOP 4.1.3 MTBCF: The mean time between failures (MTBCF) shall be equivalent to a dual channel system having a single channel mean time between failure (MTBF) of 750 hours and an antenna MTBF of 10,000 hours including RMM. (Therefore, total system MTBCF of 1304 hours).

MOP 4.1.4 MTBCMA: 1070 hours.

MOP 4.1.5 MTTR: No greater than 0.5 hours.

MOP 4.1.6 Redundant System Reconfiguration: System reconfigures in less than 4 seconds.

MOP 4.1.7 MTR: The system Mean Time to Restore (MTR) shall be not more than 0.5 hours.

MOS 4.2 Integrated Diagnostics: Does the ASR-11 detect and isolate faults within the system?

MOP 4.2.1 BIT/FIT Detection/Isolation Rate (Auto): 90% or greater to an ambiguity group of three line replacement units or less using automatic mode.

MOP 4.2.2 BIT/FIT Detection/Isolation Rate (Automatic/Manual): 95% or greater to one LRU using automatic and manual modes.

MOP 4.2.3 BIT/FIT Detection/Isolation Rate (All Means): 100%.

MOP 4.2.4 BIT False Alarm Rate: (None Specified).

MOS 4.3 Preventative Maintenance: Will the required preventative maintenance require excessive downtimes that will impact air traffic control?

MOP 4.3.1 Maintenance Frequency: No more than 4 visits per year with a total time required less than 12 staff hours?

MOP 4.3.2 Preventative Maintenance Tasks: Accomplished with ASR-11 on-line without degrading system performance.

MOS 4.4 Equipment Certification: Can the ASR-11 system equipment certification, for both scheduled and as a result of a failure/repair, be readily performed on site and remotely?

MOP 4.4.1 Remote Equipment Certification: The ASR-11 System is certifiable remotely.

MOP 4.4.2 On-Site Certification: The ASR-11 certification is readily performed on-site using the guidance in its maintenance handbook.

MOS 4.5 Spares Provisioning: Are adequate spare parts available and distributed to both designated levels of ASR-11 maintenance (i.e., site and depot)?

MOP 4.5.1 Spares Provisioning: Sufficient types and quantities of spare parts available at both designated levels of ASR-11 maintenance (i.e., site and depot).

MOS 4.6 System Documentation: Does the ASR-11 Technical Instruction Book (TIB) accurately reflect the delivered systems and are they understandable and concise at the level of the intended reader?

MOP 4.6.1 TIB Coverage (Breadth): The Technical Instruction Books have sufficient breadth and coverage to give the technician the ability to locate and define a system casualty and to determine the corrective measures required.

MOP 4.6.2 TIB Adequacy (Depth): The ASR-11 Technical Instruction Books give sufficient detail for the diagnoses and repair of all ASR-11 System elements.

MOP 4.6.3 TIB Accuracy: The ASR-11 Technical Instruction Books are sufficiently accurate to support detailed trouble shooting and repair efforts.

MOP 4.6.4 TIB Utility: The ASR-11 Technical Instruction Books material is organized and presented in a logical and useable way.

COI 5.0 Site Adaptation and Optimization

Does the ASR-11 system design and procedures allow the radar system to be optimized, adapted to site conditions, and certified in a reasonable time by available maintenance personnel?

MOS 5.1 PSR Site Adaptation and Optimization: Can the necessary PSR adaptation/optimization process be supported in a timely manner?

MOP 5.1.1 Site Adaptation and Optimization Resources: The available procedures, test equipment, analysis tools, and Technical Operations personnel resources will support the PSR site adaptation and optimization at the various ASR-11 sites.

MOP 5.1.2 Site Reoptimization and Periodicity Procedures: Adequate procedures exist for the special and/or periodic PSR reoptimization at the various ASR-11 sites.

MOS 5.2 SSR Site Adaptation and Optimization: Can the necessary SSR adaptation/ optimization process be supported in a timely manner?

MOP 5.2.1 Site Adaptation and Optimization Resources: The provided procedures, test equipment, analysis tools, and Technical Operations personnel resources support the SSR site adaptation and optimization at the various ASR-11 sites.

MOP 5.2.2 Site Reoptimization and Periodicity Procedures: Adequate procedures exist for the special and/or periodic SSR reoptimization at the various ASR-11 sites.

COI 6.0 Interoperability

Does the ASR-11 System operate effectively within the NAS system?

MOS 6.1 Electromagnetic Interference/Compatibility: Can the ASR-11 operate within the proximity of other systems without degrading its performance or the performance of other systems?

MOP 6.1.1 ASR-11 Susceptibility: ASR-11 operations are not affected by EMI resulting from the operations of other equipment.

MOP 6.1.2 ASR-11 Compatibility: ASR-11 generated emissions do not result in electromagnetic interference degrading other systems.

MOS 6.2 External Interfaces: Does the ASR-11 provide the required interfaces for successful utilization through and with other elements of the NAS?

MOP 6.2.1 External Interfaces: The ASR-11 provides interfaces for operations with:

a)	Existing automation systems (ARTS IIA, ARTS IIE, ARTS IIIA, and PIDP (TPX-42)) with both analog and CD format inputs.

b)	Standard Terminal Automation Replacement System (STARS) for both CD and Asterisk format input.

c)	Maintenance processor subsystem (MPS).

MOS 6.3 Automation Interface: Can the ASR-11 provide four digital data ports to provide independent outputs in multiple combinations?

MOP 6.3.1 Automation Interface: The ASR-11 has four digital data ports that provide independent outputs simultaneously in any combination of the required formats.

MOS 6.4 Service Certification: Can the necessary TRACON service certifications be accomplished?

MOP 6.4.1 Certification: The ASR-11 system provides for the local and remote monitoring of PSR and SSR parameters required for service certification.

MOS 6.5 Transition Switchover: Does the ASR-11 system design and installation allow for a transition period between the existing system and the new ASR-11?

MOP 6.5.1 Transition Switchover Time: The system provides the ability to completely switch over from the ASR-11 system to the existing system or from the existing system to the ASR-11 within five minutes.

MOS 6.6 Primary Power: Is the ASR-11 operationally effective when subjected to the commercial prime power conditions experienced at the site?

MOP 6.6.1 Transients: The system recovers from short timeframe transients in voltage or amperage without degradation.

MOP 6.6.2 UPS: The UPS successfully switches to battery power when necessary without any loss of ASR-11 service.

MOP 6.6.3 Engine Generator Transition: The engine generator energizes and the ASR-11 operation successfully transitions within 10 seconds when a voltage increase or decrease of 10% or more is sensed.

COI 7.0 Safety

Is the ASR-11 system safe to operate and maintain?

MOS 7.1 Safety: Are ASR-11 personnel, equipment, or facilities exposed to unnecessary or uncontrolled hazards during operations and maintenance of the system?

MOP 7.1.1 Electrical Hazards: Personnel exposure to electrical hazards is adequately controlled through appropriate guards, interrupts, and warnings.

MOP 7.1.2 Radiation Hazards: Spurious radiation within maintenance areas is below acceptable levels and appropriate warnings and interrupts are utilized.

MOP 7.1.3 Physical Hazards: Adequate guards and barriers are in place to prevent personnel harm from required physical activity necessary to perform maintenance actions and noise in maintenance areas is below acceptable levels.

MOP 7.1.4 Other Hazards: TBD.

COI 8.0 Human Factors:

Are the controls, monitors and displays sufficient to support the air traffic controllers, the radar operators and the radar maintainers?

MOS 8.1 Controller Interface/Workload: The controller can easily perform necessary display customization and readily ascertain and confirm that the radar is performing properly.

MOS 8.2 Technical Operations INTERFACE/WORKLOAD: The on-site maintenance interface support all facets of operation and maintenance in an effective and efficient manner.

MOS 8.3 Training: Does the ASR-11 Training provide the necessary skills, experience, and knowledge to allow the successful operation, maintenance and use of the ASR-11?

MOP 8.3.1 Technical Operations/Maintenance Training: The maintenance training address both systems engineering and maintenance technician training and provides the knowledge and skills to control, operate, and maintain the system at the respective site, region, and depot levels.

MOS 8.3.2 ATC Training: The controller training provides personnel with the required knowledge and skills to fully utilize the ASR-11.

COI 9.0 Weather Detection and Display:

Does the ASR-11 provide accurate and reliable weather data suitable for safe aircraft routing by air traffic control?

MOS 9.1: Weather Detection and Display: Does the ASR-11 provide six-level weather detection capability within the coverage volume with minimal degradation from ground clutter and second time around weather sufficient to support air traffic control operations?

MOP 9.1.1 Weather Detection: The PSR will detect, categorize, and report precipitation within the six reflectivity-intensity range levels (18 to 57 dBz) defined by the National Weather Service.

MOP 9.1.2 Weather Reporting Error: 2.5 dB maximum reporting error in the absence of ground clutter, including bias, when operating in either linear or circular antenna polarization modes.

MOP 9.1.3 Weather Data Timeliness: Collect reflectivity data, within a maximum period of six scans, and output data within one scan following collection.

MOP 9.1.4 Weather Data Resolution: Data granularity of 0.5 nmi in range and 1.4 degrees.

APPENDIX E

Appendix E

IOT&E Details

E.1 IOT&E Documentation

During early program monitoring, the Office of IOT&E identifies risks and communicates these risks to the service organization via informal verbal communication and formal written communication.  IOT&E required documentation includes input to the ISP test and evaluation section, an IOT&E plan, an IOT&E procedures document, and an IOT&E Team assessment report (IOT&E Report).  Figure E1-1 depicts a generic timeline of IOT&E activities and shows when supporting IOT&E documents would normally be developed.

IOT&E Input to the ISP T&E Sections.  The Office of IOT&E reviews and comments on the service organization’s T&E strategy proposed in the ISP. The Office of IOT&E also provides the IOT&E section for the ISP. For the ISP T&E section, The Office of IOT&E documents the IOT&E activities, resources, and strategy. The Office of IOT&E has full approval of the IOT&E section of the ISP.

Office of IOT&E Co-approval of T&E Section of ISP.  The Office of IOT&E, along with the service team lead, co-approves the entire T&E section of the ISP.  The Office of IOT&E prepares a signature page for the front of the ISP T&E section and a memo to the service team lead detailing any issues or conditions prior to co-approval.

IOT&E plans and procedures.  The IOT&E plans and procedures documents should include scheduling, resources, coverage of system test, and data collection and analysis to allow a formal IOT&E Team assessment of the system’s operational readiness.

Pre-IOT&E Operational Issue Paper.  Subsequent to OT completion and prior to the IOTRD, the Office of IOT&E and the IOT&E Team prepare an issue paper for the ATO stakeholders and service organization that provides a summary of the operational issues that are being tracked as IOT&E approaches.

Reports. The IOT&E Report will be distributed to the service organization and all ATO stakeholders at the Directorate and Vice President levels.  The Report will also be sent to the ATO COO.  This Report supports a production decision or In-Service Decision.  Due to the independent nature of the IOT&E Report, there is no formal comment/review process outside of the IOT&E Team.  The IOT&E Report is based on all data available at that time.

Follow-on Assessment and Reporting.  The Office of IOT&E, along with the IOT&E Team, provides a follow-up assessment on any new operational issues identified after the ISD and a status of significant operational issues that were identified in the original IOT&E Report.  Results of the follow-up assessment are detailed in a Follow-up Report issued approximately six months following the ISD.

Figure E1-1: Generic Timeline of IOT&E Activities

E.2 IOT&E Team

Organizations that operate, maintain, or are otherwise operationally affected by the implementation of a new system are represented on the IOT&E Team.  IOT&E Teams will include subject-matter experts at both the working level and supervisory levels from Headquarters and field operations.

The Office of IOT&E coordinates with appropriate ATO offices to obtain IOT&E Team members from field facilities.  Additional participants may include FAA personnel who are system users such as the National Weather Service, and the Department of Defense.

Office of IOT&E’s Role in IOT&E. The IOT&E Program Manager from the Office of IOT&E leads and provides full administrative support to the IOT&E Team during IOT&E. The Office of IOT&E facilitates the final IOT&E Team system assessment by ensuring proper collection, analysis, and reporting of test results. The IOT&E Team reports the operational assessment of the evaluated system to the In-Service Decision authority. The Director of the Office of IOT&E represents independent test and evaluation within the FAA.

IOT&E Team Responsibility. The IOT&E Team is responsible for conducting independent operational assessments of designated programs. Although every attempt will be made to keep members’ management informed of assessments and recommendations, IOT&E Team assessments and/or recommendations will be based solely on the analyses of system performance and capabilities during IOT&E and of data collected during earlier test phases.

Role of IOT&E Team During System Test and Field Familiarization. IOT&E may use the results from selected SI System Test events to aid the resolution of COIs. Members from the IOT&E Team observe selected system test events and have access to all system test and PTR data so that a complete IOT&E assessment can be made.

Role of Office of IOT&E and IOT&E Team in COI Development. Due to the important role COIs play in system tests and operational assessments, and due to problems created by inadequate COIs, the Office of IOT&E will work with the service organization to assist in the development of a complete set of testable COIs. COIs should reflect high-level operational requirements and should avoid including "issues of the day." COIs used in the test plans by the service organization and the IOT&E Program Manager should be those defined in the Exhibit 300 Program Baseline, Attachment 1: Program Requirements.

E.3 Relationship with Service Organizations

IOT&E Program Managers are extended, non-voting members of service organizations. They attend all pertinent service organization activities and work closely with the service organizations regarding IOT&E and the early identification of operational issues and risks during the monitoring process. The IOT&E Team is provided access to SI System Test documentation, which it reviews and on which it provides comments.  The service organization may coordinate with the IOT&E PM if they would like to have a representative observe IOT&E.  During IOT&E, the service organization may decide to withdraw the system if further development and/or corrective action is required before IOT&E proceeds.

Test Working Groups (TWGs). IOT&E program managers/and Office of IOT&E support staff participate on service organization TWGs. This participation facilitates a full understanding by Office of IOT&E of the service organization’s test strategy and a full understanding by the service organization of the IOT&E strategy.

Operational Capabilities Tests and Demonstrations (OCTs, OCDs). To ensure that independence is maintained, the Office of IOT&E does not participate directly in OCDs or OCTs. Office of IOT&E personnel are present as observers, but do not have a role on the technical evaluation teams.

E.4 IOT&E Designation Process:

Key elements in the process for assigning an IOT&E program designation include:

- Potential programs for IOT&E designation are reviewed by an IOT&E Designation Board.  The IOT&E Designation Board consists of Directors of En Route and Oceanic Safety and Operational Support, Terminal Safety and Operational Support, Flight Services Safety and Operational Support, Technical Operations Support, Systems Operations and Safety, and the Office of IOT&E.  The Board’s review of programs results in a recommendation to the Vice President of Safety Services on IOT&E program designation. This IOT&E Designation Board will commit to providing sufficient resources to support the recommended program designations.

- The Board ensures that priorities are assigned based on factors such as complexity, criticality, acquisition cost, and risk.

- Program designation decisions will be re-verified at key program milestones.

E.5 IOT&E Method of System Assessment

The assessment of the operational readiness of the system will be performed by the IOT&E Team after IOT&E. The system will be assessed for Operational Readiness based on the operational issues associated with the COIs.  The IOT&E Team may not be able to fully evaluate all operational aspects of the system during IOT&E due to limitations that may be site-specific, part of the operational environment, or that otherwise prevent the collection of enough relevant information.

##### Issue Risk Assessment

The evaluation process begins by correlating the collected data from System Test, Field Familiarization, and IOT&E with the COI/MOEs/MOSs to verify that all operational requirements have been assessed.  There will be a data trail from the data elements/MOPs to the MOEs/MOSs, and in turn, to the corresponding COIs.

The IOT&E Team will analyze the data to identify issues and categorize them as either Operational Risk issues or comments.  Identified operational issues will then be assessed for operational risk using the process described below.

Operational Risk Issues: The risk ratings for these issues will be based on the consensus of the IOT&E Team members and will be supported by data that will have been collected during the evaluation, and, if applicable, data collected during earlier testing.  The level of risk will be determined by assessing both the Operational Impact and Frequency of Occurrence using the following definitions:

Operational Impacts

The Operational Impacts are defined as follows:

CRITICAL – A problem that will prevent, degrade, or interrupt operational service or jeopardize safety, and has no acceptable workaround.

MAJOR – A problem that will —

a) prevent, degrade, or interrupt operational service or jeopardize safety, but has an acceptable workaround; or

b) disable a support system function that is essential to operational or system performance analysis, and has no acceptable workaround.

MINOR – A problem that presents a level of Operational Impact not covered by the Critical or Major categories above.

Frequency of Occurrence

The Frequency of Occurrence is defined as follows:

OFTEN – A problem that repeatedly occurred while the system/service was operational within the NAS and is very likely to recur when the causal conditions exist.

OCCASIONAL – A problem that intermittently occurred while the system/service was operational within the NAS and is likely to recur when the causal conditions exist.

ISOLATED – A problem that rarely occurred while the system/service was operational within the NAS or only occurred during any type of operational testing.  The likelihood of recurrence is minimal or the specific causal conditions have not been determined.

The following table illustrates the relationship of Operational Impact to Frequency of Occurrence in the assessment of operational risk:

|  | OPERATIONAL IMPACT |
| --- | --- |
|  | MINOR | MAJOR | CRITICAL |
| FREQUENCY OF OCCURRENCE | ISOLATED | LOW | LOW/MEDIUM* | MEDIUM/HIGH* |
|  | OCCASIONAL | LOW | MEDIUM | HIGH |
|  | OFTEN | LOW/MEDIUM* | MEDIUM/HIGH* | HIGH |

* Only one risk rating will be assigned to an issue.  It will be based on Team consensus.

Comments: This category would include issues that warrant consideration and are not operational risk issues.  Some examples of issues which may fall into this category are: positive comments on system performance, concerns with interfacing systems that are not currently under assessment, required operational capabilities not included in the system under assessment (these should have been addressed in the IOTRD), and resources.

System Assessment

Once the issues have been identified and rated for risk, the system will be assessed for Operational Readiness based on the assessment of the individual issues.  The system will be assessed for Operational Readiness as follows:

- Operationally Ready:

- There are no high risk issues and the combined level of risk of all issues does not preclude operational use.

- Not Operationally Ready:

- There is at least one high risk issue or the combined level of risk of all issues precludes operational use.

IOT&E Results

Results from IOT&E will be documented in an IOT&E Report.  The report will be distributed to the service organization and all ATO stakeholders at the Directorate and Vice President levels.  The report will also be sent to the ATO COO.  In the case of joint programs with the Department of Defense, the report will be sent to the appropriate Department of Defense offices.

The IOT&E Report will normally be briefed in the week following the report’s completion.  Briefings are scheduled at the Directorate and Vice President levels for all ATO stakeholders and the service organization.  A briefing is also scheduled for key site managers.  The briefing series may be tailored as appropriate for the program.

APPENDIX F

Acronyms and Definitions

F1.0 Overview

This appendix lists the acronyms and organizational abbreviations used in the guidance document and corresponding definitions.  The appendix also defines T&E terminology that is not defined elsewhere on FAST.

F1.1 List of Acronyms

AMS	Acquisition Management System

CCD	Configuration Control Decision

CDR	Critical Design Review

CMTP	Contractor Master Test Plan

COI	Critical Operational Issue

COO	Chief Operating Officer

COTS	Commercial Off-The-Shelf

CPP	Critical Performance Parameter

FAA	Federal Aviation Administration

FAST	FAA Acquisition System Toolset

HDR	Hardware Discrepancy Report

HW	Hardware

IOC	Initial Operating Capability

IOT&E	Independent Operational Test and Evaluation

IOTRD	IOT&E Readiness Declaration

ISD	In-Service Decision

ISM	In-Service Management

ISP	Implementation Strategy and Planning

JRC	Joint Resources Council

MOE	Measure of Effectiveness

MOP	Measure of Performance

MOS	Measure of Suitability

NAS	National Airspace System

NCP	NAS Change Proposal

NDI	Non-Developmental Item

OCD	Operational Capability Demonstration

OCT	Operational Capability Test

OMB	Office of Management and Budget

ORD	Operational Readiness Date

OSD	Operational Suitability Demonstration

OT	Operational Test

P3I	Pre-Planned Product Improvements

PAT	Production Acceptance Test

PDR	Preliminary Design Review

PRD	Program Requirements Document

PTR	Program Trouble Report

R&D	Research and Development

SAT	Site Acceptance Test

SI	Solution Implementation

SLMNS	Service-Level Mission Need Statement

SSD	System Support Directive

SSM	System Support Modification

SW	Software

T&E	Test and Evaluation

TEGS	Test and Evaluation Gold Standard

VRTM	Verification Requirements Traceability Matrix

WJHTC	William J. Hughes Technical Center

F1.3 Definitions

| Acceptance Testing | Formal testing conducted to determine whether a system satisfies its acceptance criteria and to enable the customer to determine whether to accept the system. |
| --- | --- |
| Analysis | Method of verification that compares hardware or software designs with known scientific and technical principles, technical data or procedures and practices to validate that the proposed design meets with technical requirements. |
| Anomaly or Failure | Inability of a software or hardware to meet its specified test or operational requirements. |
| Baseline | A specification or product that has been formally reviewed and agreed upon, that thereafter serves as the basis for further development, and that can be changed only through formal change control procedures. |
| Build Baseline | Software components that have been compiled and formally reviewed and agreed upon, that thereafter serves as the basis for further development, and that can be changed only through formal change control procedures. |
| Case File | A proposal recorded on FAA Form 1800-2 for any change to a baseline document or any deviation from national standards that needs technical concurrence. Prelude to an NCP. |
| Case File Number | A number assigned through MIS by the preparing organization in accordance with NAS-MD-001. (Example: CFOS500-VSCS-010 CF = Case File, OS500 = organization, VSCS = system, 010 = next number in sequence) |
| Computer Software Configuration Item (CSCI) | An aggregation of software that is designated for configuration management and treated as a single entity in the configuration management process. |
| Configuration | The arrangement of a computer system or network as defined by the nature, number, and the chief characteristics of its functional elements. The functional or physical characteristics (or both) of systems hardware/software. |
| Configuration Control | An element of configuration management, consisting of the evaluation, coordination, approval or disapproval, and implementation of changes to configuration items after formal establishment of their configuration identification. |
| Configuration Management | A discipline applying technical and administrative direction and surveillance to identify and document the functional and physical characteristics of a configuration item, control changes to those characteristics, record and report change processing and implementation status, and verify compliance with specified requirements. |
| Critical Operational Issue (COI) | A key operational effectiveness or operational suitability issue that must be examined during operational test to determine the system’s capability to perform its mission. |
| (COI) Resolved | A decision based on test data that the COI requirement has been met. (e.g., COI: Is the system safe? The COI is resolved if the answer is yes.) |
| Critical Performance Parameter (CPP) | A critical system performance requirement and its associated threshold and objective values. CPPs are specified in the Requirements Attachment (RD) and Exhibit 300 Program Baseline. |
| Development Test (DT) | A series of tests designed to verify that system technical and performance requirements specified in the contract and system specification have been met. Development Tests are usually performed by the contractor and witnessed by the FAA. |
| Field Familiarization | Tests conducted at each site by Air Traffic and Technical Operations personnel to verify that the site is ready to switch over to the new system. |
| Field Site Acceptance Test | Tests performed at operational sites to validate performance prior to operational use. |
| First Article System | A prototype system upgraded after production award. |
| First Article Test | Testing of the first subsystem built by the developer. Qualification testing and acceptance testing demonstrations to show compliance with the specification requirements and the SOW. |
| Function | The purpose for which something is designed or exists (a major element of a system baseline). |
| Initial Operating Capability (IOC) | IOC is the declaration by site personnel that the system is ready for conditional operational use in the NAS and denotes the end of Field Familiarization at that site. |
| Independent Operational Test and Evaluation (IOT&E) | A assessment of a new system’s operational effectiveness and operational suitability performed by an IOT&E Team on systems designated for IOT&E by the COO. |
| Interface Control Document (ICD) | The documentation necessary to identify functional and physical characteristics between and within configuration items provided by developers used to resolve problems concerning the specified interfaces. |
| Joint Resources Council (JRC) | The FAA’s body responsible for making corporatelevel decisions. Membership consists of Associate Administrators representing all lines of business of the agency, the FAA Acquisition Executive, the Director of the Office of Financial Services, and Legal Counsel. |
| Key Site | Field site(s) where OT, and IOT&E for designated programs, is conducted. A first operational NAS site where T&E activity is conducted to verify that HW/SW modification meets user needs. It is the actual environment where the equipment is used. |
| Measure of Effectiveness (MOE) | First-level, qualitative decomposition of an operational effectiveness component associated with a COI. |
| Measure of Performance (MOP) | Quantitative values that characterize MOEs or MOSs. These values are measurable by a test process. |
| Measure of Suitability (MOS) | First-level, qualitative decomposition of an operational suitability component associated with a COI. |
| NAS Change Proposal (NCP) | Proposed changes to the system baseline. |
| National Airspace System (NAS) | The common network of U.S. airspace; air navigation facilities, equipment and services; airports or landing areas; aeronautical charts, information and services; rules, regulations and procedures; technical information; and manpower and material. Included are system components shared jointly with the military. |
| Needs and Requirements Defined | New needs identified during the In-Service phase of a system’s lifecycle generally originate from the operational environment. Needs which cannot be satisfied at the local level or validated and entered into the national requirement process. |
| Operational Capability Test/Demonstration (OCT/OCD) | A test performed by the FAA to determine whether a COTS/NDI product meets stipulated NAS requirements. |
| Operational Effectiveness | The degree to which a product accomplishes its mission when used by representative personnel in the expected operational environment. |
| Operational Readiness Date (ORD) | The operational readiness date occurs at the end of the Operational Suitability Demonstration (OSD) |
| Operational Suitability | The degree to which a product intended for field use satisfies its availability, compatibility, transportability, interoperability, reliability maintainability, safety, human factors, logistics supportability, documentation, personnel, and training requirements. |
| Operational Suitability Demonstration (OSD) | When a system achieves IOC, it enters an OSD. The OSD is a time period during which the system is operated under intense scrutiny. |
| Operational Test (OT) | A series of tests designed to demonstrate that a new system is operationally effective and operationally suitable for use in the NAS and that all technical and performance requirements specified in the Exhibit 300 Program Baseline have been met. |
| Packaging | A proposition or an offer presented to a CCB for approval, consisting of several items (software or hardware) to be fixed or included in a system baseline. |
| Peer Review | A review of a product, following defined procedures, by peers of the producers of the product for the purpose of identifying defects and improvements. |
| Performance Measurements | Verify that the system is operating within performance requirements as outlined in performance criteria. Quantifies the system impact of new functionality. |
| Plan | A detailed scheme, program, or method worked out beforehand for the accomplishment of an object. A proposed or tentative project or purpose. |
| Preliminary Design | An informal design that precedes or introduces the main design. |
| Preliminary Design Review/Critical Design Review (PDR/CDR) | Used by the developers to finalize a new design and insure initial user “buy-in” to the design/development/implementation approach. |
| Procedure | Subordinate to a process. A set of activities or steps taken to achieve a given purpose. Any specific combination of machines, tools, methods, materials, and/or people employed to develop a work product. Could be used by multiple persons in one group either separately, interleaved, recursively, or concurrently. Some activities transform inputs into outputs needed for other activities. |
| Process | A description of a course of action to be taken to perform a given task, such as, the flow of a VSCS product from start to finish. Includes multiple persons; could cross multiple groups. |
| Product | The complete set, or any of the individual items of the set, of computer programs, procedures, and associated documentation and data designated for delivery to a customer or end user. |
| Production Acceptance Test (PAT) | Contractor-conducted testing performed on each end item before it leaves the factory to verify that the end item conforms to applicable specifications, is free from manufacturing defects, and is substantially identical to the qualified system. |
| Project | An undertaking requiring concerted effort, which is focused on developing and maintaining a specific product. Typically a project includes its own funding, cost, accounting, and delivery schedule. |
| Project Life Cycle | The period of time that begins when a project plan is conceived and ends when the product produced is no longer in use by the customer. |
| Program Trouble Report (PTR) | (Sometimes referred to as Problem Trouble Report) Method used to document and report a software anomaly that occurs on a system. It includes a full description of the problem, the operational impact, if any, and the method of recovery and or operational workaround used to recover from the problem. |
| Project Planning | Determining a method of action or procedure to implement a large or major undertaking, usually one involving considerable money, personnel, and equipment. |
| Quality | (1) The degree to which a system, component, or process meets specified requirements. (2) The degree to which a system, component, or process meets customer or user needs or expectations. |
| Quality Assurance | (1) A planned and systematic pattern of all actions necessary to provide adequate confidence that a work product conforms to established technical requirements. (2) A set of activities designed to evaluate the process by which work products are developed and/or maintained. |
| Requirements Traceability Matrix (RTM) | The project specification RTM details the contractor testing needed to ensure the designed hardware and/ or software satisfies the functional and performance requirements in the FAA system/segment project specification. |
| Scope of Delivery Defined via Stakeholder/User Prioritization | The scope of the project is initially set prior to beginning the development phase and monitored throughout the project. Using the prioritized list (based on stakeholders) and estimated timeframes and costs, a determination is made as to which needs are packaged into the next system release and its proposed release date. |
| Site Acceptance Test (SAT) | Testing conducted at a field facility, by the vendor, that demonstrates that the system is installed and integrated with other site equipment and is operating properly. |
| Site Program Bulletin | A directive used to authorize field release of changes to existing software programs, new software packages, and associated documentation. |
| Stability Testing | Verification that the system operates properly over an extended time period (typically run continuously for 48 to 72 hours). To be realistic, a typical “load” on the system is usually applied. |
| Subsystem | A combination of sets, groups, etc., that performs an operational function within a system and is a major subdivision of the system. |
| System | A collection of components organized to accomplish a specific function or set of functions. |
| System Baseline | A set of hardware, software, and documentation configuration items that define a configuration that is adapted or suited to support the function for which the system is designed or exists. |
| System Development Plan | The collection of plans that describe the activities to be performed for the system release on a project. It governs the management of the activities to be performed. |
| System Requirement | A condition or capability that must be met or possessed by a system or system component to satisfy a condition or capability needed by a user to solve a problem. |
| System Requirements Review | A review conducted jointly by users and developers to insure that requirements are documented, understood and prioritized. |
| System Support Directive | A directive used to authorize field release of changes to existing hardware/software, new hardware/software, and associated documentation. The SSD replaces EEMs, SPBs, etc. |
| System Test | A series of tests, conducted under the direction of the service organization that are designed to verify that a NAS system meets its specified requirements. The most important subsets of System Test are: Development Test, Operational Test, Production Test, and Site Acceptance Test. |
| System Testing | A series of tests performed to ascertain the stability, suitability, and functionality of a system. |
| Task | (1) A sequence of instructions treated as a basic unit of work. (2) A well-defined unit of work in the process that provides management with a visible checkpoint into the status of the project. Tasks have readiness criteria (preconditions) and completion criteria (post-conditions). |
| Test | Method of verification that measures equipment’s performance under specific configurations and after the controlled application of known stimuli. Results are measured, compared against previous success criteria and then evaluated to determine the degree of compliance. |
| Test Environment | Simulated operational environment used during System Test to revalidate existing performance and verify new functionality/system fixes. Typical parameters/limitations when testing in a simulated operational environment include system size/configuration (# of peripherals, interfaces, etc.), system loading (#/types of stimulus put into system under test), etc. |
| Test Tools | Automated HW/SW support equipment that allows the re-verification of existing baseline performance and the T&E of new functions/fixes. The thoroughness of the tools and the amount of automation of the tools directly affect the level of verification that can be done in a reasonable timeframe. |
| Validation | The process of evaluating a system during or at the end of the development process to determine whether it satisfies specified requirements. |
| Verification | The process of evaluating a system to determine whether the products of a given development phase satisfy the conditions imposed at the start of that phase. |

# Text boxes

- Define It

- Design It

- Build It

- Test It

- Key Site/National Deployment

Acquisition Management

Research and Systems Analysis

Investment

Analysis

In-Service Management

Solution Implementation

Mission

Analysis

Contract

Award

In-Service

Decision

Final

Investment

Decision

Mission Need

Decision

Initial

Investment

Decision

- Support Development of OMB Exhibit 300 and attachments

- Analyze and Demonstrate Feasibility of Candidate Solutions

- Assess Testability of Requirements in PRD

- Support Development of COIs and CPPs

- Develop High-level Test Strategies for Promising and Recommended Solutions

- Risk Reduction

- Prototype Evaluation

- OCD or OCT

- Specification Development

- Risk Reduction

- Support Production Decision

- Proposal Evaluation

- SI System Test

- Development Test

- Operational Test

- Production Acceptance Test

- Site Acceptance Test

- Independent Operational Test and Evaluation

- SI Field Familiarization

- Risk Reduction

Figure 3-1:  Tests and Test Activities Associated with NAS Acquisition Programs (Revised04/2002)

Acquisition Management

Initial

Investment

Decision

(JRC-2a)

- Support Development of APB, ASP, IPP, and RD

- Analyze and Demonstrate Feasibility of Candidate Solutions

- Assess Testability of Requirements in RD

- Support Development of COIs and CPPs

- Develop High Level Test Strategies for promising and recommended solutions

- Risk Reduction

- Identify Needed Modifications and Improvements

- ISM Development Test

- ISM System Test

- ISM Key Site Test

- ISM Field Acceptance Test and Field Familiarization

- SI System Test

- Development Test

- Operational Test

- Production Acceptance Test

- Site Acceptance Test

- Independent Operational Test & Evaluation

- SI Field Familiarization

- Risk Reduction

- Prototype Evaluation

- OCD or OCT

- Specification Development

- Risk Reduction

- Support Production Decision

- Proposal Evaluation

Mission

Analysis

Solution Implementation

In-Service Management

Investment

Analysis

Mission Need

Decision

Final

Investment

Decision

(JRC-2b)

In-Service

Decision

Contract

Award

Air Traffic Automation Operational Suitability Requirement Check List:

- Review Documentation		(

- Review Site Adaptation Changes	(

- Review Potential Impacts		(

- Develop Test Plan			(

- Coordinate with Stakeholders		(

- Schedule Implementation		(

- Log Entry			(

Installation and

Check-Out

(INCO)

Delivery

Contract

Acceptance

Inspection

CAI

Site

Acceptance

Testing (SAT)

Field Familiarization

Initial

Operating

IOC

Operational Suitability

OSD

Joint

Acceptance

Inspection

Joint Acceptance Inspection

Operational

Readiness

ORD

Commissioning

SAT

IOT&E Starts

Air Traffic Automation Operational Suitability Requirement Checklist:

- Review Documentation

- Review Site Adaptation Changes

- Review Potential Impacts

- Develop Test Plan

- Coordinate with Stakeholders

- Schedule Implementation

- Log Entry

Air Traffic Automation Operational Suitability Requirement Checklist:

- Review Documentation

- Review Site Adaptation Changes

- Review Potential Impacts

- Develop Test Plan

- Coordinate with Stakeholders

- Schedule Implementation

- Log Entry

RD

Test Plan

Test

Procedures

Real World Example

COI 1   COVERAGE

Does the DASR/ASR-11 performance

and coverage volume support air

traffic control operations?

MOE 1.1 -  Radar Coverage

MOE 1.2 - Beacon Coverage

MOE 1.N ...

MOP  1.1.1  Radar Altitude Coverage

MOP 1.1.2  Radar Azimuth Coverage

Does the ASR-11 system design and

procedures allow the radar system to

be optimized, adapted to site

conditions, and certified in a

reasonable time by available

maintenance personnel?

COI 2   SITE ADAPTATION

AND OPTIMIZATION

COI 3   HUMAN FACTORS

Are the controls, monitors, and

displays sufficient to support the air

traffic controllers, the radar operators,

and the radar maintainers?

MOS 2.1 PSR Site Adaptation

and Optimization

MOP 2.1.1 Site Adaptation and

Optimization Resources

MOP 2.1.2 Site Reoptimization

and Periodicity

Procedures

MOS 2.2 SSR Site Adaptation

and Optimization

MOS 2.N ...

MOS 3.1 Controller Interface/

Workload

MOS 3.2 Training

MOP 3.2.1 Technical Ops/

Maintenance Training

MOP 2.N ...

MOS 3.N ...

MOP 3.N ...

IOTRD

Early IOT&E

IOT&E

- Facilitate COI

Development

System Test

DT

OT

Field Familiarization

System Development

Investment Analysis

IOT&E

Monitoring System Test

Information Gathering

IOC

- Conduct Initial IOT&E

Strategy Session

- Develop PMP

IOC

ORD

- Refine IOT&E Strategy

- IOT&E Early Operational

Assessment/Early IOT&E

(as required)

- Initial Field Coordination

- Develop Pre-IOT&E Operational

Issue Paper

- Review IOTRD Exceptions

- Draft IOTRD Response

- Final Key Site Coordination

- IOT&E “Good-to-Go” Session

1 month prior to IOTRD

12 months prior to IOTRD

- Form IOT&E Team

- IOT&E Key Site/Area Briefs

- Develop IOT&E Plans/Procedures

IOT&E report

Complete

ISD

Pre-Briefs

ISD

Follow-Up

Evaluation

IOT&E

Designation

OMB

Exhibit 300

Approved

Follow-up

Activities