Summary Notes

MCH Training Program 2006-2007 Strategic Planning Workgroups

Family-Centered and Family-Directed Practices Workgroup conference call

August 29, 2007

Next call scheduled for (Tuesday) October 9    12:30-1:30 pm Eastern time

Workgroup Participants:

Barbara Levitz ,Angela Miney, Mark Smith.

MCH TRC:

Anita Farel

We used the meeting to assess where we are vis a vis our Workplan, confirm finished and nearly-finished activities and address gaps.

A recommendation was made to put a “note to the reader”, with each of our deliverables, to consider the products from Workgroup as primarily conceptual.  That is, the contents are meant to stimulate thinking about local program customs and resources and should be adapted and leveraged accordingly.  In other words, we’re offering our best thinking about themes and concepts that should be a foundation for all curricula.  We could list workgroup member’s names and email addresses or encourage readers to get technical assistance to pursue some of the ideas in more depth.

Workgroup Activities

1.  Identify available family-centered care curricula and materials and analyze for utility.  We are nearing completion on this activity.  Susan Horky and Tawara Goode are attending to specific details and then this will be sent to all Workgroup members for a virtual vote of approval to post.

2.  Develop indicators of comprehensive instruction in family-centered care.

Determine shared (operational) definition of fcc  We recommend the Bureau’s most recent definition

Identify core elements of comprehensive FCC curricula  The core elements are included in the indicators we developed last spring.

MCHB Training Programs will integrate families in program planning, implementation and evaluation.

Trainees will be able to demonstrate competence in and/or articulate the importance of these activities

Trainees will demonstrate ability to effectively communicate across cultural and linguistic groups.

Clarify the evidence needed to demonstrate that students have had comprehensive training in family centered care

Develop recommendations for reporting requirements to be approved by MCHB We made recommendations for the performance measure.

- Develop indicators for field placements that lead to cultural competency and understanding of family centered care.  This was developed by Barbara Levitz and Mark Smith (attached)

Identify current field placements that re considered “family centered” We need examples from Workgroup members

Develop criteria for assessing whether a placement leads to cultural competency and to an understanding of family-centered care.

Mark Smith sent 3 self-assessment instruments for our consideration (attached).  Barbara Levitz sent two assessment documents that are attached.  The first document is a self-assessment to be completed by trainees both pre and post the field placement experience (originally developed by the Wisconsin LEND program).  Barbara developed the second document from a variety of sources, is an assessment completed by families to evaluate how a trainee demonstrated family-centered and family-directed practices during their field placement with the family.

Make recommendations for reporting requirements to be approved by MCHB

4.  Identify and assess current continuing education module’s and teaching strategies targeted to faculty.

Develop criteria for assessing education modules and strategies

Review materials and identify promising models in family-centered care continuing education for faculty.  In order to do this, FCC workgroup members are asked to identify materials they have found useful for their own programs.

Develop recommendations for placing faculty education materials on Training Program Website.

Faculty development might be accomplished through lectures, Title V staff meeting with faculty, panels with families or individual families participating in courses.  FCC workgroup members are asked to share ideas about what they have found to be useful.

5.  Develop criteria for MCH Training Advisory Boards and place on Training Program Website.

Identify current MCH family, consumer and community advisory board development resources  Angela Miney, Barbara Levitz and Mark Smith developed the attached Guidelines for Family Advisory Boards.

Identify “core” goals and components of an effective advisory board

AUCD resources

.