APPENDIX B.14

CONTRACT CLOSEOUT CHECK LIST

# Memorandum

Date: 		3-Jan-98

To:		Director of Construction and Contract Administration

##### From:		Resident Engineer

Subject:	Contract CF720, North Point Station and Parking Deck Contract Closeout

This is to advise that Contract CF720, North Point Station and Parking Deck, is ready for formal closeout by the ARTA Board.  The Contract completion date was December 7, 1997.  The final Contract amount is $42,657,320.00, leaving a Contingency balance of $226,181.00.

The tabulation below is a complete checklist of closeout actions, reflecting their current status.

ITEM									STATUS

- Certificates of Beneficial Occupancy/Substantial Completion 	Complete		6/2/97

- Punch List								Complete	          7/17/97

- Liquidated Damages 						N/A	          	               N/A

4.   Temporary Construction Easement Signoffs			Complete                  5/20/97

5.   Change Orders Issued 						Complete	          6/18/97

6.   Claims 								Closed 		4/6/97

7.   Final Quantities 							Agreed			5/2/97

8.   Equipment/System Testing 					Accepted 		7/8/97

9.   Spare Parts/Spare Materials 					Received                   8/14/97

10. Operation & Maintenance Manuals 				Received     	          7/27/97

11.  Warranties 							Accepted     	          8/24/97

12.  Project Record Documents 					Accepted		9/2/97

13.  Final Corrected Shop Drawings 					Accepted                 10/12/97

14.  Product Data Book						Accepted                 10/12/97

15.  Final Labor Summary 						Received                 11/14/97

16.  List of Subcontractors 						Received                 11/14/97

17.  Affidavit of Final Payment					Received     	          12/7/97

18.  Final Payment 							Processed                12/20/97

19.  Final Marta Audit 						Complete                11/21/97

20.  Certificate of Completion 					Complete                  12/7/97

21.  Sign Offs by County & State 					County Pending

22.  Contract Files & Closeout Book				 	Forecast Comp.         1/15/98