Manual for Preparation

of

Cost Estimates

for

- VA Facilities

Office of Construction & Facilities Management

Cost Estimating & A/E Evaluation Service (00CFM1B)

810 Vermont Avenue, N.W.

Washington, D.C. 20420

Department of

Veterans Affairs

Table of Contents

CHAPTER 1:  CRITERIA UNIQUE TO VA

1.1	General Requirements

1.2	Presentation

  - Veterans Administration Hospital Building System

1.4	Need to Review All Pertinent   Sections of the VA Technical Information Resources

1.4.1	Description of the Technical Information Resources

1.4.2	Responsibility of Design Engineer

1.5	Computer Aided Facilities Management Requirements

CHAPTER 2:  CODING AND UNITS OF MEASURE CHARTS

2.1	General Requirements

2.2	Code Level A

2.3	Code Level B

2.4	Code Level C

2.5	Code Level D

CHAPTER 3: BUILDING SYSTEM DESCRIPTIONS

CHAPTER 4:  FORMS

4.1	Project Data Sheet No. 1

4.2	Project Data Sheet No. 2

4.3	VA Form HO-18B, Estimate Worksheet

4.4	VA Form HO-18C, Cost Summary Sheet

CHAPTER 5:  MATRIX

5.1	General Requirements

CHAPTER 6:  DETAILED TAKE-OFF

CHAPTER 7:  COSTS

CHAPTER 8:  SUBMISSION REQURIEMENTS

8.1	Market Survey

8.1.1	Local Market Survey

8.1.2	Schematics (S-1 & S-2)

8.1.3	Design Development (DD-1 & DD-2)

8.1.4	Construction Document (CD-1 & CD-2)

8.2	General Items

###### ATTACHMENTS

Attachment A:	Sample Estimate Submittal Forms

Attachment B:	Sample Matrix

Attachment C:	Sample Estimating Worksheet

Attachment D:	Building Systems Description

Attachment E:	Coding and Units of Measure Charts

Attachment F:	Procedure for Computation of Building Gross Area

INDEX

Blue indicates links. Chapters or various sections in chapters will open upon clicking of these links.

# MANUAL FOR PREPARATION OF COST ESTIMATES

# FOR VA FACILITIES

# 1  CRITERIA UNIQUE TO VA

# 1.1  GENERAL REQUIREMENTS

1.1.1	 A project estimate shall show the current cost of construction on the date of the estimate. The estimate should reflect current costs on the date the estimate is received and anticipated local escalation to the midpoint of construction, i.e., date of estimate plus ½ of construction duration.

1.1.2	 The level of detail for this estimate shall be consistent with the degree of completeness of the drawings being submitted.  Simply stated, this means that if a construction element is shown, it must be priced; if it is shown in detail, it must be priced in detail.  For detailed elements, "lump sum" or "allowance" figures will not be acceptable.  Project estimates will include all elements within the contractor’s bid such as insurance, bonds, hazardous abatement and any other such items.  Submission requirements are indicated in VA Program Guide PG-18-15D, AE Quality Alert – Cost Estimating; located on the web at www.va.gov/facmgt/standard/aeinfo/alertcos.doc.

# 1.2  PRESENTATION

1.2.1  Provide a separate estimate with different summary sheets and supporting take-off worksheets for each building.

1.2.2  Provide separate estimates for new construction, alteration work and site work.

1.2.3  A recapitulation sheet listing each new building, each renovated building and site work shall precede the summary sheets.

1.2.4  Project site work recapitulation sheets will include all costs for the entire site and not specific to a singular building.

1.2.5  Submit building gross area computations with sketch as shown in Attachment F, Procedure for Computation of Building Gross Area.

1.2.6  Computerized estimates are acceptable if all data is shown in the same format as the VA Forms.

# 1.3  VETERANS ADMINISTRATION HOSPITAL BUILDING SYSTEM

1.3.1  Hospitals Incorporating VA Hospital Building System (VAHBS) – Current VA policy is to design new hospital buildings for continuing adaptability and the integration of the various systems, subsystems and functional zones throughout the facility.  In accordance with these principals, the VA has published the VAHBS Research Study Report (Red Book) which can be found on the website at http:/www.va.gov/facmgt/standard/bsds.asp.  The Red Book consists of three volumes: Volume 2-Data Base contains a detailed data base on user needs, functional requirements, costs, labor unions, and laws and regulations.  This volume should be used and adhered to in developing cost estimates for new construction utilizing the VAHBS.

1.3.2  It is also important that the cost estimate incorporate current trends in cost escalation of materials and labor and how the use of VAHBS can reduce these costs through scheduling efficiencies.  These trends are outlined in the Supplement to Development Study which is found on the same website.

1.3.3  The Red Book details an approach to the design and construction of large, multi-story hospital buildings based on the principal of integrating systems and service zones with a prototype design.  The primary objective of systems integration are cost control, improved building performance, schedule reduction and the ability to modify the building as new systems are developed, modifications arise and campus growth is initiated.

1.3.4  To prepare an estimate using the VAHBS prototype design, the estimating team must understand the need for specialized design for the service systems in each part of the building.  A detailed discussion on this approach is outlined within the Red Book and the subsequent Supplement to Development Study.  The estimate must be structured to breakout the portions of the estimate which are unique to the Red Book prototype design and incorporate the various building subsystems.

1.3.5  The prototype design incorporates eight specific building subsystems that are the integrated subsystems.  These are structure, partitions, walk-on platforms (interstitial spaces) which are the subsystems; HVAC, plumbing, fire protection, electrical power distribution and low voltage systems (telephone/data distribution) which are the service systems.

Telephone/Data Distribution

Fire Protection (sprinkler & standpipes)

# 1.4  NEED TO REVIEW ALL PERTINENT SECTIONS OF THE VA TECHNICAL INFORMATION RESOURCES

# 1.4.1  DESCRIPTION OF THE TECHNICAL INFORMATION RESOURCES

# 1.4.1.1  Specific Practice Design Manuals

# See Technical Information Library (TIL) http://www.va.gov/facmgt/standard/manuals_hosp.asp

Purpose:  To convey the general and specific VA design philosophy for medical facilities

1.4.1.1.1  The Manuals accomplish this purpose by:

Explaining specific design methodologies.

Listing acceptable system types.

Setting the overall energy consumption target.

Codifying certain code interpretations.

Listing values for design parameters.

Referencing certain sections of the Master Specification.

Containing examples of certain design elements.

1.4.1.1.2  The Architect-Engineer shall submit to the VA a list of Design Manuals along with their TIL posted dates that were in effect on date of contract award.

# 1.4.1.2  Architect-Engineer (AE) Submission Instructions

# See A/E Information http://www.va.gov/facmgt/ae/des_sub.asp

Purpose:  To provide a staged listing of tasks in various design categories as a way to define the AE scope in order to assure thorough and timely completion of the final design package and bid documents

1.4.1.2.1  The Instructions accomplishes this purpose by:

Progressively listing tasks as Schematic, Design Development and Construction Documents stages.

Requiring task completion and submission for each stage according to a Critical Path Method (CPM) calendar.

Implementation of a QA/QC process to assure a quality design product.

Life cycle analysis of alternatives in order to optimize the design/cost tradeoff.

Listing and detailing all the drawings, calculations and specifications required for a complete design package.

Indicating the final distribution of bid documents.

1.4.1.2.2  Architect Engineer shall submit specifications at the Construction Documents (CD1) submittal to include an electronic version of the VA Master Specifications with tracked changes or modifications displayed.

# 1.4.1.3  Master Specifications

# See TIL http://www.va.gov/facmgt/standard/spec_idx.asp

Purpose:  Defines a standardized method for the AE to assure that the contractor provides equipment and systems that meet the design intent in terms of performance, quality and cost.

1.4.1.3.1  The Specifications accomplish this by:

Specific narrative descriptions of required equipment and system construction.

Listing applicable standards and codes and references.

Requiring individual submittal of equipment and systems for review and approval prior to contractor purchase.

Defining specific installation methods to be used.

# 1.4.1.4  AE Checklist

# See TIL http://www.va.gov/facmgt/standard/ae_checklist.asp

Purpose:  Provides the VA Peer Reviewer with a minimum list of critical items which must be included in each AE submission.

1.4.1.4.1  The Checklist accomplishes this by:

Referring to all applicable VA design tools which apply for the specific project.

Detailing certain Life Safety and Co-ordination requirements.

# 1.4.1.5  Design Alerts

# See TIL http://www.va.gov/facmgt/standard/d_alert.asp

Purpose:  Communicates current design issues and solutions.

1.4.1.5.1  The Design Alerts accomplish this by:

Publishing periodic alert memos.

Summarizing design solutions.

# 1.4.1.6  Quality Alerts

# See TIL http://www.va.gov/facmgt/standard/q_alerts.asp

Purpose:  Communicates quality deficiencies from recent AE design submissions

1.4.1.6.1  The Quality Alerts accomplish this by:

Publishing checklists of design details often missed.

Including references to technical resources.

# 1.4.1.7  Design Guides

# See TIL http://www.va.gov/facmgt/standard/dg_idx.asp

Purpose:  Provides the designer with specific layout templates and medical equipment lists for all types of spaces/uses, and specific design parameters for structural, electrical and mechanical service.

# 1.4.1.7.1  The Design Guides accomplish this by:

Publishing design narrative.

Including functional diagrams and layout plates.

Listing standards.

# 1.4.1.8  Design and Construction Procedures

# See TIL http://www.va.gov/facmgt/standard/proc_idx.asp

Purpose:  Establishes minimum consistent design/construction practices

1.4.1.8.1  The Procedures section accomplishes this by:

Referencing applicable codes and policies.

- Describing standard drawing formats.

- Listing security strategies.

- Including miscellaneous design details.

# 1.4.1.9  National CAD Standards and Details

# See TIL http://www.va.gov/facmgt/standard/details.asp

Purpose:  To promote standardization of CAD documents submitted to the VA

1.4.1.9.1  The Standards section accomplishes this by:

Providing downloadable equipment schedules.

Listing symbols and abbreviations.

Providing downloadable standard details in .dwg or .dwf format.

1.4.1.9.2  The Architect-Engineer shall utilize the VA Standard Details to the fullest extent possible.  A modification to a Standard Detail requires the approval of the VA Contracting Officer prior to use.

# 1.4.1.10  Physical Security Design Manual for VA Facilities - Mission Critical Facilities and Life Safety Protected Facilities (Formerly CD-54)

# See http://www.va.gov/facmgt/standard/physecurity.asp

Purpose:  Sets physical security standards for facilities required to continue operation during a natural or man-made extreme event and for facilities that are required to protect the life safety of patients and staff in an emergency.

1.4.1.10.1  The Manuals accomplish this by:

Sets objectives for physical security.

Provides strategies for use in design and construction to provide protection to VA facilities.

Provides cost effective design criteria.

# 1.4.1.11  Technical Summaries

# See TIL http://www.va.gov/facmgt/standard/tsum_idx.asp

Purpose: To provide in summary form the basic requirements stated in the HVAC Design Manual for Hospital Projects.

1.4.1.11.1  The Technical Summaries accomplish this by:

Publishing periodic bulletins.

Including updated design information.

# 1.4.1.12  Cost Estimating Manual

# See Cost Estimating http://www.va.gov/facmgt/cost-estimating/

Purpose:  To convey the general and specific VA cost estimating philosophy for medical facilities.

1.4.1.12.1  The Manual accomplishes this by:

Explaining specific estimating methodologies.

Containing examples of certain design elements.

1.4.1.13  Sustainable Design Manual for New Hospitals, Replacement Hospitals, Ambulatory Care, Clinical Additions, Outpatient Clinics and Nursing Homes

Purpose:  Incorporate sustainable design practices to improve building environment and to provide for cost savings for long term building operations and maintenance.

1.4.1.13.1  The Manual accomplishes this by:

Prescribing the use of integrated design practices.

Provides strategies for optimization of energy performance.

Provides strategies for protection and conservation of water resources

Provides strategies for enhancement of indoor environmental quality

Provides strategies for reduction of environmental impact of materials.

# 1.4.2  RESPONSIBILITY OF THE DESIGN ENGINEER

1.4.2.1  Review all sections for application to topic under question.  Every effort has been made to locate design data in only one place to avoid confusion.  However, with a resource as large as the TIL, and with ongoing revisions in order to represent the latest technology, it is important to assure that the correct design requirements and data are being used.  This will require reviewing several sections that may bear on the design

1.4.2.2  Conduct periodic reviews of the Design and Quality Alerts.  Periodically throughout the design process the Design Engineer must check the Design Alerts for changes in design requirements or specification interpretations, as well as track design deficiencies noted in other projects by reviewing the Quality Alerts.

1.4.2.3  Bring design questions and issues to the attention of the VA.  The Design Engineer will find extensive guidance in the TIL, but occasionally there will be a question or an issue that requires additional clarification.  When submitted to the VA for clarification, the issue and the answer will often appear in the Design Alerts if it is believed that the issue will be experienced by other design teams.

# 1.5  COMPUTER AIDED FACILITIES MANAGEMENT REQUIREMENTS

1.5.1  The VA intends to implement Computer Aided Facility Management (CAFM) systems in all new and replacement hospital construction, and in all existing hospitals as feasible.  The CAFM concept requires that all pertinent data regarding a (hospital) facility be contained in a master digital database, accessible by facilities personnel at their workstations for use in operations, energy/cost management, maintenance and for planning modifications in facility infrastructure due to space utilization changes.

1.5.2  The requirement for access to a master digital database drives the need to compile all architectural/engineering design data (plans, specifications, calculations, equipment selections, equipment submittal, commissioning/balance reports and job related communications, whether in letter or e-mail format) and cost estimating data in a digital, electronic format from the very start of a project.  Thus, this need for digital data will affect the requirements for submission (see Architect/Engineer Information-Design Submission Requirements).

1.5.3  While the VA may not have the complete software concept determined yet for the ultimate CAFM configuration, Architects/Engineers are to begin the digital submission process now.

1.5.4  All cost estimates will be submitted in electronic formats for storage requirements to the CAFM.  Hard copies will be accepted in addition to electronic copies if requested by the VACFM team.  Acceptable electronic formats include but are not limited to pdf formats or electronic programs that a pdf file can be generated from.

# 2  CODING AND UNITS OF MEASURE CHARTS

# 2.1  GENERAL REQUIREMENTS

2.1.1  Charts provided in Attachment E.

2.1.2  Use the units of measure indicated in Attachment E. Use these charts for the quantity take-off with the units of measure shown, then apply prices to those units of measure.  If no unit of measure is given for a particular cost item, choose a unit of measure consistent with the item.

2.1.3  Use codes to provide levels of detail required under "CODE" on Form HO-18b, Estimate Worksheet; Form HO-18c, Cost Summary Sheet; and Coding and Units of Measure Charts.

# 2.2  CODE LEVEL A

Major system.  Example: Mechanical Systems.

# 2.3  CODE LEVEL B

Level A further divided.  Example: Plumbing and HVAC.

# 2.4  CODE LEVEL C

Level B with subsections further divided.  Example:  Plumbing divided into domestic water, storm water, sanitary waste and vent, fuel gas, fuel oil, and plumbing fixtures.

# 2.5  CODE LEVEL D

2.5.1  Level C with sub-subsections further divided.  Example:  HVAC distribution divided into ductwork, air distribution devices, HVAC piping and AHU & terminal units.

2.5.2  For items, which do not logically fit under any of the systems or sub-systems on Attachment E, place a 99 in the code section of the VA Form HO-18B under the level detail represented by the new item. This will alert the VA estimator that a new or unusual item is included in the estimate, which is not stored in the computer data bank.

# 3  BUILDING SYSTEM DESCRIPTIONS

See Attachment D.

4  FORMS

# 4.1  PROJECT DATA SHEET NO. 1

A two-page form used to supply quantitative as well as qualitative information about the project.  A separate Data Sheet No. 1 shall be supplied for alteration and new for each building.  Additional Data Sheets No. 1 summarizing the entire project shall also be submitted.

# 4.2  PROJECT DATA SHEET NO. 2

An one-page form used to supply current labor rates for all labor building trades.

# 4.3  VA FORM HO-18b, ESTIMATE WORKSHEET

This form indicates the division of cost between labor and material for each cost item, and extends the level of estimate beyond Form HO-18c.

# 4.4  VA FORM HO-18c, COST SUMMARY SHEET

A two-page form used to summarize costs at the "B" level of detail.

# 5  MATRIX

# 5.1 GENERAL REQUIREMENTS

5.1.1  Form provided in Attachment B.

5.1.2  Prepare a Matrix with the VA's building systems as column headings for conversion from CSI format take-off estimates.  That is: GENERAL CONDITIONS, FOUNDATIONS, SUBSTRUCTURE, SUPERSTRUCTURE, EXTERIOR CLOSURE, ROOFING, INTERIOR FINISHES, CONVEYING SYSTEMS, MECHANICAL, ELECTRICAL, EQUIPMENT, BUILDING TOTALS, SITE PREPARATION, SITE IMPROVEMENTS, SITE UTILITIES, SITE TOTAL, AND PROJECT TOTAL.  Rows will identify the CSI format specification sections that are utilized for the project.

# 6  DETAILED TAKE-OFF

6.1  Form provided in Attachment C.

6.2  Each line item shall indicate unit of measure, quantity, labor cost per unit, material (including any equipment) cost per unit, and a total cost.  Each specification section shall be broken down into sub-sections of the Building Systems format and each sub-section sub-totaled.  The level of breakdown to be consistent with the VA design requirements.  The sub-section sub-totals shall be entered in the appropriate Matrix section.  This will also allow cross-checking to assure that all areas affected by the specification sections have been estimated.

# 7  COSTS

All costs shown on Attachment A, VA Form HO-18c, Cost Summary Sheet, and on the extended summary as outlined under Design Development 2 & Construction Document 1 submissions, shall include all labor insurance and taxes, sales taxes on material and applicable contractor markup.  All General Contractor’s labor insurance and taxes, sales taxes and applicable contractor markups shall be included under General Conditions and shall be shown on VA Forms HO-18b and c as applicable.

# 8  SUBMISSION REQUIREMENTS

# 8.1  MARKET SURVEY

# 8.1.1  LOCAL MARKET SURVEY

8.1.1.1  The consultant shall conduct a complete and detailed "Local Market Survey", exploring all factors that will affect the estimated bid cost at the date of receipt of contractor bids. Pertinent data shall be gathered by interviewing local firms having knowledge of the construction activity in the area.  Possible sources are, but not limited to, the following: general and subcontractors, contractors and builders associations, local government officials, architectural and engineering firms, builders’ exchange and construction-reporting firms, and bankers and commercial mortgage firms.  Particular emphasis should be placed on ascertaining the availability of mechanical and electrical sub-contractors.  The survey report, which will list sources of data, should reflect the recent and expected future bidding conditions that may influence the cost of VA construction.

8.1.1.2  Such surveys will be conducted at each stage of design.  Sources of information and minimum listings within the report shall include the following:

8.1.1.2.1  General Contractors

8.1.1.2.2  Subcontractors (Mechanical and electrical subcontractors must be contacted and referenced in this section)

8.1.1.2.3  Building associations

8.1.1.2.4  Local government agencies

8.1.1.2.5  Architectural and engineering firms

8.1.1.2.6  Builders exchange and construction reporting firms

8.1.1.2.7  Financial institutions to cover cost of construction money

8.1.1.2.8  Local VA facilities management

8.1.1.2.9  Labor unions and agencies

8.1.1.2.10  Labor supply, strike possibilities, availability of skilled labor covering all major sub trades.  The labor cost differential between closed shop and open shop competition.

8.1.1.2.11  Material availability, shortages, oversupplies or normal market conditions including increases in cost.

8.1.1.2.12  The “Hunger Factor” among general and sub contractors.  Estimate the anticipated number of bidders (both general and sub contractors) and their respective experience on similar projects.

8.1.1.2.13  Ascertain level of interest amongst general and sub contractors specifically concerning their desire to work with the local VA, and the VA in general, as opposed to other owners.

8.1.1.2.14  Local developers and development agencies

8.1.1.2.15  Professional bodies

8.1.1.2.16  List recently bid local projects determining the type of project and relating a cost per square foot of construction for each to allow comparative analysis with VA projects.

8.1.1.2.17  List all similar and major projects, which are planned to be constructed in the same timeframe.

# 8.1.2  SCHEMATICS (S-1 & S-2)

Conduct survey with reference to both current market conditions and forecast projected to date of bid/award.

# 8.1.3  DESIGN DEVELOPMENT (DD-1 & DD-2)

Re-survey, verify, refine, and report the previously gathered data and make all necessary changes as required to reflect the current and anticipated local market conditions, noting all outside forces, such as regional building booms.  The required estimate submissions shall include the detailed survey’s findings as reflected by the cost of materials, labor, and equipment along with all mark-ups associated with the general and appropriate sub contractors.

# 8.1.4  CONSTRUCTION DOCUMENT (Each Submission)

Intensify the survey process and report all data gathered.  The report shall clearly depict the pending current market conditions noting all outside influences.  The final estimate should incorporate the survey’s conclusions and reflect the current bidding climate, including information on the expected number of bidders, both general and sub-contractors, the grade of competition among contractors, and other conditions that may have impact on the VA’s construction project.  The survey will not be limited to statistical data but include professional opinions on the risks associated with market conditions including the estimated financial effect.

# 8.2  GENERAL ITEMS

8.2.1  A new gross area take-off is required with each estimate submission.  See Attachment F.

8.2.2  Each estimate must be broken down by building with new construction, alteration work and site work separated.

# 8.2.3  SCHEMATICS 1 (S1) AND SCHEMATICS 2 (S2)

As a minimum, the S1 submittal shall include a Level "A" breakdown of the base construction cost, i.e., divided into 12 major systems. The S2 submittal shall be broken down to Level "B".  Included in both of these submittals shall be a copy of VA Form HO-18c, and Project Data Sheet No. 1 with the available items filled in for the total project as well as for each building.  Alteration costs shall be reported separately from the cost of new construction.

# 8.2.4  DESIGN DEVELOPMENT 1 (DD1)

This submission shall include a two-page VA Form HO-18c, Level "B" detail and a PROJECT DATA SHEET NO. 1 with the available items filled in for the entire project, as well as separately for each building.  A single Project Data Sheet No. 2 containing current local labor rates is also required.  Alteration costs shall be reported separately from the cost for new construction.  Supplement each VA Form HO-18c with VA Form HO-18b, which shows the division of costs between labor and material.

# 8.2.5  DESIGN DEVELOPMENT 2 (DD2)

8.2.5.1  Provide Matrix described in Article 5; VA Form HO-18c, Cost Summary Sheet, completed to level "B" detail; VA Form HO-18b, Cost Estimate Worksheets,, to show the division of costs between labor and material; a detailed Project Data Sheet No. 1 completed in its entirety with all applicable items filled in for the entire project as well as separately for each building; and Project Data Sheet No. 2 containing local labor rates.

8.2.5.2  Alteration costs and site work shall each be reported separately from the cost of new building construction.  The amount of detail provided in this submission must be consistent with the completeness of the drawings.  Quantities such as "LS" or "LOT" should be a minimum.

8.2.5.3  For proper coding beyond Level "B", the AE shall refer to Attachment E, Coding and Unit of Measure Reference Chart.

8.2.5.4  Asbestos Abatement Estimate:  Show total costs for asbestos abatement provided by the Professional Industrial Hygienist (PIH) as a separate cost item below the total base construction cost on the Level "B" Cost Summary Sheet.

8.2.5.5  Each item description shall clearly define all materials and work operations that define a line item in the estimate including but not limited to sizes of structural members, thickness of materials, sizes of equipment, items ancillary to the work, underground installations and locations.

# 8.2.6  Construction Document 1 (Each Submission)

This submission shall include everything required in the DD2 Submission.  It differs from the DD2 Submission only in the level of detail required.  Provide a complete quantity survey estimate.  No lump sums will be permitted without explanation.  (Note:  Lump sums shown on Attachment E, Coding and Unit Measure Charts, are permitted due to summation of dissimilar items).

--END--

PROJECT DATA SHEET NO. 1 (2 pages)	DATE:  ____________________

LOCATION:  ____________________________________	PROJECT NO:  ______________

TITLE:  ______________________________________________________________________

DESIGNER:  ___________________________________________________________________

SUBMISSION NO:  _________	BUILDING NO.:  _________	BOECKH INDEX:  _________

AREA CALCULATIONS

1

BASEMENT:  ________________GSF (m2)	MECHANICAL:  ___________________SF (m2)

SUB-BSMT:  _________________GSF (m2)	CIRCULATION:  __________________SF (m2)

PENTHOUSE:  _______________GSF (m2)	CONSTRUCTION:  ________________SF (m2)

FLOORS (TOTAL):  ___________GSF (m2)	DESIGN NET:  ___________________	SF (m2)

AREA OF BLDG:  _____________GSF (m2)	AREA OF BLDG:  ________________	_SF (m2)

(SUM OF ABOVE)	(SUM OF ABOVE)

INTERSTITIAL SPACE:  ________GSF (m2)	PROGRAM NET:  _________________SF (m2)

HEIGHT OF INTERSTITIAL SPACE: ____FT (mm)   ALTERATION: ___________________SF (m2)

CONN. CORR.:  _____________GSF (m2)

QUANTITATIVE BUILDING DESCRIPTION

2

ROOF:  ____________________SF (m2)	WINDOWS:  ______________________SF (m2)

EXT. WALL:  ________________SF (m2)	EST. DOORS:  ____________________LEAVES

(INCLUDE WINDOWS & DOORS)

INT. WALL:  _________________SF (m2)	INT. DOORS:  _____________________LEAVES

(INCLUDE DOORS)

NO. OF FLOORS:  __________________	(EXCLUDE BSMT, SUB-BSMT,PENT,ETC)

NO. OF ELEVATORS:  _______________	STOPS EACH:  __________________________

CALCULATED A/C LOAD:  ____TONS (KW)

NO. OF CHILLERS:  ________________	TOTAL TONS (KW):  ______________________

NO. OF COOLING TOWERS:  ________	TOTAL TONS (KW):  ______________________

SOLAR PANELS:  _____________SF (m2)

NO. OF BOILERS:  _________________	TOTAL LBS/HR (kg/h):  ____________________

NO. OF FUEL OIL TANKS:  __________	TOTAL CAPACITY:  _______________________

PROJECT DATA SHEET NO 1 (CONT'D)

ELECTRICAL LOAD:  ____________KVA

NO OF EMER. GEN:  _______________	TOTAL KW:______________________________

NO. OF PLUMBING FIXTURES:  ______TOTAL

QUALITATIVE BUILDING DESCRIPTION (TYPE & MATERIAL)

3

FOUNDATION:

SUB STRUCTURE:

SUPER STRUCTURE:

EXTERIOR CLOSURE:

ROOFING:

INTERIOR WALLS:

REMARKS (DESCRIBE UNUSUAL FEATURES)

4

PROJECT DATA SHEET NO. 2

LABOR RATES AS OF __________________________

(Including Fringe Benefits)

LABORER______________________________	PAINTER ______________________________

EQUIPMENT OPERATOR	GLAZIER ______________________________

CRANE OPERATOR ___________________	ELEVATOR CONSTRUCTOR ______________

HEAVY EQUIPMENT ___________________	INSULATION WORKER ___________________

SMALL EQUIPMENT ___________________	CARPENTER ____________________________

CEMENT MASON _______________________	PLUMBER ______________________________

BRICK MASON _________________________	STEAMFITTER __________________________

STRUCTURAL IRON WORKER ____________	SHEETMETAL WORKER __________________

REINFORCING STEEL ___________________	ELECTRICIAN __________________________

ROOFER ______________________________	MILLWRIGHT __________________________

PLASTER ______________________________	TEAMSTER ____________________________

| ‘ |  |  |  |  |  |  |  |  |  |  |  | DATE |  |  |  | SHEET NO. |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ESTIMATE WORKSHEET |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | OF |  |  |
| PROJECT NO. |  |  |  | LOCATION |  |  |  |  |  | PROJECT NAME |  |  |  |  |  |  |  |  |
| TYPE OF ESTIMATE |  |  |  | ESTIMATOR | NEW | ALT. |  |  | INDEX NO. | BUILDING NO./NOS. |  |  |  |  | ESTIMATE NO. |  |  |  |
| CODE |  |  |  | SYSTEM/SUBSYSTEM | LABOR |  |  |  |  |  | MATERIALS |  |  |  |  |  | TOTAL |  |
| A | B | C | D |  | QUANTITY |  | UNIT | $/UNIT |  | TOTAL | QUANTITY |  | $/UNIT | $/UNIT |  | TOTAL |  | COST |

VA FORM HO-18b

DEC 1995

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DATE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| COST SUMMARY SHEET |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT NO. |  |  |  |  |  | LOCATION |  |  |  |  |  | PROJECT NAME |  |  |  |  |  |  |  |  |  |
| TYPE OF ESTIMATE |  |  |  |  |  | ESTIMATOR | GROSS AREA (New) | GROSS AREA (Alt.) |  | INDEX NO. |  |  |  |  | BUILDING NO./NOS. |  |  |  | ESTIMATE NO. |  |  |
|  |  |  |  |  |  |  | m2 (SQ.FT.) | m2 ( SQ.FT.) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CODE |  |  |  |  |  | SYSTEM/SUBSYSTEM |  | QUANTITY |  | UNIT |  |  | $/UNIT |  | $/m2 ($/GSF) |  | SUBSYSTEM COST |  | SYSTEM COST |  |  |
| A | B |  | C | D |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 01 |  |  |  |  |  | FOUNDATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 10 |  |  |  |  | STANDARD |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 20 |  |  |  |  | SPECIAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 02 |  |  |  |  |  | SUBSTRUCTURE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 10 |  |  |  |  | SLAB ON GRADE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 20 |  |  |  |  | BASEMENT EXCAVATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 30 |  |  |  |  | BASEMENT WALLS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 03 |  |  |  |  |  | SUPERSTRUCTURE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 10 |  |  |  |  | FLOOR CONSTRUCTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 20 |  |  |  |  | ROOF CONSTRUCTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 30 |  |  |  |  | STAIR CONSTRUCTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 04 |  |  |  |  |  | EXTERIOR CLOSURE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 10 |  |  |  |  | EXTERIOR WALLS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 20 |  |  |  |  | EXTERIOR DOORS AND WINDOWS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DATE |
| COST SUMMARY SHEET (continued) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT NO. |  |  |  |  |  | LOCATION |  |  |  |  |  | PROJECT NAME |  |  |  |  |  |  |  |  |  |
| TYPE OF ESTIMATE |  |  |  |  |  | ESTIMATOR | GROSS AREA (New) | GROSS AREA (Alt.) |  | INDEX NO. |  |  |  |  | BUILDING NO./NOS. |  |  |  | ESTIMATE NO. |  |  |
|  |  |  |  |  |  |  | m2 (SQ.FT.) | m2 ( SQ.FT.) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CODE |  |  |  |  |  | SYSTEM/SUBSYSTEM |  | QUANTITY |  | UNIT |  |  | $/UNIT |  | $/m2 ($/GSF) |  | SUBSYSTEM COST |  | SYSTEM COST |  |  |
| A | B |  | C | D |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 05 |  |  |  |  |  | ROOFING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 06 |  |  |  |  |  | INTERIOR CONSTRUCTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 10 |  |  |  |  | PARTITIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 20 |  |  |  |  | INTERIOR FINISHES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 30 |  |  |  |  | SPECIALTIES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 07 |  |  |  |  |  | CONVEYING SYSTEMS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 01 |  |  |  |  | ELEVATORS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 02 |  |  |  |  | MOVING STAIRS/WALKS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 03 |  |  |  |  | DUMBWAITERS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 04 |  |  |  |  | PNEUMATIC TUBES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 05 |  |  |  |  | OTHER CONVEYING SYSTEMS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 10 |  |  |  |  | PLUMBING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 20 |  |  |  |  | HVAC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DATE |
| COST SUMMARY SHEET (continued) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT NO. |  |  |  |  |  | LOCATION |  |  |  |  |  | PROJECT NAME |  |  |  |  |  |  |  |  |  |
| TYPE OF ESTIMATE |  |  |  |  |  | ESTIMATOR | GROSS AREA (New) | GROSS AREA (Alt.) |  | INDEX NO. |  |  |  |  | BUILDING NO./NOS. |  |  |  | ESTIMATE NO. |  |  |
|  |  |  |  |  |  |  | m2 (SQ.FT.) | m2 ( SQ.FT.) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CODE |  |  |  |  |  | SYSTEM/SUBSYSTEM |  | QUANTITY |  | UNIT |  |  | $/UNIT |  | $/m2 ($/GSF) |  | SUBSYSTEM COST |  | SYSTEM COST |  |  |
| A | B |  | C | D |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 30 |  |  |  |  | FIRE PROTECTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 40 |  |  |  |  | MEDICAL GASES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 50 |  |  |  |  | SEWAGE TREATMENT (New) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 55 |  |  |  |  | SEWAGE TREATMENT (Alterations) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 09 |  |  |  |  |  | ELECTRICAL SYSTEMS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 10 |  |  |  |  | BASIC MATERIALS AND METHODS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 20 |  |  |  |  | LIGHTING - POWER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 30 |  |  |  |  | SPECIAL ELECTRICAL SYSTEMS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 40 |  |  |  |  | COMMUNICATIONS SYSTEMS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 50 |  |  |  |  | ELECTRICAL HEATING SYSTEMS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | GENERAL CONDITIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11 |  |  |  |  |  | EQUIPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DATE |
| COST SUMMARY SHEET (continued) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT NO. |  |  |  |  |  | LOCATION |  |  |  |  |  | PROJECT NAME |  |  |  |  |  |  |  |  |  |
| TYPE OF ESTIMATE |  |  |  |  |  | ESTIMATOR | GROSS AREA (New) | GROSS AREA (Alt.) |  | INDEX NO. |  |  |  |  | BUILDING NO./NOS. |  |  |  | ESTIMATE NO. |  |  |
|  |  |  |  |  |  |  | m2 (SQ.FT.) | m2 ( SQ.FT.) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CODE |  |  |  |  |  | SYSTEM/SUBSYSTEM |  | QUANTITY |  | UNIT |  |  | $/UNIT |  | $/m2 ($/GSF) |  | SUBSYSTEM COST |  | SYSTEM COST |  |  |
| A | B |  | C | D |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 10 |  |  |  |  | SPECIAL EQUIPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 20 |  |  |  |  | FURNISHINGS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 30 |  |  |  |  | SPECIAL CONSTRUCTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | TOTAL BUILDING COSTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12 |  |  |  |  |  | SITEWORK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 10 |  |  |  |  | SITE PREPARATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 20 |  |  |  |  | SITE IMPROVEMENTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 30 |  |  |  |  | SITE UTILITIES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 40 |  |  |  |  | OFF SITE WORK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | TOTAL BASE CONSTRUCTION COST |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| REMARKS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

VA FORM HO-18c

DEC 1995

| MATRIX - VA BUILDING SYSTEMS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TITLE: NEW CLINIC ADDITION |  |  |  |  | PROJECT NO: 583-A42 |  |  | LOCATION: INDIANAPOLIS, (WTS), IN |  |  |  | BUILDING NO: |  |  |  |  |
| SPEC | FOUND’N | SUBSTR | SUPERSTR | EXTERIOR | ROOFING | INTERIOR | CONVEYING | MECHANICAL | ELECTRICAL | EQUIPMENT | TOTAL BLDG | PREP | IMPROVE | UTILITIES | TOTAL SITE | TOTAL PROJ |
| 00 72 00 | $238,495 | $49,555 | $552,456 | $368,755 | $61,934 | $735,755 | $111,880 | $1,042,583 | $468,045 | $116,060 | $3,764,798 | $16,888 | $49,909 | $63,196 | $29,993 | $3,794791 |
| 02 41 00 |  |  |  |  |  |  |  |  |  |  | $0 | $168,879 |  |  | $168,879 | $!68,879 |
| 00 30 00 | $459,590 | $483,623 | $4,637,796 |  | $3,290 |  |  |  |  |  | $5,584,299 |  |  |  | $0 | $5,584,299 |
| 00 30 53 |  |  | $89,712 |  |  |  |  |  |  |  | $89,712 |  |  |  | $0 | $89,712 |
| 03 51 16 |  |  |  | $560,595 |  |  |  |  |  |  | $560,595 |  |  |  | $0 | $560,595 |
| 04 20 00 |  |  |  | $964,497 |  | $543,472 |  |  |  |  | $1,507,969 |  |  |  | $0 | $1,507,969 |
| 05 12 00 |  |  | $729,404 | $490,379 |  |  |  |  |  |  | $1,219,783 |  |  |  | $0 | $1,219,783 |
| 06 10 00 |  |  |  |  |  |  |  |  |  |  | $0 |  |  |  | $0 | $0 |
| 07 11 13 |  | $11,931 |  |  | $3,672 |  |  |  |  |  | $15,603 |  |  |  | $0 | $15,603 |
| 07 22 00 |  |  | $67,650 |  |  |  |  |  |  |  | $67,650 |  |  |  | $0 | $67,650 |
| 07 51 00 |  |  |  |  | $612,377 |  |  |  |  |  | $612,377 |  |  |  | $0 | $612,377 |
| 07 60 00 |  |  |  |  |  |  |  |  |  |  | $0 |  |  |  | $0 | $0 |
| 07 92 00 |  |  |  |  |  |  |  |  |  |  | $0 |  |  |  | $0 | $0 |
| 08 11 13 |  |  |  |  |  | $1,191,235 |  |  |  |  | $1,191,235 |  |  |  | $0 | $1,191,235 |
| 08 31 13 |  |  |  | $20,000 |  |  |  |  |  |  | $20,000 |  |  |  | $0 | $20,000 |
| 08 51 13 |  |  |  |  |  | $1,728,659 |  |  |  |  | $1,728,659 |  |  |  | $0 | $1,728,659 |
| 09 22 16 |  |  |  |  |  | $1,939,900 |  |  |  |  | $1,939,900 |  |  |  | $0 | $1,939,900 |
| 09 29 00 |  |  |  | $402,941 |  |  |  |  |  |  | $402,941 |  |  |  | $0 | $402,941 |
| 09 51 00 |  |  |  | $370,554 |  |  |  |  |  |  | $370,554 |  |  |  | $0 | $370,554 |
| 09 65 16 |  |  |  | $274,659 |  |  |  |  |  |  | $274,659 |  |  |  | $0 | $274,659 |
| 09 65 13 |  |  |  |  |  |  |  |  |  |  | $0 |  |  |  | $0 | $0 |
| 09 91 00 |  |  |  |  |  | $471,381 |  |  |  |  | $471,381 |  |  |  | $0 | $471,381 |
| 09 91 00 |  |  |  | $603,923 |  |  |  |  |  |  | $603,923 |  | $1,047 |  | $1,047 | $604,970 |
| 09 30 13 |  |  |  |  |  | $60,214 |  |  |  |  | $60,214 |  |  |  | $0 | $60,214 |
| 10 22 13 |  |  |  |  |  | $329,041 |  |  |  |  | $329,041 |  |  |  | $0 | $329,041 |
| 10 22 26 13 |  |  |  |  |  |  |  |  |  |  | $0 |  |  |  | $0 | $0 |
| 10 25 13 |  |  |  |  |  | $421,120 45,520 |  |  |  |  | $421,120 |  |  |  | $0 | $421,120 |
| 10 26 00 |  |  |  |  |  | $45,520 |  |  |  |  | $45,520 |  |  |  | $0 | $45,520 |
| 10 44 13 |  |  |  |  |  |  |  |  |  | $238.043 | $238,043 |  |  |  | $0 | $238,043 |
| 11 40 00 |  |  |  |  |  |  |  |  |  |  | $0 |  |  |  | $0 | $0 |
| 11 44 00 |  |  |  |  |  |  |  |  |  |  | $0 |  |  |  | $0 | $0 |
| 12 31 00 |  |  |  |  |  | $627,010 |  |  |  |  | $627,010 |  |  |  | $0 | $627,010 |
| 12 35 70 |  |  |  |  |  |  |  |  |  | $869,436 | $869,436 |  |  |  | $0 | $869,436 |
| 13 17 23 |  |  |  |  |  |  |  |  |  | $53,117 | $53,117 |  |  |  | $0 | $53,117 |
| 14 21 00 |  |  |  |  |  |  | $1,118,800 |  |  |  | $1,118,800 |  |  |  | $0 | $1,118,800 |
| 21 00 00 |  |  |  |  |  |  |  | $162,000 |  |  | $162,200 |  |  |  | $0 | $162,000 |
| 22 00 00 |  |  |  |  |  |  |  | $3,649,000 |  |  | $3,649,000 |  |  |  | $0 | $3,649,000 |
| 23 00 00 |  |  |  |  |  |  |  | $4,691,625 |  |  | $4,691,625 |  |  |  | $0 | $4,691,625 |
| 26 00 00 |  |  |  |  |  |  |  |  | $3,744,362 |  | $3,744,362 |  |  |  | $0 | $3,744,362 |
| 27 00 00 |  |  |  |  |  |  |  |  | $702,068 |  | $702,068 |  |  |  | $0 | $702,086 |
| 28 00 00 |  |  |  |  |  |  |  |  | $234,023 |  | $234,023 |  |  |  | $0 | $234,023 |
| 31 20 00 | $301,942 |  |  |  |  |  |  |  |  |  | $301,942 |  |  |  | $0 | $301,942 |
| 31 62 00 | $1, 626,420 |  |  |  |  |  |  |  |  |  | $1,626,420 |  |  |  | $0 | $1,626,420 |
| 32 05 23 |  |  |  |  |  |  |  |  |  |  | $0 |  | $104,324 |  | $104,324 | $104,324 |
| 32 12 16 |  |  |  |  |  |  |  |  |  |  | $0 |  | $187,981 |  | $187,981 | $187,981 |
| 32 90 00 |  |  |  |  |  |  |  |  |  |  | $0 |  | $205,739 |  | $205,739 | $205,739 |
| 33 00 00 |  |  |  |  |  |  |  |  |  |  | $0 |  |  | $631,957 | $631,957 | $631,957 |
| TOTAL | $2,623.447 | $545.109 | $6,077,018 | $4,056,303 | $681,273 | $8,093,307 | $1,230,680 | $9,545,208 | $5,148,498 | $1,276,656 | $39,277,499 | $185,767 | $549,000 | $695,153 | $1,729,920 | $41,007,419 |

This worksheet is an example only of probable project costs.  Not all categories used in the VA Specifications – MasterFormat 2004 have been shown on this example.  The estimator must reference the website at http://www.va.gov/facmgt/stand/spec/mf04 to determine which MF04# should be included in this worksheet as applicable to the individual projects.

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DATE |  |  |  |  | SHEET NO. |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ESTIMATE WORKSHEET |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | OF |  |  |
| PROJECT NO. |  |  |  |  | LOCATION |  |  |  |  |  |  |  | PROJECT NAME |  |  |  |  |  |  |  |  |  |
| 101-001 |  |  |  |  | VAMC, ANY CITY, USA |  |  |  |  |  |  |  | SAMPLE PROJECT |  |  |  |  |  |  |  |  |  |
| TYPE OF ESTIMATE |  |  |  |  | ESTIMATOR |  | NEW |  | ALT. | INDEX NO. |  |  | BUILDING NO./NOS. |  |  |  |  |  | ESTIMATE NO. |  |  |  |
| DD1 |  |  |  |  | JOHN DOE |  | X |  |  | 1000.0 |  |  | 12 |  |  |  |  |  | CD-1 |  |  |  |
| CODE |  |  |  | SYSTEM/SUBSYSTEM |  | LABOR |  |  |  |  |  |  |  | MATERIALS |  |  |  |  |  |  |  | TOTAL |
| A | B | C | D |  |  | QUANTITY |  | UNIT |  |  | $/UNIT | TOTAL |  | QUANTITY |  | UNIT | $/UNIT | TOTAL |  |  | COST |  |
| 01 |  |  |  | FOUNDATION |  | 55,255 |  | SF |  |  | 1.74 | 96,177 |  | 55,255 |  | SF | 1.78 | 98,235 |  |  | 194,412 |  |
|  | 10 |  |  | STANDARD |  | 55,255 |  | SF |  |  | .62 | 34,171 |  | 55,255 |  | SF | .60 | 33,416 |  |  | 67,587 |  |
|  |  | 01 |  | EXCAVATION |  | 1,273 |  | CY |  |  | 2.00 | 2,546 |  | 1,273 |  | CY | 1.00 | 1,273 |  |  | 3,819 |  |
|  |  | 02 |  | CONCRETE 4000 PSI |  | 314 |  | CY |  |  | 14.00 | 4,396 |  | 2,980 |  | CY | 50.50 | 15,857 |  |  | 20,253 |  |
|  |  | 03 |  | FORMWORK |  | 8,000 |  | SF |  |  | 2.00 | 16,000 |  | 8,000 |  | SF | 1.00 | 8,000 |  |  | 24,000 |  |
|  |  | 04 |  | REINFORCING |  | 16 |  | T |  |  | 200 | 3,200 |  | 16 |  | T | 450 | 7,200 |  |  | 10,400 |  |
|  |  | 05 |  | FINISH |  | 7,579 |  | SF |  |  | .32 | 2,425 |  | 7,579 |  | SF | .02 | 152 |  |  | 2,577 |  |
|  |  | 06 |  | BACKFILL |  | 959 |  | CY |  |  | 5.84 | 5,604 |  | 959 |  | CY | .97 | 934 |  |  | 6538 |  |
|  | 20 |  |  | SPECIAL |  | 55,255 |  | SF |  |  | 1.12 | 68,006 |  | 55,255 |  | SF | 1.17 | 64,819 |  |  | 126,825 |  |
|  |  | 01 |  | DRILL 20"/60 PIER |  | 2,862 |  | LF |  |  | 3.25 | 9,302 |  | 2,862 |  | LF | 1.75 | 5,009 |  |  | 14,311 |  |
|  |  | 02 |  | DRILL 24"/72 PIER |  | 1,890 |  | LF |  |  | 3.75 | 7,088 |  | 1,890 |  | LF | 2.00 | 3,780 |  |  | 10,868 |  |
|  |  | 03 |  | DRILL 28"/84 BELLED PIER |  | 252 |  | LF |  |  | 4.50 | 1,134 |  | 252 |  | LF | 2.50 | 630 |  |  | 1,764 |  |
|  |  | 04 |  | HAUL OFF SPOIL |  | 1,162 |  | CY |  |  | 3.00 | 3,486 |  | 1,162 |  | CY | 3.00 | 3,486 |  |  | 6,972 |  |
|  |  | 05 |  | 400 PSI CONCRETE |  | 1,028 |  | CY |  |  | 7.00 | 7,196 |  | 1.028 |  | CY | 50.500 | 51,914 |  |  | 59,110 |  |
|  |  | 06 |  | REBAR |  | 52 |  | T |  |  | 200.0 | 10,400 |  | 52 |  | T | 450.0 | 23,400 |  |  | 33,800 |  |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DATE |  |  |  | SHEET NO. |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ESTIMATE WORKSHEET |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | OF |  |  |
| PROJECT NO. |  |  |  |  | LOCATION |  |  |  |  |  |  |  | PROJECT NAME |  |  |  |  |  |  |  |  |
| 101-001 |  |  |  |  | VAMC, ANY CITY, USA |  |  |  |  |  |  |  | SAMPLE PROJECT |  |  |  |  |  |  |  |  |
| TYPE OF ESTIMATE |  |  |  |  | ESTIMATOR |  | NEW | ALT. |  | INDEX NO. |  |  | BUILDING NO./NOS. |  |  |  |  |  | ESTIMATE NO. |  |  |
| DD1 |  |  |  |  | JOHN DOE |  | X |  |  | 1000.0 |  |  | 12 |  |  |  |  |  | CD-1 |  |  |
| CODE |  |  |  | SYSTEM/SUBSYSTEM |  | LABOR |  |  |  |  |  |  |  | MATERIALS |  |  |  |  |  |  | TOTAL |
| A | B | C | D |  |  | QUANTITY |  |  | UNIT |  | $/UNIT | TOTAL |  | QUANTITY |  | UNIT | $/UNIT | TOTAL |  | COST |  |
| 02 |  |  |  | SUBSTRUCTURE |  | 55,255 |  |  | SF |  | .49 | 27,217 |  | 55,255 |  | SF | .92 | 50,858 |  | 78,075 |  |
|  | 10 |  |  | SLAB ON GRADE |  | 55,255 |  |  | SF |  | .49 | 27,217 |  | 55,255 |  | SF | .92 | 50,858 |  | 78,075 |  |
|  |  | 01 |  | 10 MIL POLY |  | 55,255 |  |  | SF |  | .02 | 1,105 |  | 55,255 |  | SF | .05 | 2,763 |  | 3,868 |  |
|  |  | 02 |  | EDGE FORM |  | 3,350 |  |  | LF |  | 2.00 | 6,700 |  | 3,350 |  | LF | .50 | 1,675 |  | 8,375 |  |
|  |  | 03 |  | 4000 PSI CONC. CURED |  | 844 |  |  | CY |  | 23.05 | 19,412 |  | 844 |  | CY | 55.00 | 46,420 |  | 65,832 |  |
|  | 30 |  |  | BASEMENT WALLS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | -0- |  |
| 03 |  |  |  | SUPERSTRUCTURE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 10 |  |  | FLOOR (AT MECHANICAL |  | 2,980 |  |  | SF |  | .47 | 1,406 |  | 2,980 |  | SF | .93 | 3,194 |  | 4,600 |  |
|  |  | 01 |  | WIRE MESH |  | 32 |  |  | SF |  | 8 | 256 |  | 32 |  | SF | 16.00 | 512 |  | 768 |  |
|  |  | 02 |  | 4000 PSI CONC. |  | 49 |  |  | CY |  |  |  |  |  |  |  | 50.500 | 2,475 |  | 2,475 |  |
|  |  | 03 |  | PUMP CONC. |  | 49 |  |  | CY |  | 4.00 | 196 |  | 49 |  | CY | 3.00 | 147 |  | 343 |  |
|  |  | 04 |  | PLACE, FINISH, CURE |  | 2,980 |  |  | SF |  | .32 | 954 |  | 2,980 |  | SF | .02 | 60 |  | 1,014 |  |

VA FORM HO-18b

NOV 2006

01.	FOUNDATIONS

This element includes all work below the level of the lowest floor construction (usually slab on grade).  It is sub-divided at level B into:

Standard Foundations

- 	Which includes regular type spread footing foundations

Special Foundations and Conditions, etc

-	Which includes piling and caissons, underpinning, dewatering, raft

The section includes foundation walls up to the top of the lowest floor construction, but excludes slab on grade. Includes any excavation necessary to reduce levels or to form basements, or any backfillinq to generally raise levels.

Note that rock excavation is considered a special abnormal condition and is to be included with special foundation work.

All earthwork associated with site development is included in section 12 (Site Work).

02.	SUBSTRUCTURE

This element includes the enclosing horizontal and vertical elements required to form a basement, together with the necessary mass excavation.

At level B it is subdivided into:

Slab on Grad

-	Including all underfill, foundation drainage, trenches in slab, pits and bases

Basement Walls

-	Including required moisture protection

The section does not include any suspended structural slabs and supporting interior walls and columns contained within basements, which are to be carried in section 03.

In cases where slopping site conditions create variable basement levels, note that only basement walls below grade are to be carried in this section. All other walls above grade are to be included in section 04.

The items included in this section can perhaps best be described by the term "bath tub", comprising essentially basement walls.

In cases where no basements are present, then only slab on grade is included in this section.

03.	SUPERSTRUCTURE

This element includes all structural slabs, decks and supports within basements and above grade (see sketch 02 substructure). It is subdivided at level B into the following:

Floor Construction

-	Including balconies and ramps

Roof Construction

-	Both pitched and flat and including canopies and special roofing systems

Interstitial space

-	Horizontal walk-on platform/ceiling subsystem for the service systems above the functional spaces

Stair Construction

-	Note that the structural work will include both horizontal items (slabs, decks, etc.) and vertical structural components, columns and interior structural walls. Exterior load bearing walls are not included in this section but section 04.

Stair finishes are included in section 06.

04.	EXTERIOR CLOSURE

This element includes all vertical and horizontal closure features. It is subdivided at level B into:

Exterior Walls

-	Being the solid exterior closure element

Exterior Doors and Windows

-	Also including curtain walls

Loading bearing exterior walls will be included here and not in section 03. Structural frame elements at exterior such as columns, beams, spandrels, etc., would be included in section 03, with only applied exterior finishes (e.g. paint, stucco, etc.) being included here.

Finishes to the inside face of walls which are not an integral part of the wall construction, will be included in 0620.

05.	ROOFING

This element includes all waterproof roof coverings and insulation, together with skylights, hatches, ventilators and all required trim. The system proceeds directly to a level C breakdown.

In addition to roof coverings, the element includes all waterproof membranes and traffic toppings over below grade enclosed areas, balconies and the like.

06.	INTERIOR CONSTRUCTION

This element includes all architectural interior construction and is subdivided at level B into the following categories:

Partitions

-	Which also includes toilet partitions, interior balance of trades, doors and frames

Interior Finishes

-	To walls, floors and ceilings

Specialties

-	Standard built-in items and specialties, such as toilet accessories and other built-ins, which would commonly be found in most building types

The element does not include interior structural walls, which are included in section 03.

Any special equipment, built-in or movable, will be found in section 11.

07.	CONVEYING SYSTEMS

This element is identical--to U.C.I. division 14 and includes elevators, escalators, etc. and also pneumatic tube systems, conveyers, chutes, etc.

08.	MECHANICAL

This element closely parallels CSI Division 15. It is subdivided at level B into the following:

Plumbing

- 	Including drainage

Heating, Ventilating and Air Conditioning

Fire Protection

- 	Including sprinklers

Medical Gas Systems

Exterior site utilities are to be included in section 1230.

09.	Electrical

This element closely parallels CSI Division 16. It is subdivided at level B into the following:

Basic Materials and Methods

-	Distribution and Panelboards

-	Include: Switchboards, panelboards, starters, motor connections, motor control centers, circuit breakers, generator sets, wires/conduits, equipment transformers, bus duct

-	Branch Wiring and Devices

-	Include: Receptacles outlet boxes, multi-outlet assemblies, raceways, junction boxes, pull boxes, cable management systems, wires/conduits

Lighting and Power

-	Lighting Fixtures Include: Interior lights, exit lights, surgical lights, entrance lights switches, energy conservation devices, wire/conduits

Special Electrical Systems

-	Emergency Power and Lights Include: Emergency light fixtures, switches, panels and wires/conduits, battery powered emergency lights

Other Special Electrical Systems

-	Include: Lightning protection, grounding system, wires/conduits, x-ray electrical system, uninterruptible power system

Communication Systems

-	Fire Alarm System:  Devices and Wiring

-	Nurse Call System:  Devices and Wiring

-	Telecommunications:  Devices and Wiring

-	Closed Circuit Television Systems:  Devices and Wiring

-	PBPU'S - PIPU'S:  Devices and Wiring

-	Medical Gas Alarm Panel:  Devices and Wiring

Security Systems

Electrical Heating Systems

-	Include: Control devices and wiring to boilers, baseboard heaters and HVAC Systems

10.	GENERAL CONDITIONS AND PROFIT

This element includes all site overhead items, mobilization, demobilization, together with a pro rata charge of the general contractor's head office overhead expense and a profit mark-up. When construction management contracts are used, the later often becomes a fee and may be carried elsewhere.

For convenience, estimators-have traditionally included in General Conditions certain costs which could be considered distributable to a work section (e.g. sales taxes, labor fringe benefits, equipment for placing concrete, etc.). In this breakdown, such items shall be distributed to the work sections.

Note that this section includes only general contractor's or construction managers' general condition items and that all subcontractors' overheads and profit should be included in each respective work section.

CLARIFICATION

In filling out the project cost data sheets, the general contractor's overhead and profit on subcontractors' work should be included in General Conditions and Profit. However, the general contractor's overhead and profit on his own work and the subcontractors' overhead and profit should be included in the cost of each item of work.

11.	EQUIPMENT

This element accords fairly closely with CSI Divisions 11, 12 and 13. It is subdivided at level B into:

Specialized Equipment

-	i.e., food service, laboratory, etc.

Furnishings

Special Construction

As furniture is funded from separate sources, there is no further development of this sub-element here.

12.	SITE WORK

This element includes all work outside the immediate building confines and is subdivided at level B into the following:

Site Preparation

- 	Clearing, demolition and earth moving

Site Improvement

- 	Landscaping, paving, parking, roads, etc.

Site utilities

-	Storm & sanitary sewers

-	Domestic water, fire protection water, hot & chilled water

-	Steam & condensate

-	Electrical

-	Utilities

-	Substations, etc.

-	Telecommunications, data, fire alarm, security, campus systems

Off-site work

- 	For special railroad and marine work and any other off-site construction required

Note that general grading to reduce levels over the site occupied by the building will be included in this section.

This site utilities sub-section does not include the following elements:

Heat Generating System

Cooling Generating System

These elements are contained within the Mechanical (08) section of the Logic Tree.

In the event that a "Campus" situation exists which includes a central energy facility (separate building), a completely separate Logic Tree should be developed for this building and its contents.

The Site Utility sections of the Logic Tree, therefore, contain distribution elements only, with source elements being contained within buildings.

| SYSTEM OR SUBSYSTEM | CODE |  |  |  | UNIT OF MEASURE |
| --- | --- | --- | --- | --- | --- |
| NAME | A | B | C | D |  |
| FOUNDATION STANDARD EXCAVATION-BACKFILL (FOUND) CONCRETE-FORMS-RB (FOUND) MASONRY SPECIAL ROCK EXCAVATION DEWATERING STRUCTURAL STEEL (FOUND) PILES AND CAISSONS UNDERPINNING SUB-STRUCTURE SLAB ON GRADE GRANULAR FILL BELOW FOUND OR UNDERSLAB DRAIN CONCRETE-FORMS-RB (SOG) WATER DAMPROOFING (SOG) THERMO-INSULATION BASEMENT WALLS CONCRETE-FORMS-RB (BSMT WALL) MASONRY (BSMT WALL) WATER-DAMPROOFING (BSMT WALL) SUPER-STRUCTURE FLOOR CONSTRUCTION CONCRETE-FORMS-RB (FLOOR) PRECAST STRUCT COMP FLOOR STRUCTURAL STEEL (FLOOR) ROUGH CARPENTRY FRM DECK HVY. TIMBER PREFAB STR (FLOOR) CEMENTITIOUS DECKS (FLOOR) ROOF CONSTRUCTION CONCRETE-FORMS-RB (ROOF) PRECAST STRUCT. COMPONENTS (RF) STRUCTURAL STEEL (ROOF) ROUGH CARP FRAME-DECK (ROOF) HVY TIMBER PREFAB STR. CEMENTITIOUS DECKS (ROOF) INTERSTITIAL CONSTRUCTION CONCRETE-FORMS-RB (INTERSTITIAL) PRECAST STRUCT. COMPONENTS (IS) STRUCTURAL STEEL (INTERSTITIAL) ROUGH CARP FRAME-DECK (INTER) CEMENTITIOUS DECKS (INTER) STAIR CONSTRUCTION CONCRETE-FORMS-RMS (STAIRS) METAL STAIRS WOOD STAIRS SOLAR ENERGY (STRUCTURAL STEEL) | 01 02 03 | 10 20 10 20 10 20 30 40 | 01 02 03 01 02 03 04 05 01 02 03 04 05 01 02 03 01 02 03 04 05 06 01 02 03 04 05 06 01 02 03 04 05 01 02 03 |  | FOOT PRINT AREA FOOT PRINT AREA CU YDS (m3) EXCAVATION CU YDS (m3) CONCRETE SQ FT (m2) MASONRY FOOT PRINT AREA CU YDS (m3) EXCAVATION LUMP SUM TONS OF STEEL LF (m) PILES & CAISSONS CU YDS (m3) CONCRETE SQ FT (m2)(SOG) SQ FT (m2)(SOG) TONS (t) OF FILL LF (m) PIPE Cu YDS (m3) CONCRETE SQ FT (m2) CONTACT AREA SQ FT (m2) CONTACT AREA SQ FT (m2) WALL CU YDS (m3) CONCRETE SQ FT (m2) MASONRY SQ FT (m2) CONTACT AREA SQ FT (m2) AREA FL & RF SQ Ft (m2) AREA FLOOR CU YDS (m3) CONCRETE SQ FT (m2) AREA COMPS TONS (t) OF STEEL BOARD FT (m) OF LUMBER BOARD FT (m) OF LUMBER SQ FT (m2) DECK SQ FT (m2) AREA ROOF CU YDS (m3)CONCRETE SQ FT (m2) AREA OF COMPS TONS (t) OF STEEL BOARD FT (m) OF LUMBER BOARD Ft (m) OF LUMBER SQ FT (m2) DECK SQ FT(m2)AREA FLR & CEIL CU YDS (m3)CONCRETE SQ FT (m2) AREA OF COMPS TONS (t) OF STEEL BOARD FT (m) OF LUMBER SQ FT (m2) DECK RISERS # OF RISERS FLIGHTS # OF RISERS TONS (t) OF STEEL OR CU YDS (m3) CONCRETE |
| EXTERIOR CLOSURE EXTERIOR WALL CONCRETE-FORMS-RB (EXT WALL) PRECAST CONCRETE (EXT WALL) MASONRY (EXT WALL) ROUGH CARPENTRY (EXT WALL) EXT WOOD SIDING & TRIM WATER-DAMPROOFING (EXT WALL) THERMAL INSULATION (EXT WALL) PREFORM SIDING PNLS. (EXCLD MAT.) PREFORM SIDING PNLS. (MATERIAL) SEALANT-CAULKS WALL FINISHES (EXT) SUN-CONTROL DEVICES MISC METAL (EXT WALL) EXTERIOR DOORS & WINDOWS DOOR-FRAME-HDWARE (EXT) WINDOWS (EXT) CURTAIN WALLS (INCLD STRE FRT) ROOFING ROUGH CARP EXCPT FRME. & DECK THERMAL INSULATION (ROOF) ROOFING (SHINGLES, TILES, ETC.) MEMBRANE-TOPPING (INCLD BLT-UP) SHEET-METAL & ACCESSORIES (ROOF) INTERIOR CONSTRUCTION PARTITIONS PARTITIONS (FIXED) ROUGH CARPENTRY (PARTITIONS) DOOR-FRAMES-HDWARE (INTERIOR) WINDOWS (INTERIOR) COMPARTMENTS & CUBICLES PARTITIONS (MOVABLE) INTERIOR FINISHES CONCRETE FINISH WOOD PANELING WALL FINISHES (INTERIOR) FLOOR COVERING (RESILIENT) ACOUSTICAL CEIL TREATMENT SPECIAL FLOOR-MAR, TERRAZZO, ETC SPECIAL FLOOR COVERING-COAT PAINTING (INTERIOR) CEILING (OTHER THAN ACOUST) | 04 05 06 | 10 20 00 10 20 | 01 02 03 4 05 06 07 08 09 10 11 12 13 01 02 03 01 02 03 04 05 01 02 03 04 05 06 01 02 03 04 05 06 07 08 09 |  | SQ FT (m2) WALLS & OPENS SQ FT (m2) WALL CU YDS (m3) CONCRETE CU FT (m3) CONCRETE SQ FT (m2) MASONRY BOARD FT (m) LUMBER SQ FT (m2) SIDING SQ FT (m2) CONTACT AREA SQ FT (m2) CONTACT AREA SQ Ft (m2) WALL SQ FT (m2) WALL LUMP SUM SQ FT (m2) WALL LUMP SUM POUNDS (kg) METAL SQ FT (m2) AREA OPENINGS # OF LEAVES SQ FT (m2) WINDOWS SQ FT (m2) CURTAIN WALLS SQ FT (m2) AREA ROOF BOARD FT (m) LUMBER SQ FT (m2) CONTACT AREA SQ FT (m2) AREA ROOF SQ FT (m2) AREA ROOF LUMP SUM SQ FT (m2) FLOOR AREA SQ FT (m2) AREA PARTNS SQ Ft (m2) AREA PARTNS BOARD FT (m) LUMBER # OF LEAVES SQ FT (m2) AREA WINDOWS LUMP SUM SQ Ft (m2) AREA PARTNS SQ FT (m2) FIN.SURFACE SQ FT (m2) FIN. SURFACE SQ FT (m2) PANEL SQ FT (m2) FIN. SURFACE SQ FT (m2) FLOOR AREA SQ FT (m2) ACOUST CEIL SQ Ft (m2) FLOOR AREA SQ FT (m2) FLOOR AREA SQ Ft (m2) PAINT SURFACE SQ FT (m2) CEILING |
| SPECIALTIES MISC ORNAMENTAL MTL (BLDG) FINISH CARP-MILLWORK-CABINETS PLASTIC FABRICATION CHALK-TACK-BOARDS SIGNS TOILET-BATH-WARDROBE ACCES ACCESS FLOORING LOCKERS SHELVING MISC SPECIALTIES CONVEYING SYSTEMS ELEVATORS MOVING STAIRS/WALKS DUMBWAITERS PNEUMATIC TUBE SYSTEM OTHER CONVEYING SYSTEMS HOISTS & CRANES MATERIAL HANDLING CHUTES CONVEYORS (BELT, ROLLER, ETC.) MECHANICAL SYSTEMS PLUMBING DOMESTIC WATER SUPPLY SANITARY WASTE & VENT PLUMBING EQUIPMENT PLUMBING FIXTURES RAIN WATER DRAINS (INT) HVAC HEAT GENERATING SYSTEM HEAT GENERATING SYSTEM DISTRIBUTION SYSTEM DUCTWORK AHU & THERMAL UNITS HVAC PIPING (INT) AIR DISTRIBUTION DEVICES CONTROLS TEST & BALANCE FIRE PROTECTION AUTOMATIC SPRINKLER SYSTEM OTHER FIRE PROTECTION SYSTEM SPECIFY: MEDICAL GAS SYSTEM MEDICAL GAS PIPING MEDICAL GAS EQUIPMENT SEWAGE TREATMENT (NEW) | 06 07 08 | 30 10 20 30 40 50 10 20 30 40 55 | 01 02 03 04 05 06 07 08 09 10 01 02 03 04 01 02 03 04 05 01 02 03 04 01 02 01 02 | 01 02 03 04 | SQ FT (m2) FLOOR AREA POUNDS (kg) OF METAL LUMP SUM LUMP SUM LUMP SUM LUMP SUM LUMP SUM SQ Ft (m2) FLOOR AREA # OF LOCKERS # OF SHELVES LUMP SUM # OF STOPS FLIGHTS OR LENGTH # OF STOPS # OF STATIONS CAPACITY IN POUNDS (kg) LENGTH IN FT (m) # OF FIXTURES LENGTH OF PIPE IN FT (m) LENGTH OF PIPE IN FT LUMP SUM # OF FIXTURES LENGTH OF PIPE IN FT (m) TONS (KW) MBTU (FEFR/J) MBTU (J) OR LBS/HR(kg/s) TONS (KW) OF REFRIG. TONS (KW) MBTU (FEFR/J) LBS (kg) OF SHEET METAL # OF UNITS LENGTH OF PIPE IN FT (m) # OF UNITS TONS (KW) MBTU (FEFR/J) ONLY SQ FT (m2) PROTECT. AREA # OF HEADS # OF STATIONS SERVED LENGTH OF PIPE IN FT (m) # OF PIECES |
| SEWAGE TREATMENT (ALT) SOLAR ENERGY MECH SYSTEM (BLDG) ELECTRICAL SYSTEM BASIC MATERIALS & METHODS DISTRIBUTION & PANEL BOARDS BRANCH WIRING & DEVICES LIGHTING LIGHTING FIXTURES SPECIAL ELECTRICAL SYSTEMS EMERGENCY POWER & LIGHTS OTHER SPECIFY: COMMUNICATION SYSTEM FIRE ALARM SYSTEM NURSE CALL SYSTEM TELECOMMUNICATIONS CLOSED CIRCUIT TELEVISION SYS PIPUS & PBPUS MEDICAL GAS PANELS SECURITY SYSTEMS ELECTRICAL HEATING SYSTEM GENERAL CONDITIONS GENERAL REQUIREMENTS EQUIPMENT SPECIAL EQUIPMENT BUILT IN MAINT EQUIPMENT FOOD SERVICE VENDING WASTE HANDLING POSTAL DARKROOM ECCLESIASTICAL EDUCATIONAL ATHLETIC LABORATORY LAUNDRY LIBRARY MEDICAL MORTUARY PHARMACY WATER TREATMENT FINISHES SPECIFY: | 09 10 11 | 60 10 20 30 40 50 10 20 | 01 02 01 01 02 01 02 03 04 05 06 07 01 02 03 04 05 06 07 08 09 10 11 12 13 14 15 16 |  | SQ FT (m2) SOLAR PANEL KW SEE KVA ATTACHMENT KVA “D” KVA FIG. NO. 1 SQ FT (m2)SERVED SQ FT (m2)SERVED SQ FT (m2)SERVED SQ FT (m2)SERVED SQ FT (m2)SERVED SQ FT (m2)SERVED SQ FT (m2)SERVED SQ FT (m2)SERVED SQ FT (m2)SERVED SQ FT (m2)SERVED # OF PUPUS & PBPUS # OF PANELS SQ FT (m2)SERVED LUMP SUM DURATION OF CONTRACT DURA. OF CONT. WEEKS # OF PIECES OF EQUIPMENT # OF PIECES OF EQUIPMENT # OF PIECES OF EQUIPMENT # OF PIECES OF EQUIPMENT # OF PIECES OF EQUIPMENT # OF PIECES OF EQUIPMENT # OF PIECES OF EQUIPMENT # OF PIECES OF EQUIPMENT # OF PIECES OF EQUIPMENT # OF PIECES OF EQUIPMENT # OF PIECES OF EQUIPMENT # OF PIECES OF EQUIPMENT # OF PIECES OF EQUIPMENT # OF PIECES OF EQUIPMENT # OF PIECES OF EQUIPMENT # OF PIECES OF EQUIPMENT # OF PIECES OF EQUIPMENT # OF PIECES OF EQUIPMENT |
| SPECIAL CONSTRUCTION SPECIAL PURPOSE ROOMS AUDIOMETRIC CLEAN OTHER SPECIFY: RADIATION PROTECTION THERAPEUTIC POOLS OTHER SPECIAL CONSTRUCTION SPECIFY: TOTAL BUILDING COST SITEWORK SITE PREPARATION CLEARING DEMOLITION (GENERAL) DEMOLITION (BUILDING) EARTHWORK (SITE) SITE IMPROVEMENTS PAVING (OTHER THAN MASONRY) LANDSCAPING CONCRETE-FORM-RB (SITE) PRECAST COMPONENTS (SITE) MASONRY PAVING (SITE) MISC ORNAMENTAL MTLS (SITE) FLAG POLES FREE STANDING STACKS SITE UTILITIES TUNNELS LAWN SPRINKLERS MECH UTILITIES ELEC UTILITIES SUB-STATIONS & TRANSFORMERS SUBSTATIONS/XFMR BUILDING OR ENCLOS (UNLESS SELF CONTAINED) EMERGENCY GENERATORS EMER GEN BLDG/ENCLOSURE CHILLER BUILDING BOILER PLANT CONVENTIONAL ENERGY SUPPLY (OIL TANKS, GAS METERS, ETC.) SOLAR ENERGY SYSTEM (SITE) (COLLECTION, DISTR, STORAGE) OFF SITE WORK SPECIFY: TOTAL BASE CONSTRUCTION COST | 11 12 | 30 10 20 30 40 | 01 02 03 04 01 02 03 04 01 02 03 04 05 06 07 08 01 02 03 04 05 06 07 08 09 10 11 12 | 01 02 03 | SQ FT (m2)OF ROOM SQ FT (m2)OF ROOM SQ FT (m2)OF ROOM SQ FT (m2)OF ROOM PROTECT AREA SQ FT (m2) VOLUME OF CU FT (m3) DESIGN NET AREA SQ FT (m2)(INCL IN PROJ) SQ FT (m2)(INCL IN PROJ) SQ FT (m2)(CLEARED) LUMP SUM CU FT (m3) BUILDING SQ FT (m2)(INVOLVED) SQ FT (m2)(INCL IN PROJ) SQ YDS (m2) SURFACE SQ FT (m2) LANDSCAPE CU YDS (m3) CONCRETE LUMP SUM SQ FT (m2) SURFACE POUNDS (kg) METAL # OF POLES HEIGHT OF STACK SQ FT (m2)(INCL IN PROJ) LENGTH IN FT (m0 SQ FT (m2) SPRINKLED LENGTH OF PIPE LF(m) DIR BURY OR DUCTBK KVA OF SUBSTATIONS SQ FT (m2)BLDG/ENCLOSED KW OF GENERATOR SQ FT (m2)BLDG/ENCLOSED SQ FT (m2)BLDG/ENCLOSED SQ FT (m2)BLDG/ENCLOSED SQ FT (m2)SOLAR PANEL LUMP SUM |

PROCEDURE FOR COMPUTATION OF BUILDING GROSS AREA

l.  The AE shall submit to the Contracting Officer a report of the gross area of his design at each of his submissions.

2.  The AE shall prepare the gross area computation as follows: Submit a small-scale plan of each individual floor. Subdivide each floor into rectangle with each rectangle designated by a capital letter. List all the letters on one floor alphabetically. Clearly indicate length and width of each lettered area and the total square meters (footage) of each lettered area in tabular form. Show the sum of these areas as the "Designed Gross Area".

3.  Area Computation: (See Attached Diagram)

4.  List of Computations:

First Floor Area	L	W		S.F. (m2)

A	X	Y	=	s.f. (m2)
B	"	"	=
CC	"	"	=
etc.	"	"	=
Design Gross Area for the first floor:		s.f. (m2)
(Similar computation for every floor)

Recapitulation
Basement		s.f. (m2)
1st floor		s.f. (m2)
2nd Floor		s.f. (m2)
Penthouse		s.f. (m2)
Total Designed		Target Gross

Gross Area _________ s.f. (m2)	Area 	__________ s.f. (m2)

5.  Special Areas To Be Considered:

a.	Exterior Stacks and Chimneys:
Count free standing masonry stacks only once. Exterior masonry stacks attached to the building are counted an each floors. Exterior stacks that are not enclosed in masonry are not counted.

b. Areas Which Are Not Counted in Gross Area:
Pipe basement or crawl space
Areaways either grilled over or open
Cat-Walks
Outside ramps or steps (without cover)
Cooling towers
Exposed mechanical equipment enclosed with a screen wall but not roofed
Fuel tanks or pneumatic tanks placed underground
Oxygen storage tanks placed on a slab at ground level enclosed by a fence or screen
Mezzanine or balcony in two-story rooms when mezzanine or balcony is a grille floor without equipment
Porches
Outside balconies
Areaways
Leading platforms
Covered driveways
Other roofed areas or passage without enclosing walls

DIAGRAM SHOWING METHOD OF SUBDIVIDING BUILDING FOR GROSS AREA CONSTRUCTION

INDEX

BUILDING SYSTEM DESCRIPTIONS						3, ATCH D

CODING AND UNITS OF MEASURE						2

Code Level A									2.2

Code Level B									2.3

Code Level C									2.4

Code Level D									2.5

COMPUTER AIDED FACILITIES MANAGEMENT				1.5

COSTS										7

DESIGN DEVELOPMENT

General Items									8.2.5

Market Survey									8.1.3

DETAILED TAKE OFF								6, ATCH C

FORMS									4

Cost Summary Worksheet							4.4, ATCH A

Estimate Worksheet								4.3, ATCH A

Project Data Sheet #1								4.1, ATCH A

Project Data Sheet #2								4.2, ATCH A

MARKET SURVEY								8.1

Construction Document							8.1.4

Design Development								8.1.3

Schematics									8.1.2

MATRIX									5, ATCH B

TECHNICAL INFORMATION RESOURCES					1.4.1

AE Checklists 									1.4.1.4

AE Submission Instructions							1.4.1.2

Cost estimating Manual							1.4.1.12

Design Alerts									1.4.1.5

Design and Construction Procedures						1.4.1.8

Design Guides									1.4.1.7

Master Specifications								1.4.1.3

National CAD Standards							1.4.1.9

Physical Security Design Manual for VA Facilities				1.4.1.10

Practice Design Manuals							1.4.1.1

Quality Alerts									1.4.1.6

Sustainable Design Manual for New Hospitals,

Replacement Hospitals, Ambulatory Care, Clinical Additions,

Outpatient Clinics and Nursing Homes					1.4.1.13

Technological Summaries							1.4.1.11