LOGO TO COPY

America Saves Week Talking Points

America Saves is a national social marketing campaign that encourages individuals, particularly low and moderate income persons, to save money, reduce debt and build wealth.

Launched in 2001 with one city, Cleveland, Ohio, America Saves has now 53 local, state and national campaigns: Examples include Philadelphia Saves, Utah Saves, San Diego Saves, NY State Saves, Texas Saves, Kansas City Saves, Milwaukee Saves, Miami Saves, Tennessee Saves, Silicon Valley – South Bay Saves, Military Saves, Youth Saves, Black America Saves, Hispanic Saves, and America Saves through Homeownership.

Currently more than 61,000 Savers: top Savings Goals are

- Emergency Fund

- Savings & Investment

- Homeownership

- Retirement Savings

|  | $1 to $25 | $26 to $50 | $51 to $75 | $76 to $100 | $101 to $200 | $201 to $500 | $501 to$1000 | #Per Goal | Average $ |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Emergency Fund | 4565 | 2925 | 246 | 0 | 762 | 450 | 54 | 9002 | $68 |  |
| Savings/ investment | 3704 | 1923 | 135 | 1070 | 603 | 486 | 63 | 7984 | $74 |  |
| Homeownership | 3077 | 1824 | 230 | 1437 | 59 | 686 | 95 | 7408 | $93 |  |

America Saves has been congratulated by Federal Reserve Chairman Ben Bernanke upon reaching 50,000 Savers.

America Saves has over 500 financial institutions both banks and credit unions providing no or low fee, low opening balance savings accounts that allow small savers to achieve success.

More than 1,000 non profit organizations, companies, government agencies, educational institutions, religious institutions, and unions are involved.

America Saves Week, February 25 – March 4, 2007, is a new and expanded effort aimed at reaching more institutions and individuals to increase awareness on the need to save money, reduce debt and build wealth with a primary focus on Financial Action – commitments to save, invest and build wealth.

National partners include: Department of Defense, IRS, Federal Reserve Bank, Cooperative State Research, Education, and Extension Service (CSREES), USDA, and participating land-grant university Extension Services, National Foundation for Credit Counseling, United Way of America,  National Black Caucus of States Institute, Corporation for Enterprise Development, Annie E. Casey Foundation, Family, Career and Community Leaders of America (FCCLA), and National Community Tax Coalition.

Any and all organizations, institutions and companies are encouraged to identify goals that are measurable and can demonstrate impact. These will be compiled on an annual basis, proclaimed and announced, and then measured every year to determine impact and progress. These goals can include for example a financial institution announcing a goal of opening 1,000 new savings accounts targeted to branches in low and moderate income neighborhoods; employers announcing a goal of increasing employee participation into a 401k program by 2%; a religious institution announcing that every congregant will have by one year a minimum of $500 in a savings account for emergencies; a non profit organization announcing that 100 people will be saving towards homeownership and reach their goal within two years; a school system that announces 75% of all their middle and high school students will open a savings account and have a minimum of $25 deposited within 6 months..

These numbers will be tallied and announced in aggregate both locally and part of the national America Saves Week impact report.

ORGANIZING BENEFITS

America Saves Week 		February 25 – March 4, 2007

- Building local partnerships and networks related to financial education

- Increased visibility through local media

- State and national collection and aggregation of evaluation data

- Marketing and expansion of existing financial education programs

- Flexibility to develop programs for local needs and cultural relevancy

- User-friendly materials and administrative support from the Consumer Federation of America

- An opportunity to highlight annual financial accomplishments

How To:

Send Notification Letter

Send notification letter to decision makers at potential and current partner organizations asking for participation, support endorsement

Distribute Resource –

Community wide distribution—posters, flyers, newsletter inserts, press release/story (those campaigns that have identified a media partner for America Saves Week, utilize that partnership.)

Organizational distribution—site visits with decision makers, distribution of activities material and secure participation.

Develop FI Promotion-

With bank and credit union partners encourage promotion through:  statement stuffer, teller info, posters, IRS split refund two pager, press releases, incorporate Week into their brand ads.

Promote Split Refund

Take advantage of existing partnerships to promote refund split. paycheck stuffers, payroll provider’s participation,

Press Event Announcing National Partnership

January press event to announce partnership with Washington event and local events.

Saver Week Press Event

A second press event during America Saves Week to recognize participation and celebrate success to date.

AS Week Timeline Grid

Before				           During					After

Promotion: fliers, fact sheet,		Issue press release.                  	Continue regular

announcements, presentations ..         Announce completed               	program activity and

Engage and enroll current                  or to be completed                    	enroll savers.

program participants as savers.           activity.                                    Participate in evaluation.

Identify and develop                           Hold event with partner.

partnerships with  bank or

credit union.

# Level 1

Dec		Jan		Feb		March		April

- Promotion -------------------------------------------------------------

- Fliers, announcements, presentations …

- Identify/develop ----------------------------------------------------------------------------

Financial institution partner

- Identify activities   -----------------

- Enroll Savers --------------------------------------------------------------------------------

- Press release/announcement			   ----------------------

- Evaluation							     ------------------

- Press release/announcement			                          ----------

Level 2

Nov	        Dec	         Jan	           Feb	          March		April

- Promotion -------------------------------------------------------------------------------

- Identify/develop

- Partners -------------------------------------------------------------------------------------------------

- Identify/develop   --------------------------------------------------------------------------------------Financial institution partners

- Plan activities                     -----------------------------------------

- Develop master activity list                              ------------------

- Enroll savers                   ------------------------------------------------------------------------------

- Press release/announcements                                                    ------------------

- Post event                                                                                                         -------------

- Evaluation                                                                                                        --------------

- Press release/announcements							  --------

Level 3

Sept.	Oct.	Nov.	Dec.	Jan.	Feb.	Mrch.	April

- Identify/develop partners -----------------------------------------------------------------------

- Planning                                            -----------------------------------------

- Activities defined                                                                        ---------

- Promotion                                                  ---------------------------------------------

- Master activity list defined                                                      ----------

- Enroll savers                        ---------------------------------------------------------------------

- Press release/announcements                                                                  ----------

- Post event                                                                                                        -----------

- Evaluation                                                                                                            ----------

- Press release/announcements

- ------

SAMPLE LETTER TO INVITE ORGANIZATION AND LEADERSHIP PARTICPATION

SAMPLE…SAMPLE…SAMPLE….SAMPLE….SAMPLE….SAMPLE….SAMPLE

Dear

Currently, the national savings rate is 0%, something that has not occurred since the Great Depression.  A recent study, commissioned by Consumer Credit Counseling Service, revealed that overall consumer debt has increased by 38% for households at all income levels over the last year.  Delaware Valley households are taking on more debt and saving less than ever before.

To combat these startling statistics, Philadelphia Saves, is organizing our first annual event – Philadelphia Saves Week, February 25 – March 4, 2007.

Philadelphia Saves, a local offshoot of the America Saves campaign, has made significant progress in the last three years, helping over 2,600 Philadelphians save money and build wealth.  By becoming Philadelphia Savers, these individuals have committed to saving over 3.7 million dollars toward a specific financial goal.

Federal Reserve Chairman Bernake has encouraged all America Saves campaigns to expand efforts and combat the low savings rate. Philadelphia Saves Week will focus on promoting savings and motivating individuals, particularly those in low-moderate income households, to take FINANCIAL ACTION.

The goal of Philadelphia Saves Week is to generate targeted activities from a variety of organizations across the region resulting in behavior change among individuals and families.  We ask that you participate in this campaign in one or more of the following ways:

- Demonstrate support through a written endorsement

- Promote Philadelphia Saves Week and encourage participation from other organizations and institutions

- Participate by engaging your organization in one or more of the activities outlined in the attached “Suggested Activities List”

Through educational events, contests and other fun activities, you can join other local financial institutions, non-profits, corporations, government agencies and the media in showing your support and commitment to wealth building.  However, one of the great things about the Week model is that activities can occur before, during, or after the Week, and still have the results (or projected results) announced at high-profile media events.

The attached fax reply describes the various opportunities for your organization to participate.  Please look it over and reply by _____.  Also enclosed is a fact sheet on both America and Philadelphia Saves campaigns.  We look forward to your support and participation.

Sincerely,

National Partners:

Consumer Federation of America, Cooperative State Research, Education, and Extension Service (CSREES), USDA, and participating land-grant university Extension Services, United Way of America, Department of Defense, the Internal Revenue Service, National Foundation for Credit Counseling, Federal Reserve Bank, National Black Caucus of States Institute, Corporation for Enterprise Development, National Community Tax Coalition, Family, Career and Community Leaders of America (FCCLA) and

SAMPLE PROCLOMATION

2007 AMERICA (or community or organization name) SAVES WEEK

BY (TITLE OF OFFICIAL MAKING PROCLAMATION)

A PROCLAMATION

WHEREAS, personal and household savings is fundamental to America’s (or community or organization) stability and vitality; and

WHEREAS, adequate emergency savings, retirement funds, and safe debt-income ratios are critical components of personal financial security; and

WHEREAS, America Saves is a national social marketing campaign to persuade, encourage, and motivate Americans to take financial action in building wealth through saving money and reducing debt;

WHEREAS, (name of organization or community) is a partner in the America Saves campaign and is committed to helping its (members, citizens, clients, customers, and/or employees) take immediate financial action to Build Wealth, Not Debt;

NOW, THEREFORE, (I, Name, Title, or name of governing body) do/does hereby proclaim the February 25 – March 4, 2007 as

AMERICA (or community or organization name) SAVES WEEK

AND DO DECLARE (statement of ASW related goal)

I/WE HEREBY call upon all (members, citizens, clients, customers, and/or employees) to (increase 401k contributions, start or increase an emergency fund, challenge employees or customers to save, or other goal related action) or take another positive wealth-building action during AMERICA (or community or organization name) SAVES WEEK, and pledge to sustain that action during the following year.

IN WITNESS WHEREOF, I/we have hereunto set my/our hand(s) this (date) day of (month), 2006/07.

(Signature/s)

MEMORANDUM

To:		America Saves Coordinators

From:		George Barany and Steve Brobeck

Re:		Ideas for America Saves Week press release

______________________________________________________________________________

We suggest you consider including the following elements in press releases that announce your local/regional Saves Week:

- Date and major events:  Week selected (probably February 25 to March 4 in 2007).  Major events scheduled for that week, especially those to which the public is invited.

- Expected local impacts:  Savers reached, dollars saved, institutions affected.  And give examples -- e.g., x bank has set a goal of opening up 200 savings accounts for low-income households, y employer has set a goal of enrolling 100 new employees in its 401k retirement plan, z nonprofit has set a goal of persuading 150 of those it serves to roll their loose change and deposit it in savings.

- Local participants:  Institutional leaders, the broad range of participating institutions, and the number of these institutions.

Relation to America Saves Week and America Saves:  x Saves Week is part of a larger nationwide America Saves Week that includes local, regional, and national organizations.  Local Saves weeks are being organized in ... (to be filled in).  National partners include Consumer Federation of America, Cooperative State Research, Education, and Extension Service (CSREES), USDA, and participating land-grant university Extension Services, United Way of America, Department of Defense, IRS, Federal Reserve Bank, National Foundation for Credit Counseling,  National Black Caucus of States Institute, Corporation for Enterprise Development, Annie E. Casey Foundation, Family, Career and Community Leaders of America (FCCLA), and National Community Tax Coalition.... 	(list others).

America Saves is a five-year old effort to encourage non-saving Americans to save through a social marketing approach.  About 1,000 organizations in some 50 local areas participate, and these organizations have encouraged and assisted hundreds of thousands of savers, especially the some 60,000 who have enrolled as American Savers.

- National Savings Needs:  Most Americans do not have adequate savings to meet major emergencies, let alone accumulate enough savings for retirement.  The typical American household has less than $100,000 in net wealth, including home equity and 401k accumulations, and only about $10,000 in net financial assets.  Lower income families have much fewer resources.  The fact that the national savings rate is negative, while the prices of homes and securities are basically stagnant, suggests, in terms of household savings, we are moving backwards.

- Include a quote or two or three, in part to recognize key leaders of the Saves Week.

Suggested Activity List for America Saves Week

Employers

- Distribute Saves fliers and brochures

- Display  Saves posters

- Send one or more stock emails regarding Saves Week

- Place Saves Week article(s) in internal newsletter

- Enclose a Saves flier as a payroll stuffer

- Place a notice of and information about  Saves Week on internal computer system

- Place a link to Saves on company website or internal network

- Increase 401k participation and contributions through one or more motivational workshops

- Provide access to no fee savings accounts through Saves enrollment – presentation(s), motivational workshop(s), and or topic seminar(s) i.e. EITC, Homeownership; Auto Purchase …

- Host an event featuring Saves and 401k provider, Bank for products and services

Financial institutions

- Target a number of new savings accounts to be opened

- Target a number of new savings accounts to be opened specifically for LMI

- Target a number of low cost CD’s to be opened

- Target a number of Savings Bonds Series I to be sold

- Distribute Saves Week fliers at branches

- Make available Saves Week fliers at teller windows

- Make available Saves brochures and enrollment forms at Teller windows

- Host motivational workshops with partner organizations such as schools, non profits or at a library

- Enclose Saves Week brochure, flier in statement envelopes

- Feature  Saves Week on website

- Put a link on website to Saves

- Utilize Saves Week as part of Bank at Work presentations

- Target a number of Bank at Work presentations as part of  Saves Week

- Send a number of bank staff into schools to provide financial education and Saves enrollment as part of the week

- Feature Saves Week in advertising campaign

- Hold a press event promoting  Saves Week and the commitment of targeted numbers

Non Profit Organizations

- Distribute Saves Week fliers, brochure and/or posters

- Place Saves Week article in newsletter and/or community newspaper

- Host motivational workshops for clients, constituents, members

- Declare a goal of new savings accounts opened, dollars to be saved, homes to be purchased, new business to be opened, students to attend college

- Host EITC workshops

- Establish VITA sites

- Organize local Money Fairs at the public library

Religious Institutions

- Distribute Saves Week fliers, brochures and display posters

- Place Saves Week article in newsletter/bulletin(s)

- Place Saves Week flier in the weekly bulletin for one month prior

- Host motivational workshop(s), presentation(s), topic seminar(s)

- Preach a sermon relative to Saves Week

- Declare a goal that every congregant enroll as a Saver, and/or open a savings account, and/or have at the end of one year $500 - $1,000 in a savings account, and/or open an IRA, and/or ..

- Organize with other congregations a Money Fair

Political Leaders

- Proclamations

- Public endorsements

- Mailings encouraging others to be involved

- Hosting an event/rally for Savings

- Encouraging government employees to participate and enroll

- Issuing press releases and conducting interviews

Educational Institutions

- Distribute Saves fliers and brochures to students and employees

- Display Saves posters

- Send one or more stock emails regarding Saves Week to students and employees

- Place Saves Week article(s) in employees newsletter and school newspaper

- Enclose a Saves flier as a payroll stuffer

- Place a notice of and information about Saves Week on internal computer system

- Place a link to Saves on school website and internal network

- Increase deferred compensation participation and contributions through one or more motivational workshops

- Provide access to no fee savings accounts through Saves enrollment – presentation(s), motivational workshop(s), and or topic seminar(s) i.e. EITC, Homeownership; Auto Purchase …

- Host an event featuring Saves and Deferred Compensation provider, Bank for products and services

Libraries

- Distribute Saves fliers and brochures to patrons and employees

- Display  Saves posters

- Set up display/area for reading/research and web access to Saving, Debt reduction and Wealth building

- Host Motivational Workshops and Topic Seminars for Patrons and employees

- Encourage enrollment as a Saver at check out and information desks

- Hold contests/activities targeted to youth on Saving and Wealth Building

- Send one or more stock emails regarding  Saves Week to employees

- Place Saves Week article(s) in employees newsletter and patron news

- Enclose a Saves flier as a payroll stuffer

- Place a notice of and information about Saves Week on internal computer system

- Place a link to Cleveland Saves on website and internal network

- Increase deferred compensation participation and contributions through one or more motivational workshops

- Provide access to no fee savings accounts through Saves enrollment – presentation(s), motivational workshop(s), and or topic seminar(s) i.e. EITC, Homeownership; Auto Purchase …

- Host an event featuring Saves and Deferred Compensation provider, Bank for products and services