- FINAL Cruise Instructions

FOCI

- NOAA Ship MILLER FREEMAN, MF-03-10

- July 18 – August 9, 2003

- Chief Scientist: Edward D. Cokelet, NOAA/PMEL

- FINAL CRUISE INSTRUCTIONS

  - Cruise Title – Global Ocean Ecosystems Dynamics (GLOBEC) Juvenile Salmon Survey

  - Cruise Numbers

    - Cruise Number – MF-03-10

    - FOCI Number – 6MF03

  - Cruise Dates

    - Departure – Depart Friday, July 18, 2003, from Kodiak, Alaska.

    - Arrival – Arrive Saturday, August 9, 2003, in Juneau, Alaska.

  - Operating Area – Gulf of Alaska and Shelikof Strait

- CRUISE OVERVIEW

  - Cruise Objectives – The cruise objective is to continue a multi-year set of measurements begun in July-August 1996 by NOAA’s Auke Bay Laboratory's Ocean Carrying Capacity program.  Their goal is to determine the distribution of juvenile salmon in the ocean as they begin migrating from their natal streams to the deep ocean.  This research was augmented in 2001 by U.S. GLOBEC to refocus the research in the Gulf of Alaska and to add oceanographic measurements.  We will also collect data on any, and all, salmon sharks captured.  This will contribute to an ongoing study of salmon sharks as part of a thesis study by a graduate student at the University of Washington.  The data will be used to determine reproductive life history, age/sex structure of the population, and basic demographic information.

  - Applicability – These instructions, with FOCI Standard Operating Instructions for NOAA Ship MILLER FREEMAN, dated April 8, 2002, present complete information for this cruise.

  - Participating Organizations

NOAA – Pacific Marine Environmental Laboratory (PMEL)

7600 Sand Point Way N.E.

Seattle, Washington 98115-6439

NOAA – Alaska Fisheries Science Center (AFSC)

Auke Bay Laboratory (ABL)

11305 Glacier Highway

Juneau, Alaska 99801-8626

University of Washington (UW)

School of Aquatic and Fishery Science

P.O. Box 355020

Seattle, Washington 98195-5020

  - Personnel

    - Chief Scientist

| Name | Gender | Affiliation | E-mail Address |
| --- | --- | --- | --- |
| Edward D. Cokelet | Male | NOAA/PMEL | Edward.D.Cokelet@noaa.gov |
| (206) 526-6820 |  |  |  |

    - Participating Scientists

| Name | Gender | Affiliation | E-mail Address |
| --- | --- | --- | --- |
| Edward D. Cokelet | Male | NOAA/PMEL | Edward.D.Cokelet@noaa.gov |
| William J. Floering | Male | NOAA/PMEL | William.Floering@noaa.gov |
| Antonio J. Jenkins | Male | NOAA/PMEL | Antonio.Jenkins@noaa.gov |
| Angela M. Middleton | Female | NOAA/ABL | Angela.Middleton@noaa.gov |
| Christine M. Kondzela | Female | NOAA/ABL | Chris.Kondzela@noaa.gov |
| Jamal Moss | Male | NOAA/ABL | Jamal.Moss@noaa.gov |
| Daniel Badger | Male | UW | dbadger@u.washington.edu |
| Rhys Smoker | Male | HSU | rjs27@humboldt.edu |
| Kim Meline | Female | Teacher at Sea | kmeline@mail.bethel.wednet.edu |
| Ed Farley | Male | NOAA/ABL | Ed.Farley@noaa.gov |
| James M. Murphy | Male | NOAA/ABL | Jim.Murphy@noaa.gov |
| Calvin W. Mordy | Male | NOAA/PMEL | Calvin.W.Mordy@noaa.gov |

    - Scientists Departing After Fishing Gear Trials on Saturday, July 19, 2003

| Name | Gender | Affiliation | E-mail Address |
| --- | --- | --- | --- |
| Ed Farley | Male | NOAA/ABL | Ed.Farley@noaa.gov |
| James M. Murphy | Male | NOAA/ABL | Jim.Murphy@noaa.gov |
| Calvin W. Mordy | Male | NOAA/PMEL | Calvin.W.Mordy@noaa.gov |

  - Administration

    - Ship Operations

- Marine Operations Center, Pacific

1801 Fairview Avenue East

Seattle, Washington 98102-3767

Telephone: (206) 553-4548

Fax: (206) 553-1109

- Commander Michele Bullock, NOAA

Chief, Operations Division, Pacific (MOP1)

Telephone: (206) 553-8705

Cellular: (206) 390-7527

- E-mail: Michele.Bullock@noaa.gov

- Larry Mordock

Deputy Chief, Operations Division (MOP1x1)

Telephone – Work: (206) 553-4764

Home: (206) 365-3567

Cellular: (206) 465-9316

- E-mail: Larry.Mordock@noaa.gov

    - Scientific Operations

Dr. Phyllis J. Stabeno, PMEL		Ed Farley, ABL

Telephone: (206) 526-6453			Telephone: (907) 789-6085

E-mail: Phyllis.Stabeno@noaa.gov		E-mail: Ed.Farley@noaa.gov

- OPERATIONS

  - Data To Be Collected

- Conduct a Conductivity, Temperature, and Depth (CTD) profiler cast, surface Tucker trawl, and surface trawl at each station,

- Make continuous underway measurements of the ocean current with the Acoustic Doppler Current Profiler (ADCP),

- Make continuous underway measurements with the Thermosalinograph, Fluorometer, and Nutrient sensor,

- Deploy six (6) ARGOS satellite-tracked drifting buoys and a few Argo floats,

- Recover and deploy a subsurface, ADCP current-meter mooring in Shelikof Strait, and

- Collect data on size, sex, reproductive state, age, stomach contents, genetics and blood hormones on any, and all, salmon sharks (Lamna ditropis) captured.

    - Scientific Computer System (SCS) – The ship's SCS shall operate throughout the cruise, acquiring and logging data from navigation, meteorological, oceanographic, and fisheries sensors.  See FOCI Standard Operating Instructions for NOAA Ship MILLER FREEMAN (SOI 5.2) for specific requirements.

  - Staging Plan – The scientific party will make arrangements to use a United States Coast Guard vehicle in Kodiak, Alaska, to move personnel and gear. Auke Bay Laboratory’s Ed Farley and Jim Murphy will be on board for fishing gear trials only and will depart the vessel on Saturday, July 19, 2003.  Therefore, the fishing gear must be rigged in a timely manner for the gear trials on the first day at sea.  Additionally, PMEL’s Dr. Calvin W. Mordy will be on board the ship Thursday, July 16, 2003, to set up his underway nutrient meter and will remain on board for fishing gear trials and depart the ship on Saturday, July 19, 2003.

See Section 9.1 MF-03-10 Equipment Inventory for a complete listing of equipment weights and dimensions that will be on board during the cruise.

    - Transported by NOAA Ship MILLER FREEMAN – Fishing gear to be transported by NOAA Ship MILLER FREEMAN from Dutch Harbor, Alaska, to Kodiak, Alaska, on Cruise MF-03-08 and stored in Kodiak, Alaska, on Tuesday, June 3, 2003:

- Two (2) midwater trawls (CanTrawl 400/0.580’s) – 2,000-lbs,

- Two (2) sets of 5-m Net Systems trawl doors (4 doors, total) – 1,000-lbs,

- One (1) sorting table (approximately 5’x10’, containing sampling supplies) – 1,200-lbs, and

- Six to eight (6-8) net floats – 150-lbs.

    - Fishing Gear Loaded in Kodiak, Alaska – Gear to be loaded in Kodiak, Alaska, on Thursday, July 17, 2003:

- Fishing gear listed above,

- Mooring gear,

- Approximately six (6) ARGOS satellite-tracked drifters from FOCI,

- Canadian Argo floats, and

- Miscellaneous gear and computers.

  - De-staging Plan – Auke Bay Laboratory's (ABL) samples and some of their gear will be off-loaded in Juneau, Alaska.  PMEL's computers and mooring gear and ABL's fishing gear will be off-loaded in Seattle.  The scientific party will make arrangements for vehicles to transport personnel and gear in Juneau, Alaska, between August 9-10, 2003, and in Seattle, Washington, upon ship arrival on a mutually agreeable date.  No samples or gear will be left aboard after that time.

  - Cruise Plan – The scientific party, with assistance from ship personnel, will load gear on Thursday, July 17, 2003, and depart Kodiak, Alaska, on Friday, July 18, 2003, for 24 hours of fishing gear trials.  The purpose of the fishing gear trials is to ensure that the trawl fishes in the same manner as on board the charter vessel which we have used since 1996.  The continuity of sampling is important to relate one year's results to another's.  After the fishing trials, three (3) scientists will debark in Kodiak, Alaska, on Saturday, July 19, 2003, and then the ship will commence sampling on the Cape Chiniak line.  Thereafter, continue sampling in the order of the chart depicted in Section 9.5 MF-03-10 Cruise Trackline.

Typically each day will begin at 06:00 Alaska Daylight Time (ADT) with a station.  Each station begins with a Conductivity, Temperature, and Depth (CTD) profiler cast to the shallower of 1,500 meters, or 10 meters off the bottom.  Following this is a surface Tucker trawl for five minutes at about 1 knot to make the net fish efficiently with a wire angle of approximately 30°.  At selected stations, we will redeploy the Tucker and do an oblique trawl down to 20 meters and back.  Lastly, we will commence the main surface trawl.  Once deployed, we trawl for 30 minutes at 3 to 5.5 knots.  The net mensuration gear and visual sightings of the net are used to determine if it is fishing at the surface at the correct net opening.  This is monitored by the ship operator throughout the tow, and ship speed is increased or decreased depending on how the net is fishing and the placement of the doors (i.e. surface ready to skate or too deep and sinking the net).  The trawl is brought aboard; the catch is sorted, measured, and sampled.  During this time the ship will get underway to the next station, ten or more nautical miles away.  We plan for about two hours on each station.  The last station finishes before 22:00 ADT each day; we do not want to fish at night.  On Friday, August 1, 2003, sunrise is at 06:04 ADT and sunset at 22:27 ADT.  Most lines are designed to be completed in one or two days of work with transits between lines at night so that we are ready to cast and fish at 06:00 ADT the next day.

The ship’s Acoustic Doppler Current Profiler (ADCP), thermosalinograph, fluorometer, and nutrient sensor will operate continuously during the cruise.  Scientific Computer System (SCS) should be stopped and restarted once per day.

A subsurface ADCP mooring will be recovered and deployed at the southeast end of the Cape Kekurnoi line.  This mooring is relatively small, and we plan for mooring operations without the trawlway platform in place.  See Section 9.2 MF-03-10 Cape Kekurnoi Subsurface ADCP Mooring Diagram.

Approximately six (6) satellite-tracked drifting buoys and a few profiling Argo floats will be deployed at the Chief Scientist's discretion.

  - Station Locations – See Section 9.4 MF-03-10 Cruise Itinerary and Section 9.5 MF-03-10 Cruise Trackline.

  - Station Operations – The following are operations to be conducted on this cruise.  The procedures for these operations are listed in the FOCI Standard Operating Instructions for NOAA Ship MILLER FREEMAN (SOI).  Operations not addressed in the SOI and changes to standard procedures are addressed below:

- CTD/Water Sample Operations (SOI 3.2.1),

- Chlorophyll Sampling Operations (SOI 3.2.10) – One to four Niskin bottle per cast, and

- ARGOS Satellite Tracked Drifter Buoy Deployments (SOI 3.2.11).

    - Surface Trawls for Juvenile Salmon – Protocols for surface trawls with the CanTrawl nets will be provided by Auke Bay Laboratory’s scientists Ed Farley and James Murphy during fishing trials conducted immediately after departure from Kodiak, Alaska.

    - Surface Tucker Trawls – Protocols for surface Tucker trawls will be provided by Auke Bay Laboratory’s scientists Ed Farley and James Murphy during fishing trials conducted immediately after departure from Kodiak, Alaska. The Tucker will be equipped with 0.505-mm mesh netting and be towed along the surface.  Trawling will be for five minutes at about 1 knot to make the net fish efficiently with a wire angle of approximately 30°.

After the bridge gives permission, the survey technician and one or two scientists will deploy and recover the Tucker trawl.  The ship's speed should be adjusted to maintain a wire angle of 30° during the entire tow, which is accomplished by the survey technician relaying wire angles to the bridge by radio. When the nets reach the surface, they are brought aboard and hosed with saltwater to wash the sample into the cod-end.  The sample is preserved. Flow meters in the nets record the amount of water filtered.  The scientists on watch are responsible for recording times, maximum depth, wire outs, and flow meter.

    - Oblique Tucker Trawls – Protocols for oblique Tucker trawls will be provided by Auke Bay Laboratory’s scientists Ed Farley and James Murphy during fishing trials conducted immediately after departure from Kodiak, Alaska.  Oblique Tucker trawls may be conducted at up to 20 selected stations.  The Tucker will be equipped with 0.505-mm mesh netting and be towed within the upper 20 to 40 meters of the water column targeting juvenile salmon prey items.

After the bridge gives permission, the survey technician and one or two scientists will deploy and recover the Tucker trawl.  The ship's speed should be adjusted to maintain a wire angle of 30° during the entire tow, which is accomplished by the survey technician relaying wire angles to the bridge by radio. When the nets reach the surface, they are brought aboard and hosed with saltwater to wash the sample into the cod-end.  The sample is preserved. Flow meters in the nets record the amount of water filtered.  The scientists on watch are responsible for recording times, maximum depth, wire outs, and flow meter.

    - Salmon Shark Measurements

      - External Measurement and Samples:

- Length (pre-caudal, fork and total),

- Weight,

- Girth,

- Clasper Inner Length (males only),

- Blood, and

- Genet

      - Internal Measurements – Stomach contents should be taken on board the ship, while internal measurements of the reproductive tracts can be measured on board or shipped to the University of Washington.

- Lengths of ovaries, oviductal glands, oviducts, uterus, or testis,

- Widths of above,

- Weights of above,

- Count of developed ova in ovary,

- Sizes of randomly selected ova,

- Embryo lengths, weights and yolk sac weights if present,

- Stomach Contents, and

- Removal of tissues to be sent back to the lab.

      - Photographs – Photographs should be taken often and essay of all stages of data collection.  A more detailed description of sampling procedures is available in Protocol for Shark Biological Sampling prepared by participating investigators.  Any questions or requests for sampling manual can be directed to:

- Cindy A Tribuzio

University of Washington

School of Aquatic and Fishery Science

Telephone: (206) 221-6776

- E-mail: Tribuzio@u.washington.edu

  - Underway Operations – The following are underway operations to be conducted on this cruise.  The procedures for these operations are listed in the FOCI Standard Operating Instructions for NOAA Ship MILLER FREEMAN (SOI).  Operations not addressed in the SOI and changes to standard procedures are addressed below.

- Acoustic Doppler Current Profiler (ADCP) Operations (SOI 3.2.13),

- Scientific Computer System (SCS) data acquisition (SOI 5.2),

- Fluorometer monitoring (SOI 5.3),

- Thermosalinograph monitoring (SOI 5.3),

- SIMRAD EK 500 Scientific Echosounder Monitoring (SOI 3.2.12), and

- Nutrient sensor monitoring to be detailed by Dr. Calvin W. Mordy.

  - Applicable Restrictions – If time permits, the ship may be requested to enter Glacier Bay, Alaska, near the end of the cruise.  Communication with the United States National Park Service may be appropriate.

  - Small Boat Operations – A small boat may be utilized to transport personnel ashore after the gear trials off Kodiak, Alaska.   A small boat may be needed for the recovery and deployment of the mooring.

- FACILITIES

  - Equipment and Capabilities Provided by Ship

- Oceanographic winch with slip rings and 3-conductor cable terminated for CTD,

- Manual wire-angle indicator,

- Sea-Bird Electronics’ SBE 911plus CTD system with stand, each CTD system should include underwater CTD, weights, and pinger.  There should be one deck unit for the two systems,

- Fourteen( 14) 10-liter Niskin sampling bottles for use with rosette (10 plus 4 spares),

- AUTOSAL salinometer, for CTD field corrections,

- Meter block for plankton tows,

- Wire speed indicators and readout for quarterdeck, Rowe, and Marco winches,

- For meteorological observations: Two (2) anemometers (one R. M. Young system interfaced to the SCS), calibrated air thermometer (wet-and dry-bulb) and a calibrated barometer and/or barograph,

- Freezer space for storage of biological samples at -60° C,

- SIMRAD EQ-50 echosounder,

- JRC JFV-200R color sounder recorder,

- RD Instruments’ ADCP written to Iomega Zip drive,

- Bench space in DataPlot for PCs, monitor, printer,

- Use of Pentium PC in DataPlot for data analysis,

- Scientific Computer System (SCS),

- Stern platform removed for trawling,

- Ship outfitted for trawling with ABL's 200 x 45 x 15 meter CanTrawl net and doors,

- Laboratory space with exhaust hood, sink, lab tables, and storage space,

- Sea-water hoses and nozzles to wash nets (quarterdeck and aft deck),

- Adequate deck lighting for night-time operations,

- Navigational equipment including GPS and radar,

- Safety harnesses for working on quarterdeck and fantail,

- Ship’s crane(s) used for loading and/or deploying, and

- Net mensuration gear:  WesMar 3rd wire system with spares.

  - Equipment and Capabilities Provided by Scientists

- Sea-Bird Electronics’ SBE 911plus CTD system to be used with PMEL stand,

- PMEL PC with SEASOFT software for CTD data collection and processing,

- Fluorometer and light meter to be mounted on CTD,

- CTD stand modified for attachment of fluorometer,

- Conductivity and temperature sensor package to provide dual sensors on the primary CTD,

- CTD rosette sampler,

- IAPSO standard water,

- Spare wire angle indicator,

- Tucker trawl,

- Subsurface ADCP mooring,

- Six (6) ARGOS satellite-tracked drifting buoys,

- Miscellaneous scientific sampling and processing equipment,

- Sorting tables and baskets for processing trawl catches,

- Underway nutrient meter and chemicals

- Two (2) CanTrawl 400/580 midwater trawls – bundled approximately 10' x 12', about 2,000-lbs total weight,

- Four (4) Net System trawl doors – about 500-lbs each,

- One (1) Fish Sorting Table (about 5' x 10') with supplies stored aboard – around 1,200-lbs,

- Six to eight (6-8) net floats, and

- Salmon shark autopsy gear.

- DISPOSITION OF DATA AND REPORTS

  - The following data products will be included in the cruise data package:

- NOAA Form 77-13d – Deck Log – Weather Observation Sheets,

- Electronic Marine Operations Abstracts,

- SCS backup to recordable compact diskette (CD-RW),

- Calibration Sheets for all ship's instruments used,

- PMEL CTD Weather Observation Logs,

- CTD Cast Information/Rosette Log,

- Autosalinometer Logs,

- ADCP Log Sheets,

- ADCP Iomega Zip and/or recordable compact diskette (CD-RW),

- Electronic Navigation suite’s export files on diskette, and

- Ultra-cold Freezer Temperature Daily Log (SOI 5.4).

  - Pre- and Post-cruise Meetings – Cruise meetings may be held in accordance with FOCI Standard Operating Instructions for NOAA Ship MILLER FREEMAN (SOI 5.5).

- ADDITIONAL PROJECTS

  - Definition – Ancillary and piggyback projects are secondary to the objectives of the cruise and should be treated as additional investigations.  The difference between the two types of secondary projects is that an ancillary project does not have representation aboard and is accomplished by the ship's force.

  - Ancillary Projects – Any ancillary work done during this project will be accomplished with the concurrence of the Chief Scientist and on a not-to-interfere basis with the programs described in these instructions and in accordance with the NOAA Fleet Standing Ancillary Instructions.

  - Piggyback Projects – None.

- HAZARDOUS MATERIALS

  - Inventory – See Section 9.3 MF-03-10 HAZMAT Inventory for complete inventory listing of HAZMATs being brought on board for the cruise.

The formalin solution will be made up aboard by diluting formaldehyde with seawater to a 10% solution.  All formaldehyde will be stored on deck in a sealed plastic ice chest, or in a cool, well ventilated area away from heat and flame. The spill kit contains: absorbent material (vermiculite), Hazmat bags to contain used absorbent, safety goggles, latex gloves, MSDS for 37% formaldehyde solution, MSDS for 10% formaldehyde solution. Notify Angela Middleton if a spill occurs.

  - Material Safety Data Sheet (MSDS) – All MSDSs can be found on the OERD HAZMAT Emergency Guidelines – MSDS compact diskette dated January 15, 2003, supplied to the ship.

- MISCELLANEOUS

  - Communications – Specific information on how to contact the NOAA Ship MILLER FREEMAN and all other fleet vessels can be found at:

http://www.pmc.noaa.gov/phone.htm

  - Important Telephone and Facsimile Numbers and E-mail Addresses

    - Pacific Marine Environmental Laboratory (PMEL):

FOCI – Ocean Environmental Research Division (OERD2):

- (206) 526-4700 (voice)

- (206) 526-6485 (fax)

Administration:

- (206) 526-6810 (voice)

- (206) 526-6815 (fax)

- E-Mail: FirstName.LastName@noaa.gov

    - Alaska Fisheries Science Center (AFSC):

FOCI – Resource Assessment and Conservation Engineering (RACE):

- (206) 526-4171 (voice)

- (206) 526-6723 (fax)

- E-Mail: FirstName.LastName@noaa.gov

    - NOAA Ship MILLER FREEMAN – Telephone methods listed in order of increasing expense:

Homeport – Seattle, Washington:

- (206) 553-4589

- (206) 553-4581

- (206) 553-8344

United States Coast Guard – Kodiak, Alaska:

- (907) 487-9752

- (907) 487-9753

- (907) 487-4397

- (907) 487-4398

Cellular:

- (206) 660-7167

INMARSAT Mini-M:

- 011-872-761-267-346 (voice/PBX)

- 011-872-761-267-347 (voice)

- 011-872-761-267-348 (fax)

- INMARSAT B:

- 011-872-330-394-120 (voice)

- 011-872-330-394-121 (fax)

E-Mail: NOAA.Ship.Miller.Freeman@noaa.gov (mention the person’s name in SUBJECT field)

    - Marine Operations Center, Pacific (MOP)

Operations Division (MOP1):

- (206) 553-4548 (voice)

- (206) 553-1109 (facsimile)

- E-Mail: FirstName.LastName@noaa.gov

- E-Mail to Radio Room: Radio.Room@noaa.gov

- APPENDICES

  - MF-03-10 Equipment Inventory

| Equipment | Qty | Dimension | Weight |  | Total Weight |  |
| --- | --- | --- | --- | --- | --- | --- |
| Midwater Trawl, CanTrawl 400/580 | 2 |  | 1,000 | lbs | 2,000 | lbs |
| Net Systems Trawl Doors | 4 | 5 Meters | 500 | lbs | 2,000 | lbs |
| Sorting Table, w/Sampling Supplies | 1 | 5' x 10' | 1,200 | lbs | 1,200 | lbs |
| Net Floats | 6-8 |  | 150 | lbs | 150 | lbs |
| Subsurface ADCP Float, Syntactic Foam | 1 | 36" Diameter | 300 | lbs | 300 | lbs |
| Floats, Steel | 2 | 30" Diameter | 150 | lbs | 300 | lbs |
| Aanderaa RCM-9 Current Meter | 1 |  | 35 | lbs | 35 | lbs |
| SeaBird Electronic (SBE) Microcat | 1 |  | 20 | lbs | 20 | lbs |
| EG&G Acoustic Release | 1 |  | 50 | lbs | 50 | lbs |
| Chain, Mooring | 1 | 16 Meters | 100 | lbs | 100 | lbs |
| 5/16" SS Wire | 1 | 25 Meters | 15 | lbs | 15 | lbs |
| Railway Wheels (2), Mooring Anchor | 1 |  | 1,700 | lbs | 1,700 | lbs |
| Miscellaneous Shackles and Swivels |  |  | 100 | lbs | 100 | lbs |
|  |  | TOTAL WEIGHT: |  |  | 7,970 | lbs |

  - MF-03-10 Cape Kekurnoi Subsurface ADCP Mooring Diagram

  - MF-03-10 HAZMAT Inventory

| Chemical | CAS Number | Quantity | H | F | R | Storage Color Code | Hazard Class | Packing Group Number | UN | Reportable Quantity | Response Indices |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ammonium Chloride | 12125-02-9 | 42.0-g | 1 | 0 | 0 | General | Not regulated |  | 9085 | 5,000-lbs | 1 |
| Cupric Sulfate, Pentahydrate | 7758-99-8 | 40.0-g | 2 | 0 | 0 | Hazardous Waste | 9 | III | 3077 | 400-lbs | 2 |
| Formaldehyde, 37% | mix | 16-24-l | 3 | 2 | 2 | Flammable | 3 & 8 | III | 1198 | 100-lbs | 3 |
| Formalin | mix | 2-l | 3 | 2 | 2 | Flammable | 3 & 8 | III | 1198 | 100-lbs | 3 |
| Hydrochloric Acid, Solution | 7647-01-0 | 500.0-ml | 3 | 0 | 2 | Corrosive | 8 | II | 1789 | 5,000-lbs | 4 |
| Imidazole | 288-32-4 | 82.0-g | 2 | 1 | 1 | Corrosive | 8 | III | 3263 | 5-kg | 5 |
| N-1-Napthylethylenediamine Dihydrochloride | 1465-25-4 | 3.0-g | 2 | 1 | 1 | General | Not regulated |  |  | None | 6 |
| Potassium Nitrate | 7757-79-1 | 2.0-g | 1 | 0 | 3 | Reactive | 5.1 | III | 1486 | 100-kg | 5 |
| Sulfanilamide | 63-74-1 | 30.0-g | 0 | 1 | 1 | General | Not regulated |  |  | None | 7 |

Spill Response 1: Ventilate area of leak or spill. Wear appropriate personal protective equipment. Sweep up and containerize for reclamation or disposal. Vacuuming or wet sweeping may be used to avoid dust dispersal. Place material in closed container.

Spill Response 2: Ventilate area of leak or spill. Keep unnecessary and unprotected people away from area of spill. Wear appropriate personal protective equipment. Pick up and place in a suitable container for reclamation or disposal, using a method that does not generate dust. U.S. Regulations (CERCLA) requires reporting spills and releases to soil, water and air in excess of reportable quantities. The toll free number for the U.S. Coast Guard National Response Center is (800) 424-8802.

Spill Response 3: Ventilate area of leak or spill. Remove all sources of ignition. Wear appropriate personal protective equipment. Isolate hazard area. Keep unnecessary and unprotected personnel from entering. Contain and recover liquid when possible. Use non-sparking tools and equipment. Collect liquid in an appropriate container or absorb with an inert material (e. g., vermiculite, dry sand, or earth), and place in a chemical waste container. Do not use combustible materials, such as saw dust. Do not flush to sewer! If a leak or spill has not ignited, use water spray to disperse the vapors, to protect personnel attempting to stop leak, and to flush spills away from exposures. U.S. Regulations (CERCLA) requires reporting spills and releases to soil, water and air in excess of reportable quantities. The toll free number for the U.S. Coast Guard National Response Center is (800) 424-8802.

Spill Response 4: Ventilate area of leak or spill. Wear appropriate personal protective equipment. Isolate hazard area. Keep unnecessary and unprotected personnel from entering. Contain and recover liquid when possible. Neutralize with alkaline material (soda ash, lime), then absorb with an inert material (e. g., vermiculite, dry sand, earth), and place in a chemical waste container. Do not use combustible materials, such as saw dust. Do not flush to sewer! U.S. Regulations (CERCLA) requires reporting spills and releases to soil, water and air in excess of reportable quantities. The toll free number for the U.S. Coast Guard National Response Center is (800) 424-8802.

Spill Response 5: Remove all sources of ignition. Ventilate area of leak or spill. Wear appropriate personal protective equipment. Clean up spills in a manner that does not disperse dust into the air. Use non-sparking tools and equipment. Reduce airborne dust and prevent scattering by moistening with water. Pick up spill for recovery or disposal and place in a closed container.

Spill Response 6: Ventilate area of leak or spill. Wear appropriate personal protective equipment. Pick up and place in a suitable container for reclamation or disposal, using a method that does not generate dust.

Spill Response 7: Ventilate area of leak or spill. Wear appropriate personal protective equipment. Sweep up and containerize for reclamation or disposal. Vacuuming or wet sweeping may be used to avoid dust dispersal. Place material in closed container.

  - MF-03-10 Cruise Itinerary

| Transect | Stn ID | Latitude |  |  | Longitude |  |  | Dist (nm) | Spd (kts) | Transit (hrs) | On Stn (Hrs) | Arrive (Local) | Depart (Local) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Depart Kodiak, Alaska |  | 57° | 43.727' | N | 152° | 31.288' | W |  |  |  |  |  | 7/18/2003 14:00 |
| Gear Trials | CCH1 | 57° | 35.400' | N | 152° | 09.600' | W | 8.0 | 10.5 | 0.8 | 24 | 7/18/2003 16:29 | 7/19/2003 16:29 |
| Cape Chiniak | CCH1 | 57° | 35.400' | N | 152° | 09.600' | W | 0.0 | 10.5 | 0.0 | 2 | 7/19/2003 16:29 | 7/19/2003 18:29 |
| Cape Chiniak | CCH2 | 57° | 22.200' | N | 151° | 56.400' | W | 15.0 | 10.5 | 1.4 | 2 | 7/19/2003 19:54 | 7/19/2003 21:54 |
| Cape Chiniak | CCH3 | 57° | 09.000' | N | 151° | 43.800' | W | 14.9 | 10.5 | 1.4 | 8.68 | 7/19/2003 23:19 | 7/20/2003 8:00 |
| Cape Chiniak | CCH4 | 56° | 55.800' | N | 151° | 30.000' | W | 15.2 | 10.5 | 1.4 | 2 | 7/20/2003 9:27 | 7/20/2003 11:27 |
| Cape Chiniak | CCH5 | 56° | 42.600' | N | 151° | 16.800' | W | 15.0 | 10.5 | 1.4 | 2 | 7/20/2003 12:53 | 7/20/2003 14:53 |
| Cape Chiniak | CCH6 | 56° | 29.400' | N | 151° | 03.600' | W | 15.1 | 10.5 | 1.4 | 2 | 7/20/2003 16:19 | 7/20/2003 18:19 |
| Cape Chiniak | CCH7 | 56° | 16.800' | N | 150° | 51.000' | W | 14.4 | 10.5 | 1.4 | 2 | 7/20/2003 19:41 | 7/20/2003 21:41 |
| Cape Kaguyak | CKAG6 | 55° | 40.800' | N | 152° | 54.600' | W | 78.0 | 10.5 | 7.4 | 2.89 | 7/21/2003 5:07 | 7/21/2003 8:00 |
| Cape Kaguyak | CKAG5 | 55° | 54.000' | N | 153° | 07.800' | W | 15.1 | 10.5 | 1.4 | 2 | 7/21/2003 9:27 | 7/21/2003 11:27 |
| Cape Kaguyak | CKAG4 | 56° | 06.600' | N | 153° | 20.400' | W | 14.4 | 10.5 | 1.4 | 2 | 7/21/2003 12:49 | 7/21/2003 14:49 |
| Cape Kaguyak | CKAG3 | 56° | 15.600' | N | 153° | 29.400' | W | 10.3 | 10.5 | 1.0 | 2 | 7/21/2003 15:48 | 7/21/2003 17:48 |
| Cape Kaguyak | CKAG2 | 56° | 28.800' | N | 153° | 42.600' | W | 15.1 | 10.5 | 1.4 | 2 | 7/21/2003 19:14 | 7/21/2003 21:14 |
| Cape Kaguyak | CKAG1 | 56° | 42.000' | N | 153° | 55.800' | W | 15.1 | 10.5 | 1.4 | 9.33 | 7/21/2003 22:40 | 7/22/2003 8:00 |
| Cape Kekurnoi | CK3 | 57° | 25.980' | N | 154° | 46.020' | W | 6.1 | 10.5 | 0.6 | 11.44 | 7/22/2003 20:34 | 7/23/2003 8:00 |
| Cape Kekurnoi | CK2 | 57° | 34.980' | N | 155° | 03.000' | W | 12.8 | 10.5 | 1.2 | 2 | 7/23/2003 9:14 | 7/23/2003 11:14 |
| Cape Kekurnoi | CK1 | 57° | 42.000' | N | 155° | 16.980' | W | 10.3 | 10.5 | 1.0 | 2 | 7/23/2003 12:12 | 7/23/2003 14:12 |
| Mooring | 02SSP-3B | 57° | 29.016' | N | 154° | 48.440' | W | 20.1 | 10.5 | 1.9 | 6 | 7/23/2003 16:07 | 7/23/2003 22:07 |
| Cape Nukshak | CN1 | 58° | 22.020' | N | 153° | 55.980' | W | 15.6 | 10.5 | 1.5 | 4.17 | 7/24/2003 3:50 | 7/24/2003 8:00 |
| Cape Nukshak | CN2 | 58° | 10.980' | N | 153° | 40.980' | W | 13.6 | 10.5 | 1.3 | 2 | 7/24/2003 9:17 | 7/24/2003 11:17 |
| Cape Nukshak | CN3 | 58° | 03.000' | N | 153° | 27.000' | W | 10.9 | 10.5 | 1.0 | 2 | 7/24/2003 12:19 | 7/24/2003 14:19 |
| Gore Point | GP1 | 59° | 10.020' | N | 150° | 55.980' | W | 32.2 | 10.5 | 3.1 | 7.29 | 7/25/2003 0:42 | 7/25/2003 8:00 |
| Gore Point | GP2 | 59° | 01.980' | N | 150° | 51.000' | W | 8.4 | 10.5 | 0.8 | 2 | 7/25/2003 8:48 | 7/25/2003 10:48 |
| Gore Point | GP3 | 58° | 52.980' | N | 150° | 43.980' | W | 9.7 | 10.5 | 0.9 | 2 | 7/25/2003 11:43 | 7/25/2003 13:43 |
| Gore Point | GP4 | 58° | 43.980' | N | 150° | 37.980' | W | 9.5 | 10.5 | 0.9 | 2 | 7/25/2003 14:38 | 7/25/2003 16:38 |
| Gore Point | GP5 | 58° | 34.980' | N | 150° | 29.400' | W | 10.0 | 10.5 | 1.0 | 2 | 7/25/2003 17:35 | 7/25/2003 19:35 |
| Gore Point | GP6 | 58° | 25.020' | N | 150° | 22.200' | W | 10.6 | 10.5 | 1.0 | 11.4 | 7/25/2003 20:36 | 7/26/2003 8:00 |
| Gore Point | GP7 | 58° | 16.020' | N | 150° | 16.020' | W | 9.6 | 10.5 | 0.9 | 2 | 7/26/2003 8:55 | 7/26/2003 10:55 |
| Gore Point | GP8 | 58° | 07.020' | N | 150° | 09.000' | W | 9.7 | 10.5 | 0.9 | 2 | 7/26/2003 11:50 | 7/26/2003 13:50 |
| Gore Point | GP9 | 57° | 58.020' | N | 150° | 02.400' | W | 9.7 | 10.5 | 0.9 | 2 | 7/26/2003 14:45 | 7/26/2003 16:45 |
| Gore Point | GP10 | 57° | 49.980' | N | 149° | 55.800' | W | 8.8 | 10.5 | 0.8 | 2 | 7/26/2003 17:36 | 7/26/2003 19:36 |
| Gore Point | GP11 | 57° | 39.000' | N | 149° | 48.600' | W | 11.6 | 10.5 | 1.1 | 11.3 | 7/26/2003 20:42 | 7/27/2003 8:00 |
| Gore Point | GP12 | 57° | 29.400' | N | 149° | 41.400' | W | 10.3 | 10.5 | 1.0 | 2 | 7/27/2003 8:59 | 7/27/2003 10:59 |
| Gore Point | GP13 | 57° | 20.400' | N | 149° | 33.600' | W | 9.9 | 10.5 | 0.9 | 2 | 7/27/2003 11:56 | 7/27/2003 13:56 |
| Gore Point | GP14 | 57° | 11.400' | N | 149° | 25.800' | W | 9.9 | 10.5 | 0.9 | 2 | 7/27/2003 14:53 | 7/27/2003 16:53 |
| Seward | GAK 13 | 58° | 05.880' | N | 147° | 47.580' | W | 75.7 | 10.5 | 7.2 | 7.92 | 7/28/2003 0:05 | 7/28/2003 8:00 |
| Seward | GAK 12 | 58° | 14.580' | N | 147° | 55.980' | W | 9.8 | 10.5 | 0.9 | 2 | 7/28/2003 8:56 | 7/28/2003 10:56 |
| Seward | GAK 11 | 58° | 23.280' | N | 148° | 04.320' | W | 9.7 | 10.5 | 0.9 | 2 | 7/28/2003 11:52 | 7/28/2003 13:52 |
| Seward | GAK 10 | 58° | 32.520' | N | 148° | 12.720' | W | 10.2 | 10.5 | 1.0 | 2 | 7/28/2003 14:50 | 7/28/2003 16:50 |
| Seward | GAK 9 | 58° | 40.800' | N | 148° | 21.000' | W | 9.3 | 10.5 | 0.9 | 2 | 7/28/2003 17:44 | 7/28/2003 19:44 |
| Seward | GAK 8 | 58° | 47.520' | N | 148° | 29.400' | W | 8.0 | 10.5 | 0.8 | 11.51 | 7/28/2003 20:29 | 7/29/2003 8:00 |
| Seward | GAK 7 | 58° | 58.320' | N | 148° | 37.800' | W | 11.6 | 10.5 | 1.1 | 2 | 7/29/2003 9:07 | 7/29/2003 11:07 |
| Seward | TBD | 59° | 07.020' | N | 148° | 46.200' | W | 9.7 | 10.5 | 0.9 | 24 | 7/29/2003 12:02 | 7/30/2003 12:02 |
| Seward | GAK 6 | 59° | 07.020' | N | 148° | 46.200' | W | 0.0 | 10.5 | 0.0 | 2 | 7/30/2003 12:02 | 7/30/2003 14:02 |
| Seward | GAK 5 | 59° | 15.720' | N | 148° | 54.480' | W | 9.7 | 10.5 | 0.9 | 2 | 7/30/2003 14:57 | 7/30/2003 16:57 |
| Seward | GAK 4 | 59° | 24.480' | N | 149° | 02.880' | W | 9.8 | 10.5 | 0.9 | 2 | 7/30/2003 17:53 | 7/30/2003 19:53 |
| Seward | GAK 3 | 59° | 33.180' | N | 149° | 11.280' | W | 9.7 | 10.5 | 0.9 | 11.2 | 7/30/2003 20:48 | 7/31/2003 8:00 |
| Seward | GAK 2 | 59° | 41.520' | N | 149° | 19.620' | W | 9.3 | 10.5 | 0.9 | 2 | 7/31/2003 8:54 | 7/31/2003 10:54 |
| Seward | GAK 1 | 59° | 50.700' | N | 149° | 28.020' | W | 10.1 | 10.5 | 1.0 | 2 | 7/31/2003 11:52 | 7/31/2003 13:52 |
| Cape Cleare | CC1 | 59° | 44.400' | N | 147° | 49.200' | W | 1.1 | 10.5 | 0.1 | 13.31 | 7/31/2003 18:41 | 8/1/2003 8:00 |
| Cape Cleare | CC2 | 59° | 40.200' | N | 147° | 43.800' | W | 5.0 | 10.5 | 0.5 | 2 | 8/1/2003 8:29 | 8/1/2003 10:29 |
| Cape Cleare | CC3 | 59° | 34.200' | N | 147° | 36.600' | W | 7.0 | 10.5 | 0.7 | 2 | 8/1/2003 11:09 | 8/1/2003 13:09 |
| Cape Cleare | CC4 | 59° | 28.500' | N | 147° | 28.800' | W | 6.9 | 10.5 | 0.7 | 2 | 8/1/2003 13:48 | 8/1/2003 15:48 |
| Cape Cleare | CC5 | 59° | 21.420' | N | 147° | 21.000' | W | 8.1 | 10.5 | 0.8 | 2 | 8/1/2003 16:35 | 8/1/2003 18:35 |
| Cape Cleare | CC6 | 59° | 13.800' | N | 147° | 09.600' | W | 9.6 | 10.5 | 0.9 | 2 | 8/1/2003 19:30 | 8/1/2003 21:30 |
| Cape Cleare | CC7 | 59° | 03.600' | N | 146° | 58.200' | W | 11.8 | 10.5 | 1.1 | 9.38 | 8/1/2003 22:37 | 8/2/2003 8:00 |
| Cape Cleare | CC8 | 58° | 52.800' | N | 146° | 43.800' | W | 13.1 | 10.5 | 1.2 | 2 | 8/2/2003 9:14 | 8/2/2003 11:14 |
| Cape St. Elias | CSE5 | 59° | 09.000' | N | 144° | 36.000' | W | 67.8 | 10.5 | 6.5 | 2 | 8/2/2003 17:42 | 8/2/2003 19:42 |
| Cape St. Elias | CSE4 | 59° | 19.200' | N | 144° | 36.000' | W | 10.2 | 10.5 | 1.0 | 11.34 | 8/2/2003 20:40 | 8/3/2003 8:00 |
| Cape St. Elias | CSE3 | 59° | 28.800' | N | 144° | 36.000' | W | 9.6 | 10.5 | 0.9 | 2 | 8/3/2003 8:55 | 8/3/2003 10:55 |
| Cape St. Elias | CSE2 | 59° | 37.800' | N | 144° | 36.000' | W | 9.0 | 10.5 | 0.9 | 2 | 8/3/2003 11:47 | 8/3/2003 13:47 |
| Cape St. Elias | CSE1 | 59° | 48.000' | N | 144° | 36.000' | W | 10.2 | 10.5 | 1.0 | 2 | 8/3/2003 14:45 | 8/3/2003 16:45 |
| Cape Yakataga | CY1 | 60° | 03.600' | N | 142° | 26.400' | W | 57.0 | 10.5 | 5.4 | 8.83 | 8/3/2003 23:10 | 8/4/2003 8:00 |
| Cape Yakataga | CY2 | 59° | 54.000' | N | 142° | 29.400' | W | 9.7 | 10.5 | 0.9 | 2 | 8/4/2003 8:56 | 8/4/2003 10:56 |
| Cape Yakataga | CY3 | 59° | 44.400' | N | 142° | 31.800' | W | 9.7 | 10.5 | 0.9 | 2 | 8/4/2003 11:51 | 8/4/2003 13:51 |
| Cape Yakataga | CY4 | 59° | 34.200' | N | 142° | 34.200' | W | 10.3 | 10.5 | 1.0 | 2 | 8/4/2003 14:50 | 8/4/2003 16:50 |
| Cape Yakataga | CY5 | 59° | 27.600' | N | 142° | 35.400' | W | 6.6 | 10.5 | 0.6 | 2 | 8/4/2003 17:27 | 8/4/2003 19:27 |
| Cape Yakataga | CY6 | 59° | 18.000' | N | 142° | 38.400' | W | 9.7 | 10.5 | 0.9 | 11.62 | 8/4/2003 20:23 | 8/5/2003 8:00 |
| Cape Yakataga | CY7 | 59° | 07.800' | N | 142° | 40.800' | W | 10.3 | 10.5 | 1.0 | 2 | 8/5/2003 8:59 | 8/5/2003 10:59 |
| Cape Yakataga | CY8 | 58° | 57.600' | N | 142° | 43.200' | W | 10.3 | 10.5 | 1.0 | 2 | 8/5/2003 11:58 | 8/5/2003 13:58 |
| Cape Yakataga | CY9 | 58° | 48.000' | N | 142° | 45.600' | W | 9.7 | 10.5 | 0.9 | 2 | 8/5/2003 14:53 | 8/5/2003 16:53 |
| Ocean Cape | OC10 | 58° | 01.200' | N | 140° | 25.200' | W | 87.2 | 10.5 | 8.3 | 6.82 | 8/6/2003 1:11 | 8/6/2003 8:00 |
| Ocean Cape | OC9 | 58° | 10.800' | N | 140° | 21.600' | W | 9.8 | 10.5 | 0.9 | 2 | 8/6/2003 8:56 | 8/6/2003 10:56 |
| Ocean Cape | OC8 | 58° | 20.400' | N | 140° | 18.000' | W | 9.8 | 10.5 | 0.9 | 2 | 8/6/2003 11:52 | 8/6/2003 13:52 |
| Ocean Cape | OC7 | 58° | 30.000' | N | 140° | 15.000' | W | 9.7 | 10.5 | 0.9 | 2 | 8/6/2003 14:48 | 8/6/2003 16:48 |
| Ocean Cape | OC6 | 58° | 40.200' | N | 140° | 11.400' | W | 10.4 | 10.5 | 1.0 | 2 | 8/6/2003 17:47 | 8/6/2003 19:47 |
| Ocean Cape | OC5 | 58° | 53.400' | N | 140° | 06.600' | W | 13.4 | 10.5 | 1.3 | 10.94 | 8/6/2003 21:04 | 8/7/2003 8:00 |
| Ocean Cape | OC4 | 59° | 03.000' | N | 140° | 03.000' | W | 9.8 | 10.5 | 0.9 | 2 | 8/7/2003 8:56 | 8/7/2003 10:56 |
| Ocean Cape | OC3 | 59° | 13.200' | N | 139° | 59.400' | W | 10.4 | 10.5 | 1.0 | 2 | 8/7/2003 11:55 | 8/7/2003 13:55 |
| Ocean Cape | OC2 | 59° | 22.800' | N | 139° | 55.800' | W | 9.8 | 10.5 | 0.9 | 2 | 8/7/2003 14:51 | 8/7/2003 16:51 |
| Ocean Cape | OC1 | 59° | 32.400' | N | 139° | 51.600' | W | 9.8 | 10.5 | 0.9 | 2 | 8/7/2003 17:47 | 8/7/2003 19:47 |
| Spare Time |  | 59° | 32.400' | N | 139° | 51.600' | W | 0.0 | 10.5 | 0.0 | 15.3 | 8/7/2003 19:47 | 8/8/2003 11:05 |
| Arrive Juneau, Alaska |  | 58° | 22.619' | N | 134° | 39.168' | W | 1.3 | 10.5 | 0.1 |  | 8/9/2003 9:00 |  |

  - MF-03-10 Cruise Trackline