## Deferred Maintenance

Deferred Maintenance is defined in DOE Order 430.1b, Real Property Asset Management Order as "maintenance that was not performed when it should have been or was scheduled to be and which, therefore, is put off or delayed for a future period".

DM for each asset are developed by each site primarily via condition assessment surveys and entered in DOE’s web-based Facility Information Management System (FIMS). DM data in FIMS is updated in September each year per the DOE annual call. DM data are reported to the Federal Real Property Council.

DM is used to calculate the Asset Condition Index (ACI) performance measure. ACI is calculated as “1 minus the ratio of DM to Replacement Plant Value (RPV)”. The greater the DM the lower the ACI. DM that yields an ACI less than established goals is a concern.

ACI targets are based on the mission dependency status of a facility as shown below. The targets are set by OMB in the Three Year Rolling Timeline (TYRT) which implements DOE's Asset Management Plan.  The goal for mission critical facilities is set higher than that for mission dependent facilities.

|  | ACI |  |  |  |
| --- | --- | --- | --- | --- |
| Mission Dependency of Asset | FY 2006 | FY 2007 | FY 2008 | Long Term |
| Mission Critical | 0.96 | 0.962 | 0.964 | 0.98 |
| Mission Dependent | 0.946 | 0.947 | 0.948 | 0.95 |
| Not Mission Dependent | 0.95 | 0.9 | 0.85 | 0.85 |

SC has issued a decision tree for determining mission dependency of an asset. The general SC philosophy is that all facilities are mission related (i.e., Mission Critical or, Mission Dependent, Non Critical) unless they are non-operating excess. Also, laboratory buildings (FIMS Usage Category 700) are automatically designated as Mission Critical; however a site may request approval from SC-31.2 for a lower designation. Based on the SC approach, SC mission critical facilities account for $6.24B (80%) of SC’s $7.8B of general purpose facilities RPV.

Deferred Maintenance Backlog Reduction

Extensive deferred maintenance backlogs compromises mission accomplishment primarily in the long run as facilities slowly deteriorate and become outmoded to the point that they are no longer cost effective, reliable, safe, secure and energy efficient to operate; are not mission ready; and, pose as a marginal work environment for world class scientists.  SC deferred maintenance backlog at the end of FY 2007 is estimated to be $518,000,000.  For example, the asset condition index long-term (FY 2015) target for mission critical facilities is 0.98 or above, where the index is computed as 1 less the ratio of deferred maintenance to replacement plant value. A higher index indicates lower deferred maintenance.

SC’s deferred maintenance backlog exceeds the DOE Asset Condition Index goal by $232,000,000.  See table.

Deferred maintenance backlog reduction activities are currently funded primarily by the laboratories as overhead, charged to all users of the laboratory facilities.

To help ensure that DM does not grow, SC has set maintenance investment targets for our laboratories that, overall, exceed 2% of the laboratory’s replacement plant value.  This target is commensurate with the annual maintenance funding level recommended by the National Academy of Sciences of 2–4% of the replacement plant value.  Since implementation of this goal in 2005, SC’s DM has not grown.

SC’s main strategy for reducing deferred maintenance is SC’s proposed Infrastructure Modernization Initiative, which will modernize the general purpose infrastructure at SC laboratories. The initiative focuses on increased funding for line item construction projects which will result in significant additional reductions to the deferred maintenance backlog. SLI is developing measures for tracking the progress of the initiative in reducing deferred maintenance, as well as improving mission readiness, improving operational reliability and safety, and reducing the footprint and average age of facilities.

Deferred maintenance and ACI are imperfect measures for determining mission readiness.  The 2004 National Research Council Report, “Intelligent Sustainment and Renewal of DOE F&I”, therefore measuring only the physical condition is inadequate.  For example, the physical condition of a facility might be perfect (i.e., ACI = 1), but if the facility cannot meet the mission needs at all, then its MCI should be 0.”   SC is working to develop additional/alternative methods to determine Mission Readiness.

Deferred Maintenance by Lab FY 07

Projections of Deferred Maintenance in the Outyears

Projections of DM backlogs are required to assess the impacts of planned facility and infrastructure investments on ACI and MII.

The following process is repeated for each year for which a DM estimate is needed.  The DM of facilities planned for removal in the upcoming year is subtracted from the base DM yielding an adjusted DM.  Then, the estimated DM to be removed as a result of the maintenance program, deferred maintenance reduction initiative, IGPP, GPP and line items is subtracted from the adjusted DM, yielding a further adjusted DM.  Then, this adjusted DM is escalated by the escalation factor and, then increased further by estimated DM backlog growth as explained below.  This final DM becomes the base DM for the following year and the process is repeated as needed for the planning period which is generally 10 years including the base year.

The facilities to be removed are based on the site disposition plan (i.e., "estimated disposition year" in FIMS).   The DM used is the DM for the facility to be removed that is currently in FIMS escalated to the year it is to be removed.

The DM to be removed as a result of the maintenance program, deferred maintenance reduction initiative, IGPP, GPP and line items is based on the site's sustainment and recapitalization investment plan.  The DM should be escalated to the year it is to be removed.

Both the site sustainment and recapitalization investment plan and the site disposition plan are based on the planning scenario for which funding guidance has been provided.

Generally, the Department recommends a 2.3% escalation rate however the rate used should be based on local conditions.

There are 2 kinds of DM backlog growth (BG).  BG 1 reflects increased DM scope due to further deterioration of existing DM.  For example a leaking valve stains ceiling tiles, the need to replace something instead of merely repairing it or, the need to increase the quantity to be repaired or replaced.  BG 1 is set at .8% of the existing DM backlog and is based on a study Whitestone did for the Department.  Sites can adjust the BG 1 if they have sufficient historical data to develop statistical valid alternative factor.

BG 2 is an estimate of the increase in DM scope resulting from not funding maintenance sufficiently to preclude an increase in DM.  This increase in DM scope must be estimated based on the specifics of the site’s F&I sustainment planning.  For example, it may be well known that some large maintenance items will not be funded in year x and will be deferred.  To the extent that these large items are known, they need to be included in BG 2.  Sites that have experienced increasing DM backlogs over the last few years should pay particular attention to DM backlog growth due to insufficient maintenance funding.