## Goal 1A
POLK SWCD ANNUAL WORK PLAN |  |  |  |  | JULY 1, 2005 TO JUNE 30, 2006
Goal # 1 | Offer conservation planning process and technical and financial assistance to resource owners and
communities directed towards the conservation or wise use of soil and water resources within Polk Co.
Objective A | Provide technical and financial assistance and information to landowners and managers.
| Start Date | *Responsible | ***Days |  | Needed | Budget | Days | Date | Product or
Specific Tasks | End Date | Person(s) | Needed | Partners | Resources | Category | Spent | Completed | Outcome
Provide assistance with individual conservation plans. | July 2005 June 2006 | Elliott, Rudenko | 50 Staff 10 Directors | NRCS, FSA, ODFW, DU, ODF,USF&W | Surveying, design work, cost-share $ | Payroll-Technical Position |  |  | To implement conservation on the ground
Conduct "First Step" planning workshops throughout the year | July 2005 June 2006 | Elliott, Rudenko | 15 Staff | As needed | Notebooks, Projector, Maps, Ads | Payroll-Tech Special Events, Prod. |  |  | To provide group assistance rather then one on one
WHIP (administer funds, manage projects) | July 2005 June 2006 | Hastings, Elliott | 20 Staff | NRCS; FWS |  | Technical |  |  | Complete WHIP contracts
Provide information on financial assistance programs to landowners | July 2005 June 2006 | Rudenko, Elliott | 12 Staff | NRCS, FSA, | Brochures, Printed Materials | Payroll, Education Material |  |  | Provide information to landowners
Conduct CREP (outreach and planning) | July 2005 June 2006 | Ahr | 130 Staff | FSA, NRCS | Application Materials, Ads | CREP Grant, Admin |  |  | CREP contracts; streambank restoration
Coordinate Workgroups | July 2005 June 2006 | Clawson, Rudenko, Elliott, Hastings | 5 Staff 3 Directors | Participating Agencies | Speakers, materials, ads, site | Payroll-Technical Position |  |  | Participatie in inter-Agencies
NRCS Contribution Agreement | July 2005 June 2006 | Hastings, Thomson | 35 Staff | NRCS | Surveying, design work, cost-share $ | Payroll-Technical Position |  |  | Payment for plans written
Provide Technical Assistance for Wellhead Protection | July 2005 June 2006 | Rudenko, Elliott | 5 Staff 3 Directors | NRCS, FSA | Program rules | Payroll-Technical Position |  |  | Safe Groundwater
Provide input in Farmbill implementation | July 2005 June 2006 | Elliott, Thomson | 2 Staff 2 Director | NRCS; Local Work Group |  | Payroll-Technical Position |  |  | Farm Bill priorities specific for Polk Co. producers
*Responsible Person(s) Column: A person(s) will take the lead on a task and see that it is completed, they may either do it alone or with assistance.
**Quantity Column: An estimated number.
***Days Needed Column: Shows total number of days needed to complete the task. It does not necessarily represent total time allocated for one person, several people may be working on the task. Example ~ 3 people working on one day equals 3 days needed. Directors include Directors of Emeritus, Associate Directors, and elected Directors.

## Goal 1B
POLK SWCD ANNUAL WORK PLAN |  |  |  |  | JULY 1, 2005 TO JUNE 30, 2006
Goal # 1 | Offer conservation planning process, technical & financial assistance to landowners & communities,
whatever their source, directed towards the conservation of soil & water resources within Polk County.
Objective B | Provide general conservation assistance throughout Polk County
| Start Date | *Responsible | ***Days |  | Needed | Budget | Days | Date | Product or
Specific Tasks | End Date | Person(s) | Needed | Partners | Resources | Category | Spent | Completed | Outcome
Collect & maintain lists of available sources of assistance | July 2005 June 2006 | Rudenko, Elliott | 10 Staff | Consultants, Resource Agencies | Computer program, available info | Payroll-Technical Position |  |  | Fact sheets, web site, database
Provide basic conservation information & referrals to the public | July 2005 June 2006 | Directors, District and NRCS Staff | 5 staff | Consultants, Resource Agencies | Brochures, Web-sites, info packets | Payroll-Mgr. Technical Position |  |  | Provide requested information to the public
Promote and use the Coordinated Resource Management Process | July 2005 June 2006 | NRCS,SWCD Directors, Rudenko, Elliott | 5 staff | NRCS, FSA, ODFW, DU, ODF,USF&W | Literature, presentations workshops | Payroll-Mgr. Technical Position |  |  | To help implement conservation on the ground
Develop communication process to serve clientele (newsletters, articles, etc) | July 2005 June 2006 | Hastings, Rudenko, Elliott | 9 Staff 3 Directors | Public | Needs not yet known | Payroll-Mgr. Technical Position |  |  | Communication with clientele in need of conservation assistance
Weed Projects | July 2005 June 2006 | Hastings, Rudenko, Elliott | 30 Staff 120 Interns | M/Y/P Weed Coop.; landowners | Grant Funds | Payroll-Mgr. Technical Position |  |  | Invasive weed inventory & control
Provide Grant Process Assistance | July 2005 June 2006 | Hastings, Rudenko, Elliott | 15 Staff | Angencies and Polk County Public | Computer program, available info | Payroll-Mgr. Technical Position |  |  | Connect people with grant money
Indentify possible workshops on various topics as needed | July 2005 June 2006 | Whitaker, Hastings, Rudenko, Elliott | 10 Staff 4 Directors | Extension, NRCS, other agencies | Speakers, materials, ads, site | Payroll, Special Events, Ad |  |  | Present helpful topics to the public and resourece users
Provide site specific info on soils using GIS & NRCS Soils info | July 2005 June 2006 | Thomson, Rudenko, Elliott | 8 Staff | Polk County, NRCS, FSA | Arc View, printer, data | Payroll-Technical Position |  |  | Tools for conservation and land use planning

## Goal 2A
POLK SWCD ANNUAL WORK PLAN |  |  |  |  | JULY 1, 2005 TO JUNE 30, 2006
Goal # 2 | Support the Oregon Plan through watershed management within Polk County.
Objective A | Support existing & emerging watershed councils through agreements, memberships,
fiscal management, information or technical assistance.
| Start Date | *Responsible | ***Days |  | Needed | Budget | Days | Date | Product or
Specific Tasks | End Date | Person(s) | Needed | Partners | Resources | Category | Spent | Completed | Outcome
Provide a liaison, outreach and technical assistance for WCS activity in Polk Co. | July 2005 June 2006 | Thomson, Rudenko, Elliott | 25 Staff 25 Diretors | Basin Councils, NRCS | As requested | Payroll-Technical Person |  |  | Provide needed assistance as requested
Monitor and Update Watershed Councils thru MOUs | July 2005 June 2006 | Hastings | 15 Staff | Watershed Councils | Computer, watershed information | Payroll-Manager |  |  | MOU's
Provide grant administration & fiscal support to WatershedCouncils ** | July 2005 June 2006 | Hastings | 30 Staff | __ | Grant writing, report administration | Payroll-Manager |  |  | Provide support to Watershed Councils
Participate as active members in Watershed Councils of Polk CO. (1) | July 2005 June 2006 | As listed below | As listed below | As listed below | As listed below | __ |  |  | As listed below
(1a) Rickreall Watershed Council | July 2005 June 2006 | Director, Staff | 4 Staff 12 Director | RWC | As requested | __ |  |  | Council Participation
(1b)Luckiamute Watershed Council | July 2005 June 2006 | Whitaker, Staff | 4 Staff 12 Director | LWC | As requested | __ |  |  | Council Participation
(1c) Glenn/Gibson Watershed Council | July 2005 June 2006 | Simmons, Staff | 4 Staff 12 Director | GGWC | As requested | __ |  |  | Council Participation
(1d) Yamhill Watershed Council | July 2005 June 2006 | Simmons, Staff | 4 Staff 12 Director | YBWC | As requested | __ |  |  | Council Participation
(1e) Spring Valley Watershed Council | July 2005 June 2006 | Simmons, Staff | 4 Staff 12 Director | YBWC | As requested | __ |  |  | Council Participation
Small Grants Team | July 2005 June 2006 | Staff, Dalton | 1 Staff 1 Director | OWEB Small Grants Team | Printing, Mailing, and facilities | Payroll-Mgr. Technical Position |  |  | Record Keeper
Grant Projects (write, manage, monitor) | July 2005 June 2006 | Elliott, Rudenko | 25 Staff | Angencies and Polk Public | As requested | Technical |  |  | Successful projects
**Includes Rickreall, Yamhill, Glen/Gibson, Luckiamute, Spring Valley

## Goal 2B
POLK SWCD ANNUAL WORK PLAN |  |  |  |  | JULY 1, 2005 TO JUNE 30, 2006
Goal # 2 | Support the Oregon Plan through watershed management within Polk County.
Objective B | Implement the Ag Water Quality Management Area Plans within Polk County.
| Start Date | *Responsible | ***Days |  | Needed | Budget | Days | Date | Product or
Specific Tasks | End Date | Person(s) | Needed | Partners | Resources | Category | Spent | Completed | Outcome
Process and handle concerns & approving plans | July 2005 June 2006 | Staff and Directors for each Zone | 5 Staff 2 Directors | Yamhill LMA SWCD | Copies of plan, printed information | Director Time |  |  | Clarify and define process
Provide planning assistance to landowners (outside of programs) | July 2005 June 2006 | Rudenko, Elliott | 10 Staff 2 Directors | Yamhill SWCD, Agencies | Field Office Tech Guide, | Payroll-Technical Person |  |  | Provide planning assistance as needed
Continue providing information to Public on AgWQA affecting Polk County | July 2005 June 2006 | Whitaker, Rudenko, Elliott | 5 Staff | Benton SWCD, ODA | Printed info, articles, speakers | Payroll-Mgr, Technical Staff |  |  | Educate landowners etc.on SB1010 process
Water Temperature Monitoring Program | July 2005 June 2006 | Redon | 10 Staff 2 Directors | DEQ Monitoring Coordinator | Hobos, hardware | Technical |  |  | Prove compliance or indicate needed improvements

## Goal 3A
POLK SWCD ANNUAL WORK PLAN |  |  |  |  | JULY 1, 2005 TO JUNE 30, 2006
Goal # 3 | Conduct educational & outreach efforts related to soil, water, and other
natural resource issues and concerns within Polk County.
Objective A | Develop and conduct conservation related activities for the residents in Polk County.
| Start Date | *Responsible | ***Days |  | Needed | Budget | Days | Date | Product or
Specific Tasks | End Date | Person(s) | Needed | Partners | Resources | Category | Spent | Completed | Outcome
Maintain, evaluate, & coordinate use of equipment. | July 2005 June 2006 | Hastings, Alvarez | 4 Staff | DEQ Monitoring Coordinator | Chemicals, replace equipment | Equipment |  |  | Routine maintenance on equipment
Coordinate with local schools/groups to use water monitoring equipment | July 2005 June 2006 | Hastings, Thomson | 10 Staff | DEQ Monitoring Coordinator | Test kit components; hobos, etc | Technical |  |  | Expose students to applied science and good stewardship
Conduct Annual Plant & Tree Sale | July 2005 June 2006 | Rudenko, White | 20 Staff 12 Director | Yamhill SWCD, Volunteers | Trees, Printed Materials | Payroll-Manager, Tree Sale |  |  | Provide product and service to Polk Co. residents
Conduct School Outreach - Soils, Insect Collecting, Water Quality, Outdoor school, etc | July 2005 June 2006 | Hastings, Rudenko, Elliott, Alvarez, Redon | 145 Staff | NRCS, RWC | Soil Boxes, Insect collecting, water monitoring equip | Technical |  |  | Expose students to natural sciences
Celebrate the Creek Day (Pet Walk; Poster contest) | Sept. 2005 | Rudenko, Elliott, Hastings, Mulkey | 3 Staff 3 directors | RWC; ODFW | publicity, paper, prizes | Technical |  | Sept. 17, 2005 | Get kids involved in watershed activities; pet waste awareness
Tours of "on-the-ground" Conservation | July 2005 June 2006 | Hastings, Rudenko, Elliott, Alvarez | 3 Tours 7 Staff 3 Directors | Private Landowners | Sites | Technical |  |  | Employee enrichment; communtiy involvement
Promote FSA's wellhead protection (CRP) | July 2005 June 2006 | Rudenko, Elliott, White | 5 Staff 7 Directors | FSA | Federal Funding | Technical |  | FSA doesn't acknowledge wellhead protection | Protection of rural residential drinking water
Comply with Civil Rights Laws | July 2005 June 2006 | all | everyday | NRCS |  |  |  |  | Fair treatment and service to all

## Goal 3B
POLK SWCD ANNUAL WORK PLAN |  |  |  |  | JULY 1, 2005 TO JUNE 30, 2006
Goal # 3 | Conduct educational & outreach efforts related to soil, water, and other natural resource issues
and concerns within Polk County.
Objective B | Provide conservation education and recognition.
| Start Date | *Responsible | ***Days |  | Needed | Budget | Days | Date | Product or
Specific Tasks | End Date | Person(s) | Needed | Partners | Resources | Category | Spent | Completed | Outcome
Participate in Local community events **** | July 2005 June 2006 | Directors, Rudenko, Hastings, Elliott | 10 Staff 15 Directors | Community |  | Payroll-Mgr. & Technical |  |  | Raise conservation awareness
Scholorship Program | July 2005 June 2006 | Rudenko, Simmons, Board | 4 Staff 7 Directors | High School | Plant Sale profits | Payroll-Mgr. & Technical |  |  | Assistance to student in natural resources
Provide conservation awards and recognition to individuals, groups *** | July 2005 June 2006 | Alvarez, Rudenko, Hastings, Elliott, Awards/Selection Committee | 4 Staff 7 Directors | Community | Nominees, awards, information | Payroll-Manager, Awards |  |  | Awards presented at Annual Meeting
Create & maintain Polk SWCD Website | July 2005 June 2006 | Alvarez, Hastings | 8 Staff | Polk County, NACD | Host site, information, contractor | Payroll-Tech., Education Materials |  |  | Greater public access to District information
Provide articles, stories, photo opportunities for media | July 2005 June 2006 | Hastings, Rudenko, Elliott, Directors | 10 Staff | Local newspapers, radio, tv | Reporters, stories, news worthy items | Payroll-Mgr. & Technical |  |  | Good exposure for District to public
Annual Poster/Speech Contest | July 2005 June 2006 | Elliott, Mulkey | 4 Staff 7 Directors | Polk Co. Schools, Polk Co. Businesses* | Publicity and Donations | Awards Payroll-Mgr. & Technical |  | 2005-09-10 | Good exposure for District to public
***Includes Teacher of the Year, Cooperator of the Year, Communications award
**** Includes Events such as Summerfest, 4th of July Parade, Arbor Day, and etc.

## Goal 3C
POLK SWCD ANNUAL WORK PLAN |  |  |  |  | JULY 1, 2005 TO JUNE 30, 2006
Goal # 3 | Conduct educational & outreach efforts related to soil, water, and other natural resource issues
and concerns within Polk County.
Objective C | Create and maintain community relationships.
| Start Date | *Responsible | ***Days |  | Needed | Budgeted | Days | Date | Product or
Specific Tasks | End Date | Person(s) | Needed | Partners | Resources | Costs | Spent | Completed | Outcome
Maintain community relationships by sending out agendas, minutes | July 2005 June 2006 | Alvarez, White | 4 Staff | Agencies, Local Govt., Groups | Meeting minutes, agendas etc. | Payroll-Manager, Postage |  |  | Good communication & information exchange
Maintain community relationships w/civic & interest groups by making presentations | July 2005 June 2006 | Dalton | 8 Staff 7 Directors | Local government, organizations | Enough time | Travel & Volunteer |  |  | Build community trust, good communication
Volunteer Recruitment and Management | July 2005 June 2006 | Hastings, Rudenko, Elliott | 24 Staff | OSU, Western, Community | Tracking, Appropriate Projects for Skill Abilities | Payroll-Mgr. & Technical |  |  | Effective volunteer efforts
Participate in the Polk County Regional Water Study | July 2005 June 2006 | Staff, Simmons | 8 Staff | Polk County Water Associations | Attend meetings | Payroll-Mgr. & Technical |  |  | Water for All

## Goal 4A
POLK SWCD ANNUAL WORK PLAN |  |  |  |  | JULY 1, 2005 TO JUNE 30, 2006
Goal # 4 | District operations will be effective, economical, efficient, and responsive to public needs,
legal requirements, and grantors.
Objective A | Meet statutory operational duties
| Start Date | *Responsible | ***Days |  | Needed | Budget | Days | Date | Product or
Specific Tasks | End Date | Person(s) | Needed | Partners | Resources | Category | Spent | Completed | Outcome
Prepare, conduct & attend monthly board meetings | July 2005 June 2006 | Hastings, Dalton, Alvarez | 28 Staff 84 Directors | NRCS, Other agencies | Facility, agendas, minutes, info | Payroll-Mgr. & Clerical, Postage |  |  | To meet legal requirments & to inform public
Write & distribute annual report | July 2005 June 2006 | Elliott | 8 Staff | NRCS, Other agencies, Councils | Articles, budget info, layout design | Payroll-Mgr., Printing, Postage |  | 2005-09-26 | To meet legal requirments & to inform public
Hold Annual Meeting | July 2005 June 2006 | Hastings, Dalton, Mulkey | 8 Staff 12 Director | NRCS, other agencies, Community | Facility, food, program, speaker | Payroll-Mgr., Annual Meeting |  | 2005-09-14 | To meet legal requirments & public awareness
Develop policies & procedures to guide District operations | July 2005 June 2006 | Hastings, Committees | 3 Staff 36 Director | All District Directors | Examples, old policy statements | Payroll-Manager |  |  | Provide guidance for District Operations
Annual Work-Plan | July 2005 June 2006 | Elliott | 3 Staff 12 Director | NRCS, Councils | Examples, Distribution | Payroll-Mgr Tech, Production |  |  | Annual work plan
Purchase and Install District Boundary Signs as Needed | July 2005 June 2006 | Rudenko, White, Simmons | 3 Staff 7 Directors | Other SWCDs | Sign, Post, Site | Equipment |  |  | To raise public awareness
Time & Money Tracking/Accountability | July 2005 June 2006 | Hastings, Alvarez | 10 Staff | ODA, OWEB, WSC, Board | Accountant | Payroll-Manager |  |  | Accountability to the Public
Pursue Building Options for Conservation Center | July 2005 June 2006 | Hastings, White, Mulkey | 12 Staff 12 Director | FSA, NRCS, Extension | Money, Land, Building | Payroll-Manager |  |  | Community Building
Public budget process | July 2005 June 2006 | Budget Officer | 10 Staff 21 Directors | Budget Committee | Old budget & work plan, year-end info, tax rate | Payroll-Manager |  |  | Adoption & submittal of budget & maintenance
OACD Bookkeeping | July 2005 June 2006 | Hastings, Simmons, Alvarez | 6 Staff | OACD | OACD Funding | Clerical, Mgr, Payroll |  |  | payment from OACD

## Goal 4B
POLK SWCD ANNUAL WORK PLAN |  |  |  |  | JULY 1, 2005 TO JUNE 30, 2006
Goal # 4 | District operations will be effective, economical, efficient, and responsive to public needs,
legal requirements and grantors.
Objective B | Conduct recruitment and internal training
| Start Date | *Responsible | ***Days |  | Needed | Budget | Days | Date | Product or
Specific Tasks | End Date | Person(s) | Needed | Partners | Resources | Category | Spent | Completed | Outcome
Conduct staff and director training | July 2005 June 2006 | Hastings | 15 Staff 7 Directors | Special Districts, ODA, NRCS | Topics, facility, instructors | Payroll-Mgr. Staff-Director Training |  |  | Informed staff and directors on district issues
Provide opportunities for professional development of board & staff (Tours) | July 2005 June 2006 | Hastings, Elliott, Rudenko, Alvarez | 5 Staff 5 Directors | Special Districts, ODA, NRCS, OSU | Notice for seminars, workshop classes, etc | Payroll-Mgr. Staff-Director Training |  |  | Development of board and staff
Develop & maintain written job descriptions-staff, volunteers, directors | July 2005 June 2006 | Hastings, Personnel Committee | 1 Staff | SWCDs, ODA, Special Districts | Other SWCD's examples | Payroll-Manager |  |  | To help clarify positions
Conduct employee reviews | July 2005 June 2006 | Hastings, Personnel Committee | 1 Staff 1 Directors | Watershed Oversite Committee | Evaluation form, job descriptions | Payroll-Manager |  |  | Clarification, promote positive additude, raises
Recruit Associate Directors, Budget Committee Members, & Volunteers | July 2005 June 2006 | Hastings, Directors | 5 Staff 14 Directors | NRCS, Watershed Councils | Information, Brochures, Articles | Payroll-Manager |  |  | Increase resources to accomplish District's goals
Comply with Civil Rights Laws | July 2005 June 2006 | Manager, Directors, Staff | everyday | NRCS, FSA | postings |  |  |  | Fair treatment and service to all