Appendix Items:

A.  Individual Project Proposal Forms . . . . . . . . . . . . . . . 3

- Communications Plan . . . . . . . . . . . . . . . . . . . . . . . . .43

Appendix A – Project Proposal Forms

| # Henski Reservoir 106 Compliance | # 3 |
| --- | --- |
| # Forest Health Timber Management | # 5 |
| # Hazardous Fuels Reduction | # 7 |
| # Henski Reservoir Survey and Design | # 9 |
| # Hackamore TSI for Forest Health | # 11 |
| # Hackamore Road Decommissioning | # 13 |
| # Hackamore Vegetative Management | # 15 |
| # Hackamore Wetland Development | # 17 |
| # Warner Mountain Rangeland Project NEPA | # 20 |
| # Warner Mountain Rangeland Monitoring | # 22 |
| # Warner Rangeland Project Range Improvement | # 50 |
| # Warner Mountain Aspen Management | # 30 |
| # Warner Mountain Burning | # 35 |
| # Warner Mountain Suppression Strategies | # 41 |
| # Communication Plan | # 43 |

# Primary Purpose: NFRM

| MODOC NATIONAL FOREST Project Proposal |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| PROJECT TITLE: Upper Pit River Watershed Restoration Project - Hackamore Project ## Henski Reservoir Section 106 Historic Preservation Compliance |  |  |  |  |  |  |
| Recommended By: (District Ranger) | /s/ Bernie Weisgerber | Staff Area: |  | Public Service/Recreation |  |  |
| - Explain the situation: (Rationale for proposing the project be included in forest program. Is there a resource need, special emphasis area, legal requirement, part of basic operations, pressing customer needs, partnership available, increment of a larger part of work, etc.) Providing quality recreation experiences with minimal impacts to ecosystem stability and condition is a national goal. Forest Plan goal is to provide a broad spectrum of recreation opportunities and experiences and to facilitate an understanding of the various resources and uses of the Modoc National Forest. The Henski wildlife viewing interpretive site can increase public awareness and appreciation for wetlands, wetland dependent wildlife, and heritage resources. The completion of the required Section 106 of the National Historic Preservation Act compliance for the determination of NRHP eligibility and mitigation of effect of the proposed recreational/interpretive development at Henski Reservoir. This work is legally required prior to any development of this proposed Visitor Information Service area. |  |  |  |  |  |  |
| - Specific the results: (Identify what is provided and activity units. For example the project will increase willow flycatcher, improve water quality, increase recreationist experience, add to tourism base of local communities. Show results in terms of enhancement to the land and resulting benefits to people.) The completion of Section 106 requirements will result in a report that includes recommendations for interpretation of the archaeological site. The required compliance efforts are: - re-initiate consultation with the State Historic Preservation Office and the Pit River Tribe to - Solicit a determination of National Register of Historic Places eligibility for the archaeological site (FS-05-09-55-0758), - Consult on the nature of the effect of the proposed undertaking on the site, - Consult on the nature of the mitigative archaeological “data recover”, and - Prepare a Memorandum of Agreement for said work prior to initiating the field work; - Conduct the necessary archaeological excavations; - Conduct the necessary laboratory work and special analyses; - Prepare a professional report of the data recovery undertaken and make final recommendations for interpretation of the archaeological site. GPRA 2.1 Quality recreation experiences with minimal impact to ecosystem stability and condition |  |  |  |  |  |  |
| - Identify necessary resources: (What needs to be assembled to complete the proposed work.) - Forest Archaeologist/Heritage Resources Management (HRM) Program Manager - Zone Archaeologist Geographical Information System (GIS) support - Zone Archaeologist Archaeological survey - Two Volunteers/International Trainees for 8 weeks each - Two vehicles and misc. supplies - Funding for special analysis (e.g., obsidian sourcing and hydration, radiocarbon, blood residue) - Forest Tribal Liaison |  |  |  |  |  |  |
| 4. Describe required actions: (Provide a chronological description of actions, time frames, personnel responsible to complete the action, and costs.) |  |  |  |  |  |  |
| Action |  |  | Responsibility |  | ### Completion Date | Cost |
| Initiate consultation with State Historic Preservation Office and Native American Tribes |  |  | HRM Program Manager/Tribal Liaison |  | 12/10/99 |  |
| Determination of eligibility/effect and Memorandum Of Agreement complete |  |  | HRM Program Manager |  | 05/01/2000 |  |
| Conduct archaeological excavations |  |  | HRM Prog Mgr/Zarch |  | 07/14/2000 |  |
| Complete artifact processing/cataloging/send special analyses out for outside lab work |  |  | Zarch/HRM crew |  | 08/14/2000 | TOTAL cost for project: |
| Complete in-service analyses and report write-up |  |  | HRM Prog Mgr/Zarch |  | 09/30/2000 | $44,360.00 |
| - Monitor the results: (Outline plans to monitor the if desired results are attained.) Track progress to date at each proposed date as listed above. Report to be completed - all except for the inclusion of the results of the special analyses by 09/30/2000; final report write-up completed in early FY2001. |  |  |  |  |  |  |

# Primary Purpose: NFTM

| MODOC NATIONAL FOREST Project Proposal |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| PROJECT TITLE: Upper Pit River Watershed Restoration Project - Hackamore Project |  |  |  |  |  |  |
| Recommended By: (District Ranger) | /s/ Bernie Weisgerber | Staff Area: |  | Ecosystems/Timber |  |  |
| 1. Explain the situation: (Rationale for proposing the project be included in forest program. Is there a resource need, special emphasis area, legal requirement, part of basic operations, pressing customer needs, partnership available, increment of a larger part of work, etc.) Implement the commercial thinning stage of the Hackamore project, prepare the first increment of timber sales and start surveys on future project areas. This project will supply timber towards the forests sell targets and treat the stands to move them toward long-term sustainability and forest health. |  |  |  |  |  |  |
| - Specific the results: (Identify what is provided and activity units. For example the project will increase willow flycatcher, improve water quality, increase recreationist experience, add to tourism base of local communities. Show results in terms of enhancement to the land and resulting benefits to people.) This project will move approximately 3,000 acres of commercial forest land toward a condition that will be sustainable over time. The manipulation of stand density will allow the timber stands to withstand wildfire and insect attack better, tree growth will be increased so late seral conditions will be achieved sooner, and existing late seral stands will be maintained longer than is now anticipated with current stocking levels. Specifically, we will mark and cruise the Amore Timber Sale this year in preparation for sale in FY2001 expected yield is 5,000 MBF or 10,000 CCF of sawlogs; we will survey for future sale within the 3000 acres. Archaeological surveys will be conducted on approximately 1,500 acres for future projects. Benefits to the land include: - Tree growth will increase thus enabling older forest conditions to be reached sooner than if the area was not managed; and - faster growing trees are more resistant to insect and disease and wildfire Benefits to the people include: - Clean, healthy-appearing forest; and - Social and economic lifestyle of the rural community will continue |  |  |  |  |  |  |
| - Identify necessary resources: (What needs to be assembled to complete the proposed work.) - Marking crew - Sale preparation personnel - Stand exam crew - Silviculturist - Engineering - Fuels specialist - Archaeologists (current and future projects) - Soil and watershed specialist - Check cruising services for cruise design and compliance inspection - Supplies including vehicles, tree paint - Contracting |  |  |  |  |  |  |
| 4. Describe required actions: (Provide a chronological description of actions, time frames, personnel responsible to complete the action, and costs.) |  |  |  |  |  |  |
| Action |  |  | Responsibility |  | ### Completion Date | Cost |
| Completion of Amore harvest prescription |  |  | Anne Mileck |  | 12/31/99 | $8800 |
| Check layout and identify existing arch sites |  |  | Dave LeBlanc, Dee Green |  | prior to mark, | $5000 |
| Mark and cruise sale |  |  | Dave LeBlanc, Glenn Martin, Marking crew, Monte White, Molly Edgerton, Celia Yamagiwa |  | Complete Mark July 20, 2000 | $153,150 tree paint; $20,000 supplies $3,000 OT $10,000 FOR and mileage for vehicles $25,000 |
| Check Cruise design and sale check cruise and cruise report |  |  | Contract - Teams |  | 8/1/2000 | $10,000 |
| Program Mgt and Contract Preparation |  |  | Paul Bailey |  | 8/15/2000 | $25,000 |
| Support to contact prep |  |  | Randy Hall |  | 8/1/2000 | $2,000 |
|  |  |  | John Ford |  | 8/1/2000 | $2,000 |
|  |  |  | Dee Green |  | 8/1/2000 | $2,000 |
| Future Surveys, ARch + 180 days crew time |  |  | Dee Green |  | 9/30/2000 | $18,000 |
| Soil and Water input |  |  | Sue Becker and Soils |  | 9/30/2000 | $4,200 |
| Stand Exam Crew for future Rx |  |  | Anne Mileck +crew |  | 9/30/2000 | $30,000 |
| Total project cost |  |  |  |  |  | $318,150 |
| 5. Monitor the results: (Outline plans to monitor the if desired results are attained.) Monitor marking and contract to see that treatment matches expectations of the NEPA document |  |  |  |  |  |  |

# Primary Purpose: WFHF

| MODOC NATIONAL FOREST Project Proposal |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| PROJECT TITLE: Upper Pit River Watershed Restoration Project - Hackamore Project Hazardous Fuels Reduction |  |  |  |  |  |  |
| Recommended By: (District Ranger) | /s/ Bernie Weisgerber | Staff Area: |  | Fire and Fuels |  |  |
| - Explain the situation: (Rationale for proposing the project be included in forest program. Is there a resource need, special emphasis area, legal requirement, part of basic operations, pressing customer needs, partnership available, increment of a larger part of work, etc.) This prescribed burning project lies within a landscape dominated by eastside pine dispersed with sizeable sagebrush and juniper flats. The area is characterized as a short-interval, fire-adapted ecosystem with a 10-15 year historic fire return interval. Wildland fire threats increase each year as long-term effects from past land use and fire management actions increase the amount of wildland vegetation and fuels accumulations available to burn. The effects of fire-exclusion activities have led to a shift in fire effects, increasing the potential for larger, more costly, damaging wildland fires. The northwestern potion of the project area has been affected by stand-replacing wildland fires twice in the last 50 years. Escalating resource values to be protected, combined with dramatic increases in fire sizes, intensities, and rapid rates of spread have compounded protection concerns over the years. Challenges and risks associated with wildland fire management are increasing in complexity and extent. |  |  |  |  |  |  |
| - Specific the results: (Identify what is provided and activity units. For example the project will increase willow flycatcher, improve water quality, increase recreationist experience, add to tourism base of local communities. Show results in terms of enhancement to the land and resulting benefits to people.) Prescribed burning will reduce fuel loading, break up fuel continuity, and remove invading species that are fire intolerant. The forest ecosystem will be healthy, sustainable, and resistant to stand replacing wildland fires. Wildland fire sizes, intensity, and rates of spread will decrease. Benefits to the land include: - Accelerated development of mid-seral stands to late-seral stage; - accelerated growth and increase stand vigor in all seral stages, providing a balanced, sustainable forest over many decades; - maintain late seral conditions in 13 Northern Goshawk territories and 4 Bald Eagle nest stands; and - enhanced mule deer fall transition range in 500 acres of decadent brush fields. Benefits to the people include: - Reduced firefighter exposure; - increased firefighter safety; and - reduced suppression difficulty during wildland firefighting efforts |  |  |  |  |  |  |
| - Identify necessary resources: (What needs to be assembled to complete the proposed work.) - Resource Specialist for NEPA planning - NEPA Decision - Geographical Information System (GIS) support - Project layout personnel - Archaeological survey - SHPO - 106 Compliance - Dozer and/or handcrew - Contract administration - Prescribed Fire Burn Plan - Prescribed fire implementation personnel - Funding: $190,000 to plan, prep, layout and prescribed burn 2,000 acres; and archaeological surveys for FY2001 implementation |  |  |  |  |  |  |
| 4. Describe required actions: (Provide a chronological description of actions, time frames, personnel responsible to complete the action, and costs.) |  |  |  |  |  |  |
| Action |  |  | Responsibility |  | ### Completion Date | Cost |
| Provide fire/fuels input to NEPA planning (15 days) |  |  | Randy Hall |  | 11/99 | $3,000 |
| GIS support (10 & 5 days) |  |  | Yvonne Studinski, Alison Coons |  | 11/99 | $3,000 |
| Burn unit layout (10 days each) |  |  | Dave McMaster, Pat Preston, Jeff Pulfer |  | 11/99 | $6,000 |
| Field preparation for prescribed burning - Bobcat, dozer, and/or handcrew |  |  | Alison Coons |  | 04/00 | $20,000 |
| Administration for field preparation (10 days) |  |  | Alison Coons |  | 04/00 | $2,000 |
| Archaeological field survey and flagging - FY00 prescribed burn implementation (5 days) |  |  | Gerry Gates |  | 04/00 | $3,000 |
| SHPO - 106 Compliance |  |  | Dee Green |  | 04/00 | $1,000 |
| Prescribed Fire Burn Plan development (5 days each) |  |  | Randy Hall, Alison Coons |  | 04/00 | $2,000 |
| Prescribed burn implementation of 2000 acres |  |  | Randy Hall and Fire/Fuels organization |  | 06/00 | $130,000 |
| Archaeological survey for FY2001 and beyond |  |  | Gerry Gates |  | 09/00 | $20,000 |
| - Monitor the results: (Outline plans to monitor the if desired results are attained.) Conduct timber inventories. Conduct nest, habitat condition, use, and population surveys for Goshawks and Bald Eagles. Conduct mule deer use surveys, vegetation sampling and mapping. Complete Post Burn Summary and Documentation requirements outlined in the Prescribed Fire Burn Plan. Complete Smoke Dispersal Monitoring outlined in the Smoke Management Plan attached to the Prescribed Fire Burn Plan. Monitor annual fire frequency and acres burned to determine fire sizes, intensities, and fuel types burned. |  |  |  |  |  |  |

# Primary Purpose: NFRM

| MODOC NATIONAL FOREST Project Proposal |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| PROJECT TITLE: Upper Pit River Watershed Restoration Project - Hackamore Project ## Henski Day Use and Watchable Wildlife Area |  |  |  |  |  |  |
| Recommended By: (District Ranger) | /s/ Bernie Weisgerber | Staff Area: |  | Public Service/ Recreation |  |  |
| 1. Explain the situation: (Rationale for proposing the project be included in forest program. Is there a resource need, special emphasis area, legal requirement, part of basic operations, pressing customer needs, partnership available, increment of a larger part of work, etc.) Providing quality recreation experiences with minimal impacts to ecosystem stability and condition is a national goal. Forest Plan goal is to provide a broad spectrum of recreation opportunities and experiences and to facilitate an understanding of the various resources and uses of the Modoc National Forest. The Henski wildlife viewing interpretive site can increase public awareness and appreciation for wetlands, wetland dependent wildlife, and heritage resources. The Henski Day Use and Watchable Wildlife Area is funded for construction in FY2001. Partial survey and design work and heritage resources excavation must be completed to construct the facility as scheduled. Survey and design will be completed and contract awarded in FY2001. |  |  |  |  |  |  |
| - Specific the results: (Identify what is provided and activity units. For example the project will increase willow flycatcher, improve water quality, increase recreationist experience, add to tourism base of local communities. Show results in terms of enhancement to the land and resulting benefits to people.) A pull-off and wildlife viewing area will be developed at Henski Reservoir, immediately adjacent to Henski Reservoir, immediately adjacent to Highway 139. Parking areas, picnic tables and public information Kiosk will be constructed. Henski Day Use and Watchable Wildlife Area will showcase an outstanding special place on the Forest. It will provide necessary facilities along State Highway 139 while providing unique wildlife viewing and interpretation opportunities. Benefits to the land include: - Watershed and fisheries habitat are enhanced. Benefits to the people include: - Watershed and fisheries habitat are enhanced. |  |  |  |  |  |  |
| - Identify necessary resources: (What needs to be assembled to complete the proposed work.) - Engineer design crew and supplies - Engineer survey crew and supplies - Heritage Resources crew (see Section 106 project proposal for details) Archaeological survey - Recreation staff |  |  |  |  |  |  |
| 4. Describe required actions: (Provide a chronological description of actions, time frames, personnel responsible to complete the action, and costs.) |  |  |  |  |  |  |
| Action |  |  | Responsibility |  | ### Completion Date | Cost |
| Survey and design |  |  | Engineering |  | 5/30/2000 | $ 4,000 |
| Excavation (see Section 106 Compliance for detailed action items) |  |  | Heritage Resources |  | 8/30/2000 | $ 44,000 |
| Design support |  |  | Recreation |  | 5/30/2000 | $ 1,000 |
| - Monitor the results: (Outline plans to monitor the if desired results are attained.) Project will be monitored by recreation staff in accordance with the Forest Plan. |  |  |  |  |  |  |

# Primary Purpose: CWKV (TSI)

| MODOC NATIONAL FOREST Project Proposal |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| PROJECT TITLE: Upper Pit River Watershed Restoration Project - Hackamore Project |  |  |  |  |  |  |
| Recommended By: (District Ranger) | /s/ Bernie Weisgerber | Staff Area: |  | Ecosystems/Silviculture |  |  |
| 1. Explain the situation: (Rationale for proposing the project be included in forest program. Is there a resource need, special emphasis area, legal requirement, part of basic operations, pressing customer needs, partnership available, increment of a larger part of work, etc.) The Hackamore Ecosystem Watershed Restoration Project is a set of integrated management actions that achieve significant results in six critical ecosystem components over a 160,000 acre landscape. Forest ecosystem health and susceptibility is one component. The forest goal is to maintain a forest ecosystem that is sustainable in the long term. This will require a healthy forest that is resistant to insect or disease activity and stand replacing fires.The project objectives are to thin overstocked stands to increase tree vigor, increase disease and insect resistance, increase three growth to achieve late seral conditions, and reduce tree density to aid in underburning with prescribed fire. In addition, in partnership with the Pacific Southwest research station the Modoc has used the Hackamore Project to develop a geographic information system (GIS) tool to quickly and accurately provide forest stand density data. The information generated can be used in combination with other data to prepare site-specific prescriptions, or aggregated for landscape analysis, to meet a variety of resource objective within the ecosystem. |  |  |  |  |  |  |
| 2. Specify the results: (Identify what is provided and activity units. For example the project will increase willow flycatcher, improve water quality, increase the recreational experience, add to tourism base of local communities. Show results in terms of enhancement to the land and resulting benefits to people.) This project is implementation of the timber sale improvement ( precommercial thinning and or release) projects and SAI Plans identified in the Hackamore Planning Area of the Upper Pit River Restoration Project. Projects are tied to Management Attainment Report (MAR) Target expectations. 900 acres of Badger I and Badger II will be precommercially thinned (PCT). Benefits to the land include: - Precommercially thinned stands are inherently more vigorous, healthier, and more likely to resist catastrophic fire. Benefits to the people include: - Clean, healthy-appearing forest that is more resistant to insect and disease and wildfire. |  |  |  |  |  |  |
| - Identify necessary resources: (What needs to be assembled to complete the proposed work.) - Silvicultural Prescriptions - Maps - Aerial photos - R5-2400-202 TimberHarvestActivityRecord-PostSaleData - R5-2400-204 Timber Sale Improvement Activity Record - SAI Plan - Silviculturist - Forester - Botanist - GIS personnel - Contracting - Inspectors |  |  |  |  |  |  |
| 4. Describe required actions: (Provide a chronological description of actions, time frames, personnel responsible to complete the action, and costs.) |  |  |  |  |  |  |
| Action |  |  | Responsibility |  | ### Completion Date | Cost |
| Project Development |  |  | Claudia Schurwanz, Paul Siegel |  |  |  |
| Resource Support Silviculture Prescriptions |  |  | Anne Mileck |  |  |  |
| Botony |  |  | Sanger, Alison |  |  |  |
| Data Support |  |  | Randall, Traci |  |  |  |
| Field/Administration |  |  |  |  |  |  |
| Total Cost |  |  |  |  | 4/4/2000 | $361,000 |
| 5. Monitor the results: (Outline plans to monitor the if desired results are attained.) All MAR Targets are reportable at 10-Month and end-of-year. All KV SAI Plan projects are subject to review annually. All projects developed through Silviculture Prescriptions include review and monitoring as part of the project |  |  |  |  |  |  |

# Primary Purpose: PAMR

| MODOC NATIONAL FOREST Project Proposal |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| PROJECT TITLE: Upper Pit River Watershed Restoration Project - Hackamore Project ## Road Decommissioning |  |  |  |  |  |  |
| Recommended By: (District Ranger) | /s/ Bernie Weisgerber | Staff Area: |  | Public Services/ Engineering |  |  |
| - Explain the situation: (Rationale for proposing the project be included in forest program. Is there a resource need, special emphasis area, legal requirement, part of basic operations, pressing customer needs, partnership available, increment of a larger part of work, etc.) The Project area encompasses approximately 160,000 acres of Devil's Garden and Doublehead Ranger Districts. The northern two-thirds is generally flat, and drains north to Clear Lake and ultimately the Klamath River. The southern end is dissected by several steep drainages that flow directly to the Pit River. Both rivers have "impaired water quality" according to the State of California. An expansive road system, consisting of surfaced and low standard roads, provides almost unlimited access to the area. The Forest Plan goal is to provide and manage a Forest Transportation system to accomplish resource management objectives while protecting resource values. The objective of the Project is to minimize potential for sediment transport and delivery to the Pit River and Klamath River; and minimize the potential for disturbance of elk and deer herds. |  |  |  |  |  |  |
| - Specify the results: (Identify what is provided and activity units. For example the project will increase willow flycatcher, improve water quality, increase recreationist experience, add to tourism base of local communities. Show results in terms of enhancement to the land and resulting benefits to people.) 25 miles of roads determined to be non-essential to management needs, recreation access, or fire suppression will be obliterated. The result will be decreased sediment delivery and transport to the Klamath and Pit Rivers. Roads will be decommissioned by restoring natural drainage, by removing fills at stream crossings, outsloping all of the road prism, constructing water bars to ensure water does not travel along roadway, ripping compacted surfaces where necessary and blocking entrances. Benefits to the land include: - By obliterating nonessential roads and restoring natural drainages, less soil will be washed downstream to the Klamath and Pit Rivers. Benefits to the people include: - The Forest Service will be able to focus attention to the maintenance of essential roads. |  |  |  |  |  |  |
| - Identify necessary resources: (What needs to be assembled to complete the proposed work.) - Construction and Maintenance crew and equipment (C&M) - Archaeologists - Engineering Technician - Vehicles - Survey Equipment - Partnership with the Modoc County Land Use Committee |  |  |  |  |  |  |
| - Describe required actions: (Provide a chronological description of actions, time frames, personnel responsible to complete the action, and costs.) |  |  |  |  |  |  |
| Action |  |  | Responsibility |  | ### Completion Date | Cost |
| Archeologist will need to flag areas to be avoided |  |  | Dee Green |  | 06/01/2000 | $ 6,000 |
| C&M Crew decommission roads |  |  | Jim Hanes |  | 09/30/2000 | $ 126,000 |
| Engineering work to control work and document results |  |  | Charlie Johnson |  | 09/30/2000 | $ 6,000 |
| - Monitor the results: (Outline plans to monitor the if desired results are attained.) The C&M crew activities are monitored by the Forest Engineer. Jim Hanes the C&M foreman sends out weekly updates on project status. Charlie Johnson will provide engineering control surveys as needed, document completion of the work, and coordinate the work in progress. |  |  |  |  |  |  |

# Primary Purpose: NFFV

| MODOC NATIONAL FOREST Project Proposal |  |  |  |
| --- | --- | --- | --- |
| PROJECT TITLE: Upper Pit River Watershed Restoration Project - Hackamore Project |  |  |  |
| Recommended By: (District Ranger) | /s/ Bernie Weisgerber | Staff Area: | Ecosystems/Silviculture |
| - Explain the situation: (Rationale for proposing the project be included in forest program. Is there a resource need, special emphasis area, legal requirement, part of basic operations, pressing customer needs, partnership available, increment of a larger part of work, etc.) This Hackamore Ecosystem Watershed Restoration Project is a set of integrated management actions that achieve significant results in six critical ecosystem components over a 160,000 acre landscape. Forest ecosystem health and sustainability is one component. The forest goal is to maintain a forest ecosystem that is sustainable in the long term. This will require a healthy forest that is resistant to insect or disease activity and stand replacing fires. The project objective is to thin overstocked stands to increase tree vigor; increase disease and insect resistance; increase three growth to achieve late seral conditions; and reduce tree density to aid in underburning with prescribed fire. In addition, in partnership with the Pacific Southwest research station the Modoc has used the Hackamore Project to develop a geographic information system (GIS) tool to quickly and accurately provide forest stand density data. The information generated can be used in combination with other data to prepare site-specific prescriptions, or aggregated for landscape analysis, to meet a variety of resource objective within the ecosystem. |  |  |  |
| - Specific the results: (Identify what is provided and activity units. For example the project will increase willow flycatcher, improve water quality, increase recreationist experience, add to tourism base of local communities. Show results in terms of enhancement to the land and resulting benefits to people.) 140 acres will be precommercially thinned to accelerate growth and increase timber stand vigor and forest health. Benefits to the land include: - Precommercially thinned stands are more vigorous, healthier, and more likely to resist catastrophic fire. Benefits to the people include: - Clean, healthy-appearing forest that is more resistant to insect and disease and wildfire. |  |  |  |
| - Identify necessary resources: (What needs to be assembled to complete the proposed work.) - Silviculture Prescriptions NEPA Decision - Maps - Aerial photos - R5-2400-202 (Timber Harvest Activity Record-Post Sale Data) - R5-2400-204 (S.I. Activity Record) - GIS tools - Fuels specialist - Wildlife specialist - Heritage Resources - Timber field crew |  |  |  |

| 4. Describe required actions: (Provide a chronological description of actions, time frames, personnel responsible to complete the action, and costs.) |  |  |  |
| --- | --- | --- | --- |
| Action | Responsibility | ### Completion Date | Cost |
| Project Development: Hackamore Project | Siegel, Schurwanz | 4/4/2000 |  |
| Resource Support Silviculture Prescriptions |  |  |  |
| Fuels |  |  |  |
| Wildlife |  |  |  |
| HRM |  |  |  |
| Project / Fieldwork/layout | Temporary field crew |  |  |
| Total Cost |  |  | $60,000 |
| - Monitor the results: (Outline plans to monitor the if desired results are attained.) All MAR Targets are reportable at 10-Month and end-of-year. All projects developed through silviculture prescriptions have review and monitoring as part of the project. |  |  |  |

# Primary Purpose: NFWL

| MODOC NATIONAL FOREST Project Proposal |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| PROJECT TITLE: Upper Pit River Watershed Restoration Project - Hackamore Project ## Wetland Development |  |  |  |  |  |  |
| Recommended By: (District Ranger) | /s/ Bernie Weisgerber | Staff Area: |  | Ecosystems/Wildlife |  |  |
| - Explain the situation: (Rationale for proposing the project be included in forest program. Is there a resource need, special emphasis area, legal requirement, part of basic operations, pressing customer needs, partnership available, increment of a larger part of work, etc.) CA has lost about 95% of its historical wetlands, a trend that occurs nationwide. Our forest has a high potential for restoring some of the wetland losses. A nationwide plan has been developed called "The North American Waterfowl Management Plan", and the Forest Service has a wildlife special emphasis program called "Taking Wing". Both programs are designed to enhance wetland habitat and increase waterfowl populations across the nation. There are numerous national initiatives stressing wildlife viewing, hunting, fishing, and T&E species management. Currently there are over 200 wetlands on the forest covering about 34,000 acres. The Modoc N.F. has a 34 year history of wetland development, Watershed Restoration Project with financial support from groups, individuals, and agencies throughout California and professional and technical expertise from the Forest. |  |  |  |  |  |  |
| - Specific the results: (Identify what is provided and activity units. For example the project will increase willow flycatcher, improve water quality, increase recreationist experience, add to tourism base of local communities. Show results in terms of enhancement to the land and resulting benefits to people.) This project includes: - Whitney Reservoirs - Construct dam, spillway, headgate and 40 waterfowl nesting islands; - Hackamore Reservoir - Construct 10 waterfowl nesting islands; and - Outyear Planning work - Engineering survey and design of Deadhorse Flat Wetland Project (FY01), Archaeological survey of the Deadhorse Flat Project area. Benefits to the land include: - An annual production of around 250 Canada geese; - between 500 and 700 ducks; and - reestablished wetlands and wetland habitat. Benefits to the people include: - Increased waterfowl hunting and wildlife viewing opportunities on the Forest; and - waterfowl hunting opportunities in other areas of California. GPRA Healthy, biologically diverse and resilient aquatic ecosystems restored and protected to maintain a variety of ecological conditions and benefits. |  |  |  |  |  |  |
| - Identify necessary resources: (What needs to be assembled to complete the proposed work.) - Heritage Resource Crew - Engineer Crews (survey and design) - Contracting - Wildlife Biologists - Botonist - Hydrologist - Construction and Maintenance - Vehicles Needs to implement project: - $75K in partnership money - Archaeological survey of portions of Hackamore Reservoir, relocate archaeological sites at Whitney - Section 106 compliance - Archaeological survey rock pit site - Archaeological survey Deadhorse Flat Res (FY2001 project) - Locate rip-rap source for islands in east bay of Reservoir F - Archaeological survey East Bay Res F (FY2001 project) - Locate Rock quarry site. Drill test of Whitney rock quarry - Drill test of Deadhorse Flat Rock pit - Conduct sensitive plant survey at Whitney and Hackamore Reservoirs. Engineering review of original Whitney design - Engineering survey and design of Deadhorse Flat project - Obtain 404 permit from Corps of Engineers (get Forest wide exemption) - Prepare, advertise and administer rock pit contract - Prepare equipment rental agreement(s) - Construction staking of Whitney dam site. Stake island locations. |  |  |  |  |  |  |
| 4. Describe required actions: (Provide a chronological description of actions, time frames, personnel responsible to complete the action, and costs.) |  |  |  |  |  |  |
| Action |  |  | Responsibility |  | ### Completion Date | Cost |
| Locate Potential Rock Pit(s) |  |  | Hanes/Studinski/Sharp |  | 10/30/99 | $1,000 |
| Arch 106 compliance |  |  | Gates |  | 11/15/99 etc. | $1,500 |
| Arch Survey potential rock pit(s) |  |  | Gates |  | 11/30/99 | $3,000 |
| Evaluate cost effectiveness of rock pit development over collecting rock from exiting sources (pipeline rock etc.) |  |  | Parkinson/Weisgerber/Sharp |  | 12/1/99 | $800 |
| Engineering review of original Whitney design |  |  | Parkinson |  | 12/1/99 | $500 |
| Arch Survey Whitney (relocate sites, etc.) |  |  | Gates |  | 12/1/99 | $1,500 |
| Drill test Whitney and Deadhorse rock pits |  |  | Hanes/Sharp |  | 12/30/99 | $2,500 |
| Arch Survey Hackamore Res for Islands |  |  | Gates |  | 12/30/99 | $1,000 |
| Engineering Survey Deadhorse Flat Reservoir |  |  | Parkinson |  | 12/30/99 | $3,000 |
| Secure Partnership funding ($75K) |  |  | Ratcliff/Flores |  | 5/1/00 | $1,500 |
| Obtain 404 Permit from Corps (Section 27 exemption best) |  |  | Becker/Studinski |  | 6/1/00 | $2,000 |
| Sensitive Plant surveys - Whitney, and Hackamore Reservoirs |  |  | Sanger |  | 6/30/00 | $800 |
| Sensitive Plant surveys - Deadhorse Flat & east bay Res F. |  |  | Sanger |  | 9/30/00 | $800 |
| Prepare and advertise rock pit contract |  |  | Parkinson |  | 6/1/00 | $25,000 |
| Prepare equipment rental agreements |  |  | Hanes |  | 6/1/00 | $500 |
| Construction staking of Whitney dam site |  |  | Parkinson |  | 8/1/00 | $800 |
| Stake island locations at Whitney & Hackamore |  |  | Studinski |  | 8/1/00 | $500 |
| Arch survey east bay Res F |  |  | Gates |  | 9/30/00 | $1,000 |
| Arch survey Deadhorse Flat Res |  |  | Gates |  | 9/30/00 | $1,000 |
| Construct Whitney dam |  |  | Parkinson |  | 9/30/00 | $45,000 |
| Construct 50 islands - Whitney/Hackamore |  |  | Parkinson |  | 9/30/00 | $100,000 |
| - Monitor the results: (Outline plans to monitor the if desired results are attained.) Administer contract and C&M crew to ensure project design specifications are being implemented as planned. It will not be necessary to monitor waterfowl production since past years information can be applied. |  |  |  |  |  |  |

# Primary Purpose: NFRG

| MODOC NATIONAL FOREST Project Proposal |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| PROJECT TITLE: Upper Pit River Watershed Restoration Project - Warner Project |  |  |  |  |  |  |
| Recommended By: (District Ranger) | /s/ Edith Asrow | Staff Area: |  | Ecosystems/Range |  |  |
| - Explain the situation: (Rationale for proposing the project be included in forest program. Is there a resource need, special emphasis area, legal requirement, part of basic operations, pressing customer needs, partnership available, increment of a larger part of work, etc.) About 150 years ago European settlers began to graze domestic livestock across the Warner Mountains. Today almost the entire landscape is covered by grazing permits. Sierra Nevada Ecosystems in the Presence of Livestock (1999), a report prepared by the Rangeland Science Team for the Pacific Southwest Station and Region, stated the pressure of livestock grazing over the past century degraded conditions in some riparian habitats on the Warner Mountain. In addition, fire suppression over the past 50 years has allowed most of the shrub habitats to mature and become decadent. This situation limits the abundance of high quality upland vegetative mosaic for wildlife as well as livestock further increasing pressure in the riparian areas. Currently 20,000 AUMs are permitted on the 350,000 acre Ranger District. |  |  |  |  |  |  |
| - Specific the results: (Identify what is provided and activity units. For example the project will increase willow flycatcher, improve water quality, increase recreationist experience, add to tourism base of local communities. Show results in terms of enhancement to the land and resulting benefits to people.) This project will result in NEPA-sufficient documentation for: - New grazing decisions on 26 range allotments, including allotments within the South Warner Wilderness - Provisions for riparian restoration and upland vegetation enhancement. Benefits to the land include: - Through livestock management, riparian areas will be restored providing clean and abundant water to the Sacramento River through the Pit River Benefits to the people include: - Social and economic lifestyle of our rural community will continue - The quality of water is improved. |  |  |  |  |  |  |
| - Identify necessary resources: (What needs to be assembled to complete the proposed work.) - Project Leader - Wildlife Biologist - Botanist - Rangeland Manager - Fisheries Biologist - Fire Ecologist - GIS Support - Heritage Resources - Silviculturist - Vegetation Ecologist - Meeting Room - Electronic Projector - PAO |  |  |  |  |  |  |
| 4. Describe required actions: (Provide a chronological description of actions, time frames, personnel responsible to complete the action, and costs.) |  |  |  |  |  |  |
| Action |  |  | Responsibility |  | ### Completion Date | Cost |
| Developed proposed action |  |  |  |  | 7/99 |  |
| Scoping |  |  |  |  | 7/99 -8/99 |  |
| Complete field review/ scoping analysis |  |  |  |  | 11/99 |  |
| Alternative development and analysis |  |  |  |  | 11/99 |  |
| Envirnomental analysis |  |  |  |  | 12/99 - 3/00 |  |
| Draft nepa document/ public review/ comment analysis |  |  |  |  | 4/00 |  |
| Complete NEPA Decision Notice(s) |  |  | District Ranger & Project Leader |  | 6/1/00 | $70,000 |
| - Monitor the results: (Outline plans to monitor the if desired results are attained.) Monitor annual implementation of grazing strategies and utilization standards. The Permittee and Forest Service will jointly identify key areas for annual monitoring. Utilization standards will be monitored before, during and after livestock grazing to determine when to move livestock to new pastures. |  |  |  |  |  |  |

PRIMARY PURPOSE_______________                         FUND CODE___________

|  | MODOC NATIONAL FOREST |  |
| --- | --- | --- |
|  | PROJECT PROPOSAL FORM |  |

PROJECT:Warner Mountain Rangeland Project-Range Implementation and Effectiveness Monitoring

| RECOMMENDED BY (District Ranger): |  |  | STAFF AREA: | Range |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Explain the situation: (Rationale for proposing the project be included in forest program. Is there a resource need, special emphasis area, legal requirement, part of basic operations, pressing customer needs, partnership available, increment of a larger part of work, etc.) The Environmental Analysis for the Warner Mountain Rangeland Project has proposed monitoring of permit compliance and monitoring of the effecrtiveness of new permit requirements in causing an appropriate rate a change in vegetative communities towards the Desired Condition. |  |  |  |  |  |  |
| 2. Specify the results: (Identify what is provided and activity units. For example, project will increase willow flycatcher, improve water quality, increase recreationist experience, add to tourism base of local communities. Show results in terms of enancement to the land and resulting benefits to people.) The proposed monitoring will allow management to know if permits are being complied with, and if permit conditons are effective in producing desired changes in vegetative communities on 350,000 acres. |  |  |  |  |  |  |
| 3. Identify necessary resources: (What needs to be assembled to complete the proposed work.) Implementation and Effectiveness Monitoring consists of the following tasks: Location and documentation of vegetative conditions of Key Areas for annual implementation monitoring; Annual monitoring of utilization on Key Areas; Location and documentation of vegetative conditions of Benchmarks for effectiveness (long-term) monitoring; and Periodic monitoring of benchmarks for effectiveness (long-term) monitoring. |  |  |  |  |  |  |
| Action |  | Responsibility |  |  | Completion Date | Cost |
| FY 2000 |  |  |  |  |  |  |
| Location of Key Areas Annual monitoring and Location of Benchmarks |  | K.C. Bordwell (+ 2 Range techs, Permittees, and other resource specialists – e.g. ecologist, botanist, & fishery biologist) |  |  | 9/30/2000 | $19,000 |

| Action | Responsibility | Completion Date | Cost |
| --- | --- | --- | --- |
| FY 2001 |  |  |  |
| Location of Key Areas Annual monitoring and Location of Benchmarks | K.C. Bordwell (+ 2 Range techs, Permittees, and other resource specialists – e.g. ecologist, botanist, & fishery biologist) | 9/30/2001 | $30,000 |
| FY 2002 |  |  |  |
| Location of Key Areas Annual monitoring and Location of Benchmarks | K.C. Bordwell (+ 2 Range techs, Permittees, and other resource specialists – e.g. ecologist, botanist, & fishery biologist) | 9/30/2002 | $30,000 |
| FY 2003 |  |  |  |
| Location of Key Areas and Annual monitoring and Monitoring of Benchmarks | K.C. Bordwell (+ 2 Range techs, Permittees, and other resource specialists – e.g. ecologist, botanist, & fishery biologist) | 9/30/2003 | $30,000 |
| FY 2004 |  |  |  |
| Location of Key Areas and Annual monitoring and Monitoring of Benchmarks | K.C. Bordwell (+ 2 Range techs, Permittees, and other resource specialists – e.g. ecologist, botanist, & fishery biologist) | 9/30/2004 | $30,000 |
| TOTAL MONITORING – ALL YEARS |  |  | $139,000 |
| 5. Monitor the results: (Outline plans to monitor to see if desired results are attained.) Included above. |  |  |  |

PRIMARY PURPOSE_______________                         FUND CODE___________

|  | MODOC NATIONAL FOREST |  |
| --- | --- | --- |
|  | PROJECT PROPOSAL FORM |  |

PROJECT  NAME:Warner Mountain Rangeland Project-Range Improvements

| RECOMMENDED BY (District Ranger): |  | STAFF AREA: | Range |
| --- | --- | --- | --- |
| 1. Explain the situation: (Rationale for proposing the project be included in forest program. Is there a resource need, special emphasis area, legal requirement, part of basic operations, pressing customer needs, partnership available, increment of a larger part of work, etc.) The Environmental Analysis for the Warner Mountain Rangeland Project has proposed range improvement projects on the Warner Mountain Ranger District. |  |  |  |
| 2. Specify the results: (Identify what is provided and activity units. For example, project will increase willow flycatcher, improve water quality, increase recreationist experience, add to tourism base of local communities. Show results in terms of enancement to the land and resulting benefits to people.) The proposed range improvement projects will improve grazing operations efficiency and move vegetative communities towards Desired Conditions on approximately 804 acres, in the following projects: Priority 1 - FY 2000 Implementation Projects (MB-1[1 ac.], MB-11 [20 ac.] and DC-4 & DC-7 [3 ac.] ) – TOTAL 24 ac. Priority 1 – FY 2001 Implementation Projects (BM-10 [20 ac.], BLC-12 [5 ac.], BLC-18 [10 ac.], BC-1 [10 ac.], DC-1 [1 ac.], LC-8a [6 ac.], LC-8b [6 ac.], F/LC-1 [6 ac.], GC-7 [5 ac.], OU-4 [1 ac.], WV-5 [1 ac.], YJ-11 [5 ac.], YJ-14 [1 ac.], and YJ-17 [1 ac.], BLC-14 [42 ac.] – TOTAL 120 ac. Priority 1 – FY 2002 Implementation Projects BM-3 [20 ac.], BM-13/DC-14 [6 ac.], BM-14/DC-15 [6 ac.], BM-14a [2 ac.], BR-13 [12 ac.], BLC-9 [6 ac.], BLC-10 [1 ac.], BLC-18 [10 ac.], BLC-19 [3 ac.], CC-3 [12 ac.], MB-6a [5 ac.], WV-4 [2 ac.] and WV-7 [12 ac.] – TOTAL 97 ac. Priority 1 – FY 2003 Implementation Projects BLC-18 [10 ac.] – TOTAL 10 ac. Priority 1 - FY 2004 Implementation Projects BLC-18 [10 ac.] – TOTAL 10 ac. Priority 2 – FY 2002-2004 Implementation Projects BM-4 [15 ac.], BM-6 [10 ac.], BM-8b [2 ac.], BM-8c [1 ac.], BM-8d [1 ac.], BMR-1 [80 ac.], BMR-3 [6 ac.], BR-14 [20 ac.], BR-15 [50 ac.], BLC-11 [5 ac.], BLC-13 [10 ac.], BLC-16 [2 ac.], BLC-17 [5 ac.] CC-5 [2 ac.], CC-8 [100 ac.], CC-10 [100 ac.], CC-11 [2 ac.], F-1 [1 ac.], F-2 [3 ac.], F-2a [5 ac.], F-3 [1 ac.], F-4 [1 ac.], F-5 [1 ac.], HM-8 [3 ac.], LC-3 [6 ac.], LC-5 [1 ac.], LC-7 [1 ac.], MB-6 [3 ac.], MC-2 [30 ac.], NC-1 [1 ac.], NC-2 [20 ac.], NP-3a [1 ac.], NP-3b [2 ac.], NP-5 [20 ac.], NP-6 [25 ac.], NP-9 [2 ac.], WV-6 [10 ac.], YJ-12 [5 ac.], YJ-13 [5 ac.], YJ-18 [1 ac.], YJ-19 [3 ac.], YJ-20 [1 ac.] TOTAL Acres Priority 2 = 563 |  |  |  |
| 3. Identify necessary resources: (What needs to be assembled to complete the proposed work.) Project layout - Identification of unit boundaries and required transportation or other service areas needed. Archeological survey - Survey, document and recommend management actions. Sensitive Plant survey. Project Implementation |  |  |  |

| Action | Responsibility | Completion Date | Cost |
| --- | --- | --- | --- |
| FY 2000 |  |  |  |
| Project layout @ $5/ac. Priority 1 - FY 2000 Implementation Projects MB-1[1 ac.], MB-11 [20 ac.] and DC-4 & DC-7 [3 ac.] TOTAL 24 ac. | K.C. Bordwell (+ 2 Range Techs) | 6/30/2000 | $120 |
| Project layout @ $5/ac Priority 1 – FY 2001 Implementation Projects BM-10 [20 ac.], BLC-12 [5 ac.], BLC-18 [10 ac.], BC-1 [10 ac.], DC-1 [1 ac.], GC-7 [5 ac.], YJ-11 [5 ac.], YJ-14 [1 ac.] TOTAL 57 ac. | K.C. Bordwell (+ 2 Range Techs) | 7/31/2000 | $285 |
| Project layout @ $5/ac Priority 1 – FY 2001 Implementation Projects LC-8a [6 ac.], LC-8b [6 ac.], F/LC-1 [6 ac.], OU-4 [1 ac.], WV-5 [1 ac.], YJ-17 [1 ac.], BLC-14 [42 ac.] TOTAL 63 ac. | K.C. Bordwell (+ 2 Range Techs) | 9/30/2000 | $315 |
| Project layout @ $5/ac Priority 1 – FY 2002 Implementation Projects BM-3 [20 ac.], BM-13/DC-14 [6 ac.], BM-14/DC-15 [6 ac.], BM-14a [2 ac.], BR-13 [12 ac.], BLC-9 [6 ac.], BLC-10 [1 ac.], BLC-18 [10 ac.], BLC-19 [3 ac.], CC-3 [12 ac.], MB-6a [5 ac.], WV-4 [2 ac.] and WV-7 [12 ac.] TOTAL 97 ac. | K.C. Bordwell (+ 2 Range Techs) | 9/30/2000 | $485 |
| Project layout @ $5/ac Priority 1 – FY 2003 Implementation Projects NONE |  |  |  |
| Project layout @ $5/ac Priority 1 - FY 2004 Implementation Projects NONE |  |  |  |

| Action | Responsibility | Completion Date | Cost |
| --- | --- | --- | --- |
| Project layout @ $5/ac Priority 2 – FY 2002-2004 Implementation Projects BM-4 [15 ac.], BM-6 [10 ac.], BM-8b [2 ac.], BM-8c [1 ac.], BM-8d [1 ac.], BMR-1 [80 ac.], BMR-3 [6 ac.], BR-14 [20 ac.], BR-15 [50 ac.], BLC-11 [5 ac.], BLC-13 [10 ac.], BLC-16 [2 ac.], BLC-17 [5 ac.]CC-5 [2 ac.], CC-8 [100 ac.], CC-10 [100 ac.], CC-11 [2 ac.], F-1 [1 ac.], F-2 [3 ac.], F-2a [5 ac.], F-3 [1 ac.], F-4 [1 ac.], F-5 [1 ac.], HM-8 [3 ac.], LC-3 [6 ac.], LC-5 [1 ac.], LC-7 [1 ac.], MB-6 [3 ac.], MC-2 [30 ac.], NC-1 [1 ac.], NC-2 [20 ac.], NP-3a [1 ac.], NP-3b [2 ac.], NP-5 [20 ac.], NP-6 [25 ac.], NP-9 [2 ac.], WV-6 [10 ac.], YJ-12 [5 ac.], YJ-13 [5 ac.], YJ-18 [1 ac.], YJ-19 [3 ac.], YJ-20 [1 ac.] TOTAL Acres Priority 2 = 563 | K.C. Bordwell (+ 2 Range Techs) | 9/30/2000 | $2,815 |
| Archeological survey @ $300 EA Priority 1 - FY 2000 Implementation Projects MB-1[1 ac.], MB-11 [20 ac.] and DC-4 & DC-7 [3 ac.] TOTAL 24 ac. | Gerry Gates | 7/31/2000 | $900 |
| Archeological survey @ $ 300 EA Priority 1 – FY 2001 Implementation Projects BM-10 [20 ac.], BLC-12 [5 ac.], BLC-18 [10 ac.], BC-1 [10 ac.], DC-1 [1 ac.], GC-7 [5 ac.], YJ-11 [5 ac.], YJ-14 [1 ac.], TOTAL 57 ac. | Gerry Gates | 9/30/2000 | $2,400 |
| Sensitive Plant survey @ $5/ac. Priority 1 - FY 2000 Implementation Projects MB-1[1 ac.], MB-11 [20 ac.] and DC-4 & DC-7 [3 ac.] TOTAL 24 ac. | Botanist | 6/30/2000 | $120 |
| Sensitive Plant survey @ $5/ac. Priority 1 – FY 2001 Implementation Projects BM-10 [20 ac.], BLC-12 [5 ac.], BLC-18 [10 ac.], BC-1 [10 ac.], DC-1 [1 ac.], GC-7 [5 ac.], YJ-11 [5 ac.], YJ-14 [1 ac.] TOTAL 57 ac. | Botanist | 9/30/2000 | $285 |
| Project implementation Priority 1 - FY 2000 Implementation Projects MB-1[1 ac.], MB-11 [20 ac.] and DC-4 & DC-7 [3 ac.] TOTAL 24 ac. | K.C. Bordwell (+ 2 Range Techs) | 9/30/2000 | $11,860 |
| TOTAL -ALL TASKS FY 2000 |  |  | $19,585 |

| Action | Responsibility | Completion Date | Cost |
| --- | --- | --- | --- |
| FY 2001 |  |  |  |
| Archeological survey @ $300 EA Priority 1 – FY 2001 Implementation Projects LC-8a [6 ac.], LC-8b [6 ac.], F/LC-1 [6 ac.], OU-4 [1 ac.], WV-5 [1 ac.], YJ-17 [1 ac.], BLC-14 [42 ac.] TOTAL 63 ac. | Gerry Gates | 7/31/2001 | $2,100 |
| Archeological survey @ $300 EA Priority 1 – FY 2002 Implementation Projects BM-3 [20 ac.], BM-13/DC-14 [6 ac.], BM-14/DC-15 [6 ac.], BM-14a [2 ac.], BR-13 [12 ac.], BLC-9 [6 ac.], BLC-10 [1 ac.], BLC-18 [10 ac.], BLC-19 [3 ac.], CC-3 [12 ac.], MB-6a [5 ac.], WV-4 [2 ac.] and WV-7 [12 ac.] TOTAL 97 ac. | Gerry Gates | 9/30/2001 | $3,900 |
| Priority 1 – FY 2003 Implementation Projects NONE |  |  |  |
| Priority 1 - FY 2004 Implementation Projects NONE |  |  |  |
| Archeological survey @ $300 EA Priority 2 – FY 2002-2004 Implementation Projects BM-4 [15 ac.], BM-6 [10 ac.], BM-8b [2 ac.], BM-8c [1 ac.], BM-8d [1 ac.], BMR-1 [80 ac.], BMR-3 [6 ac.], BR-14 [20 ac.], BR-15 [50 ac.], BLC-11 [5 ac.], BLC-13 [10 ac.], BLC-16 [2 ac.], BLC-17 [5 ac.]CC-5 [2 ac.], CC-8 [100 ac.], CC-10 [100 ac.], CC-11 [2 ac.], F-1 [1 ac.], F-2 [3 ac.], F-2a [5 ac.], F-3 [1 ac.], F-4 [1 ac.], F-5 [1 ac.], HM-8 [3 ac.], LC-3 [6 ac.], LC-5 [1 ac.], LC-7 [1 ac.], MB-6 [3 ac.], MC-2 [30 ac.], NC-1 [1 ac.], NC-2 [20 ac.], NP-3a [1 ac.], NP-3b [2 ac.], NP-5 [20 ac.], NP-6 [25 ac.], NP-9 [2 ac.], WV-6 [10 ac.], YJ-12 [5 ac.], YJ-13 [5 ac.], YJ-18 [1 ac.], YJ-19 [3 ac.], YJ-20 [1 ac.] TOTAL Acres Priority 2 = 563 | Gerry Gates | 9/30/2001 | $12,600 |
| Sensitive Plant survey @ $5/ac. Priority 1 – FY 2001 Implementation Projects LC-8a [6 ac.], LC-8b [6 ac.], F/LC-1 [6 ac.], OU-4 [1 ac.], WV-5 [1 ac.], YJ-17 [1 ac.], BLC-14 [42 ac.], TOTAL 63 ac. | Botanist | 7/31/2001 | $315 |
| Sensitive Plant survey @ $5/ac. Priority 1 – FY 2002 Implementation Projects BM-3 [20 ac.], BM-13/DC-14 [6 ac.], BM-14/DC-15 [6 ac.], BM-14a [2 ac.], BR-13 [12 ac.], BLC-9 [6 ac.], BLC-10 [1 ac.], BLC-18 [10 ac.], BLC-19 [3 ac.], CC-3 [12 ac.], MB-6a [5 ac.], WV-4 [2 ac.] and WV-7 [12 ac.] TOTAL 97 ac. | Botanist | 9/30/2001 | $ 485 |

| Action | Responsibility | Completion Date | Cost |
| --- | --- | --- | --- |
| Priority 1 – FY 2003 Implementation Projects NONE |  |  |  |
| Priority 1 - FY 2004 Implementation Projects NONE |  |  |  |
| Sensitive Plant survey @ $5/ac. Priority 2 – FY 2002-2004 Implementation Projects BM-4 [15 ac.], BM-6 [10 ac.], BM-8b [2 ac.], BM-8c [1 ac.], BM-8d [1 ac.], BMR-1 [80 ac.], BMR-3 [6 ac.], BR-14 [20 ac.], BR-15 [50 ac.], BLC-11 [5 ac.], BLC-13 [10 ac.], BLC-16 [2 ac.], BLC-17 [5 ac.]CC-5 [2 ac.], CC-8 [100 ac.], CC-10 [100 ac.], CC-11 [2 ac.], F-1 [1 ac.], F-2 [3 ac.], F-2a [5 ac.], F-3 [1 ac.], F-4 [1 ac.], F-5 [1 ac.], HM-8 [3 ac.], LC-3 [6 ac.], LC-5 [1 ac.], LC-7 [1 ac.], MB-6 [3 ac.], MC-2 [30 ac.], NC-1 [1 ac.], NC-2 [20 ac.], NP-3a [1 ac.], NP-3b [2 ac.], NP-5 [20 ac.], NP-6 [25 ac.], NP-9 [2 ac.], WV-6 [10 ac.], YJ-12 [5 ac.], YJ-13 [5 ac.], YJ-18 [1 ac.], YJ-19 [3 ac.], YJ-20 [1 ac.] TOTAL Acres Priority 2 = 563 | Botanist | 9/30/2001 | $2,815 |
| Project implementation Priority 1 – FY 2001 Implementation Projects BM-10 [20 ac.], BLC-12 [5 ac.], BLC-18 [10 ac.], BC-1 [10 ac.], DC-1 [1 ac.], GC-7 [5 ac.], YJ-11 [5 ac.], YJ-14 [1 ac.] LC-8a [6 ac.], LC-8b [6 ac.], F/LC-1 [6 ac.], OU-4 [1 ac.], WV-5 [1 ac.], YJ-17 [1 ac.], BLC-14 [42 ac.] TOTAL 120 ac. | K.C. Bordwell (+ 2 Range Techs) | 9/30/2001 | $42,550 |
| Project coordination All range improvement projects | K.C. Bordwell | 9/30/2001 | $30,000 |
| TOTAL -ALL TASKS FY 2001 |  |  | $94,765 |
| FY 2002 |  |  |  |
| Project layout - NONE |  |  |  |
| Archeological - NONE |  |  |  |
| Sensitive Plant survey - NONE |  |  |  |
| Project implementation Priority 1 – FY 2002 Implementation Projects BM-3 [20 ac.], BM-13/DC-14 [6 ac.], BM-14/DC-15 [6 ac.], BM-14a [2 ac.], BR-13 [12 ac.], BLC-9 [6 ac.], BLC-10 [1 ac.], BLC-18 [10 ac.], BLC-19 [3 ac.], CC-3 [12 ac.], MB-6a [5 ac.], WV-4 [2 ac.] and WV-7 [12 ac.] TOTAL 97 ac. | K.C. Bordwell (+ 2 Range Techs) | 9/30/2002 | $35,890 |

| Action | Responsibility | Completion Date | Cost |
| --- | --- | --- | --- |
| Project implementation Priority 2 – FY 2002-2004 Implementation Projects | K.C. Bordwell (+ 2 Range Techs) | 9/30/2002 | $12,420 |
| Projects coordination All range improvement projects | K.C. Bordwell | 9/30/2002 | $30,000 |
| TOTAL -ALL TASKS FY 2002 |  |  | $ 78,310 |
| FY 2003 |  |  |  |
| Project layout - NONE |  |  |  |
| Archeological - NONE |  |  |  |
| Sensitive Plant survey - NONE |  |  |  |
| Project implementation Priority 1 – FY 2003 Implementation Projects BLC-18 [10 ac.] | K.C. Bordwell (+ 2 Range Techs) | 9/30/2003 | $500 |
| Project implementation Priority 2 – FY 2002-2004 Implementation Project | K.C. Bordwell (+ 2 Range Techs) | 9/30/2003 | $44,500 |
| Projects coordination All range improvement projects | K.C. Bordwell | 9/30/2003 | $30,000 |
| TOTAL -ALL TASKS FY 2003 |  |  | $75,000 |
| FY 2004 |  |  |  |
| Project layout - NONE |  |  |  |
| Archeological - NONE |  |  |  |
| Sensitive Plant survey - NONE |  |  |  |
| Project implementation Priority 1 – FY 2004 Implementation Projects BLC-18 [10 ac.] | K.C. Bordwell (+ 2 Range Techs) | 9/30/2004 | $500 |
| Project implementation Priority 2 – FY 2002-2004 Implementation Project | K.C. Bordwell (+ 2 Range Techs) | 9/30/2004 | $44,500 |
| Projects coordination All range improvement projects | K.C. Bordwell | 9/30/2004 | $30,000 |
| TOTAL -ALL TASKS FY 2004 |  |  | $75,000 |
| TOTAL – ALL TASKS ALL YEARS |  |  | $342,660 |
| 5. Monitor the results: (Outline plans to monitor to see if desired results are attained.) Included above in implementation. |  |  |  |

PRIMARY PURPOSE_______________                 FUND CODE___________

|  | MODOC NATIONAL FOREST |  |
| --- | --- | --- |
|  | PROJECT PROPOSAL FORM |  |

PROJECT  NAME:Warner Mountain Rangeland Project-Aspen Management

| RECOMMENDED BY (District Ranger): |  | STAFF AREA: | Wildlife |
| --- | --- | --- | --- |
| 1. Explain the situation: (Rationale for proposing the project be included in forest program. Is there a resource need, special emphasis area, legal requirement, part of basic operations, pressing customer needs, partnership available, increment of a larger part of work, etc.) The Environmental Analysis for the Warner Mountain Rangeland Project has proposed management in aspen stands identified on the Warner Mountain Ranger District. |  |  |  |
| 2. Specify the results: (Identify what is provided and activity units. For example, project will increase willow flycatcher, improve water quality, increase recreationist experience, add to tourism base of local communities. Show results in terms of enancement to the land and resulting benefits to people.) The proposed project will change age class and species structure in approximately 1,435 acres of aspen stands as follows: South Deep Creek (40 ac.) includes CC-9; Parsnip Timber Sale (190 ac.) portion of BR-9; South Aspen Timber Sale (430 ac.) inclues portion of BR-9, GC-5, GC-6 & HM-7; North Aspen Timber Sale (725 ac.); includes BM-7, BMR-2, DC-10, MB-5, and F-1a; and Cedar Canyon Timber Sale (50 ac.) includes CC-7. |  |  |  |
| 3. Identify necessary resources: (What needs to be assembled to complete the proposed work.) Project layout - Identification of unit boundaries and required transportation or other service areas needed. Archeological survey - Survey, document and recommend management actions. Sensitive Plant survey Construct fence where proposed Designation and measurement of conifer trees to be removed in timber sale . Prepare Timber Sale Contract, advertise and award sale. Administer Timber Sale Contract. Evaluate need for underburning Control line construction - Force account or other sources. Pre-treatment of fuels - felling unmerchantable conifers to decrease competition and to increase continuity of fuel bed Prepare burn plans - Office preparation Pre-burn vegetation monitoring - Documentation of existing vegetative community. Burn contract preparation Award burn contract Administer burn contract - includes monitoring of burn implementation Post-burn vegetation monitoring - Documentation of post-burn vegetative community |  |  |  |

| Action | Responsibility | Completion Date | Cost |
| --- | --- | --- | --- |
| FY 2000 |  |  |  |
| Project layout @ $5/ac South Deep Creek (40 ac.) South Aspen (430 ac.) North Aspen (725 ac.) Cedar Canyon (40 ac.) TOTAL ACRES = 1,235 | Mary Flores | 9/30/2000 | $6,175 |
| Archeological survey @ $10/ac South Deep Creek (40 ac.) | Gerry Gates | 9/30/2000 | $400 |
| Sensitive Plant survey @ $10/ac South Deep Creek (40 ac.) | Botanist | 9/30/2000 | $400 |
| Prepare TS Contract, advertise and award @ $2,000 EA Parsnip (190 ac.) | Paul Bailey | 9/30/2000 | $2,000 |
| TOTAL - ALL TASKS FY 2000 |  |  | $8,975 |
| FY 2001 |  |  |  |
| Archeological survey @ $10/ac South Aspen (430 ac.) North Aspen (725 ac.) Cedar Canyon (40 ac.) TOTAL ACRES = 1,195 | Gerry Gates | 9/30/2001 | $11,950 |
| Sensitive Plant survey @ $10/ac South Aspen (430 ac.) North Aspen (725 ac.) Cedar Canyon (40 ac.) TOTAL ACRES = 1,195 | Botanist | 9/30/2001 | $11,950 |
| Construct fence @ 2,500/mile South Deep Creek (1.5 mile | Mary Flores | 9/30/2001 | $3,750 |
| Administer TS Contract @ $37/ac. Parsnip (190 ac.) | Paul Bailey | 9/30/2001 | $7,030 |
| Evaluate need for burning @ $2/ac. South Deep (40 ac.) | Mary Flores | 11/1/2000 | $80 |
| Control lines @ $20/ac. South Deep Creek (40 ac.) | Randy Hall | 9/30/2001 | $800 |
| Pre-treat fuels for burning @ $60/ac South Deep Creek (40 ac.) | Mary Flores | 9/30/2001 | $2,400 |
| Pre-burn vegetation monitoring @ $5/ac. South Deep Creek (40 ac.) | Mary Flores | 9/30/2001 | $200 |
| Prepare burn plan @ $2,000 EA South Deep Creek (40 ac.) | Randy Hall | 9/30/2001 | $2,000 |
| TOTAL - ALL TASKS FY 2001 |  |  | $40,160 |
| FY 2002 |  |  |  |
| Evaluate need for burning @ $2/ac. Parsnip (190 ac.) | Mary Flores | 11/1/2001 | $380 |

| Action | Responsibility | Completion Date | Cost |
| --- | --- | --- | --- |
| Control lines @ $20/ac. Parsnip (190 ac.) | Randy Hall | 9/30/2002 | $3800 |
| Pre-treat fuels for burning @ $75/ac Parsnip (190 ac.) | Mary Flores | 9/30/2002 | $14,250 |
| Pre-burn vegetation monitoring @ $5/ac. Parsnip (190 ac.) | Mary Flores | 9/30/2002 | $950 |
| Prepare burn plan @ $2,000 EA Parsnip (190 ac.) | Randy Hall | 9/30/2002 | $2,000 |
| Burn contract @ $2,000 EA South Deep Creek (40 ac.) | Randy Hall | 1/1/2002 | $2,000 |
| Award burn contract @ $100/ac. South Deep Creek (40 ac.) | Randy Hall | 6/1/2002 | $4,000 |
| Administer burn contract @ $2,000 EA South Deep Creek (40 ac.) | Randy Hall | 12/30/2002 | $2,000 |
| Designation and measurement @ $50/ac South Aspen (430 ac.) North Aspen (725 ac.) Cedar Canyon (40 ac.) TOTAL ACRES = 1,195 | Paul Bailey | 9/30/2002 | $59,750 |
| TOTAL - ALL TASKS FY 2002 |  |  | $89,130 |
| FY 2003 |  |  |  |
| Prepare TS Contract, advertise and award @ $2,000 EA South Aspen (430 ac.) | Paul Bailey | 12/31/2002 | $2,000 |
| Prepare TS Contract, advertise and award @ $2,000 EA North Aspen (725 ac.) | Paul Bailey | 4/31/2003 | $2,000 |
| Prepare TS Contract, advertise and award @ $2,000 EA Cedar Canyon (40 ac.) | Paul Bailey | 5/31/2003 | $2,000 |
| Administer TS Contract @ $37/ac. South Aspen (430 ac.) North Aspen (725 ac.) Cedar Canyon (40 ac.) TOTAL ACRES = 1,195 | Paul Bailey | 11/1/2003 | $44,215 |
| Burn contract @ $2,000 EA Parsnip (190 ac.) | Randy Hall | 1/1/2003 | $2,000 |
| Award burn contract @ $100/ac. Parsnip (190 ac.) | Randy Hall | 6/1/2003 | $19,000 |
| Administer burn contract @ $2,000 EA Parsnip (190 ac.) | Randy Hall | 12/30/2003 | $2,000 |
| Post-burn vegetation monitoring @ $5/ac. South Deep Creek (40 ac.) | Mary Flores | 9/30/2003 | $200 |
| TOTAL - ALL TASKS FY 2003 |  |  | $73,415 |

| Action | Responsibility | Completion Date | Cost |
| --- | --- | --- | --- |
| FY 2004 |  |  |  |
| Evaluate need for burning @ $2/ac. South Aspen (430 ac.) North Aspen (725 ac.) Cedar Canyon (40 ac.) TOTAL ACRES = 1,195 | Mary Flores | 11/1/2003 | $2,390 |
| Control lines @ $20/ac. South Aspen (430 ac.) North Aspen (725 ac.) Cedar Canyon (40 ac.) TOTAL ACRES = 1,195 | Randy Hall | 9/30/2004 | $23,900 |
| Pre-treat fuels for burning @ $60/ac. South Aspen (430 ac.) North Aspen (725 ac.) Cedar Canyon (40 ac.) TOTAL ACRES = 1,195 | Mary Flores | 9/30/2004 | $71,700 |
| Pre-burn vegetation monitoring @ $5/ac. South Aspen (430 ac.) North Aspen (725 ac.) Cedar Canyon (40 ac.) TOTAL ACRES = 1,195 | Mary Flores | 9/30/2004 | $5,975 |
| Prepare burn plan @ $2,000 EA South Aspen (430 ac.) North Aspen (725 ac.) Cedar Canyon (40 ac.) TOTAL ACRES = 1,195 | Randy Hall | 9/30/2001 | $6,000 |
| Post-burn vegetation monitoring @ $5/ac. Parsnip (190 ac.) | Mary Flores | 9/30/2004 | $950 |
| TOTAL - ALL TASKS FY 2004 |  |  | $110,915 |
| TOTAL - ALL TASKS FY 2000 - 2004 |  |  | $322,595 |
| FY 2005 |  |  |  |
| Burn contract @ $2,000 EA South Aspen (430 ac.) North Aspen (725 ac.) Cedar Canyon (40 ac.) TOTAL ACRES = 1,195 | Randy Hall | 1/1/2005 | $6,000 |
| Award burn contract @ $100/ac. South Aspen (430 ac.) North Aspen (725 ac.) Cedar Canyon (40 ac.) TOTAL ACRES = 1,195 | Randy Hall | 6/1/2005 | $119,500 |
| Administer burn contract @ $2,000 EA South Aspen (430 ac.) North Aspen (725 ac.) Cedar Canyon (40 ac.) TOTAL ACRES = 1,195 | Randy Hall | 12/30/2005 | $6,000 |

| Action | Responsibility | Completion Date | Cost |
| --- | --- | --- | --- |
| TOTAL - ALL TASKS FY 2005 |  |  | $131,500 |
| FY 2006 |  |  |  |
| Post-burn vegetation monitoring @ $5/ac. South Aspen (430 ac.) North Aspen (725 ac.) Cedar Canyon (40 ac.) TOTAL ACRES = 1,195 | Mary Flores | 9/30/2004 | $5,975 |
| TOTAL - ALL TASKS FY 2006 |  |  | $5,975 |
| TOTAL - ALL TASKS ALL YEARS |  |  | $460,070 |
| 5. Monitor the results: (Outline plans to monitor to see id desired results are attained.) Included above. |  |  |  |

#### PRIMARY PURPOSE_______________                         FUND CODE___________

|  | MODOC NATIONAL FOREST |  |
| --- | --- | --- |
|  | PROJECT PROPOSAL FORM |  |

PROJECT  NAME:Warner Mountain Rangeland Project-Burning

| RECOMMENDED BY (District Ranger): |  | STAFF AREA: | Wildlife |  |
| --- | --- | --- | --- | --- |
| 1. Explain the situation: (Rationale for proposing the project be included in forest program. Is there a resource need, special emphasis area, legal requirement, part of basic operations, pressing customer needs, partnership available, increment of a larger part of work, etc.) The Environmental Analysis for the Warner Mountain Rangeland Project has proposed burning projects in vegetative stands identified on the Warner Mountain Ranger District. |  |  |  |  |
| 2. Specify the results: (Identify what is provided and activity units. For example, project will increase willow flycatcher, improve water quality, increase recreationist experience, add to tourism base of local communities. Show results in terms of enancement to the land and resulting benefits to people.) The proposed project will reduce natural fuels and change age class and species structure on approximately 7,639 acres, in the following projects: Buck Mtn.(152 ac.); 12-mile (81 ac.); Bald Mtn.(289 ac.); Mt. Bidwell (246 ac.); Obsidian Mdw (310 ac.); Yankee Jim (227); Plum Valley (219 ac.); N. Parker (108 ac.); Thoms Creek (85 ac.); Corporation (188 ac.); Fandango ( 3,656 ac.); West Valley (1,638 ac.); and Venning Creek (440 ac.). |  |  |  |  |
| 3. Identify necessary resources: (What needs to be assembled to complete the proposed work.) Project layout - Identification of unit boundaries and required transportation or other service areas needed. Archeological survey - Survey, document and recommend management actions. Sensitive Plant survey. Control line construction - Force account or other sources. Pre-treatment of fuels - felling junipers to increase continuity of fuel bed. Prepare burn plans - Office preparation. Pre-burn vegetation monitoring - Documentation of existing vegetative community. Burn contract preparation Award burn contract Administer burn contract - includes monitoring of burn implementation Post-burn vegetation monitoring - Documentation of post-burn vegetative community |  |  |  |  |

| Action |  | Responsibility |  | Completion Date |  | Cost |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FY 2000 |  |  |  |  |  |  |  |  |
| Project layout @ $5/ac. Buck Mtn. (152 ac.) 12-mile (81 ac.) Bald Mtn. (289 ac.) Mt. Bidwell (246 ac.) Obsidian Mdw. II (310 ac.) TOTAL ACRES = 1078 |  | Randy Hall |  | 9/30/2000 |  | $5,390 |  |  |
| Archeological survey - NONE |  |  |  |  |  |  |  |  |
| Sensitive Plant survey @ $5/ac. Buck Mtn. (152 ac.) 12-mile (81 ac.) TOTAL ACRES = 233 |  | Botanist |  | 9/30/2000 |  | $1,165 |  |  |
| Control line construction @ $20/ac. Buck Mtn. (152 ac.) 12-mile (81 ac.) TOTAL ACRES = 233 |  | Randy Hall |  | 9/30/2000 |  | $4,660 |  |  |
| Pre-treat fuels - NONE |  |  |  |  |  |  |  |  |
| Prepare Burn Plans @ $2,000 EA Buck Mtn. (152 ac.) 12-mile (81 ac.) TOTAL ACRES = 233 |  | Randy Hall |  | 9/30/2000 |  | $4,000 |  |  |
|  | Pre-burn vegetation monitoring@$5/ac. Buck Mtn. (152 ac.) 12-mile (81 ac.) TOTAL ACRES = 233 |  | Mary Flores |  | 9/30/2000 |  | $1,165 |  |
|  | TOTAL -ALL TASKS FY 2000 |  |  |  |  |  | $16,380 |  |
|  | FY 2001 |  |  |  |  |  |  |  |
|  | Project layout @ $5/ac. Yankee Jim (227 ac.) Plum Valley (219 ac.) N. Parker (108 ac.) Thoms Creek (85 ac.) TOTAL ACRES = 639 |  | Randy Hall |  | 5/31/2001 |  | $3,195 |  |
|  | Project layout @ $5/ac. Corporation (188 ac.) Fandango (3,656 ac.) West Valley (1,638 ac.) Venning Cr. (440 ac.) TOTAL ACRES = 5,922 |  | Randy Hall |  | 7/31/2001 |  | $29,610 |  |
|  | Archeological survey @ $10/ac. Bald Mtn. (289ac.) Mt. Bidwell (246 ac.) Obsidian Mdw. II (310 ac.) Yankee Jim (227 ac.) Plum Valley (219 ac.) TOTAL ACRES = 1,291 ac. |  | Gerry Gates |  | 7/31/2001 |  | $12,910 |  |

| Action | Responsibility | Completion Date | Cost |
| --- | --- | --- | --- |
| Archeological survey @ $10/ac. N. Parker (108 ac.) Thoms Creek (85 ac.) Corporation (188 ac.) Fandango (3,656 ac.) West Valley (1,638 ac.) Venning Cr. (440 ac.) TOTAL ACRES = 6,115 | Gerry Gates | 9/30/2001 | $61,150 |
| Sensitive Plant survey @ $5/ac. Bald Mtn. (289 ac.) Mt. Bidwell (246 ac.) Obsidian Mdw. II (310 ac.) Yankee Jim (227 ac.) Plum Valley (219 ac.) TOTAL ACRES = 1,291 ac. | Botanist | 7/31/2001 | $6,455 |
| Sensitive Plant survey @ $5/ac. N. Parker (108 ac.) Thoms Creek (85 ac.) Corporation (188 ac.) Fandango (3,656 ac.) West Valley (1,638 ac.) Venning Cr. (440 ac.) TOTAL ACRES = 6,115 | Botanist | 9/30/2001 | $30,575 |
| Control line construction @ $20/ac. Bald Mtn. (289 ac.) Mt. Bidwell (246ac.) Obsidian Mdw. II (310 ac.) Yankee Jim (227 ac.) Plum Valley (219 ac.) TOTAL ACRES = 1,291 ac. | Randy Hall | 9/30/2001 | $25,820 |
| Pre-treat fuels - NONE |  |  |  |
| Prepare Burn Plans @ $2,000 EA Bald Mtn. (289 ac.) Mt. Bidwell (246ac.) Obsidian Mdw. II (310 ac.) Yankee Jim (227 ac.) Plum Valley (219 ac.) TOTAL ACRES = 1,291 ac. | Randy Hall | 9/30/2001 | $10,000 |
| Pre-burn vegetation monitoring@$5/ac. Bald Mtn. (289 ac.) Mt. Bidwell (246 ac.) Obsidian Mdw. II (310 ac.) Yankee Jim (227 ac.) Plum Valley (219 ac.) TOTAL ACRES = 1,291 ac. | Mary Flores | 9/30/2001 | $6,455 |
| Burn contract preparation@$2,000 EA Buck Mtn. (152 ac.) 12-mile (81 ac.) TOTAL ACRES = 233 | Randy Hall | 2/1/2001 | $4,000 |
| Award burn contract @$125/ac Buck Mtn. (152 ac.) 12-mile (81 ac.) TOTAL ACRES = 233 | Randy Hall | 6/1/2001 | $29,125 |

| Action | Responsibility | Completion Date | Cost |
| --- | --- | --- | --- |
| Administer burn contract @$2,000 EA Buck Mtn. (152 ac.) 12-mile (81 ac.) TOTAL ACRES = 233 | Randy Hall | 12/1/2001 | $4,000 |
| Post-burn vegetation monitoring - NONE |  |  |  |
| TOTAL -ALL TASKS FY 2001 |  |  | $223,295 |
| FY 2002 |  |  |  |
| Project layout - NONE |  |  |  |
| Archeological - NONE |  |  |  |
| Sensitive Plant survey - NONE |  |  |  |
| Control line construction @ $20/ac. N. Parker (108 ac.) Thoms Creek (85 ac.) Corporation (188 ac.) Fandango (3,656 ac.) TOTAL ACRES = 4,037 ac. | Randy Hall | 9/1/2002 | $80,740 |
| Pre-treat fuels - NONE |  |  |  |
| Prepare Burn Plans @ $2,000 EA N. Parker (108 ac.) Thoms Creek (85 ac.) Corporation (188 ac.) Fandango (3,656 ac.) TOTAL ACRES = 4,037 ac. | Randy Hall | 9/30/2002 | $8,000 |
| Pre-burn vegetation monitoring@$5/ac. N. Parker (108 ac.) Thoms Creek (85 ac.) Corporation (188 ac.) Fandango (3,656 ac.) TOTAL ACRES = 4,037 ac. | Mary Flores | 9/30/2002 | $20,185 |
| Burn contract preparation@$2,000 EA Bald Mtn. (289 ac.) Mt. Bidwell (246 ac.) Obsidian Mdw. II (310 ac.) Yankee Jim (227 ac.) Plum Valley (219 ac.) TOTAL ACRES = 1,291 ac. | Randy Hall | 2/1/2002 | $10,000 |
| Award burn contract @$125/ac Bald Mtn. (289 ac.) Mt. Bidwell (246 ac.) Obsidian Mdw. II (310 ac.) Yankee Jim (227 ac.) Plum Valley (219 ac.) TOTAL ACRES = 1,291 ac. | Randy Hall | 6/1/2002 | $161,375 |
| Administer burn contract @$2,000 EA Bald Mtn. (289 ac.) Mt. Bidwell (246 ac.) Obsidian Mdw. II (310 ac.) Yankee Jim (227 ac.) Plum Valley (219 ac.) TOTAL ACRES = 1,291 ac. | Randy Hall | 12/1/2002 | $10,000 |

| Action | Responsibility | Completion Date | Cost |
| --- | --- | --- | --- |
| Post-burn vegetation monitoring @ $5/ac. Buck Mtn. (152 ac.) 12-mile (81 ac.) TOTAL ACRES = 233 | Mary Flores | 9/30/2002 | $1,165 |
| TOTAL -ALL TASKS FY 2002 |  |  | $291,465 |
| FY 2003 |  |  |  |
| Project layout - NONE |  |  |  |
| Archeological - NONE |  |  |  |
| Sensitive Plant survey - NONE |  |  |  |
| Control line construction @ $20/ac. West Valley (1,638 ac.) Venning Cr. (440 ac.) TOTAL ACRES = 2,078 ac. | Randy Hall | 9/1/2003 | $41,560 |
| Pre-treat fuels @ $100/ac. West Valley (1,638 ac.) | Randy Hall | 9/30/2003 | $163,800 |
| Prepare Burn Plans @ $2,000 EA West Valley (1,638 ac.) Venning Cr. (440 ac.) TOTAL ACRES = 2,078 ac. | Randy Hall | 9/30/2003 | $4,000 |
| Pre-burn vegetation monitoring@$5/ac. West Valley (1,638 ac.) Venning Cr. (440 ac.) TOTAL ACRES = 2,078 ac. | Mary Flores | 9/30/2003 | $10,390 |
| Burn contract preparation@$2,000 EA N. Parker (108 ac.) Thoms Creek (85 ac.) Corporation (188 ac.) Fandango (3,656 ac.) TOTAL ACRES = 4,037 ac. | Randy Hall | 2/1/2003 | $8,000 |
| Award burn contract @$125/ac N. Parker (108 ac.) Thoms Creek (85 ac.) Corporation (188 ac.) TOTAL ACRES = 381ac. | Randy Hall | 6/1/2003 | $47,625 |
| Award burn contract @$75/ac Fandango (3,656 ac.) | Randy Hall | 6/1/2003 | $274,200 |
| Administer burn contract @$2,000 EA N. Parker (100 ac.) Thoms Creek (100 ac.) Corporation (20 ac.) Fandango (2,000 ac.) TOTAL ACRES = 2,220 ac. | Randy Hall | 12/1/2003 | $8,000 |
| Post-burn vegetation monitoring @ $5/ac. Bald Mtn. (289 ac.) Mt. Bidwell (246 ac.) Obsidian Mdw. II (310 ac.) Yankee Jim (227 ac.) Plum Valley (219 ac.) TOTAL ACRES = 1,291 ac. | Mary Flores | 9/30/2003 | $6,455 |

| Action | Responsibility | Completion Date | Cost |
| --- | --- | --- | --- |
| TOTAL -ALL TASKS FY 2003 |  |  | $564,030 |
| FY 2004 |  |  |  |
| Project layout - NONE |  |  |  |
| Archeological - NONE |  |  |  |
| Sensitive Plant survey - NONE |  |  |  |
| Control line - NONE |  |  |  |
| Pre-treat fuels - NONE |  |  |  |
| Prepare Burn Plans - NONE |  |  |  |
| Pre-burn vegetation monitoring - NONE |  |  |  |
| Burn contract preparation@$2,000 EA West Valley (1,638ac.) Venning Cr. (440 ac.) TOTAL ACRES = 2,078 ac. | Randy Hall | 2/1/2004 | $4,000 |
| Award burn contract @$125/ac Venning Cr. (440 ac.) | Randy Hall | 6/1/2004 | $55,000 |
| Award burn contract @$75/ac West Valley (1,638 ac.) | Randy Hall | 6/1/2004 | $122,850 |
| Administer burn contract @$2,000 EA West Valley (1,638 ac.) Venning Cr. (440 ac.) TOTAL ACRES = 2,078 ac. | Randy Hall | 12/1/2004 | $4,000 |
| Post-burn vegetation monitoring @ $5/ac. N. Parker (108 ac.) Thoms Creek (85 ac.) Corporation (188 ac.) Fandango (3,656 ac.) TOTAL ACRES = 4,037 ac. | Mary Flores | 9/30/2004 | $20,185 |
| TOTAL -ALL TASKS FY 2004 |  |  | $206,035 |
| FY 2005 |  |  |  |
| Post-burn vegetation monitoring @ $5/ac. West Valley (1,638 ac.) Venning Cr. (440 ac.) TOTAL ACRES = 2,078 ac. | Mary Flores | 9/30/2005 | $10,390 |
| TOTAL -ALL TASKS FY 2005 |  |  | $10,390 |
| TOTAL – ALL TASKS ALL YEARS |  |  | $1,311,595 |
| 5. Monitor the results: (Outline plans to monitor to see if desired results are attained.) Included above. |  |  |  |

# PRIMARY PURPOSE_______________      FUNDCODE___________

|  | MODOC NATIONAL FOREST |  |
| --- | --- | --- |
|  | PROJECT PROPOSAL FORM |  |

PROJECT  NAME:Warner Mountain Rangeland Project-Appropriate Suppression strategies

| RECOMMENDED BY (District Ranger): |  |  | STAFF AREA: | Fire and Fuels |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Explain the situation: (Rationale for proposing the project be included in forest program. Is there a resource need, special emphasis area, legal requirement, part of basic operations, pressing customer needs, partnership available, increment of a larger part of work, etc.) The Environmental Analysis for the Warner Mountain Rangeland Project has proposed appropriate suppression strategy areas on the Warner Mountain Ranger District. |  |  |  |  |  |  |
| 2. Specify the results: (Identify what is provided and activity units. For example, project will increase willow flycatcher, improve water quality, increase recreationist experience, add to tourism base of local communities. Show results in terms of enancement to the land and resulting benefits to people.) The proposed appropriate suppression strategy area will improve fire suppression efficiency and move vegetative communities towards Desired Conditions on approximately 10,758 acres, in the following projects: 12-mile Apprpriate Suppression Strategy Area (MB-7) [1,892 ac.]; and West Valley Appropriate Suppression Strategy Area (OU-5) [8,866 ac.] |  |  |  |  |  |  |
| 3. Identify necessary resources: (What needs to be assembled to complete the proposed work.) Archeological survey – Survey, document and recommend management actions; Sensitive Plant survey; Secure Areements; and Suppression Management Plan |  |  |  |  |  |  |
| Action |  | Responsibility |  |  | Completion Date | Cost |
| FY 2001 |  |  |  |  |  |  |
| Archeological survey of both areas @ $5/ac. x 10,758 ac. |  | Gerry Gates |  |  | 9/30/2001 | $54,000 |
| FY 2002 |  |  |  |  |  |  |
| Sensitive Plant survey |  | Botanist |  |  | 9/30/2002 | $4,000 |
| Secure Agreements |  | Randy Hall |  |  | 9/30/2002 | $7,000 |
| TOTAL - ALL TASKS FY 2002 |  |  |  |  |  | $11,000 |

| Action | Responsibility | Completion Date | Cost |
| --- | --- | --- | --- |
| FY 2003 |  |  |  |
| Prepare Suppression Management Plans (2) | Randy Hall | 9/30/2003 | $10,000 |
| TOTAL – ALL TASKS ALL YEARS |  |  | $75,000 |
| 5. Monitor the results: (Outline plans to monitor to see if desired results are attained.) Included above. |  |  |  |

Appendix B – Communications Plan

# Primary Purpose: IDP3

|  | MODOC NATIONAL FOREST |  |
| --- | --- | --- |
|  | Project Proposal |  |

PROJECT  NAME: Upper Pit River Watershed Restoration Project

Communication and Conservation Education Plan

| Recommended By: (District Ranger): | /s/ Bernie Weisgerber /s/ Edith Asrow | Staff Area: | Public Affairs |
| --- | --- | --- | --- |
| 1. Explain the situation: (Rationale for proposing the project be included in forest program. Is there a resource need, special emphasis area, legal requirement, part of basic operations, pressing customer needs, partnership available, increment of a larger part of work, etc.) The Modoc National Forest has a long history of public involvement with community, individuals and groups in management activities on the Forest. The Modoc/Washoe Experimental Stewardship Program, Pit River Watershed Alliance, Modoc County Land Use Committee, Shasta-Cascade Wonderland Association, are examples of collaborative groups. Throughout NEPA analysis, public involvement and collaboration emphasis has been an open process. Field trips, education tours, briefings, and numerous meetings with citizens have occurred, proposals have been developed that are generally supported by a variety of community and other stakeholders. Our customers expect us to continue the open communication and collaboration process, share information, expand our membership to groups mutually interested in the restoration of the Pit River Watershed, and reach out to non-traditional adiences. |  |  |  |
| 2. Specify the results: (Identify what is provided and activity units. For example, project will increase willow flycatcher, improve water quality, increase recreationist experience, add to tourism base of local communities. Show results in terms of enancement to the land and resulting benefits to people.) This project consists of: - Press releases that will keep local new media apprised on various activities taking place - Briefing papers disseminated to elected officials (federal, state, local), Forest Service employees and other stakeholders that gives background information - Newsletter that gives status report and celebrates success of projects and partners and used as tool to measure accountability - Multi-media presentations as opportunities are available to partner with others to increase public awareness - Continue government-to-government consultation with Tribes - Partnership with Natural Resource Conservation Education organization to develop a watershed curriculum for local students. Use the wetlands in the Hackamore area and Warner Mountain watershed as learning labs. Apply curriculum module to RAP Camp (Resources and People outdoor ecudation program) - Engage public in NEPA process through implementation - Participate as a member of larger watershed interest group coordinated by the North-Cal-Neva RC&D (Resource, Conservation and Development) - Planned celebration events. Benefits to the people include: - People involved will learn from one another and have a better understanding about the complexity of our natural resources. Benefits to the land include: - Because children and adults will have a better understanding about our complex encironment, they will better understand their role in taking care of it. |  |  |  |

| 3. Identify necessary resources: (What needs to be assembled to complete the proposed work.) - News Releases - Briefing Papers - Meeting Rooms - Electronic Projector - Photographs and Maps - Watershed Curriculum module - Teachers - Newsletter - Tribal Liaison - Public Affairs Department - ID Team Members as resource for publications - Community Partners - Materials for Celebrations |  |  |  |
| --- | --- | --- | --- |
| 4. Describe required actions: (Provide a chronological description of actions, time frames, personnel responsible to complete the action, and costs.) |  |  |  |
| Action | Responsibility | Completion Date | Cost |
| NEPA public involvement and collaboration Meetings, Document Publications, Legal Notices | District Rangers | Hackamore: January 2000, Warner Mtn: July 2000 | $800 |
| Continue government-to-government consultation with Ft. Bidwell Indian Community, Klamth and Pit River Tribes | District Rangers and Tribal Liason | On-going | $1200 |
| Continue collaboration with partners: permittees, news media, schools, and others mention elsewhere in this document | District Rangers and Public Affairs | On-going | $1200 |
| Develop a Briefing Paper | Public Affairs, District Rangers, and Watershed Coordinator | February 2000 | $400 |
| Announce NEPA decisions through news media | Public Affairs and District Rangers | Item #1 | $100 |
| Develop and Distribute a Project Newsletter | District Rangers, Watershed Coordinator, District Rangers | April 2000 September 2000 February 2001 July 2002 (every 5 months) | $1200 |
| Develop Natural Resource Conservation Education Module with Teachers | District Ranger – warner Mountain | September 2001 | $5000 |
| Continue education tours through project imprementation | Partners, Forest Resrouce specialists | Summer 2000 Summer 2001 Summer (life of the project) |  |
| Plan events to celebrate completion and or implementation of individual projects | Partners, District Rangers, Forest Resource specialist, Public Affairs | On-going |  |
| 5. Monitor the results: (Outline plans to monitor to see id desired results are attained.) Count number of people participating in the project Count number of partners participating in the project Evaluate success of activities through customer service responses received Evaulate success by number of unsolicited feed back (counted) |  |  |  |