Request for Proposal (RFP) Number DHHS-ORDC-VB-06-07

Date:  July 24, 2006

Prospective Offeror

Re:  Adapting Manufacturing Facilities for Production of Pandemic Influenza Vaccines

Dear Prospective Offeror:

This RFP represents HHS’s commitment to support the immediate expansion of the domestic capacity to manufacture pandemic influenza vaccines.  Adaptation of existing manufacturing facilities represents one of HHS’s multiple strategies to close the gap between current pandemic influenza vaccine supply and the stated HHS goal of 600 million doses of pandemic vaccine within six (6) months of the declaration of an influenza pandemic.

This RFP is posted on the General Services Administration’s (GSA’s) Federal Business Opportunities Internet website known as FedBizOpps Electronic Posting System (www.FedBizOpps.gov).  Any amendments to this RFP shall also be posted on the same internet website.  No other notice shall be given to prospective Offerors and it is incumbent on Offerors to make periodic inquiries.

The RFP includes Mandatory Criteria for Eligibility, which is located in section M.1.

Prospective Offerors are advised that DHHS is operating under stringent security requirements applied to all incoming mail and packages. This includes all proposals submitted under HHS solicitations by regular mail, express mail delivery, or hand-delivered directly by an offeror or by a courier service.  Please note that personal identification of couriers or Offerors is required for delivery of proposals.

In accordance with the attached RFP, Offerors are required to submit their proposals to the Contracting Officer no later than August 23, 2006, at 3:00 PM local.

Any questions concerning the RFP should be submitted in writing to Mekeba Barrett, Contract Specialist, no later than August 3, 2006 at the address specified below or you may also email your questions to mekeba.barrett@hhs.gov.  Questions should be marked “Offerors Questions, RFP-DHHS-ORDC-VB-06-07”.  Any questions and answers will be made available via the FedBizOpps website.

Letters of Intent to submit a proposal must be received by August 7, 2006.  Section J of the RFP contains a copy of the Proposal Intent Response Sheet.  Please note that your expression of intent is not binding but will greatly assist us in planning for the proposal evaluation process.

Please direct all questions to Mekeba Barrett on (202) 205-3978.

Department of Health and Human Services

By:  _________________________

David K. Beck

Chief Contracting Officer

HHS/OS/OPHEP/OPHEMC

330 Independence Avenue S.W., Room G640

Washington, DC 20201

| PAGES SOLICITATION, OFFER AND AWARD AWARD |  |  |  |  |  |  |  |  |  | 1. THIS CONTRACT IS A RATED ORDER UNDER DPAS (15 CFR 700) |  |  |  |  |  |  |  |  |  |  |  |  | RATING |  |  |  |  | PAGE OF 1 61 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2. CONTRACT NO. |  |  |  |  | 3. SOLICITATION NO. DHHS-ORDC-VB-06-07 |  |  |  |  |  |  |  |  |  | 4. TYPE OF SOLICITATION SEALED BID (IFB) X NEGOTIATED (RFP) |  |  |  |  |  | 5. DATE ISSUED 07/24/2006 |  |  |  | 6. REQUISITION/PURCHASE NO. |  |  |  |  |  |  |
| 7. ISSUED BY |  |  |  |  |  | CODE |  |  |  |  |  |  |  |  |  | 8. ADDRESS OFFER TO (If other than Item 7) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Department of Health and Human Services OS/OPHEP/OPHEMC 330 Independence Ave. SW, Room G640 Washington, DC 20201 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NOTE: In sealed bid solicitations “offer” and “offeror” mean “bid” and “bidder.” |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SOLICITATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9. Sealed offers in original and 5 copies for furnishing the supplies or services in the Schedule will be received at the place specified in Item 8 , or if (Date) (Hour) handcarried, in the depository located in See Page 30 for delivery instructions until 3:00pm local time 08/23/2006 CAUTION -- LATE Submissions, Modifications, and Withdrawals: See Section L, Provision No. 52.214-7 or 52.215-1. All offers are subject to all terms and conditions contained in this solicitation. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10. FOR INFORMATION CALL: |  |  |  | A. NAME Mekeba S. Barrett |  |  |  |  |  |  |  |  |  | - TELEPHONE (NO COLLECT CALLS) AREA CODE NUMBER: EXT: (202) 205-3978 |  |  |  |  |  |  |  |  |  | - E-MAIL ADDRESS mekeba.barrett@hhs.gov |  |  |  |  |  |  |  |
| 11. TABLE OF CONTENTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SEC. PAGE(S) SEC. PAGE(S) (x) |  | DESCRIPTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  | (x) |  |  | DESCRIPTION |  |  |  |  |  |  |  |  |  |  |  |
| PART I – THE SCHEDULE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | PART II – CONTRACT CLAUSES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| X | A | SOLICITATION/CONTRACT FORM |  |  |  |  |  |  |  |  |  |  | 1 |  |  |  | X | I |  | CONTRACT CLAUSES |  |  |  |  |  |  |  |  |  |  | 21 |
| X | B | SUPPLIES OR SERVICES AND PRICES/COSTS |  |  |  |  |  |  |  |  |  |  | 3 |  |  |  | PART III - LIST OF DOCUMENTS, EXHIBITS AND OTHER ATTACH. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| X | C | DESCRIPTION/SPECS./WORK STATEMENT |  |  |  |  |  |  |  |  |  |  | 6 |  |  |  | X | J |  | LIST OF ATTACHMENTS |  |  |  |  |  |  |  |  |  |  | 28 |
| X | D | PACKAGING AND MARKING |  |  |  |  |  |  |  |  |  |  | 11 |  |  |  | PART IV – REPRESENTATIONS AND INSTRUCTIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| X K | E | INSPECTION AND ACCEPTANCE |  |  |  |  |  |  |  |  |  |  | 12 |  |  |  |  |  |  | REPRESENTATIONS, CERTIFICATIONS, AND |  |  |  |  |  |  |  |  |  |  |  |
| X | F | DELIVERIES OR PERFORMANCE |  |  |  |  |  |  |  |  |  |  | 13 |  |  |  | X | K |  | OTHER STATEMENTS OF OFFERORS |  |  |  |  |  |  |  |  |  |  | 47 |
| X | G | CONTRACT ADMINISTRATION DATA |  |  |  |  |  |  |  |  |  |  | 15 |  |  |  | X | L |  | INSTRS., CONDS., AND NOTICES TO OFFERORS |  |  |  |  |  |  |  |  |  |  | 48 |
| X | H | SPECIAL CONTRACT REQUIREMENTS |  |  |  |  |  |  |  |  |  |  | 17 |  |  |  | X | M |  | EVALUATION FACTORS FOR AWARD |  |  |  |  |  |  |  |  |  |  | 54 |
| OFFER (Must be fully completed by offeror) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NOTE: Item 12 does not apply if the solicitation includes the provisions at 52.214-16, Minimum Bid Acceptance Period. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CALENDAR DAYS 12. In compliance with the above, the undersigned agrees, if this offer is accepted within 180 calendar days (60 calendar days unless a different period is inserted by the offeror) from the date for receipt of offers specified above, to furnish any or all items upon which prices are offered at the price set opposite each item, delivered at the designated point(s), within the time specified in the schedule. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 14. ACKNOWLEDGMENT OF AMENDMENTS (The offeror acknowledges receipt of amend- ments to the SOLICITATION for offerors and related documents numbered and dated: 13. DISCOUNT FOR PROMPT PAYMENT (See Section I, Clause No. 52-232-8) |  |  |  |  |  |  |  |  | 10 CALENDAR DAYS % |  |  |  |  |  |  |  | 20 CALENDAR DAYS % |  |  |  |  | 30 CALENDAR DAYS % |  |  |  |  | % |  |  |  |  |
|  |  |  |  |  |  |  |  |  | AMENDMENT NO. |  |  |  |  |  |  |  |  | DATE |  |  |  | AMENDMENT NO. |  |  |  |  |  |  |  | DATE |  |
| 15A.NAME AND ADDRESS OF OFFEROR (Type or Print) |  |  | CODE |  |  |  |  |  |  |  | FACILITY |  |  |  |  |  |  |  | 16. NAME AND ADDRESS OF PERSON AUTHORIZED TO SIGN OFFER |  |  |  |  |  |  |  |  |  |  |  |  |
| 15B. TELEPHONE NO. AREA CODE NUMBER EXT. |  |  |  |  |  |  | 15C. CHECK IF REMITTANCE ADDRESS IS DIFFERENT FROM ABOVE - ENTER SUCH ADDRESS IN SCHEDULE. |  |  |  |  |  |  |  |  |  |  |  | 17. SIGNATURE |  |  |  |  |  |  |  |  |  |  | 18. OFFER DATE |  |
| AWARD (To be completed by Government) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 19. ACCEPTED AS TO ITEMS NUMBERED 20. AMOUNT 22. AUTHORITY FOR USING OTHER THAN FULL AND OPEN COMPETITION: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 21. ACCOUNTING AND APPROPRIATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10 U.S.C. 2304(c)( ) 41 U.S.C. 253(c)( ) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 23. SUBMIT INVOICES TO ADDRESS SHOWN IN (4 copies unless otherwise specified) |  |  |  |  |  |  |  |  |  |  |  |  | ITEM |  |  |
| 24. ADMINISTERED BY (If other than Item 7) |  |  |  |  |  |  |  | CODE |  |  |  |  |  |  |  | 25. PAYMENT WILL BE MADE BY |  |  |  |  |  |  |  |  |  | CODE |  |  |  |  |  |
| 26. NAME OF CONTRACTING OFFICER (Type or print) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 27. UNITED STATES OF AMERICA (Signature of Contracting Officer) |  |  |  |  |  |  |  |  |  |  |  |  | 28. AWARD DATE |  |  |
| IMPORTANT -- Award will be made on this form, or on Standard Form 26, or by other authorized official written notice. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

AUTHORIZED FOR LOCAL REPRODUCTION / PREVIOUS EDITION IS UNUSABLE               STANDARD FORM 33 (REV. 9-97) / Prescribed by GSA / FAR (48 CFR) 53.214(c)

U.S. Department of Health and Human Services

Office of Public Health Emergency Preparedness

Office of Public Health and Emergency Medical Countermeasures

RFP-DHHS-ORDC-VB-06-07

Adapting Manufacturing Facilities for Production of Pandemic Influenza Vaccines

| - OFFERORS ARE RESPONSIBLE FOR ROUTINELY CHECKING THE FOLLOWING WEBSITE FOR ANY SOLICITATION AMENDMENTS. NO ADDITIONAL NOTIFICATION OF ANY AMENDMENTS WILL BE PROVIDED BY THIS OFFICE. http://www.fedbizopps.gov/ |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - SECTION A – SOLICITATION/CONTRACT FORM – OMB No. 0990-0115 NOTE: The issuance of this solicitation does not commit the government to an award. |  |  |  |  |  |  |  |  |
| - Issue Date: See SF-33 | - Due Date: See SF-33 |  |  |  |  |  |  | - Small Bus. Set-Aside: [ ]Yes [x] No 8(a) Set-Aside: [ ]Yes [x] No NAICS: 325414 (See Part IV, Section L.) |
| - Proposal Delivery Information See SF-33 |  | - Number of Awards: [ ] Only 1 Award [x] Multiple Awards |  |  |  |  | - Technical Proposal Page Limits: See Section J and L |  |
| - Issued By: See SF-33 |  |  |  | - [X] OPHEMC reserves the right to make awards without discussion. |  |  |  |  |
|  |  |  |  | ## Options: ## [ ] No [X] Yes |  | - Period of Performance: 7 - 8 years beginning on/about October 31, 2006 |  |  |
| - Primary Point of Contact: Name: Mekeba Barrett Phone: 202-205-3978 Fax: 202-205-3915 E-Mail: mekeba.barrett@hhs.gov |  |  | - Secondary Point of Contact: Name: RoseMary Mann Phone: 202-205-3979 Fax: 202-205-3915 E-Mail: rosemary.mann@hhs.gov |  |  |  |  | - Collect Calls will not be accepted. Facsimile submissions are not acceptable. |
| - Reserved |  |  |  |  |  |  |  |  |
| 17. DELIVERY ADDRESS INFORMATION |  |  |  |  |  |  |  |  |
| 18. Hand Delivery or Overnight Service (not including USPS, DHL, FedEx, UPS) – Please allow 30 minutes for processing packages through security: Mekeba Barrett Contract Specialist (NOTE: See page 30) HHS/OPHEP/OPHEMC Cohen Building 330 Independence Ave, SW Room G640 Washington, DC 20201 |  |  |  |  | 19. Packaging of Proposals: See Section J for proposals packaging instructions |  |  |  |
| 21. The Official Point of Receipt for the purpose of determining timely delivery is the address provided in Block 18, above. The original paper copy with original signatures is the official copy for recording timely receipt. If the original paper copy of your proposal is not received by the Contracting Officer or Designee at the place and time specified, then it will be considered late and handled in accordance with HHSAR 352.215-70 entitled "Late Proposals and Revisions" located in this Solicitation. FACSIMILE SUBMISSION OF PROPOSALS IS NOT ACCEPTABLE. |  |  |  |  |  |  |  |  |

Updated thru FAC 2001-27 (01/01/2005)

SECTION B--SUPPLIES OR SERVICES AND PRICES/COSTS

B.1. BRIEF DESCRIPTION OF SUPPLIES OR SERVICES

This project from the Department of Health and Human Services (HHS) through the Office of Public Health Emergency Medical Countermeasures (OPHEMC) within the Office of Public Health Emergency Preparedness (OPHEP) will provide incremental funding for multi-year, cost-sharing contracts to manufacturers for adapting manufacturing facilities for production of pandemic influenza vaccines. The adaptation approach may include retrofitting, renovation, and/or expansion of existing pilot facilities for the manufacturing of clinical investigational lots and/or commercial scale manufacturing facilities that are currently used to produce clinical investigational lots and Food and Drug Administration (FDA) licensed biological products, respectively, to emergency facilities capable of egg-based or cell culture-based bulk production and/or fill finish manufacturing of pandemic influenza vaccines. The scope of activities for which the Offeror may request funds may include conceptual and detailed architectural and mechanical engineering design (A&ME), facility construction and commissioning, facility and manufacturing equipment, and validation of facility/process/systems as required for FDA licensure for manufacturing of influenza vaccines, and warm base operation. Facilities must meet FDA guidelines for vaccine facilities, United States Department of Agriculture (USDA) and Centers for Disease Control and Prevention (CDC) biosafety containment guidelines for Select Agent usage, World Health Organization (WHO) recommendations for production of influenza vaccines from reassortants derived from avian influenza viruses, and physical security measures as outlined for BioShield products. The objective of this project is immediate expansion of domestic influenza vaccine manufacturing capacity to accommodate national influenza pandemic vaccine needs.

Eligibility requirements for these contracts include the following: (1) The facility is located in the U.S.; (2) For proposed bulk and/or fill finish manufacturing, the facilities must be used currently to manufacture FDA licensed biological products; (3) Pilot facilities, as well as commercial scale facilities shall be in compliance with FDA, USDA and CDC regulatory and biosafety guidelines for pandemic influenza vaccine manufacturing, as applicable;  (4) Commitment to share at least 25% of the overall adaptation capital cost;  (5) Commitment to maintain the retrofitted manufacturing facility to support rapid stockpile production commensurate with U.S. pre-pandemic and pandemic influenza vaccine needs.

B.2.  HHSAR 352.232-74 Estimated Cost and Fixed Fee -- Incrementally Funded Contract (Apr 1984) [For Acquisition of Vaccines – Warm Base]

(a) It is estimated that the total cost to the Government for full performance of this contract will be $__________, of which the sum of $___________ represents the estimated reimbursable costs and $___________ represents the fixed-fee.

(b) Total funds currently available for payment and allotted to this contract are $___________, of which $______________ represents the estimated reimbursable costs and $_____________ represents the fixed-fee. For further provisions on funding, see the Limitation of Funds clause.

(c) It is estimated that the amount currently allotted will cover performance through (date)_______________.

(d) The Contracting Officer may allot additional funds to the contract without the concurrence of the Contractor.

### B3.  52.216-12 Cost-Sharing Contract—No Fee (Apr 1984)   [For Retrofitting Facility]

(a) The Government shall not pay to the Contractor a fee for performing this contract.

(b) After paying 80 percent of the Government’s share of the total estimated cost of performance shown in the Schedule, the Contracting Officer may withhold further payment of allowable cost until a reserve is set aside in an amount that the Contracting Officer considers necessary to protect the Government’s interest. This reserve shall not exceed one percent of the Government’s share of the total estimated cost shown in the Schedule or $100,000, whichever is less.

B.4 Cancellation Ceiling

(a) This clause does not apply when the contract is fully funded.

(b) The total funding in B.2 (b) includes an amount that covers the cancellation charge described in FAR 52.217-2, Cancellation Under Multi-year Contracts. The cancellation charge shall not exceed _______________ (insert dollar amount or express as a percentage of total funding under B.2 (b)).

B.5. CONTRACT LINE ITEM NUMBERS (CLINS)

A.  COST PLUS FIXED FEE (CPFF)

| ITEM | SUPPLIES / SERVICES | QTY/UNIT | EST. COST | FIXED FEE | TOTAL EST. CPFF |
| --- | --- | --- | --- | --- | --- |
| 0008 | Annual Warm Base Vaccine Production (milestone 6) | 1 lot per year |  |  |  |
| 0008A | 1st Annual Warm Base Vaccine Production | 1 Lot | $ | $ | $ |
| 0008B | 2nd Annual Warm Base Vaccine Production | 1 Lot | $ | $ | $ |
| 0008C | 3rd Annual Warm Base Vaccine Production– PILOT FACILITY ONLY | 1 Lot | $ | $ | $ |
| TOTAL Cost Plus Fixed Fee (Item 0008) |  |  | $ | $ | $ |

- COST SHARING – NO FEE

  - In the table below, the offeror shall list below the portion of total cost that will be charged to the Government and the portion of total cost that the offeror will cover.  The offeror share of cost must be at least 25% of the total cost for the items listed in B.5.B (Cost Sharing – No Fee).

| ITEM | SUPPLIES / SERVICES | QTY/UNIT | GOVERNMENT SHARE OF COST | OFFEROR SHARE OF COST | TOTAL COST |
| --- | --- | --- | --- | --- | --- |
| 0001 | Conceptual Facility A&ME Plan (milestone 1) | 1 Job | $ | $ | $ |
| 0002 | Detailed Facility A&ME Plan (milestone 2) | 1 Job | $ | $ | $ |
| 0003 | Facility Regulatory Approval Plan (milestone 3) | 1 Job | $ | $ | $ |
| 0004 | Facility Operation Plan (milestone 4) | 1 Job | $ | $ |  |
| 0005 | Contract-defined Milestones (milestone 5) | 1 Job | $ | $ |  |
| 0006 | Technical Progress Reports and Executive Summary (12 of each per year) | 1 Lot | $ | $ | $ |
| 0007 | Final Report | 1 Report | $ | $ | $ |
| 0009 | Final Security Plan | 1 Report | $ | $ | $ |
| TOTAL Cost (Items 0001 – 0007 and 0009) |  |  | $ | $ | $ |

- OPTIONAL CPFF CLINS

1.  PILOT FACILITY

2.  BULK AND/OR FILL/FINISH FACILITY

| ITEM | SUPPLIES / SERVICES | QTY/UNIT | EST. COST | FIXED FEE | TOTAL EST. CPFF |
| --- | --- | --- | --- | --- | --- |
| 0010 | Annual Warm Base Vaccine Production (milestone 6) | 1 lot per year |  |  |  |
| 0010A | 4th Annual Warm Base Vaccine Production | 1 Lot | $ | $ | $ |
| 0010B | 5th Annual Warm Base Vaccine Production | 1 Lot | $ | $ | $ |
| TOTAL Cost Plus Fixed Fee (Item 0010) |  |  | $ | $ | $ |

| ITEM | SUPPLIES / SERVICES | QTY/UNIT | EST. COST | FIXED FEE | TOTAL EST. CPFF |
| --- | --- | --- | --- | --- | --- |
| 0011 | Annual Warm Base Vaccine Production (milestone 6) | 1 lot per year |  |  |  |
| 0011A | 3rd Annual Warm Base Vaccine Production | 1 Lot | $ | $ | $ |
| 0011B | 4th Annual Warm Base Vaccine Production | 1 Lot | $ | $ | $ |
| 0011C | 5th Annual Warm Base Vaccine Production | 1 Lot | $ | $ | $ |
| TOTAL Cost Plus Fixed Fee (Item 0011) |  |  | $ | $ | $ |

SECTION C - DESCRIPTION/SPECIFICATIONS

C.1. BACKGROUND/STATEMENT OF WORK

Background

Introduction and Rationale

Preparedness for public health threats is a major goal of the U.S. Department of Health and Human Services (HHS). An influenza pandemic has a great potential to cause large numbers of deaths and illnesses over a short time period. A pandemic occurs when there is an antigenic shift in influenza A virus resulting in a new human influenza strain to which most or all of the world's population is susceptible. Three pandemics occurred during the 20th century, the most severe of which, in 1918, caused over 500,000 U.S. deaths and more than 20 million deaths worldwide. Within the scientific community, it is generally believed that the occurrence of another influenza pandemic is very likely. Recent outbreaks of human disease caused by avian H5, H9, and H7 influenza strains in Asia, Europe, and North America highlight the potential of new strains to be introduced into the population. Estimates for the next pandemic, extrapolating from those of the 20th century, range from about 100,000 to over 2 million deaths in the U.S. alone.

- Influenza vaccines are considered a primary means to decrease the mortality and morbidity associated with an influenza pandemic. However, current U.S. influenza vaccine production capacity falls far short of expected pandemic response needs. Vaccines produced outside of the United States likely will be used to protect the population in its country of origin and become unavailable to the U.S., despite preexisting contractual arrangements and national treaties. In addition, and of primary concern, is the lack of dedicated U.S. facilities for seed preparation and pilot production involving potentially hazardous agents which further hampers domestic influenza vaccine production capacity.

- Adaptation of existing manufacturing facilities represents one of HHS’s multiple strategies to close the gap between current pandemic influenza vaccine supply and the stated HHS goal of 600 million doses of pandemic vaccine within six (6) months of the declaration of an influenza pandemic. Previously issued solicitations on cell culture-based vaccines and antigen-sparing pandemic vaccines are considered part of the long-term strategy to overcome the capacity shortages. However, intermediate strategies are urgently needed to respond to the current threat of a potential influenza pandemic with the highly virulent avian H5N1 influenza virus. One of the intermediate strategies is to adapt existing manufacturing facilities for production of pandemic influenza vaccines. This approach may lead to an accelerated licensure according to FDA draft guidelines published on March 2, 2006 (http://www.fda.gov/cber/vaccine/vacpubs.htm), and will lead to an immediate surge in domestic vaccine production capacity and bridge the gap between the current capacity and the implementation of the long term strategies. Expansion of domestic capacity will lead to independence of imported vaccines which are likely to be unavailable during an influenza pandemic, and reduce the risk of shortage of seasonal influenza vaccine.

- Purpose

The purpose of this solicitation is to support the immediate expansion of the domestic surge capacity to manufacture pandemic influenza vaccines. Incremental multi-year funding for cost-sharing contracts to vaccine manufacturers will support the adaptation of existing manufacturing facilities leading to FDA licensure for the production of influenza vaccines.  Ultimately this approach shall contribute to the establishment of sufficient surge capacity to alleviate U.S., and ideally, global vaccine needs during an influenza pandemic.

Objectives

The successful Offeror shall accomplish the following objectives associated with the expanded domestic capacity of pandemic influenza vaccine:

a) Complete adaptation of the existing facilities for manufacturing of pandemic influenza vaccines. Facilities may include a pilot plant, bulk manufacturing facility, and/or fill/finish facility. A pilot manufacturing plant shall be completed in two years or less and shall have the capacity to produce at least 4,000 doses of monovalent pre-pandemic or pandemic influenza vaccine per day. A bulk manufacturing facility shall be completed for regulatory review and acceptance in three years or less and shall have the capacity to produce at least 50 million doses of monovalent pre-pandemic or pandemic influenza vaccine at 15 μg HA/dose per influenza vaccine manufacturing campaign. The commercial scale manufacturing facilities and systems shall be validated for the influenza vaccine product to be licensed. The facilities shall be capable of manufacturing pandemic vaccines using Prime Contractor’s or its subcontractor’s influenza vaccine technology. The facilities shall be approved by the FDA for manufacturing of influenza vaccine, and must comply with related biosafety guidelines and recommendations issued by USDA, CDC, and WHO. The adapted facilities must be available for emergency production of pre-pandemic and pandemic influenza vaccines.

b) Obtain FDA approval for using the facility to manufacture influenza vaccines. The Offeror must seek FDA licensure for using the facility to manufacture influenza vaccines.

c) Develop a warm base operation plan to maintain the manufacturing facility to support rapid stockpile purchases commensurate with U.S. pre-pandemic and pandemic influenza vaccine needs and manufacture at least one commercial scale lot of influenza vaccine per year as designated by the U.S. Government over the course of five years post-validation of the facilities for U.S. Government possession and usage as needed.

Activities that may be supported by this solicitation shall include conceptual and detailed A&ME design, facility construction and mechanical engineering, commissioning, manufacturing equipment, and validations of facility/process/systems leading toward FDA licensure of the facility for manufacturing of influenza vaccines, and warm base operation. The objective of this project is to expand the domestic influenza vaccine supply in the event of an influenza pandemic.  Activities that will not be funded by the resulting contract(s) include utilities, purchase of land and/or disposal of biological waste.  However, these activities are eligible for consideration as part of the Offerors share of cost (see M.1a)

Mandatory Criteria for Eligibility

This solicitation is broad in scope to encourage proposal submissions from potential Offerors who manufacture FDA-licensed biological products. Because the timing of the next pandemic is uncertain and avian H5N1 influenza in Eurasia poses a substantial pandemic threat, short timelines to product licensure and availability are critical.  Therefore, only Offerors that can fulfill the following pre-requisites will be eligible for funding under this solicitation:

- The facility is located in the U.S.

- For proposed bulk and/or fill finish manufacturing, the facilities must currently be used to manufacture FDA licensed biological products. Pilot facilities, as well as commercial scale facilities shall be in compliance with FDA, USDA and CDC regulatory and biosafety guidelines for pandemic influenza vaccine manufacturing, as applicable

- Commitment to share at least 25% of the adaptation or renovation costs.

- Commitment to maintain the retrofitted manufacturing facility to support rapid stockpile production commensurate with U.S. pre-pandemic and pandemic influenza vaccine needs.

Additional information

In addition, it is critical that offerors understand the following:

This advanced development contract is milestone-driven and funding is expected to occur in phases.  Periodic assessments of progress will be conducted by HHS.  Continuation of effort on initial and subsequent milestones and associated funding will be based on contractor performance, timeliness and quality of deliverables, and consultations among Contractor, HHS, and United States Government interagency working group members.

Statement of Work

Independently and not as an agent of the government, the Contractor shall furnish all the necessary services, qualified personnel, materials, equipment, and facilities not otherwise provided by the government as needed to perform the work described below.

Milestones

I.	Milestone 1: Within three (3) months of the contract award, the Contractor shall provide to HHS for review and acceptance a milestone-driven Conceptual Facility A&ME Plan. The plan shall include the conceptual adaptation design of the facility and its production capacity.

- Milestone 2: Within six (6) months of the contract award, the Contractor shall provide to HHS for review and acceptance a milestone-driven Detailed Facility A&ME Plan.

  - The plan shall include a detailed facility adaptation design that meets USDA, CDC, and WHO’s current guidelines on biocontainment for H5N1 vaccine production.

  - The plan shall describe facility modification and mechanical commissioning strategies as required.

  - The plan shall include a list of facility and manufacturing equipment.

  - The plan shall describe a master validation plan for the facility, process, equipment and assays as required.  If technology is to be transferred, a detailed plan must be provided as part of this milestone plan.

- Milestone 3: Within nine (9) months of the contract award, the Contractor shall submit to HHS for review and acceptance a Facility Regulatory Approval Plan presenting the regulatory path for licensure of the influenza vaccine product manufactured in the bulk and/or fill/finish facilities.

- Milestone 4: Within nine (9) months of the contract award, the Contractor shall submit to HHS for review and acceptance of a Facility Operation Plan that describes feasibility for production of commercial biological products and vaccines for Government purchases during interpandemic and pandemic periods. The plan shall describe how the newly retrofitted facilities are integrated into the Contractor’s biological product franchise. The plan shall describe warm base operation with one commercial lot production each year.

- Milestone 5: Contactor defined milestones. The Contractor shall provide within nine (9) months of contract award a work breakdown structure, including comprehensive and integrated timelines (Gantt chart) and major milestones to complete the remaining scope of work toward FDA licensure of the facility for commercial scale manufacturing of influenza vaccine. The Contractor shall propose milestones at which time data will be presented summarizing results of prior activities and new plans and protocols that will be submitted for review and approval in order to guide all subsequent activities. Milestones will include:

- Detailed construction plans

- A&ME design

- Piping & instrumentation diagrams

- Facility construction

- Facility  commissioning

- Validation of facilities/process/systems

- Consistency lot manufacturing (bulk and fill/finish facilities only)

- Completion of  appropriate clinical trial (bulk and fill/finish facilities only)

- Submission of a BLA supplement  (bulk and fill/finish facilities only)

Reporting of these activities will be required on a monthly basis as a part of the contractor’s monthly technical report.

- Milestone 6: Maintaining a “Warm Base” operation.  The Contractor shall manufacture and release at least one (1) lot of vaccine product per year for post-validation of the facility in order to maintain cGMP compliance and license to produce sufficient doses of the vaccine depending on Federal regulatory guidelines.  The pandemic and or pre-pandemic vaccines, as defined by USG, that result from warm-base production shall be delivered to a USG-designated site. The Contractor shall incorporate this requirement into the work plan and timeline.

Meetings and conferences:

The Contractor shall participate in regular meetings to coordinate and oversee the contract effort as directed by the Project Officer. Such meetings may include, but are not limited to, meetings of all Contractors and subcontractors to discuss progresses of the program, meetings with individual contractors and other HHS officials to discuss the technical, regulatory, and ethical aspects of the program, and meetings with technical consultants to discuss technical data provided by the Contractor.  Monthly teleconferences with the Contractor and subcontractors with HHS officials will be held at times and dates to be determined to review technical and product development progress, except during clinical lot manufacturing when meetings shall be held on a weekly basis.

Security of Contract Operations and Information Technology:

The work performed for development, manufacture, transport, storage and distribution will be performed under a detailed security plan that ensures against theft, tampering or destruction of the specific pertinent product-related material, equipment, documents, information, and data. The Contractor shall develop a written Draft Security Plan, for the protection of physical facilities, using, for example, fencing, controlled access, surveillance equipment, 2-person integrity rule, tamper evident packaging, and armed guards.  The Contractor shall submit the Draft Security Plan to the Contracting Officer and Project Officer with the technical proposal.  The Draft Security Plan shall describe the procedures to be utilized to manage and monitor the general internal operations of the firm and a description of Offeror’s facility(ies) in which the work will be performed and related activity conducted, including work by any subcontractors and consultants.  The Draft Security Plan shall also include the Contractor’s procedures for screening and background investigations of all employees, subcontractors and consultants who have access to the development, manufacturing, transport, storage, and distribution of the product.  Such background inquiries and screening should include, but not be limited to, education, previous employment, fingerprints and complete criminal history (FBI, state, and local), credit reports, civil actions, DMV, social security account number verification, drug testing, and references.  Screening data should include the employee’s full name, any aliases, date(s) of birth, and Social Security numbers and other identifying numbers as appropriate, e.g., Passport number.  USG can audit and review at its discretion the Contractor’s personnel records in order to confirm compliance with personnel screening and background investigation requirements.  Such access will also include interviews with relevant Contractor human resources supervisory and hiring personnel.

This plan shall ensure confidentiality, integrity of, and timely access by authorized individuals to data, information and information technology systems, consistent with OMB Circular A-130, Appendix III.  This plan should also address the Contractor’s security-related due diligence on public information, marketing, advertising, including use of web site[s] impacting product and supply chain security.

This plan shall also include the security measures to be used to protect the medical countermeasure to be stored at the Contractor’s facility (e.g., refrigeration/freezer alarm systems, backup electrical power generator systems, etc.), and the contingency plan to accommodate any manufacturing and storage problems caused by natural or man-made disasters, power loss, refrigerant loss, equipment failures, etc.

The Project Officer and the Information Protection and Systems Security (IPASS) Coordinator will review the plan and submit comments to the Contractor.  The Contractor shall revise the Security Plan, if required, and submit a Final Security Plan to the Government within 30 days after receipt of the Government’s comments. Upon completion of all the required security measures, the Contractor shall supply to the Project Officer a letter certifying compliance.  Performance of work under this contract shall be in accordance with this written Security Plan.

C.2.  REPORTING REQUIREMENTS

In addition to those reports required by other terms of this contract, the Contractor(s) shall submit to the Contracting Officer and the Project Officer technical progress reports covering the work accomplished during each reporting period on a periodic basis as established by the Project Officer. These reports are subject to technical inspection and requests for clarification by the Project Officer. These reports shall be brief and factual and prepared in accordance with the following format:

I.	Technical Progress Reports: On the fifteenth of each month for the previous calendar month or within fifteen days of prescribed project milestones, the Contractor shall submit to the Project Officer and the Contracting Officer. The frequency of Technical Progress Reporting will be determined by the Contracting Officer and Project Officer during negotiations of the contract. The format and type of Technical Progress Report and Executive Summary will be provided by the Project Officer. Technical Progress Reports will include project timelines and milestones and summaries of product manufacturing, testing, and clinical evaluation. A Technical Progress Report will not be required for the period when the Final Report is due. The Contractor shall submit one copy of the Technical Progress Report electronically via e-mail. Any attachments to the e-mail report shall be submitted in Microsoft Word or Word Perfect, Microsoft Excel, Microsoft Project Manger, and/or Adobe Acrobat PDF files. Such reports shall include the following specific information:

- Title page containing Technical Progress Report, the contract number and title, the period of performance or milestone being reported, the contractor's name, address, and other contact information, the author(s), and the date of submission;

- Introduction/Background - An introduction covering the purpose and scope of the contract effort;

- Progress - The report shall detail, document, and summarize the results of work performed, test results, and milestones achieved during the period covered. Also to be included is a summary of work planned for the next reporting period;

- Issues - Issues resolved, new issues and outstanding issues are enumerated with options and recommendations for resolution. An explanation of any difference between planned progress and actual progress, why the differences have occurred, and, if project activity is delinquent, then what corrective steps are planned. Revised timelines are provided.

- Invoices – Summary of any invoices submitted during the reporting period.

- Action Items – Summary table of activities or tasks to be accomplished by a certain date and by whom.

- Distribution List – A list of persons receiving the Technical Progress report

- Attachments – Results on the project provided as attachments

II.	The Executive Summary, which shall accompany each Technical Progress Report, will be formatted as a Microsoft Power Point presentation and include the following:

A.	Title page containing Executive Title, the contract number and title, the period of performance or milestone being reported, the contractor's name and the date of submission;

B.	Project Progress presented as milestone events, test results, tasks, and other activities achieved during the reporting period as talking point bullets;

C.	Project Issues presented headings and each item as a talking point bullet.

D.  	Action items - summary table of activities or tasks to be accomplished by a certain date and by whom

III.	Final Reports - By the expiration date of the contract, the Contractor shall submit a comprehensive Final Report that shall detail, document, and summarize the results of the entire contract work. The report shall explain comprehensively the results achieved. A draft Final Report will be submitted to the Project Officer for review and revision, then the original, four copies, and an electronic file containing the Final Report with revisions shall be submitted to the Project Officer for distribution to the Contracting Officer and the Program.

SECTION D--PACKAGING, MARKING AND SHIPPING

D.1. SHIPPING

I. Method of Delivery

Unless otherwise specified by the Contracting Officer or the Contracting Officer’s representative, delivery of items, to be furnished to the government under this contract (including invoices), shall be made by the United States Postal Service mail delivery, overnight mail delivery or courier service.

For delivery of the vaccine lots under Milestone 6, the Contracting Officer or the Contracting Officer’s representative will provide delivery instructions prior to the delivery date.

II. Addressees – For all contract deliverables.

Project Officer							Contracting Officer

HHS/OPHEP/OPHEMC					HHS/OPHEP/OPHEMC

330 Independence Avenue	 SW				330 Independence Avenue	 SW

Room G640								Room G640

Washington, D.C. 20201					Washington, D.C. 20201

SECTION E--INSPECTION AND ACCEPTANCE

The Contracting Officer or the duly authorized representative will inspect and accept materials and services to be delivered under the contract. The contract will identify who will perform inspections and where the inspections will be performed. In addition, the following clause is incorporated by reference:

FAR Clause No.52.246-9, INSPECTION OF RESEARCH AND DEVELOPMENT (SHORT FORM) (APR 1984)

SECTION F--DELIVERIES OR PERFORMANCE

F.1. PERIOD OF PERFORMANCE

Base Period

The period of performance for items 0001 through 0007, 0008A, 0008B, 0008C (Pilot Facility ONLY) and 0009 of this contract is from the date of contract award to _______months after contract award.

Delivery will be required F.O.B. Destination as set forth in FAR 52.247-35, F.O.B. DESTINATION, WITHIN CONSIGNEE’S PREMISES (APR 1984).

Optional Periods

| Item No. | Period | Performance Period |
| --- | --- | --- |
| 0010A | Option Year 1 | Sixty (60) months and one day after the effective date of contract through seventy-two (72) months after the effective date of contract. |
| 0010B | Option Year 2 | Seventy-two (72) months and one day after the effective date of contract through eighty-four (84) months after the effective date of contract. |
| 0011A | Option Year 1 | Sixty (60) months and one day after the effective date of contract through seventy-two (72) months after the effective date of contract. |
| 0011B | Option Year 2 | Seventy-two (72) months and one day after the effective date of contract through eighty-four (84) months after the effective date of contract. |
| 0011C | Option Year 3 | Eighty-four (84) months and one day after the effective date of contract through ninety-six (96) months after the effective date of contract. |

F.2. Technical Report Distribution

| CLIN | Deliverable | Quantity | Due Date |
| --- | --- | --- | --- |
| 0006 | Technical Progress Report | Original – C.O. 2 Copies – P.O. 1 Electronic Copy – P.O. | 1st Report due on/before ________; thereafter, due on/before the 15th of the month or milestone following each reporting period. Not due when Final is due. |
| 0006 | Executive Summary | Original – C.O. 2 Copies – P.O. 1 Electronic Copy – P.O. | 1st Report due on/before ________; thereafter, due on/before the 15th of the month following each anniversary date of the contract. Not due when Final is due. |
| 0007 | Final Report | Original – C.O. 2 Copies – P.O. 1 Electronic Copy – P.O. | Due on/before the completion date of the contract. |

F.3. Other Contract Deliverables

| CLIN | Deliverable | Quantity | Due Date |
| --- | --- | --- | --- |
| 0001 | Conceptual Facility A&ME Plan (milestone 1) | Original – C.O. 2 Copies – P.O. 1 Electronic Copy – P.O. | Three (3) months after contract award. |
| 0002 | Detailed Facility A&ME Plan (milestone 2) | Original – C.O. 2 Copies – P.O. 1 Electronic Copy – P.O. | Within Six (6) months after contract award. |
| 0003 | Facility Regulatory Approval Plan (milestone 3) | Original – C.O. 2 Copies – P.O. 1 Electronic Copy – P.O. | Within Nine (9) months after contract award. |
| 0004 | Facility Operation Plan (milestone 4) | Original – C.O. 2 Copies – P.O. 1 Electronic Copy – P.O. | Within Nine (9) months after contract award. |
| 0008 | Warm Base Vaccine Lot Production (milestone 6) | 1 Lot per year | End of each contract year for five years following facility validation and regulatory approval. Delivered to designated USG site. |
| 0005 | Contractor Defined Milestones (milestone 5) | Original – C.O. 2 Copies – P.O. 1 Electronic Copy – P.O. | Within 9 months after contract award |
| 0009 | Final Security Plan | Original – C.O. 2 Copies – P.O. 1 Electronic Copy – P.O. | 30 Days after Government’s Final Comments |

F.4. STOP WORK ORDER

The following clause is incorporated by reference:

FAR CLAUSE 52.242-15, STOP WORK ORDER (AUG 1989) with ALTERNATE I (APR 1984)

SECTION G.--CONTRACT ADMINISTRATION DATA

G.1. CONTRACTING OFFICER

1) The Contracting Officer is the only individual who can legally commit the Government to the expenditure of public funds.  No person other than the Contracting Officer can make any changes to the terms, conditions, general provisions or other stipulations of this contract.

2) The Contracting Officer is the only person with authority to act as agent of the Government under this contract. Only the Contracting Officer has authority to: (1) direct or negotiate any changes in the statement of work; (2) modify or extend the period of performance; (3) change the delivery schedule; (4) authorize reimbursement to the Contractor any costs incurred during the performance of this contract; or (5) otherwise change any terms and conditions of this contract.

3) No information, other than that which may be contained in an authorized modification to this contract, duly issued by the Contracting Officer, which may be received from any person employed by the United States Government, or otherwise,  shall be considered grounds for deviation from any stipulation of this contract.

G.2. PROJECT OFFICER

The Government's Project Officer(s) will be identified in the contract.

The Project Officer is responsible for: (1) monitoring the Contractor's technical progress, including the surveillance and assessment of performance and recommending to the Contracting Officer changes in requirements; (2) interpreting the statement of work and any other technical performance requirements; (3) performing technical evaluation as required; (4) performing technical inspections and acceptances required by this contract; and (5) assisting in the resolution of technical problems encountered during performance.

G.3. KEY PERSONNEL

Contractor personnel considered by the Government to be essential to contract performance will be identified here. The Contracting Officer must be notified prior to replacing any of these individuals on the contract.

NAME						TITLE					COMPANY

[To be specified prior to award]

G. 4.  INVOICE SUBMISSION

Invoices will be submitted in accordance with "Invoice/Financing Request Instructions” attached to this contract.  Addresses for submitting invoices will be included in the contract.

G. 5. CONTRACT FINANCIAL REPORT

a.	 Financial reports will be submitted to the Contracting Officer.

b.	The first financial report shall cover the period consisting of the FIRST FULL THREE CALENDAR MONTHS following the date of the contract, in addition to any fractional part of the initial month.  Thereafter, reports will be on a quarterly basis.

c.	The Contracting Officer may require the Contractor to submit detailed support for costs for each CLIN listed in section B contained in one or more interim financial reports.  This clause does not supersede the record retention requirements in FAR Part 4.7.

d.	The following is an example listing of expenditure categories to be reported:

Expenditure Category						Percentage of

A      							Effort/Hours

(1)	 Direct Labor

(a) Principal Investigator

(b) Co-Principal Investigator

(c) Key Personnel

(i)

(ii)

(iii)

(2)	Other Professional Personnel

(3)	Personnel - Other

(4)	Fringe Benefits

(5)	Accountable Personal Property

(6)	Materials/Supplies

(7)	Patient Care Costs

(8)	Travel

(9)	Consultant Costs

(10)	Premium Pay

(11)	Computer Costs

(12)	Subcontract Costs

(13)	Other Direct Costs

(14)	Indirect Costs

(15)	G&A Expense

(16)	Total Cost

(17)	Fee (where applicable)

(18)	Total Cost (Government Share & Contractor Share or Cost Plus Fixed Fee)

e.	The Government may unilaterally revise the expenditure categories to reflect the allotment of additional funds.

G. 6.  INDIRECT COST RATES

Profit making and non-profit organizations will negotiate provisional and/or final indirect cost rates with their cognizant Government Audit Agency.

Indirect cost rate ceilings are hereby established on indirect costs reimbursable under this contract.  The Government shall not be obligated to pay the Contractor any additional amount on account of indirect costs in excess of the ceiling rates listed below:

Cost Center		TBD

Period			TBD

Rate			TBD

Base			TBD

G. 7.  POST AWARD EVALUATION OF PAST PERFORMANCE

Interim and final evaluations of contractor performance shall be conducted on this contract in accordance with FAR 42.15. The final performance evaluation shall be completed at the time of completion of work. Interim and final evaluations will be submitted to the Contractor as soon as practicable. The Contractor will be permitted thirty days to review the document and to submit additional information or a rebutting statement.

SECTION H--SPECIAL CONTRACT REQUIREMENTS

H. 1. HUMAN SUBJECTS

Research involving human subjects shall not be conducted under this contract until the protocol developed in the SOW has been approved by DHHS, written notice of such approval has been provided by the Contracting Officer, and the Contractor has provided to the Contracting Officer a properly completed Optional Form 310 certifying Institutional Review Board (IRB) review and approval of the protocol. The human subject certification can be met by submission of the Contractor's self designated form, provided that it contains the information required by the Optional Form 310.

H. 2.  HUMAN MATERIALS

It is understood that the acquisition and supply of all human specimen material (including fetal material) used under this contract will be obtained by the Contractor in full compliance with applicable State and Local laws and the provisions of the Uniform Anatomical Gift Act in the United States and that no undue inducements, monetary or otherwise, will be offered to any person to influence their donation of human material.

H. 3. ANIMAL WELFARE ASSURANCE

The Contractor shall obtain, prior to the start of any work under this contract, an approved Animal Welfare Assurance from the Office of Human Research Protections (OHRP), Office of the Director, NIH, as required by Section I-43-30 of the Public Health Service Policy on Humane Care and Use of Laboratory Animals. The Contractor shall maintain such assurance for the duration of this contract, and any subcontractors performing work under this contract involving the use of animals shall also obtain and maintain an approved Animal Welfare Assurance.

H. 4. SUBCONTRACTING PROVISIONS

- Small Business Subcontracting Plan

  - The Small, Small Disadvantaged and Women Owned Small Business Subcontracting Plan, dated ___________ is attached hereto and made a part of this contract.

  - The failure of any Contractor or subcontractor to comply in good faith with FAR Clause 52.219-8 entitled "Utilization of Small Business Concerns" incorporated in this contract and the attached Subcontracting Plan will be a material breach of such contract or subcontract and subject to the remedies reserved to the Government under FAR Clause 52.219-16 entitled, "LIQUIDATED DAMAGES--SUBCONTRACTING PLAN."

- Subcontracting Reports

As of October 28, 2005 the Electronic Subcontract Reporting System (eSRS) is available for use by all civilian agencies and their contractors at www.esrs.gov.  The eSRS will eliminate both standard forms Subcontracting Reports for Individual Contracts (formerly SF 294) and Summary Subcontract Reports (formerly SF 295) paper submissions, and contractors will now submit all their reports electronically to a single, government wide system.  The eSRS is the latest system under the umbrella of the Integrated Acquisition Environment (IAE).

All civilian agency contractors must now submit their Summary Subcontract Reports into the eSRS.

No contractors of any agency will be required to submit the Subcontracting Reports for Individual Contracts into the eSRS for fiscal year 2004.

No contractors of any agency will be required to submit mid-year reports for fiscal year 2005 (normally due April 30 for the period ended March 31st) into the eSRS.  This exemption applies to both the Subcontracting Reports for Individual Contracts and the Summary Subcontract Reports.

Frequently Asked Questions and other information are available on the eSRS website at www.esrs.gov. If you have any further questions or comments, you may contact the SBA at eSRS@sba.gov or the IAE at integrated.acquistion@gsa.gov.

H. 5. CONFIDENTIALITY OF INFORMATION

The following information is covered by HHSAR 352.224-70, confidentiality of Information (APR 1984): Data obtained from human subjects

H. 6.  REVIEW AND APPROVAL

The Contractor shall not release any reports, manuscripts, press releases, or abstracts about the work being performed under this contract without approval in writing in advance from the Government.

H. 7.  IDENTIFICATION AND DISPOSITION OF DATA

The Contractor will be required to provide certain data generated under this contract to the Department of Health and Human Services (DHHS).  DHHS reserves the right to review any other data determined by DHHS to be relevant to this contract.  The contractor shall keep copies of all data required by the Food and Drug Administration (FDA) relevant to this contract for the time specified by the FDA.

H. 8. EPA ENERGY STAR REQUIREMENTS

In compliance with Executive Order 12845 (requiring Agencies to purchase energy efficient computer equipment) all microcomputers, including personal computers, monitors, and printers that are purchased using Government funds in performance of a contract shall be equipped with or meet the energy efficient low-power standby feature as defined by the EPA Energy Star program unless the equipment always meets EPA Energy Star efficiency levels. The microcomputer, as configured with all components, must be Energy Star compliant.

This low-power feature must already be activated when the computer equipment is delivered to the agency and be of equivalent functionality of similar power managed models. If the equipment will be used on a local area network, the vendor must provide equipment that is fully compatible with the network environment. In addition, the equipment will run commercial off-the-shelf software both before and after recovery from its energy conservation mode.

H. 9. REPORTING MATTERS INVOLVING FRAUD, WASTE AND ABUSE

Anyone who becomes aware of the existence or apparent existence of fraud, waste and abuse in DHHS funded programs is encouraged to report such matters to the HHS Inspector General's Office in writing or on the Inspector General's Hotline. The toll-free number is 1-800-HHS-TIPS (1-800-447-8477). All telephone calls will be handled confidentially. The e-mail address is Htips@os.dhhs.gov.

Office of Inspector General
Department of Health and Human Services
TIPS HOTLINE
P.O. Box 23489
Washington, DC 20026

H. 10. ACKNOWLEDGMENT OF FEDERAL FUNDING

A.	Section 507 of P.L. 104-208 mandates that contractors funded with Federal dollars, in whole or in part, acknowledge Federal funding when issuing statements, press releases, requests for proposals, bid solicitations and other documents. Contractors are required to state (1) the percentage and dollar amounts of the total program or project costs financed with Federal money, and (2) the percentage and dollar amount of the total costs financed by nongovernmental sources.

This requirement is in addition to the continuing requirement to provide an acknowledgment of support and disclaimer on any publication reporting the results of a contract funded activity.

B.	Publication and Publicity

The Contractor shall acknowledge the support of the Department of Health and Human Service, Office of Public Health Emergency Preparedness, Office of Public Health Emergency Medical Countermeasures whenever publicizing the work under this contract in any media by including an acknowledgment substantially as follows:

"This project has been funded in whole or in part with Federal funds from the Office of Public Health Emergency Preparedness, Office of Public Health and Emergency Medical Countermeasures, under Contract No. [insert #]"

H. 11. NEEDLE EXCHANGE

Pursuant to Section 505 of Public Law 105-78, contract funds shall not be used to carry out any program of distributing sterile needles or syringes for the hypodermic injection of any illegal drug. Section 505, however, is subject to the condition stated in Section 506. Specifically, Section 506 states that after March 31, 1998, a program for exchanging needles and syringes for used hypodermic needles and syringes may be carried out in a community if: (1) the Secretary of Health and Human Services determines that exchange projects are effective in preventing the spread of HIV and do not encourage the use of illegal drugs; and (2) the project is operated in accordance with criteria established by the Secretary for preventing the spread of HIV and for ensuring that the project does not encourage the use of illegal drugs.

H. 12. PRESS RELEASES

Pursuant Section 506 of P.L. 109-149, the Departments of Labor, Health and Human Services, and Education, and Related Agencies Appropriations Act, 2006, the contractor shall clearly state, when issuing statements, press releases, requests for proposals, bid solicitations and other documents describing projects or programs funded in whole or in part with Federal money that: (1) the percentage of the total costs of the program or project which will be financed with Federal money; (2) the dollar amount of Federal funds for the project or program; and (3) the percentage and dollar amount of the total costs of the project or program that will be financed by nongovernmental sources.

H. 13.  PROHIBITION ON CONTRACTOR INVOLVEMENT WITH TERRORIST ACTIVITIES

The Contractor acknowledges that U.S. Executive Orders and Laws, including but not limited to Executive Order 13224 and Public Law 107-56, prohibit transactions with, and the provisions of resources and support to, individuals and organizations associated with terrorism.  It is the legal responsibility of the contractor to ensure compliance with these Executive Orders and Laws.  This clause must be included in all subcontracts issued under this contract.

H. 14.   MANUFACTURING STANDARDS

The Current Good Manufacturing Practice requirement (CGMP) of the Federal Food, Drug and Cosmetic Act (FDCA section 501(a)(2)(B); the CGMP regulations for finished pharmaceuticals (21 CFR Parts 210-211); and applicable regulations governing biological products (21 CFR Parts 600-610) will be the standards to be applied for manufacturing, processing and packing of this vaccine product.

If at any time during the life of the contract, the Offeror fails to comply with these requirements in the manufacturing, processing and packaging of this vaccine product and such failure results in a material adverse effect on the safety, purity or potency of this vaccine product (a material failure) as identified by CBER, the Offeror shall have thirty (30) calendar days from the time such material failure is identified to cure such material failure.  If the Offeror fails to take such an action within the thirty (30) calendar day period, then the contract may be terminated.

H. 15.  ANTI-LOBBYING PROVISIONS

The contractor is hereby notified of the restrictions on the use of Department of Health and Human Service’s funding for lobbying of Federal, State and Local legislative bodies.

Section 1352 of Title 32, United States Code (Public Law 101-121, effective 12/23/89), among other things, prohibits a recipient (and their subcontractors) of a Federal contract, grant, loan, or cooperative agreement from using appropriated funds (other than profits from a federal contract) to pay any person for influencing or attempting to influence an officer or employee of any agency, a Member of Congress, an officer or employee of Congress, or an employee of a Member of Congress in connection with any of the following covered Federal actions; the awarding of any Federal contract; the making of any Federal grant; the making of any Federal loan; the entering into of any cooperative agreement; or the modification of any Federal contract, grant, loan, or cooperative agreement.  For additional information of prohibitions against lobbying activities see FAR Subpart 3.8 and FAR Clause 52.203-12.

In addition, the current Department of Health and Human Services Appropriations Act provides that no part of any appropriation contained in this Act shall be used, other than for normal and recognized executive-legislative relationships, for publicity or propaganda purposes, for the preparation, distribution, or use of any kit, pamphlet, booklet, publication, radio, television, or video presentation designed to support, or defeat legislation pending before the Congress, or any State or Local legislature except in presentation to the Congress, or any State or Local legislative body itself.

The current Department of Health and Human Services Appropriations Act also provides that no part of any appropriation contained in this Act shall be used to pay the salary or expenses of any contract or grant recipient, or agent acting for such recipient, related to any activity designed to influence legislation or appropriations pending before the Congress, or and State or Local legislature.

H. 16.  POSSESSION, USE AND TRANSFER OF SELECTED BIOLOGICAL AGENTS OR TOXINS

The following notice is applicable when contract performance is expected to involve possession, use and/or transfer of select biological agents or toxins: Notice to Offerors of Requirements of: 42 CFR Part 73, Select Agents and Toxins (relating to public health and safety); Agricultural Bioterrorism Protection Act of 2002, which consists of 7 CFR Part 331, Possession, Use, and Transfer of Biological Agents and Toxins (relating to plant health or plant products); and 9 CFR Part 121, Possession, Use, and Transfer of Biological Agents and Toxins (relating to human and animal health, animal health or animal products) - December 13, 2002

For prime or subcontract awards to domestic institutions who possess, use, and/or transfer Select Agents under this contract, the institution must complete registration with the Centers for Disease Control and Prevention (CDC), Department of Health and Human Services (DHHS) or the Animal and Plant Health Inspection Services (APHIS), U.S. Department of Agriculture (USDA), as applicable, before using DHHS funds for research involving Select Agents. No DHHS funds can be used for research involving Select Agents if the final registration certificate is denied. For prime or subcontract awards to foreign institutions who possess, use, and/or transfer Select Agents under this contract, the institution must provide information satisfactory to the DHHS that a process equivalent to that described in 42 CFR 73 (http://www.cdc.gov/od/sap/docs/42cfr73.pdf ) for U.S. institutions is in place and will be administered on behalf of all Select Agent work sponsored by these funds before using these funds for any work directly involving the Select Agents. In the technical proposal, the offeror must include details about the select agent and the quantity proposed to be used during contract performance. When requested by the contracting officer during negotiations, potential awardees must provide information addressing the following key elements for the foreign institutions: safety, security, training, procedures for ensuring that only approved/appropriate individuals have access to the Select Agents, and any applicable laws, regulations and policies equivalent to 42 CFR 73. An NIAID-chaired committee of U.S. federal employees (including representatives of DHHS grants/contracts and scientific program management, CDC, Department of Justice and other federal intelligence agencies, and Department of State) will assess the policies and procedures for comparability to the U.S. requirements described in 42 CFR Part 73. Toward this end, when requested during negotiations, potential awardees will be asked to provide key information delineating any laws, regulations, policies, and procedures applicable to the foreign institution for the safe and secure possession, use, and transfer of Select Agents. This includes concise summaries of safety, security, and training plans, and applicable laws, regulations, and policies. For the purpose of security risk assessments, foreign institutions must provide the names of all individuals who will have access to the Select Agents and procedures for ensuring that only approved and appropriate individuals have access to Select Agents under the resulting contract. If the proposed contract work will not involve Select Agents, the offeror must include a statement in their technical proposal that the proposed work does not now nor will it in the future (i.e. throughout the life of the award) involve Select Agents. Listings of HHS Select Agents and Toxins, biologic agents and toxins, and Overlap agents or toxins as well as information about the registration process, can be obtained on the Select Agent Program.

# PART II – CONTRACT CLAUSES

## SECTION I - CONTRACT CLAUSES

THE FOLLOWING PAGES CONTAIN A LISTING(S) OF GENERAL CLAUSES WHICH WILL BE APPLICABLE TO MOST CONTRACTS RESULTING FROM THIS RFP.  HOWEVER, THE ORGANIZATIONAL STRUCTURE OF THE SUCCESSFUL OFFEROR(S) WILL DETERMINE THE SPECIFIC GENERAL CLAUSES TO BE CONTAINED IN THE CONTRACT(S) AWARDED FROM THIS RFP.  OFFERORS ARE ENCOURAGED TO REVIEW THESE CLAUSES AND TO DISCUSS ANY QUESTIONS THEY MAY HAVE ABOUT THEM DURING NEGOTIATIONS.   THE FULL TEXT OF THESE CLAUSES MAY BE ACCESSED ELECTRONICALLY AT THESE ADDRESSES:  http://www.acquisition.gov/comp/far/index.html.

http://www.dhhs.gov/oamp/dap/hhsar.html/

I.1. GENERAL CLAUSES

General Clauses for a Cost-Reimbursement Research and Development Contract

FEDERAL ACQUISITION REGULATION (FAR) (48 CFR CHAPTER 1) CLAUSES:

| FAR CLAUSE NO. | DATE |  |  | TITLE |
| --- | --- | --- | --- | --- |
| 52.202-1 |  | Jul 2004 | Definitions (Over $100,000) |  |
| 52.203-3 |  | Apr 1984 | Gratuities (Over $100,000) |  |
| 52.203-5 |  | Apr 1984 | Covenant Against Contingent Fees (Over $100,000) |  |
| 52.203-6 |  | Jul 1995 | Restrictions on Subcontractor Sales to the Government (Over $100,000) |  |
| 52.203-7 |  | Jul 1995 | Anti-Kickback Procedures (Over $100,000) |  |
| 52.203-8 |  | Jan 1997 | Cancellation, Rescission, and Recovery of Funds for Illegal or Improper Activity (Over $100,000) |  |
| 52.203-10 |  | Jan 1997 | Price or Fee Adjustment for Illegal or Improper Activity (Over $100,000) |  |
| 52.203-12 |  | Sep 2005 | Limitation on Payments to Influence Certain Federal Transactions (Over $100,000) |  |
| 52.204-4 |  | Aug 2000 | Printed or Copied Double-Sided on Recycled Paper (Over $100,000) |  |
| 52.204-7 |  | Jul 2006 | Central Contractor Registration |  |
| 52.209-6 |  | Jan 2005 | Protecting the Government's Interests When Subcontracting With Contractors Debarred, Suspended, or Proposed for Debarment (Over $25,000) |  |
| 52.215-2 |  | Jun 1999 | Audit and Records - Negotiation (Over $100,000) |  |
| 52.215-8 |  | Oct 1997 | Order of Precedence - Uniform Contract Format |  |
| 52.215-10 |  | Oct 1997 | Price Reduction for Defective Cost or Pricing Data |  |
| 52.215-12 |  | Oct 1997 | Subcontractor Cost or Pricing Data (Over $500,000) |  |
| 52.215-14 |  | Oct 1997 | Integrity of Unit Prices (Over $100,000) |  |
| 52.215-15 |  | Oct 2004 | Pension Adjustments and Asset Reversions |  |
| 52.215-18 |  | Jul 2005 | Reversion or Adjustment of Plans for Post-Retirement Benefits (PRB) other than Pensions |  |
| 52.215-19 |  | Oct 1997 | Notification of Ownership Changes |  |
| 52.215-21 |  | Oct 1997 | Requirements for Cost or Pricing Data or Information Other Than Cost or Pricing Data - Modifications |  |
| 52.216-7 |  | Dec 2002 | Allowable Cost and Payment |  |
| 52.216-8 |  | Mar 1997 | Fixed Fee |  |
| 52.219-8 |  | May 2004 | Utilization of Small Business Concerns (Over $100,000) |  |
| 52.219-9 |  | Jul 2005 | Small Business Subcontracting Plan (Over $500,000, $1,000,000 for Construction) |  |
| 52.219-16 |  | Jan 1999 | Liquidated Damages - Subcontracting Plan (Over $500,000, $1,000,000 for Construction) |  |
| 52.222-2 |  | Jul 1990 | Payment for Overtime Premium (Over $100,000) (Note: The dollar amount in paragraph (a) of this clause is $0 unless otherwise specified in the contract.) |  |
| 52.222-3 |  | Jun 2003 | Convict Labor |  |
| 52.222-21 |  | Feb 1999 | Prohibition of Segregated Facilities |  |
| 52.222-26 |  | Apr 2002 | Equal Opportunity |  |
| 52.222-35 |  | Dec 2001 | Equal Opportunity for Special Disabled Veterans, Veterans of the Vietnam Era, and Other Eligible Veterans |  |
| 52.222-36 |  | Jun 1998 | Affirmative Action for Workers with Disabilities |  |
| 52.222-37 |  | Dec 2001 | Employment Reports on Special Disabled Veterans, Veterans of the Vietnam Era, and Other Eligible Veterans |  |
| 52.222-50 |  | Apr 2006 | Combating Trafficking in Persons |  |
| 52.223-6 |  | May 2001 | Drug-Free Workplace |  |
| 52.223-14 |  | Aug 2003 | Toxic Chemical Release Reporting (Over $100,000) |  |
| 52.225-1 |  | Jun 2003 | Buy American Act - Supplies |  |
| 52.225-13 |  | Feb 2006 | Restrictions on Certain Foreign Purchases |  |
| 52.227-1 |  | Jul 1995 | Authorization and Consent, Alternate I (Apr 1984) |  |
| 52.227-2 |  | Aug 1996 | Notice and Assistance Regarding Patent and Copyright Infringement (Over $100,000) |  |
| 52.227-11 |  | Jun 1997 | Patent Rights - Retention by the Contractor (Short Form) (Note: In accordance with FAR 27.303(a)(2), paragraph (f) is modified to include the requirements in FAR 27.303(a)(2)(i) through (iv). The frequency of reporting in (i) is annual. |  |
| 52.227-14 |  | Jun 1987 | Rights in Data - General |  |
| 52.232-9 |  | Apr 1984 | Limitation on Withholding of Payments |  |
| 52.232-17 |  | Jun 1996 | Interest (Over $100,000) |  |
| 52.232-20 |  | Apr 1984 | Limitation of Cost |  |
| 52.232-23 |  | Jan 1986 | Assignment of Claims |  |
| 52.232-25 |  | Oct 2003 | Prompt Payment, Alternate I (Feb 2002) |  |
| 52.232-33 |  | Oct 2003 | Payment by Electronic Funds Transfer--Central Contractor Registration |  |
| 52.233-1 |  | Jul 2002 | Disputes |  |
| 52.233-3 |  | Aug 1996 | Protest After Award, Alternate I (Jun 1985) |  |
| 52.233-4 |  | Oct 2004 | Applicable Law for Breach of Contract Claim |  |
| 52.242-1 |  | Apr 1984 | Notice of Intent to Disallow Costs |  |
| 52.242-3 |  | May 2001 | Penalties for Unallowable Costs (Over $500,000) |  |
| 52.242-4 |  | Jan 1997 | Certification of Final Indirect Costs |  |
| 52.242-13 |  | Jul 1995 | Bankruptcy (Over $100,000) |  |
| 52.244-2 |  | Aug 1998 | Subcontracts, Alternate I (January 2006) |  |
| 52.244-5 |  | Dec 1996 | Competition in Subcontracting (Over $100,000) |  |
| 52.244-6 |  | Feb 2006 | Subcontracts for Commercial Items |  |
| 52.245-9 |  | Aug 2005 | Use and Charges |  |
| 52.246-23 |  | Feb 1997 | Limitation of Liability (Over $100,000) |  |
| 52.249-6 |  | May 2004 | Termination (Cost-Reimbursement) |  |
| 52.249-14 |  | Apr 1984 | Excusable Delays |  |
| 52.253-1 |  | Jan 1991 | Computer Generated Forms |  |

DEPARTMENT OF HEALTH AND HUMAN SERVICES ACQUISITION REGULATION (HHSAR) (48 CFR CHAPTER 3) CLAUSES:

| HHSAR CLAUSE NO. | DATE |  |  | TITLE |
| --- | --- | --- | --- | --- |
| 352.202-1 |  | Jan 2001 | Definitions - with Alternate paragraph (h) (Jan 2001) |  |
| 352.216-72 |  | Oct 1990 | Additional Cost Principles |  |
| 352.223-70 |  | Jan 2001 | Safety and Health |  |
| 352.224-70 |  | Apr 1984 | Confidentiality of Information |  |
| 352.228-7 |  | Dec 1991 | Insurance - Liability to Third Persons |  |
| 352.232-9 |  | Apr 1984 | Withholding of Contract Payments |  |
| 352.233-70 |  | Apr 1984 | Litigation and Claims |  |
| 352.242-71 |  | Apr 1984 | Final Decisions on Audit Findings |  |
| 352.270-6 |  | Jul 1991 | Publications and Publicity |  |
| 352.270-7 |  | Jan 2001 | Paperwork Reduction Act |  |
| 352.270-9 |  | Jan 2001 | Care of Live Vertebrate Animals |  |
| [End of GENERAL CLAUSES FOR A COST-REIMBURSEMENT RESEARCH AND DEVELOPMENT CONTRACT - Rev. 04/19/2006]. |  |  |  |  |

I.2. AUTHORIZED SUBSTITUTIONS OF CLAUSES

Authorized substitutions and/or modifications of the General Clauses will be based on the type of contract and Contractor and will be determined during negotiations.  The following clauses may be applicable and may be made a part of the resultant contract.

FAR Clause 52.232-20, Limitation of Cost, is deleted in its entirety and FAR Clause 52.232-22, Limitation of Funds (APRIL 1984) is substituted therefore. [Note: When this contract is fully funded, FAR Clause 52.232-22, Limitation of Funds will no longer apply and FAR Clause 52.232-20, Limitation of Cost will become applicable.]

### I.3.  ADDITIONAL CONTRACT CLAUSES

The following clause(s), as applicable, will be made part of the resultant contract.  Please note that any contract resulting from this solicitation is not limited to the clauses listed below.  These clauses represent some of the most commonly used.  Any additional clauses deemed necessary by the Government will be discussed during negotiations.

## 52.204-8 Annual Representations and Certifications (Jan 2006).

Annual Representations and Certifications (Jan 2006)

(a)(1) The North American Industry Classification System (NAICS) code for this acquisition is 325414.

(2) The small business size standard is 500.

(3) The small business size standard for a concern which submits an offer in its own name, other than on a construction or service contract, but which proposes to furnish a product which it did not itself manufacture, is 500 employees.

(b)(1) If the clause at 52.204-7, Central Contractor Registration, is included in this solicitation, paragraph (c) of this provision applies.

(2) If the clause at 52.204-7 is not included in this solicitation, and the offeror is currently registered in CCR, and has completed the ORCA electronically, the offeror may choose to use paragraph (c) of this provision instead of completing the corresponding individual representations and certifications in the solicitation. The offeror shall indicate which option applies by checking one of the following boxes:

[  ] (i) Paragraph (c) applies.

[  ] (ii) Paragraph (c) does not apply and the offeror has completed the individual representations and certifications in the solicitation.

(c) The offeror has completed the annual representations and certifications electronically via the Online Representations and Certifications Application (ORCA) website at http://orca.bpn.gov. After reviewing the ORCA database information, the offeror verifies by submission of the offer that the representations and certifications currently posted electronically have been entered or updated within the last 12 months, are current, accurate, complete, and applicable to this solicitation (including the business size standard applicable to the NAICS code referenced for this solicitation), as of the date of this offer and are incorporated in this offer by reference (see FAR 4.1201); except for the changes identified below [offeror to insert changes, identifying change by clause number, title, date]. These amended representation(s) and/or certification(s) are also incorporated in this offer and are current, accurate, and complete as of the date of this offer.

FAR Clause # Title Date Change

____________ _________ _____ _______

Any changes provided by the offeror are applicable to this solicitation only, and do not result in an update to the representations and certifications posted on ORCA.

(End of provision)

52.215-17 Waiver of Facilities Capital Cost of Money (October 1997)

52.243-2, Changes—Cost Reimbursement (August 1987)

I.4 Additional Contract Clauses of   SECTION I – Added in full text

### 52.217-7  Option for Increased Quantity—Separately Priced Line Item (Mar 1989)

The Government may require the delivery of the numbered line item, identified in the Schedule as an option item, in the quantity and at the price stated in the Schedule. The Contracting Officer may exercise the option by written notice to the Contractor within [insert in the clause the period of time in which the Contracting Officer has to exercise the option]. Delivery of added items shall continue at the same rate that like items are called for under the contract, unless the parties otherwise agree.

### 52.217-8  Option to Extend Services (Nov 1999)

The Government may require continued performance of any services within the limits and at the rates specified in the contract. These rates may be adjusted only as a result of revisions to prevailing labor rates provided by the Secretary of Labor. The option provision may be exercised more than once, but the total extension of performance hereunder shall not exceed 6 months. The Contracting Officer may exercise the option by written notice to the Contractor within _____ [insert the period of time within which the Contracting Officer may exercise the option].

### 52.217-9  Option to Extend the Term of the Contract (Mar 2000)

(a) The Government may extend the term of this contract by written notice to the Contractor within the period of performance; provided that the Government gives the Contractor a preliminary written notice of its intent to extend at least _____ days [60 days unless a different number of days is inserted] before the contract expires. The preliminary notice does not commit the Government to an extension.

(b) If the Government exercises this option, the extended contract shall be considered to include this option clause.

(c) The total duration of this contract, including the exercise of any options under this clause, shall not exceed ___________ (months) (years).

52.222-39 Notification of Employee Rights Concerning Payment of Union Dues or Fees.

Notification of Employee Rights Concerning Payment of Union Dues or Fees (Dec 2004)

(a) Definition. As used in this clause—

“United States” means the 50 States, the District of Columbia, Puerto Rico, the Northern Mariana Islands, American Samoa, Guam, the U.S. Virgin Islands, and Wake Island.

(b) Except as provided in paragraph (e) of this clause, during the term of this contract, the Contractor shall post a notice, in the form of a poster, informing employees of their rights concerning union membership and payment of union dues and fees, in conspicuous places in and about all its plants and offices, including all places where notices to employees are customarily posted. The notice shall include the following information (except that the information pertaining to National Labor Relations Board shall not be included in notices posted in the plants or offices of carriers subject to the Railway Labor Act, as amended (45 U.S.C. 151-188)).

Notice to Employees

Under Federal law, employees cannot be required to join a union or maintain membership in a union in order to retain their jobs. Under certain conditions, the law permits a union and an employer to enter into a union-security agreement requiring employees to pay uniform periodic dues and initiation fees. However, employees who are not union members can object to the use of their payments for certain purposes and can only be required to pay their share of union costs relating to collective bargaining, contract administration, and grievance adjustment.

If you do not want to pay that portion of dues or fees used to support activities not related to collective bargaining, contract administration, or grievance adjustment, you are entitled to an appropriate reduction in your payment. If you believe that you have been required to pay dues or fees used in part to support activities not related to collective bargaining, contract administration, or grievance adjustment, you may be entitled to a refund and to an appropriate reduction in future payments.

For further information concerning your rights, you may wish to contact the National Labor Relations Board (NLRB) either at one of its Regional offices or at the following address or toll free number:

National Labor Relations Board
Division of Information
1099 14th Street, N.W.
Washington, DC 20570
1-866-667-6572
1-866-316-6572 (TTY)

To locate the nearest NLRB office, see NLRB's website at http://www.nlrb.gov.

(c) The Contractor shall comply with all provisions of Executive Order 13201 of February 17, 2001, and related implementing regulations at 29 CFR Part 470, and orders of the Secretary of Labor.

(d) In the event that the Contractor does not comply with any of the requirements set forth in paragraphs (b), (c), or (g), the Secretary may direct that this contract be cancelled, terminated, or suspended in whole or in part, and declare the Contractor ineligible for further Government contracts in accordance with procedures at 29 CFR Part 470, Subpart B—Compliance Evaluations, Complaint Investigations and Enforcement Procedures. Such other sanctions or remedies may be imposed as are provided by 29 CFR Part 470, which implements Executive Order 13201, or as are otherwise provided by law.

(e) The requirement to post the employee notice in paragraph (b) does not apply to—

(1) Contractors and subcontractors that employ fewer than 15 persons;

(2) Contractor establishments or construction work sites where no union has been formally recognized by the Contractor or certified as the exclusive bargaining representative of the Contractor’s employees;

(3) Contractor establishments or construction work sites located in a jurisdiction named in the definition of the United States in which the law of that jurisdiction forbids enforcement of union-security agreements;

(4) Contractor facilities where upon the written request of the Contractor, the Department of Labor Deputy Assistant Secretary for Labor-Management Programs has waived the posting requirements with respect to any of the Contractor’s facilities if the Deputy Assistant Secretary finds that the Contractor has demonstrated that—

(i) The facility is in all respects separate and distinct from activities of the Contractor related to the performance of a contract; and

(ii) Such a waiver will not interfere with or impede the effectuation of the Executive order; or

(5) Work outside the United States that does not involve the recruitment or employment of workers within the United States.

(f) The Department of Labor publishes the official employee notice in two variations; one for contractors covered by the Railway Labor Act and a second for all other contractors. The Contractor shall—

(1) Obtain the required employee notice poster from the Division of Interpretations and Standards, Office of Labor-Management Standards, U.S. Department of Labor, 200 Constitution Avenue, NW, Room N-5605, Washington, DC 20210, or from any field office of the Department’s Office of Labor-Management Standards or Office of Federal Contract Compliance Programs;

(2) Download a copy of the poster from the Office of Labor-Management Standards website at http://www.olms.dol.gov; or

(3) Reproduce and use exact duplicate copies of the Department of Labor’s official poster.

(g) The Contractor shall include the substance of this clause in every subcontract or purchase order that exceeds the simplified acquisition threshold, entered into in connection with this contract, unless exempted by the Department of Labor Deputy Assistant Secretary for Labor-Management Programs on account of special circumstances in the national interest under authority of 29 CFR 470.3(c). For indefinite quantity subcontracts, the Contractor shall include the substance of this clause if the value of orders in any calendar year of the subcontract is expected to exceed the simplified acquisition threshold. Pursuant to 29 CFR Part 470, Subpart B—Compliance Evaluations, Complaint Investigations and Enforcement Procedures, the Secretary of Labor may direct the Contractor to take such action in the enforcement of these regulations, including the imposition of sanctions for noncompliance with respect to any such subcontract or purchase order. If the Contractor becomes involved in litigation with a subcontractor or vendor, or is threatened with such involvement, as a result of such direction, the Contractor may request the United States, through the Secretary of Labor, to enter into such litigation to protect the interests of the United States.

I.5   DEVIATION to FAR 52.245-5

The resulting contract will include either 52.245-5 or as prescribed in FAR 45.106(f)(1), this clause with its Alternate 1 will be used if the awardee is a nonprofit institution of higher education.  The deviation eliminates the requirement that the Government take title to property purchased under the resulting contract(s).   Requesting an individual deviation to 52.245-5, Government Property (Cost-Reimbursement, Time-and-Material, or Labor-Hour Contracts).

EITHER

### 52.245-5  Government Property (Cost-Reimbursement, Time-and-Material, or Labor-Hour Contracts) – DEVIATED

(c) Title.  (1) The Government shall retain title to all Government-furnished property.

(2) Title to all property purchased by the Contractor for which the Contractor is entitled to be reimbursed as a direct item of cost under this contract shall pass to and vest in the Contractor upon the vendor’s delivery of such property.

(3) All Government-furnished property and all property acquired by the Contractor, title to which vests in the Government or the Contractor under this paragraph, are subject to the provisions of this clause.   If title to equipment vests in the Contractor under this paragraph (c)(2), the Contractor agrees that no charge will be made to the Government for any depreciation, amortization, or use under any existing or future Government contract or subcontract thereunder. The Contractor shall furnish the Contracting Officer a list of all equipment to which title is vested in the Contractor under this paragraph (c)(2) within 10 days following the end of the calendar quarter during which it was received or purchased.

OR

### 52.245-5 Government Property (Cost-Reimbursement, Time-and-Material, or Labor-Hour Contracts), Alternate 1 – DEVIATED

(c) Title. (1) The Government shall retain title to all Government-furnished property.

(2) Title to all property purchased by the Contractor for which the Contractor is entitled to be reimbursed as a direct item of cost under this contract shall pass to and vest in the Contractor upon the vendor’s delivery of such property.

(3) All Government-furnished property and all property acquired by the Contractor, title to which vests in the Government or the Contractor under this paragraph, are subject to the provisions of this clause.   If title to equipment vests in the Contractor under this paragraph (c)(2), the Contractor agrees that no charge will be made to the Government for any depreciation, amortization, or use under any existing or future Government contract or subcontract thereunder. The Contractor shall furnish the Contracting Officer a list of all equipment to which title is vested in the Contractor under this paragraph (c)(2) within 10 days following the end of the calendar quarter during which it was received or purchased.

(4) Vesting title under this paragraph (c) is subject to civil rights legislation, 42 U.S.C. 2000d. Before title is vested and by signing this contract, the Contractor accepts and agrees that—

“No person in the United States or its outlying areas shall, on the ground of race, color, or national origin, be excluded from participation in, be denied the benefits of, or be otherwise subjected to discrimination under this contemplated financial assistance (title to equipment).”

I. 6.  Department of Health and Human Services Acquisition Regulations (HHSAR)

(48 CFR Chapter 3) Clauses:  Full text of these clauses can be found at

http://www.dhhs.gov/oamp/dap/hhsar.html/

352.270-8, Protection of Human Subjects (January 2001)

Note:  The Office for Human Research Protections (OHRP), Office of the Secretary (OS), Department of Health and Human Services (DHHS) is the office responsible for oversight of the Protection of Human Subjects and should replace Office for Protection from Research Risks (OPRR), National Institutes of Health (NIH) wherever it appears in this clause.

PART III - LIST OF DOCUMENTS, EXHIBITS AND OTHER ATTACHMENTS

## SECTION J - LIST OF ATTACHMENTS

The following Attachments are provided in full text with this Solicitation:

1. PACKAGING AND DELIVERY OF PROPOSALS

2. PROPOSAL INTENT RESPONSE SHEET [SUBMIT ON/BEFORE: August 7, 2006]

[NOTE:  Your attention is directed to the "Proposal Intent Response Sheet".  If you intend to submit a proposal, you must complete this form and return it to this office via fax or e-mail on or before the date identified above. The receipt of this form is critical as it contains information essential for the Program’s coordination and review of proposals.]

3. APPLICABLE TO TECHNICAL PROPOSAL (INCLUDE THESE DOCUMENTS/FORMS WITH YOUR TECHNICAL PROPOSAL):

- Technical Proposal Cover Sheet

- Technical Proposal Cost Information

- Summary of Related Activities

- Optional Form 310, Protection of Human Subjects Assurance Identification/Certification/Declaration [When applicable, all institutions must have the form reviewed and approved by their Institutional Review Committee.]

- Government Notice for Handling Proposals

4. APPLICABLE TO BUSINESS PROPOSAL (INCLUDE WITH YOUR BUSINESS PROPOSAL):

- Proposal Summary and Data Record

- Breakdown  of Proposed Estimated Cost (plus fee) and Labor Hours, proposed Subcontracts

- and all other items of costs (i.e., travel, materials and supplies, etc.)

- Offeror’s Points of Contact

- Disclosure of Lobbying Activities, OMB Form LLL

- 5.  CHART OF ABBREVIATIONS

PACKAGING/DELIVERY/ELECTRONIC SUBMISSION OF THE PROPOSAL

Read all instructions on this page and in the RFP before mailing or submitting forms, proposals, or CDs.

Your proposal will have two separate parts.

- Business proposal

- Technical proposal

In addition, several other forms are required -- see the RFP and the table below for details.

You will submit your proposal in two formats: paper and CDs or USB Drives.

- The paper proposal with original signatures is the official, legally binding copy. There are no acceptable substitutes.

- The CD or USB memory stick versions of the proposal are for the benefit of OPHEMC. Electronic versions may or may not be used for review, at the discretion of OPHEMC.

As a potential offeror, you must routinely check the FedBizOpps for amendments because we do not notify you directly of changes.

Send your proposal to OPHEMC at the address below. If you have any questions, ask the primary or secondary OPHEMC contacts specified in the RFP.

Hand written proposals will not be accepted.

PAPER SUBMISSION:  The paper copy is the official copy for recording timely receipt of proposals.

SUBMISSION OF PROPOSALS BY FACSIMILE IS NOT ACCEPTABLE

WARNING:   You are advised to read and carefully follow the instructions listed in this RFP.  Failure to adhere to these instructions and to the specified limitations for size of paper and electronic proposals may result in the rejection of your proposal.  Proposals will not be returned to the offeoror.

NUMBER OF COPIES:

| Document | Number of Copies | Page Limits | File Size |
| --- | --- | --- | --- |
| Technical Proposal | One (1) bound SIGNED ORIGINAL. Five (5) copies bound in three ring binders CDs or USB Drives | Limited to not-to-exceed 40 Pages | Unlimited |
| Technical Proposal Appendices All materials shall be available electronically (i.e. SOPs, Pertinent Manuals, Figures or Data, and Letters of Collaboration/Intent). | One (1) bound SIGNED ORIGINAL. Five (5) copies bound in three ring binders . CDs or USB Drives | This information is included in the total page limitation of 250 pages. | Unlimited |
| Business Proposal | One (1) bound SIGNED ORIGINAL. Five (5) bound copies. in three ring binders CDs or USB Drives | Limited to not-to-exceed 250 pages | Unlimited |
| Representations and Certifications | Provide representations and certifications electronically via the BPN website (www.bpn.gov/orca) | N/A | N/A |

TECHNICAL PROPOSAL PAGE LIMITS INCLUDE:  The technical approach to be used by the Offeror(s) in order to implement the requirements stated in the Statement of Work.  TOTAL PAGE COUNT DOES NOT INCLUDE:  1 Cover and Back Page; 1 Table of Contents; Section Dividers that do not contain information other than title of Section.

PAGES IN EXCESS OF THIS LIMITATION WILL BE REMOVED FROM THE PROPOSAL AND WILL NOT BE PROVIDED TO THE REVIEWERS TO BE READ OR EVALUATED.

DELIVERIES BY United States Postal Service (USPS), DHL, FedEx, AND United Parcel Service (UPS) WILL BE TO THE FOLLOWING ADDRESS:

Attn:

Mekeba Barrett

Contract Specialist

HHS/OPHEP/OPHEMC

Cohen Building

330 Independence Ave. SW Rm G640

Washington, D.C. 20201

Phone: 202-205-3978

ALL OTHER COURIER DELIVERIES WILL BE TO THE FOLLOWING ADDRESS.  ALLOW 30 MINUTES FOR PROCESSING PACKAGES THROUGH SECURITY:

Hubert H. Humphrey Building

200 Independence Ave. SW Lobby

Washington, D.C. 20201

Marked for Attn:

Mekeba Barrett

Contract Specialist

HHS/OPHEP/OPHEMC

Cohen Building

330 Independence Ave. SW Rm G640

Washington, D.C. 20201

Phone: 202-205-3978

PROPOSAL INTENT RESPONSE SHEET

RFP No.: 	DHHS-ORDC-VB-06-07

RFP Title: 	 “Retrofitting Manufacturing Facilities for Production of Pandemic Influenza Vaccines”

Please review the attached Request for Proposal. Furnish the information requested below and return this page by

August 7, 2006. Your expression of intent is not binding but will greatly assist us in planning for proposal evaluation.

[ ] DO INTEND TO SUBMIT A PROPOSAL

[ ] DO NOT INTEND TO SUBMIT A PROPOSAL FOR THE FOLLOWING REASONS:

Company/Institution Name (print): ______________________________________

Address (print): _______________________________________________________

_____________________________________________________________________

_____________________________________________________________________

_____________________________________________________________________

Project Director's Name (print): _________________________________________

Title (print): __________________________________________________________

Signature/Date: _______________________________________________________

Telephone Number and E-mail Address (print clearly):

_____________________________________________________________________

_____________________________________________________________________

Names of Collaborating Institutions and Investigators (include Subcontractors and Consultants) (print):

_________________________________________________________________

_________________________________________________________________

_________________________________________________________________

_________________________________________________________________

(Continue list on a separate page if necessary)

RETURN VIA FAX OR E-MAIL TO:

HHS/OS/OPHEP/OPHEMC

330 Independence Avenue

Room G640

Washington, D.C. 20201

Attn:  Mekeba Barrett

RFP-HHS-ORDC-VB-06-07

FAX# (202) 205-3915

Email:   mekeba.barrett@hhs.gov

TECHNICAL PROPOSAL COVER SHEET

IN RESPONSE TO RFP-DHHS-ORDC-VB-06-07

TITLE: “Retrofitting Manufacturing Facilities for Production of Pandemic Influenza Vaccines”

OFFEROR (Primary organization/institution):

Name and Address:

PRINCIPAL INVESTIGATOR:

OFFEROR PERSONNEL Name (Last, First, Initial) and Degree(s)*

SUBCONTRACTOR ORGANIZATIONS (If more than one, list each organization and its personnel separately):

Name and Address:

PRINCIPAL INVESTIGATOR:

SUBCONTRACTOR PERSONNEL Name (Last, First, Initial) and Degree(s)*

COLLABORATORS or CONSULTANTS:

Name [Last, First, Initial) Degree(s)] Organization

* List all co-investigators/key personnel

TECHNICAL PROPOSAL COST INFORMATION/SUMMARY OF LABOR

AND DIRECT COSTS (Sample)

COST SHARING LINE ITEMS ONLY

| COST ELEMENT | Milestone 1 Government Share (Period Covered) |  | Milestone 1 Contractor Share (Period Covered) | Milestone 2 Government Share (Period Covered) | Milestone 2 Contractor Share (Period Covered) | Milestone 3 Government Share (Period Covered) | Milestone 3 Contractor Share (Period Covered) | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Labor Category | (Hours) |  |  | (Hours) | (Hours) | (Hours) | (Hours) | (Hours) |
| DIRECT LABOR COST: |  | $ |  | $ | $ | $ | $ | $ |
| MATERIAL COST: |  | $ |  | $ | $ | $ | $ | $ |
| TRAVEL COST: |  | $ |  | $ | $ | $ | $ | $ |
| CONSULTANTS: |  | $ |  | $ | $ | $ | $ | $ |
| SUBCONTRACTS: |  | $ |  | $ | $ | $ | $ | $ |
| CLINICAL TRIAL/PATIENT CARE COSTS: |  | $ |  | $ | $ | $ | $ | $ |
| EQUIPMENT |  | $ |  | $ | $ | $ | $ | $ |
| OTHER DIRECT COSTS |  | $ |  | $ | $ | $ | $ | $ |
| OTHER (Specify) |  | $ |  | $ | $ | $ | $ | $ |
| TOTAL DIRECT COST: |  | $ |  | $ | $ | $ | $ | $ |
| TOTAL COST: |  | $ |  | $ | $ | $ | $ | $ |
| TOTAL DIRECT COST: |  | $ |  | $ | $ | $ | $ | $ |

Specific Instructions:

1.	Do not include any individual salary information

2.	Do not include any indirect cost or fee.

3.	Do not submit the total amount of proposal.

4.	Submit this information as a portion of the Technical Proposal.

TECHNICAL PROPOSAL COST INFORMATION/SUMMARY OF LABOR

AND DIRECT COSTS (Sample)

COST PLUS FIXED FEE LINE ITEMS ONLY

| COST ELEMENT | Milestone 1 (Period Covered) | Milestone 2 (Period Covered) |  | Milestone 3 (Period Covered) | Milestone 4 (Period Covered) | Milestone 8A (Period Covered) | Milestone 8B (Period Covered) | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| DIRECT LABOR: |  |  |  |  |  |  |  |  |
| Labor Category | (Hours) | (Hours) | (Hours) |  | (Hours) | (Hours) | (Hours) | Total |
| (Title and Name– use additional pages as necessary) |  |  |  |  |  |  |  |  |
| DIRECT LABOR COST: | $ | $ | $ |  | $ |  | $ | $ |
| MATERIAL COST: | $ | $ | $ |  | $ |  | $ | $ |
| TRAVEL COST: | $ | $ | $ |  | $ |  | $ | $ |
| CONSULTANTS: | $ | $ | $ |  | $ |  | $ | $ |
| SUBCONTRACTS: | $ | $ | $ |  | $ |  | $ | $ |
| CLINICAL TRIAL/PATIENT CARE COSTS: | $ | $ | $ |  | $ |  | $ | $ |
| EQUIPMENT | $ | $ | $ |  | $ |  | $ | $ |
| OTHER DIRECT COSTS | $ | $ | $ |  | $ |  | $ | $ |
| OTHER (Specify) | $ | $ | $ |  | $ |  | $ | $ |
| TOTAL DIRECT COST: | $ | $ | $ |  | $ |  | $ | $ |
| TOTAL COST: | $ | $ | $ |  | $ |  | $ | $ |
| TOTAL DIRECT COST: | $ | $ | $ |  | $ |  | $ | $ |

Specific Instructions:

1.	Do not include any individual salary information

2.	Do not include any indirect cost or fee.

3.	Do not submit the total amount of proposal.

4.	Submit this information as a portion of the Technical Proposal.

SUMMARY OF RELATED ACTIVITIES

The following specific information must be provided by the offeror pertaining to the Project Director, Principal Investigator, and each of any other proposed key professional individuals designated for performance under any resulting contract.

a.	Identify the total amount of all presently active federal contracts/cooperative agreements/grants and commercial agreements citing the committed levels of effort for those projects for each of the key individuals* in this proposal.

Professional's Name and Title/Position:

Identifying Number			Agency				Total Effort Committed

1.

2.

3.

4.

*If an individual has no obligation(s), so state.

b.	Provide the total number of outstanding proposals, exclusive of the instant proposal, having been submitted by your organization, not presently accepted but in an anticipatory stage, which will commit levels of effort by the proposed professional individuals*.

Professional's Name and Title/Position:

Identifying Number				Agency			Total Effort Committed

1.

2.

3.

4.

*If no commitment of effort is intended, so state.

c.	Provide a statement of the level of effort to be dedicated to any resultant contract awarded to your organization for those individuals designated and cited in this proposal.

Name					Title/Position			Total Proposed Effort

1.

2.

3.

4.

OMB No. 0990-0263

Approved for use through 11/30/2008

| Protection of Human Subjects Assurance Identification/IRB Certification/Declaration of Exemption (Common Rule) |  |
| --- | --- |
| Policy: Research activities involving human subjects may not be conducted or supported by the Departments and Agencies adopting the Common Rule (56FR28003, June 18, 1991) unless the activities are exempt from or approved in accordance with the Common Rule. See section 101(b) of the Common Rule for exemptions. Institutions submitting applications or proposals for support must submit certification of appropriate Institutional Review Board (IRB) review and approval to the Department or Agency in accordance with the Common Rule. | Institutions must have an assurance of compliance that applies to the research to be conducted and should submit certification of IRB review and approval with each application or proposal unless otherwise advised by the Department or Agency. |

| 1. Request Type [ ] ORIGINAL [ ] CONTINUATION [ ] EXEMPTION | 2. Type of Mechanism [ ] GRANT [ ] CONTRACT [ ] FELLOWSHIP [ ] COOPERATIVE AGREEMENT [ ] OTHER:_____________________________ | 3. Name of Federal Department or Agency and, if known, Application or Proposal Identification No. |
| --- | --- | --- |
| 4. Title of Application or Activity |  | 5. Name of Principal Investigator, Program Director, Fellow, or Other |

6. Assurance Status of this Project (Respond to one of the following)

[ ] This Assurance, on file with Department of Health and Human Services, covers this activity:

Assurance Identification No.                                                  , the expiration date                             IRB Registration No.  ____________________

[ ] This Assurance, on file with (agency/dept)____________________________________________________________________, covers this activity.

Assurance No._____________________, the expiration date_              __     IRB Registration/Identification No.__________________(if applicable)

[ ] No assurance has been filed for this institution. This institution declares that it will provide an Assurance and Certification of IRB review and                       approval upon request.

[ ] Exemption Status: Human subjects are involved, but this activity qualifies for exemption under Section 101(b), paragraph___________.

7. Certification of IRB Review (Respond to one of the following IF you have an Assurance on file) [ ] This activity has been reviewed and approved by the IRB in accordance with the Common Rule and any other governing regulations. by: [ ] Full IRB Review on (date of IRB meeting) _____ or [ ] Expedited Review on (date) [ ] If less than one year approval, provide expiration date _____________________ [ ] This activity contains multiple projects, some of which have not been reviewed. The IRB has granted approval on condition that all projects covered by the Common Rule will be reviewed and approved before they are initiated and that appropriate further certification will be submitted.

8. Comments

| 9. The official signing below certifies that the information provided above is correct and that, as required, future reviews will be performed until study closure and certification will be provided. |  | 10. Name and Address of Institution |  |
| --- | --- | --- | --- |
| 11. Phone No. (with area code) 12. Fax No. (with area code) 13. Email: |  |  |  |
| 14. Name of Official |  | 15. Title |  |
| 16. Signature |  |  | 17. Date |

Authorized for local Reproduction                                          				                                                        Sponsored by HHS

Public reporting burden for this collection of information is estimated to average less than an hour per response. An agency may not conduct or sponsor, and a person is not required to respond to, a collection of information unless it displays a currently valid OMB control number. Send comments regarding this burden estimate or  any other aspect of this collection of information, including suggestions for reducing this burden to: OS Reports Clearance Officer, Room 503 200 Independence Avenue, SW., Washington, DC 20201.  Do not return the completed form to this address.

NOTE:	This Notice is for the Technical Evaluation Review Group who will be reviewing the proposals submitted in response to this RFP.  THE OFFEROR SHALL PLACE A COPY OF THIS NOTICE BEHIND THE TITLE PAGE OF EACH COPY OF THE TECHNICAL PROPOSAL.

# GOVERNMENT NOTICE FOR HANDLING PROPOSALS

This proposal shall be used and disclosed for evaluation purposes only, and a copy of this Government notice shall be applied to any reproduction or abstract thereof.  Any authorized restrictive notices which the submitter places on this proposal shall be strictly complied with.  Disclosure of this proposal outside the Government for evaluation purposes shall be made only to the extent authorized by, and in accordance with, the procedures in HHSAR 352.215-1.

(e) Restriction on disclosure and use of data. 
            (1) The proposal submitted in response to this request may contain data (trade secrets; business data, e.g., commercial information, financial information, and cost and pricing data; and technical data) which the offeror, including its prospective subcontractor(s), does not want used or disclosed for any purpose other than for evaluation of the proposal. The use and disclosure of any data may be so restricted; provided, that the Government determines that the data is not required to be disclosed under the Freedom of Information Act, 5 U.S.C. 552, as amended, and the offeror marks the cover sheet of the proposal with the following legend, specifying the particular portions of the proposal which are to be restricted in accordance with the conditions of the legend. The Government's determination to withhold or disclose a record will be based upon the particular circumstances involving the record in question and whether the record may be exempted from disclosure under the Freedom of Information Act. The legend reads:
        Unless disclosure is required by the Freedom of Information Act, 5 U.S.C. 552, as amended, (the Act) as determined by Freedom of Information (FOI) officials of the Department of Health and Human Services, data contained in the portions of this proposal which have been specifically identified by page number, paragraph, etc. by the offeror as containing restricted information shall not be used or disclosed except for evaluation purposes.
        The offeror acknowledges that the Department may not be able to withhold a record (data, document, etc.) nor deny access to a record requested pursuant to the Act and that the Department's FOI officials must make that determination. The offeror hereby agrees that the Government is not liable for disclosure if the Department has determined that disclosure is required by the Act.
        If a contract is awarded to the offeror as a result of, or in connection with, the submission of this proposal, the Government shall have right to use or disclose the data to the extent provided in the contract. Proposals not resulting in a contract remain subject to the Act.
        The offeror also agrees that the Government is not liable for disclosure or use of unmarked data and may use or disclose the data for any purpose, including the release of the information pursuant to requests under the Act. The data subject to this restriction are contained in pages (insert page numbers, paragraph designations, etc. or other identification).
            (2) In addition, the offeror should mark each page of data it wishes to restrict with the following statement:
        "Use or disclosure of data contained on this page is subject to the restriction on the cover sheet of this proposal or quotation."
            (3) Offerors are cautioned that proposals submitted with restrictive legends or [[Page 4256]] statements differing in substance from the above legend may not be considered for award. The Government reserves the right to reject any proposal submitted with a nonconforming legend.

| DEPARTMENT OF HEALTH AND HUMAN SERVICES PROPOSAL SUMMARY AND DATA RECORD |  | RFP/CONTRACT NUMBER |  |  |  |
| --- | --- | --- | --- | --- | --- |
| PROJECT TITLE (Title or RFP or Contract Proposal) |  |  |  |  |  |
| LEGAL NAME AND ADDRESS OF OFFEROR |  | PLACE OF PERFORMANCE (Full address including ZIP) |  |  |  |
| TYPE OF CONTRACT PROPOSED  COST-REIMBURSEMENT  FIXED PRICE  COST-PLUS-FIXED-FEE  OTHER |  |  |  |  |  |
| ESTIMATED TIME REQUIRED TO COMPLETE PROJECT |  |  |  |  |  |
| ESTIMATED DIRECT COSTS IN PROPOSED YEAR (From Budget |  | PROPOSED STARTING DATE |  |  |  |
| DOES THIS PROPOSAL INCLUDE A SUBCONTRACT  YES  NO (If yes, please furnish name and location of organization, description of services, basis for selection, responsible person employed by subcontractor and cost information.) |  |  |  |  |  |
| NAME AND TITLE OF PRINCIPAL INVESTIGATOR | SOCIAL SECURITY NO. |  |  | EST. HOURS WEEKLY | AREA CODE/TEL.NO. |
| NAME AND TITLE OF CO-INVESTIGATOR (Use attachment if necessary.) |  |  |  |  |  |
| NAME AND TITLE OF INDIVIDUAL(S) AUTHORIZED TO NEGOTIATE CONTRACTS |  |  | AREA CODE/TELEPHONE NUMBER |  |  |
| NAME AND TITLE OF INDIVIDUAL(S) AUTHORIZED TO EXECUTE CONTRACTS |  |  | AREA CODE/TELEPHONE NUMBER |  |  |

DOES THIS PROPOSAL INVOLVE EXPERIMENTS WITH HUMAN SUBJECTS           YES      NO

Institution’s General Assurance re: Human Subjects                                          DATE APPROVED                             PENDING

Institution’s Review Board’s Approval of this Proposal                                       DATE APPROVED                             PENDING

An example of the informed consent for this study is enclosed                            YES      NO

A Clinical Protocol is enclosed                                                                         YES      NO

| OFFEROR’S ACKNOWLEDGMENT OF AMENDMENTS TO THE RFP (Use attachment if necessary) |  |  |  |
| --- | --- | --- | --- |
| ERRATA NUMBER | DATE | ERRATA NUMBER | DATE |
| NAME, ADDRESS, AND PHONE NUMBER OF COGNIZANT GOVERNMENT AUDIT AGENCY |  | NUMBER OF EMPLOYEES CURRENTLY EMPLOYED |  |
|  |  | DOLLAR VOLUME OF BUSINESS PER ANNUM |  |
|  |  | THIS OFFER EXPIRES DAYS FROM THE DATE OF THIS OFFER (120 days if not specified) |  |

FOR THE INSTITUTION

| SIGNATURE OF PRINCIPAL INVESTIGATOR | SIGNATURE OF BUSINESS REPRESENTATIVE |
| --- | --- |
| TYPED NAME AND TITLE | TYPED NAME AND TITLE |
| EMPLOYER IDENTIFICATION NUMBER | DATE OF OFFER |

Provision of the Social Security Number is voluntary.   Authority for requesting this information is provided by Title III, Section 301, and Title IV of the Public Health Service Act, as amended.

BREAKDOWN OF PROPOSED ESTIMATED COST (PLUS FEE)

AND LABOR HOURS

# INSTRUCTIONS FOR USE OF THE FORMAT

Proposals submitted u under this RFP will require cost analyses and or audits of each element of cost proposed.  Offeror(s) will be asked to submit supporting documentation to verify the accuracy of all proposed costs.  Supporting documents will be required for labor rates, equipment, subcontracts, consultant costs, clinical trials costs, and any other significant category.  For further information concerning requirements for Cost or Pricing Data, see Item 24 under Section L.

1.	Refer to Business Proposal Instructions, Section L of this solicitation. The Instructions contain the requirements for proper submission of cost/price data which must be adhered to.

2.	This format has been prepared as a universal guideline for all solicitations issued by the OPHEP/OPHEMC. It may require amending to meet the specific requirements of this solicitation.  For example, this solicitation may require the submission of cost/price data for three years listed on this form.  (See Section L.1., General Information for the estimated duration of this project.)  If this solicitation is phased, identify each phase in addition to each year.  Total each year, phase, and sub-element.

3.	This format must be used to submit the breakdown of all proposed estimated cost elements. List each cost element and sub-element for direct costs, indirect costs and fee, if applicable. In addition, provide detailed calculations for all items. For example:

a.	For all personnel, list the name, title, rate per hour and number of hours proposed. If a pool of personnel is proposed, list the composition of the pool and how the cost proposed was calculated. List the factor used for prorating Year One and the escalation rate applied between years.

Offeror's proposal should be stated in the same terms as will be used to account for and record the effort under a contract.  If percentages of effort are used, the basis to which such percentages are applied must also be submitted by the offeror.  The attached format should be revised to accommodate direct labor proposed as a percentage of effort.

b.	For all materials, supplies, equipment (including binding bids for all equipment greater than $5,000), and other direct costs, list all unit prices, etc., to detail how the calculations were made.

c.	For all indirect costs, list the rates applied and the base the rate is applied to.

d.	For all travel, list the specifics for each trip.

e.	For any subcontract proposed, submit a separate breakdown format.  This shall include cost support, full breakdown of all cost related to subcontracts, and all other internal costs.

f.	Justification for the need of some cost elements may be listed as an attachment, i.e., special equipment, above average consultant fees, etc.

4.	If the Government has provided "uniform pricing assumptions" for this solicitation, the offeror must comply with and identify each item.

5.	It is requested that you use the ELECTRONIC SPREADSHEET that is provided below to prepare your business proposal in lieu of the hardcopy contained in this Attachment.  It is in EXCEL format and has instructions for use and submission.

If you are unable to access this document electronically, you may request a copy from the Contracting Officer identified on the cover page of this solicitation.

For security purposes, please include a hard copy of the completed spreadsheet and submit the electronic file with your proposal.

BREAKDOWN OF PROPOSED ESTIMATED COST AND LABOR HOURS (Sample)

COST SHARING LINE ITEMS ONLY

| COST ELEMENT | Milestone 1 Government Share (Period Covered) | Milestone 1 Contractor Share (Period Covered) |  | Milestone 2 Government Share (Period Covered) | Milestone 2 Contractor Share (Period Covered) | Milestone 3 Government Share (Period Covered) | Milestone 3 Contractor Share (Period Covered) | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| DIRECT LABOR: |  |  |  |  |  |  |  |  |
| Labor Category Rate | (Hours) | (Hours) | (Hours) |  | (Hours) | (Hours) | (Hours) | Total |
| (Title and Name– use additional pages as necessary) |  |  |  |  |  |  |  |  |
| DIRECT LABOR COST: | $ | $ | $ |  | $ | $ | $ | $ |
| MATERIAL COST: | $ | $ | $ |  | $ | $ | $ | $ |
| TRAVEL COST: | $ | $ | $ |  | $ | $ | $ | $ |
| CONSULTANTS: | $ | $ | $ |  | $ | $ | $ | $ |
| SUBCONTRACTS: | $ | $ | $ |  | $ | $ | $ | $ |
| CLINICAL TRIAL/PATIENT CARE COSTS: | $ | $ | $ |  | $ | $ | $ | $ |
| EQUIPMENT | $ | $ | $ |  | $ | $ | $ | $ |
| OTHER DIRECT COSTS | $ | $ | $ |  | $ | $ | $ | $ |
| OTHER (Specify) | $ | $ | $ |  | $ | $ | $ | $ |
| TOTAL DIRECT COST: | $ | $ | $ |  | $ | $ | $ | $ |
| FRINGE BENEFIT COST: (if applicable) % of Direct Labor Cost | $ | $ | $ |  | $ | $ | $ | $ |
| INDIRECT COST: % of Total Direct Cost | $ | $ | $ |  | $ | $ | $ | $ |
| GRAND TOTAL ESTIMATED COST | $ | $ | $ |  | $ | $ | $ | $ |

*The above breakdown shall be used for each milestone in the Statement of Work, including any proposed offeror milestones (refer to milestone five (5) of the statement of work).

BREAKDOWN OF PROPOSED ESTIMATED COST (PLUS FEE) AND LABOR HOURS (Sample)

COST PLUS FIXED FEE LINE ITEMS ONLY

| COST ELEMENT | Milestone 1 (Period Covered) | Milestone 2 (Period Covered) |  | Milestone 3 (Period Covered) | Milestone 4 (Period Covered) | Milestone 8A (Period Covered) | Milestone 8B (Period Covered) | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| DIRECT LABOR: |  |  |  |  |  |  |  |  |
| Labor Category Rate | (Hours) | (Hours) | (Hours) |  | (Hours) | (Hours) | (Hours) | Total |
| (Title and Name– use additional pages as necessary) |  |  |  |  |  |  |  |  |
| DIRECT LABOR COST: | $ | $ | $ |  | $ |  |  | $ |
| MATERIAL COST: | $ | $ | $ |  | $ |  |  | $ |
| TRAVEL COST: | $ | $ | $ |  | $ |  |  | $ |
| CONSULTANTS: | $ | $ | $ |  | $ |  |  | $ |
| SUBCONTRACTS: | $ | $ | $ |  | $ |  |  | $ |
| CLINICAL TRIAL/PATIENT CARE COSTS: | $ | $ | $ |  | $ |  |  | $ |
| EQUIPMENT | $ | $ | $ |  | $ |  |  | $ |
| OTHER DIRECT COSTS | $ | $ | $ |  | $ |  |  | $ |
| OTHER (Specify) | $ | $ | $ |  | $ |  |  | $ |
| TOTAL DIRECT COST: | $ | $ | $ |  | $ |  |  | $ |
| FRINGE BENEFIT COST: (if applicable) % of Direct Labor Cost | $ | $ | $ |  | $ |  |  | $ |
| INDIRECT COST: % of Total Direct Cost | $ | $ | $ |  | $ |  |  | $ |
| TOTAL COST: | $ | $ | $ |  | $ |  |  | $ |
| FEE: % of Total Est. Cost (where applicable) | $ | $ | $ |  | $ |  |  | $ |
| GRAND TOTAL ESTIMATED CPFF | $ | $ | $ |  | $ |  |  | $ |

*The above breakdown shall be used for each milestone in the Statement of Work, including any proposed offeror milestones (refer to milestone five (5) of the statement of work).

OFFEROR’S POINTS OF CONTACT

Complete the following and return with the BUSINESS PROPOSAL.

Name, Title and Address* of Business Representative with whom daily contact is required

| Name: | Telephone: |
| --- | --- |
| Title: | Fax: |
| Office: | E-Mail: |
| Organization: |  |
| *Street Address: |  |
| City, State, Zip Code: |  |

Name, Institutional Title and Address of Proposed Principal Investigator

| Name: | Telephone: |
| --- | --- |
| Title: | Fax: |
| Office: | E-Mail: |
| Organization: |  |
| *Street Address: |  |
| City, State, Zip Code: |  |

Subcontractor(s):  Name, Institutional Title and Address of Proposed Principal Investigator

| Name: | Telephone: |
| --- | --- |
| Title: | Fax: |
| Office: | E-Mail: |
| Organization: |  |
| *Street Address: |  |
| City, State, Zip Code: |  |

These exact addresses are necessary to ensure that contact can be made with the proper individual(s) in the most expeditious manner.

*Please use actual street address, not P.O. Box.

DISCLOSURE OF LOBBYING ACTIVITIES			      Approved by OMB

0348-0046

Complete this form to disclose lobbying activities pursuant to 31 U.S.C. 1352

(See reverse for public burden disclosure.)

| 1. Type of Federal Action: a. contract b. grant c. cooperative agreement d. loan e. loan guarantee f. loan insurance | 2. Status of Federal Action: a. bid/offer/application b. Initial award c. post-award |  |  |  |  | 3. Report Type: a. initial filing b. material change For Material Change Only: year ______ quarter _______ date of last report________ |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 4. Name and Address of Reporting Entity:  Prime  Subawardee Tier_____, if known: Congressional District, if known: |  |  | 5. If Reporting Entity in No. 4 is Subawardee, Enter Name and Address of Prime Congressional District, if known: |  |  |  |  |  |
| 6. Federal Department/Agency: |  |  | 7. Federal Program Name/Description CFDA Number, if applicable: __________________ |  |  |  |  |  |
| 8. Federal Action Number, if known: |  |  | 9. Award Amount, if known: $ |  |  |  |  |  |
| 10. a. Name and Address of Lobbying Entity (if individual, last name, first name, MI): (attach Continuation Sheet(s) |  |  | b. Individual Performing Services (including address if different from No. 10a) (last name, first name, MI) SF-LLL-A, if necessary) |  |  |  |  |  |
| 11. Amount of Payment (check all that apply): $__________  actual  planned |  |  | 13. Type of Payment (check all that apply):  a. retainer  b. one-time fee  c. commission  d. contingent fee  e. deferred  f. other; specify: _____________________________ |  |  |  |  |  |
| 12. Form of Payment (check all that apply):  a. cash  b. in-kind; specify: nature_____________ value______________ |  |  |  |  |  |  |  |  |
| 14. Brief Description of Services Performed or to be Performed and Date(s) of Service, including officer(s), employee(s), or Member(s) contacted, for payment indicated in Item 11: (attach Continuation Sheet(s) SF-LLL-A, if necessary) |  |  |  |  |  |  |  |  |
| 15. Continuation Sheet(s) SF-LLL-A attached: |  | Yes |  | No |  |  |  |  |
| 16. Information requested through this form is authorized by title 31 U.S.C. section 1352. This disclosure of lobbying activities is a material representation of fact upon which reliance was placed by the tier above when this transaction was made or entered into. This disclosure is required pursuant to 31 U.S.C. 1352. This information will be reported to the Congress semi-annually and will be available for public inspection. Any person who fails to file the required disclosure shall be subject to a civil penalty of not less than $10,000 and not more than $100,000 for each failure. |  |  |  |  | Signature:______________________________________ Print Name:_____________________________________ Title:________________________________________ Telephone No.:_________________Date:____________ |  |  |  |
| Federal Use Only |  |  |  |  | Authorized for Local Reproduction Standard Form—LLL |  |  |  |

DISCLOSURE OF LOBBYING ACTIVITIES

CONTINUATION SHEET

Approved by OMB

0348-0046

Reporting Entity:_________________________________________________ Page _____ of _____

Authorized for Local Reproduction

Standard Form--LLL-A

INSTRUCTIONS FOR COMPLETION OF SF-LLL, DISCLOSURE OF LOBBYING ACTIVITIES

This disclosure form shall be completed by the reporting entity, whether subawardee of prime Federal recipient, at the initiation or receipt of a covered Federal action, or a material change to a previous filing, pursuant to title 31 U.S.C. section 1352.  The filing of a form is required for each payment or agreement to make payment to any lobbying entity for influencing of attempting to influence an officer or employee of any agency, a Member of Congress, an officer or employee of Congress, or an employee of a Member of Congress in connection with a covered Federal action.  Use the SF-LLL-A Continuation Sheet for additional information if the space on the form is inadequate.  Complete all items that apply for both the initial filing and material change report.  Refer to the implementing guidance published by the Office of Management and Budget for additional information.

1.	Identify the type of covered Federal action for which lobbying activity is and/or has been secured to influence the outcome of a covered Federal action.

2.	Identify the status of the covered Federal action.

3.	Identify the appropriate classification of this report.  If this is a follow-up report caused by a material change to the information previously reported, enter the year and quarter in which the change occurred.  Enter the date of the last previously submitted report by this reporting entity for this covered Federal action.

4.	Enter the full name, address, city, state and zip code of the reporting entity.  Include Congressional District, if known.  Check the appropriate classification of the reporting entity that designates if it is, or expects to be, a prime or subaward recipient.  Identify the tier of the subawardee, e.g., the first subawardee of the prime is the 1st tier.  Subawards include but are not limited to subcontracts, subgrants and contract awards under grants.

5.	If the organization filing the report in item 4 checks "Subawardee," then enter the full name, address, city, state and zip code of the prime Federal recipient.  Include Congressional District, if known.

6.	Enter the name of the Federal agency making the award or loan commitment.  Include at least one organizational level below agency name, if known.  For example, Department of Transportation, United States Coast Guard.

7.	Enter the Federal program name or description for the covered Federal action (item 1).  If known, enter the full Catalog of Federal Domestic Assistance (CFDA) number for grants, cooperative agreements, loans, and loan commitments.

8.	Enter the most appropriate Federal identifying number available for the Federal action identified in item 1 (e.g., Request for Proposal (RFP) number, Invitation for Bid (IFB) number, grant announcement number, the contract, grant, or loan award number, the application/proposal control number assigned by the Federal agency).  Include prefixes, e.g., "RFP-DE-90-001."

9.	For a covered Federal action where there has been an award or loan commitment by the Federal agency, enter the Federal amount of the award/loan commitment for the prime entity identified in item 4 or 5.

10.	(a)	Enter the full name, address, city, state and zip code of the lobbying entity engaged by the reporting entity  identified in item 4 to influence the covered Federal action.

(b)	Enter the full names of the individual(s) performing services, and include full address if different from 10(a); Enter Last Name, First Name, and Middle Initial (MI).

11.	Enter the amount of compensation paid or reasonably expected to be paid by the reporting entity (item 4) to the lobbying entity (item 10).  Indicate whether the payment has been made (actual) or will be made (planned).  Check all boxes that apply.  If this is a material charge report, enter the cumulative amount of payment made or planned to be made.

12.	Check the appropriate box(es).  Check all boxes that apply.  If payment is made through an in-kind contribution, specify the nature and value of the in-kind payment.

13.	Check the appropriate box(es).  Check all boxes that apply.  If other, specify nature.

14.	Provide a specific and detailed description of the services that the lobbyist has performed, or will be expected to perform, and the date(s) of any services rendered.  Include all preparatory and related activity, not just time spent in actual contact with Federal officials.  Identify the Federal official(s) or employee(s) contacted or the officer(s), employee(s), or Member(s) of Congress that were contacted.

15.	Check whether or not a SF-LLL-A Continuation Sheet(s) is attached.

16.	The certifying official shall sign and date the form, print his/her name, title and telephone number.

Public reporting burden for this collection of information is estimated to average 30 minutes per response, including time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and completing and reviewing the collection of information. Send comments regarding the burden estimate or any other aspect of this collection of information, including suggestions for reducing this burden, to the Office of Management and Budget, Paperwork Reduction Project (0348-0046), Washington, D.C. 20503.

CHART OF ABBREVIATIONS

DHHS/HHS					Department of Health and Human Services

FDA						Food Drug and Administration

USDA						United States Department of Agriculture

CDC						Centers for Disease Control and Prevention

WHO						World Health Organization

A&ME						Agriculture and Mechanical Engineering Design

BLA						Biological License Application

USG						United States Government

CGMP						Current Good Manufacturing Practice

CLIN						Contract Line Item Number

NIH							National Institutes of Health

FAR						Federal Acquisition Regulations

OPHEP						Office of Public Health and Emergency Preparedness

OPHEMC				Office of Public Health and Emergency Medical Countermeasures

RFP				Request for Proposal

CPFF				Cost Plus Fixed Fee

GSA				General Services Administration

FPR				Final Proposal Revision

CWP				Contractor Work Plan

GAO				General Accounting Office

NAICS				North American Industry Classification  System

PART IV – REPRESENTATIONS AND INSTRUCTIONS

Representations, Certifications, and Other Statements of Offerors or Quoters (Negotiated).

- REPRESENTATIONS AND CERTIFICATIONS

Federal Acquisition Circular (FAC 2001-26), published on December 20, 2004, implements the Online Representations and Certifications Application (ORCA) effective on January 1, 2005.  The ORCA became a Federal mandate as published in the Federal Acquisition Circular 2001-26, FAR case 2002-024, and now requires the use of ORCA in Federal solicitations as a part of the proposal submission process.

ORCA is part of the Business Partner Network (BPN) which is a component of the Integrated Acquisition Environment (IAE) E-Gov initiative.  It is a web-based system that centralizes and standardizes the collection, storage and viewing of many of the FAR required representations and certifications previously found in solicitations. With ORCA, you now have the ability to enter and maintain your representation and certification information, at your convenience, via the Internet at http://orca.bpn.gov. In addition, rather than receiving and reviewing paper submissions, government contracting officials can access ORCA and review your information online as a part of the proposal evaluation process. You will no longer be required to submit representations and certifications completed in ORCA with each offer.

The final rule requires offerors to: (a)  provide representations and certifications electronically via the BPN website (www.bpn.gov/orca) thus reducing the administrative burden on vendors who have been submitting the same reps and certs repeatedly for various solicitations,  (b) to maintain the representations and certifications at least annually so they stay current, (c) to make changes that affect only one solicitation by completing sections of specific provisions that are required by the FAR, included in the solicitation.  This will result in a reduced paperwork burden for both offerors and contracting officers thus fulfilling one of the goals of IAE to re-use data as much as possible throughout the Federal procurement life cycle.

To comply with this requirement and to register in ORCA, you will need to have two items: an active Central Contractor Registration (CCR) record and a Marketing Partner Identification Number (MPIN) identified in that CCR record. Your DUNS number and MPIN act as your company’s ID and password into ORCA. (Visit www.ccr.gov for more information on creating and entering your MPIN). The basic information provided in your CCR record is used to pre-populate a number of fields in ORCA. Vendors are reminded to protect their MPIN from unauthorized use.  Once in ORCA you will be asked to review pertinent information pre-populated from CCR, provide a point of contact, and answer a questionnaire that contains up to 26 questions. The questionnaire is to help you gather information you need for the clauses. The questionnaire is not the official version. Be sure to read the provisions carefully.

The answers you provide are then automatically entered into the actual FAR provisions. You are required to review your information, as inserted, in context of the full-text provisions for accuracy; acknowledge three additional read-only provisions; and click a time/date stamp before final submission. You will need to review and/or update your ORCA record when necessary, but at least annually in order to maintain its active status.  Detailed information regarding ORCA, how to submit your record, and whom to call for assistance can be found on ORCA’s homepage at http://orca.bpn.gov  under “Help.”  The ORCA site contains an ORCA Application Handbook and an ORCA Quick Reference Guide.  To access them, simply click on the "Help" link at the top of the ORCA homepage.

IF YOU INTEND TO SUBMIT A PROPOSAL, YOU MUST COMPLY WITH THE ABOVE REQUIREMENT.

(See FAR Clause 52.204-8 listed I.3.)

SECTION L - INSTRUCTIONS, CONDITIONS, AND NOTICES TO OFFERORS

The following information is specific to this solicitation.

I.	GENERAL INFORMATION

ITEM 1:	FAR Clause 52.215-1, INSTRUCTIONS TO OFFERORS-COMPETITIVE ACQUISTION (Jan 2004), and its Alternate I are applicable to this solicitation.

In accordance with HHSAR 352.215-1, paragraph (e) is substituted for subparagraph (e) of the provision at FAR 52.215-1.

(e)Restriction on disclosure and use of data.

(1) The proposal submitted in response to this request may contain data (trade secrets; business data, e.g., commercial information, financial information, and cost and pricing data; and technical data) which the offeror, including its prospective subcontractor(s), does not want used or disclosed for any purpose other than for evaluation of the proposal. The use and disclosure of any data may be so restricted; provided, that the Government determines that the data is not required to be disclosed under the Freedom of Information Act, 5 U.S.C. 552, as amended, and the offeror marks the cover sheet of the proposal with the following legend, specifying the particular portions of the proposal which are to be restricted in accordance with the conditions of the legend. The Government's determination to withhold or disclose a record will be based upon the particular circumstances involving the record in question and whether the record may be exempted from disclosure under the Freedom of Information Act. The legend reads: Unless disclosure is required by the Freedom of Information Act, 5 U.S.C. 552, as amended, (the Act) as determined by Freedom of Information (FOI) officials of the Department of Health and Human Services, data contained in the portions of this proposal which have been specifically identified by page number, paragraph, etc. by the offeror as containing restricted information shall not be used or disclosed except for evaluation purposes.

The offeror acknowledges that the Department may not be able to withhold a record (data, document, etc.) nor deny access to a record requested pursuant to the Act and that the Department's FOI officials must make that determination. The offeror hereby agrees that the Government is not liable for disclosure if the Department has determined that disclosure is required by the Act.

If a contract is awarded to the offeror as a result of, or in connection with, the submission of this proposal, the Government shall have right to use or disclose the data to the extent provided in the contract. Proposals not resulting in a contract remain subject to the Act.

The offeror also agrees that the Government is not liable for disclosure or use of unmarked data and may use or disclose the data for any purpose, including the release of the information pursuant to requests under the Act. The data subject to this restriction are contained in pages (insert page numbers, paragraph designations, etc. or other identification).

(2) In addition, the offeror should mark each page of data it wishes to restrict with the following statement:  "Use or disclosure of data contained on this page is subject to the restriction on the cover sheet of this proposal or quotation."

(3) Offerors are cautioned that proposals submitted with restrictive legends or statements differing in substance from the above legend may not be considered for award. The Government reserves the right to reject any proposal submitted with a nonconforming legend.

As prescribed in FAR 15.209(a)(1), the following paragraph (f)(4) is substituted for the paragraph (f)(4) of the basic provision:

(f)(4)  The Government intends to evaluate proposals and award a contract after conducting discussions with offerors whose proposals have been determined to be within the competitive range. If the Contracting Officer determines that the number of proposals that would otherwise be in the competitive range exceeds the number at which an efficient competition can be conducted, the Contracting Officer may limit the number of proposals in the competitive range to the greatest number that will permit an efficient competition among the most highly rated proposals. Therefore, the offeror's initial proposal should contain the offeror's best terms from a price and technical standpoint.

ITEM 2:	NAICS CODE AND SIZE STANDARD

Note: The following information is to be used by the offeror in preparing its Representations and

Certifications (See Section K of this RFP), specifically in completing the provision entitled, SMALL BUSINESS PROGRAM REPRESENTATION, FAR Clause 52.219-1.

(1) The NAICS Code is 325414.

(2) The small business size standard is 500 employees.

ITEM 3:	THIS REQUIREMENT IS NOT SET-ASIDE FOR SMALL BUSINESS. However, the Federal Acquisition Regulation (FAR) requires in every solicitation, (except for foreign acquisitions) the inclusion of the North American Industry Classification System (NAICS) Code and corresponding size standard which best describes the nature of the requirement in the solicitation.

ITEM 4:	TYPE OF CONTRACT AND NUMBER OF AWARD(S)

It is anticipated that one or more awards will be made from this solicitation and that the award(s) will be made on/about October 31, 2006.

It is anticipated that the award(s) from this solicitation will be a multiple-year, cost-reimbursement, completion type contract, with a period of performance of seven (7) to eight (8) years as agreed to during negotiations, and that incremental funding will be used.

ITEM 5.	PRE-PROPOSAL CONFERENCE

The decision to have this conference depends largely on the lead-time available to the Government for research in connection with questions submitted by offerors.   Currently, there is no plan to hold a pre-proposal conference for this requirement.  If a pre-proposal conference is planned, a notice will be posted on the Federal Business Opportunities website for this RFP.

Questions about this RFP should be submitted to the primary point of contact specified in Block 13 of page 2 of the solicitation and the envelope/subject line should be marked, “RFP No. DHHS-ORDC-VB-06-07.”  Letters containing questions can also be faxed to 202-205-3915.   A set of all questions and answers will be posted as an amendment to the RFP in the FedBizOpps at the conclusion of the conference.  Any questions concerning the RFP should be submitted in writing to Mekeba Barrett, Contract Specialist, no later than August 3, 2006

In the event a pre-proposal conference is held, because of space limitations, each prospective offeror shall be limited to a total of 3 representatives.  Attendance at the pre-proposal conference is recommended; however, attendance is not a prerequisite for proposal submission and will not be considered a factor in proposal evaluation.

ITEM 6.	PRE-AWARD SITE VISIT

A pre-award site visit MAY be held to inspect the proposed facilities of offerors determined to be within the competitive range.  The pre-award site visit will be held for the purpose of verifying the information presented in the proposal including but not limited to the condition, size, security and feasibility for retrofitting of the facility being proposed under this RFP.

Reasonable notification will be given to the offerors within the competitive range, prior to a planned pre-award site visit.  In the event of a pre-award site visit, the contractor should plan on a one (1) day site-visit by Government personnel to the facility being proposed in this RFP.

ITEM 7:	COMMITMENT OF PUBLIC FUNDS

The Contracting Officer is the only individual who can legally commit the Government to the expenditure of public funds in connection with the proposed procurement.  Any other commitment, either explicit or implied, is invalid.

ITEM 8:	COMMUNICATIONS PRIOR TO CONTRACT AWARD

Offerors shall direct all communications to the attention of the Contract Specialist or Contracting Officer cited on the face page of this RFP.  Communications with any other Government official regarding this RFP is strictly prohibited and may disqualify your proposal for further consideration.

ITEM 9:	SERVICE OF PROTEST (AUGUST 1996) - FAR 52.233-2

(a) Protests, as defined in section 33.101 of the Federal Acquisition Regulation, that are filed directly with an agency, and cop  ies of any protests that are filed with the General Accounting Office (GAO), shall be served on the Contracting Officer (Complete address and contact information can be found on the SOLICITATION/OFFER and AWARD cover page, Block 7, of the RFP) by obtaining written and dated acknowledgment of receipt.

(b) The copy of any protest shall be received in the office designated above within one day of filing a protest with the GAO.

ITEM 10:	LATE PROPOSALS AND REVISIONS, HHSAR 352.215-70, is applicable to this solicitation.

II. GENERAL INSTRUCTIONS

ITEM 11:	AUTHORIZED OFFICIAL AND SUBMISSION OF PROPOSAL

The proposal must be signed by an official authorized to bind your organization and must stipulate that it is predicated upon all the terms and conditions of this RFP. Your proposal shall be submitted in the number of copies, to the addressees, and marked as indicated in the Attachment entitled,

PACKAGING AND DELIVERY OF PROPOSAL, Part III, Section J hereof. Proposals will be typewritten, paginated, reproduced on letter size paper and will be legible in all required copies. To expedite the proposal evaluation, all documents required for responding to the RFP should be placed in the following order:

I. COVER PAGE

Include RFP title, number, name of organization, DUNS No., identification of the proposal part, and indicate whether the proposal is an original or a copy.

II. TECHNICAL PROPOSAL

It is recommended that the technical proposal consist of a cover page, a table of contents, and the information requested in the Technical Proposal Instructions and as specified in SECTION J, List of Attachments.

III. BUSINESS PROPOSAL

It is recommended that the business proposal consist of a cover page, a table of contents, and the information requested in the Business Proposal Instructions and as specified in SECTION J, List of Attachments.

ITEM 12:    Alternate Proposals

The offeror may, at its discretion, submit alternate proposals or proposals that deviate from this solicitation’s requirements; provided that the offeror also submits a proposal for performance of the work as specified in the statement of work. Alternate proposals may be considered if performance would be improved or not compromised, and if they are in the best interest of the Government. Alternate proposals, or deviations from any requirements of this RFP, must be clearly identified.

ITEM 13:	Use of the Metric System of Measurement

It is the policy of the Department of Health and Human Services to support the Federal transition to the metric system and to use the metric system of measurement in all procurements, grants, and other business related activities unless such use is impracticable or is likely to cause significant inefficiencies.

The offeror is encouraged to prepare their proposal using either "Hard Metric," "Soft Metric," or "Dual Systems" of measurement. The following definitions are provided for your information:

Hard Metric - The replacement of a standard inch-pound size with an accepted metric size for a particular purpose. An example of size substitution might be: selling or packaging liquids by the liter instead of by the pint or quart (as for soft drinks), or instead of by the gallon (as for gasoline).

Soft Metric - The result of a mathematical conversion of inch-pound measurements to metric equivalents for a particular purpose. The physical characteristics are not changed.

Dual Systems - The use of both inch-pound and metric systems. For example, an item is designed, produced, and described in inch-pound values with soft metric values also shown for information or

comparison purposes.

ITEM 14:	Potential Award Without Discussions, The Government reserves the right to award a contract without discussions if the Contracting Officer determines that the initial prices are fair and reasonable and that discussions are not necessary.

- ITEM 15: 	Small Business Subcontracting Plan, is applicable to this solicitation and the following information is provided to supplement this item to assist in proposal preparation.  A Subcontracting Plan must be submitted with the original proposal and will be subject to negotiations if your proposal is determined to be in the competitive range.  Small Business Subcontracting Plan Format (must be submitted with your original Business Proposal) http://www.hhs.gov/osdbu/forms.html

The anticipated minimum subcontracting goals for this RFP are as follows:

- 23% for Small Business

- 5% for Small Disadvantaged Business

- 5% for Women-Owned Small Business

- 3% for HUBZone Small Business

- 3% for Veteran-Owned Small Business

- 3% Service-Disabled Veteran-Owned Small Business.

ITEM 16:	Extent of Small Disadvantaged Business Participation is applicable to this solicitation.

ITEM 17:	Past Performance Information is applicable to this solicitation and the following information is provided to supplement this item to assist in proposal preparation:

Past Performance information shall be submitted as part of the Business proposal.

1. Offerors shall submit the following information as part of their business proposal for both the Offeror and proposed major subcontractors.

2. The Offeror shall provide a list of the last three (3) contracts completed during the past three years and all contracts currently in process. Contracts listed may include those entered into by the Federal Government, agencies of state and local governments and commercial customers. Offerors that are newly formed entities without prior contracts should list contracts as required above for all key personnel:

a. Name of Contracting Organization

b. Contract Number

c. Total Contract Value

d. Description of Requirement

e. Contract Officer's name and telephone number

ITEM 18:	Solicitation Provisions Incorporated by Reference: The following provisions are applicable to this solicitation.

Facilities Capital Cost of Money, FAR Clause 52.215-16, (June 2003).

Order of Precedence-Uniform Contract Format, FAR Clause 52.215-8, (October 1997).

Preaward On-Site Equal Opportunity Compliance Evaluation, (Over $10,000,000), FAR Clause

52.222-24, (February 1999).

### III.	TECHNICAL PROPOSAL INSTRUCTIONS

ITEM 19:	Human Subjects, is applicable to this solicitation.  See the Statement of Work and Section M.5 for additional information concerning human subjects.

ITEM 20: Animal Welfare Assurance

### The Contractor shall obtain, prior to the start of any work under this contract, an approved Animal Welfare Assurance from the Office of Human Research Protections (OHRP), Office of the Director, NIH, as required by Section I-43-30 of the Public Health Service Policy on Humane Care and Use of Laboratory Animals. The Contractor shall maintain such assurance for the duration of this contract, and any subcontractors performing work under this contract involving the use of animals shall also obtain and maintain an approved Animal Welfare Assurance.

Offerors must submit their plan on how they will comply with all requirements concerning the use of animals for experimentation and be in accordance with any requirements specified in the http://grants.nih.gov/grants/olaw/olaw.htm.

ITEM 21: Technical Proposal Instructions

TECHNICAL PROPOSAL INSTRUCTIONS

General Comment:  Offerors may identify tasks, among those described in this solicitation, for which they plan to utilize subcontractors.  This approach is encouraged if it allows the offeror to more efficiently perform the numerous responsibilities required by this project.  Offerors should describe the activities to be subcontracted, the method and level of integration between the prime and any proposed subcontractor(s), and the expected advantages of such an approach.

The technical proposal may not exceed 40 pages.  The appendix of the technical proposal may note exceed 250 pages. The technical proposal should provide specific information addressing the elements listed in the Statement of Work and those specified below

(a)  General Instructions:

(1)Minimum Mandatory Requirements Instructions:  This shall consist of the Offeror’s complete information necessary to demonstrate the Offeror fully meets the mandatory criteria for elgibility described in section C. The offeror shall include a summary that clearly addresses each mandatory criteria as described in Section C.  The mandatory criteria for eligibility shall include enough information to demonstrate that the offeror meets the mandatory criteria for eligibility.  This section of your technical proposal shall be clearly marked and  shall not exceed one (two-sided) page in length and will be used alone to evaluate and establish if the offeror meets the mandatory criteria for eligibility.  Those summaries failing to meet the mandatory criteria for eligibility will be eliminated from further review and consideration.  Offerors that DO NOT demonstrate that they meet these mandatory criteria for eligibility will be ineligible for award, and proposals submitted by these Offerors will not be further evaluated.  This evaluation shall be subjective and based upon the content, completeness, and thoroughness of the data submitted.  In order to be considered for further evaluation as shown under the technical evaluation criteria in Section M, offerors must fully meet all of the mandatory criteria for eligibility described in section C of this solicitation.

(2)Proposals which merely offer to conduct a program in accordance with the requirements of the Government’s statement of work will not be eligible for award.  The technical proposal should contain an explanation of the proposed technical approach in conjunction with the tasks to be performed in achieving the project objectives.

(3)	A detailed work plan must be submitted indicating how each aspect of the statement of work is to be accomplished. This plan should be in as much detail as considered necessary to fully explain your proposed technical approach or method. This includes technology transfer and area/equipment qualification after each manufacturing step.  The technical proposal should reflect a clear understanding of the nature of the work being undertaken.

(4) The proposal will include a Contractor Work Plan (CWP) that describes the activities to be performed in response to the RFP requirements and a single Gantt chart to include all activities described in the CWP with a time-phased and task-linked budget.  The level of detail contained in the CWP and the corresponding Gantt chart will be sufficient to facilitate management and execution of the contract by the successful offeror.

(5)  Description of the key scientific, technical and managerial risks posed by the project and plans to mitigate such risks.

(6)	The technical proposal must include information on how the project is to be organized, staffed, and managed. This information should demonstrate your understanding of important events or tasks and their management. You must explain how the management and coordination of consultant and/or subcontractor efforts will be accomplished.

(7)	The technical proposal must list the names and proposed duties of the professional personnel, consultants, and key subcontractor employees assigned to the project. Their resumes should be included and should contain information on education, background, recent experience, and specific or technical accomplishments. The approximate percentage of time each individual will be available for this project must be stated. The proposed staff hours of each individual should be allocated against each project task or subtask.

(8)  Go/No Go decision tree with quantitative and qualitative criteria for evaluating the scientific and engineering merit of progressing to the next stage of the project.

(9)	The technical proposal must provide the general background, experience, and qualifications of the organization. Similar or related contracts, subcontracts, or grants should be included and contain the name of the customer, contract or grant number, dollar amount, time of performance, and the names and telephone numbers of the project officer and contracting officer/grants officer.

(10)	The technical proposal must contain a discussion of present or proposed facilities and equipment that will be used in the performance of the contract.  Further, the Offeror shall submit a Draft Security Plan addressing Security of Contract Operations as outlined in the SOW.

(11) The technical proposal must not contain reference to cost; however, resource information, such as data concerning labor hours and categories, material, subcontracts, etc., must be contained in the technical proposal so that your understanding of the statement of work can be evaluated.  See Attachment entitled “TECHNICAL PROPOSAL COST INFORMATION/SUMMARY OF LABOR AND DIRECT COSTS (Sample)” in Section J. for recommended format.

The technical proposal must be prepared and submitted in the following format and, as a minimum, must include the following including the offerors demonstrated ability to meet the absolute criteria for eligibility outlined in Section M:

The technical proposal should be prepared and submitted, in a format to facilitate proposal evaluation, in accordance with the criteria specified in Section M. hereof, i.e., the proposal should contain a separate section addressing the offerors ability to meet the mandatory criteria for eligibility; a separate section addressing the offerors understanding and purpose of the problem; a separate section addressing the offerors understanding of the methodology and technical approach; a separate section addressing the offerors organizational experience and personnel; a separate section addressing the offerors facilities, and a separate section addressing the offerors past performance information.

### IV.	BUSINESS PROPOSAL INSTRUCTIONS

ITEM 22: 	Proposal Cover Sheet, is applicable to this solicitation and is included under Section J

ITEM 23:	Requirements for Cost or Pricing Data or Information Other than Cost and Pricing Data [FAR Clause 52.215-20 (October 1997)], is applicable to this solicitation.

ITEM 24: 	Incremental Funding is applicable to this solicitation.

ITEM 25:   Contractor shall provide a cost breakdown of all key elements in their proposal to meet milestone five (5) of the statement of work.  Contractor shall list cost and cost plus fixed fee for these elements on the table in Section B.5.

SECTION M - EVALUATION FACTORS FOR AWARD

GENERAL

Selection of an Offeror for contract award will be based on an evaluation of proposals against four factors.  The non-cost factors in order of importance are:  technical, past performance and Small Disadvantaged Business (SDB) participation.  In addition, prior to award, the Offeror’s proposal must be considered acceptable for use of human subjects and animal welfare.  Offerors are advised that in the evaluation process, all evaluation factors other than cost or price, when combined, are significantly more important than cost or price.  Technical activities must connect directly to costs in the business proposal.  The trade off process described in FAR 15.101-1 may be employed.  This process permits tradeoffs among cost/price and non-cost factors and allows the USG to consider award (s) to other than the lowest priced or highest technically rated Offeror. In any case, the Government reserves the right to make an award(s) to that Offeror whose proposal provides the best overall value to the Government. For the purposes of section C and M of this RFP, the U.S. is defined as the fifty states, the District of Columbia, and Puerto Rico.

The evaluation will be based on the demonstrated capabilities of the prospective Contractors in relation to the needs of the project as set forth in the RFP.  The merits of each proposal will be evaluated carefully.  Each proposal must document the feasibility of successful implementation of the requirements of the RFP.  Offerors must submit information sufficient to evaluate their proposals based on the detailed criteria listed below.

Contract(s) will be awarded to the Offeror(s) whose proposal is considered to be the most advantageous to the Government, cost and other factors (identified below) considered. Each Offeror must submit a proposal that separately addresses evaluation criteria specified below as they relate to the statement of work and delivery requirements.

M.1. Mandatory Criteria for Eligibility

The offeror shall meet ALL of the mandatory criteria for eligibility from the date of contract award throughout the life of this contract or as modified.  The mandatory criteria for eligibility are described in Section C.  The offeror shall provide an index, matrix, or dedicated section in the technical proposal that will address each particular mandatory criteria for eligibility.

1a. Organization

The Offeror may be one of the following types of organizations or companies:

- A single, fully integrated and independent pharmaceutical company

- Research or Academic Institution.

- Partnership of a Prime Contractor with legitimate subsidiary or corporate partner that performs U.S.-based manufacturing of vaccine or other medical devices.

- Consortium with the Offeror as the Prime Contractor and Subcontractors such as Contract Manufacturing Organizations and/or Contract Research Organizations as members that perform U.S.-based vaccine manufacturing and/or clinical studies.

- The Offeror will be required to propose cost sharing for this requirement.  At a minimum the contractor will be required to fund twenty-five (25%) of the total cost of the project.

1b. Manufacturer of FDA licensed biological product

- For bulk manufacturing and/or fill finish, the facility is currently used to manufacture FDA-licensed biological product.

1c. Proposed Manufacturing Location and Commitment to Produce Products Suitable for Stockpiling

The proposed manufacturing site shall be located in the U.S.  The Offeror shall provide written evidence of a firm commitment by the Offeror that the Offeror will establish and maintain the facility for pandemic vaccine production.

2.  Timeline and Intent for U.S. Product Licensure

Given the ongoing threat of an influenza pandemic, it is essential that efforts funded as a result of this requirement lead to FDA approval of a facility that can be used to produce pandemic vaccines to protect the U.S. population in the event of an influenza pandemic. Therefore, Offerors must commit to the following to be considered for award:

  - Provision of a clear and comprehensive plan and timeline for FDA licensure of the facility presented in the proposal.

    - Including a description of key scientific, technical and managerial risks posed by the project, and plans to mitigate such risks

    - Go/No Go decision tree with quantitative and qualitative criteria for evaluating the scientific and engineering merit of progressing to the next stage of the project.

  - Submission of a BLA supplement for the licensed influenza vaccine product manufactured in the proposed commercial scale manufacturing facility within thirty (30) months of a contract award. (For bulk manufacturing and/or fill/finish facility proposals only)

M.2. Technical Evaluation Criteria

Each set of proposals shall be evaluated according to the criteria and points as set forth below:

| Evaluation Criteria | Points |
| --- | --- |
| 1. Methodology and Approach | 30 |
| 2. Facilities | 30 |
| 3. Organizational Experience | 15 |
| 4. Personnel | 10 |
| 5. Timeline to licensure | 15 |
| TOTAL | 100 |

1. Methodology and Approach

(a) The technical proposal shall provide a Contractor's Work Plan (CWP) that describes the activities to be performed in response to the RFP requirements and a single Gantt chart to include all activities described in the CWP with a time-phased and task-linked budget specifying activities to be supported by the government. The level of detail contained in the CWP and the corresponding Gantt chart should be sufficient to facilitate management and execution of the contract by the successful Offeror(s).

(b) The technical proposal must list biological products currently and previously manufactured at the proposed facilities. For proposed bulk and/or fill finish manufacturing, the Offeror must identify FDA licensed biological products which are currently manufactured at the proposed facilities. The proposal shall provide a brief description of the manufacturing process. The proposal shall describe location and the biosafety containment of the facilities.

(c) The technical proposal must describe in detail the Offeror’s approach to adapt the facilities for manufacturing of pandemic influenza vaccines. The proposal must describe in detail the manufacturing process for pandemic influenza vaccine. If the Primary Contractor does not manufacture FDA licensed influenza vaccine, the proposal should address the extent to which the Prime Contractor has unencumbered access to vaccine production technology. The proposal must describe in detail the biocontainment and physical security of the proposed facility.  The proposal shall describe a validation master plan for facility, process and release assays, equipment and system. The proposal shall address the regulatory approval path. The proposal shall describe how the manufacturing activities related to production of commercial biological products and pandemic influenza vaccines in the newly retrofitted facilities will be coordinated.

(d) The technical proposal should describe in detail the Offeror’s work plan, including cost sharing ratios, to complete all activities identified in the statement of work. Discuss phasing and integration of development of pandemic vaccines and facility related activities.  Indicate anticipated difficulties in carrying out the SOW and potential approaches to overcome them. Decision trees for the critical pathway for product development should be provided for manufacturing facility, clinical evaluation, and regulatory licensure plan.

(e) The technical proposal should describe the extent to which the Offeror has unencumbered access to intellectual property necessary to fulfill its obligations under the contract.   Accordingly, the U.S. Government requires written evidence of the extent to which the Offeror has secured access to such intellectual property, know-how and tangible materials for influenza vaccine manufacturing at the adapted/retrofitted manufacturing facility.  The U.S. Government expects and intends to require that the Offeror will take all steps necessary to secure this access.

2. Facilities

The proposal shall describe the Offeror’s current manufacturing facilities. As application for bulk and/or fill finish manufacturing facilities, the proposal shall describe the current manufacturing activities, including FDA licensed biological product. The proposal shall summarize findings of FDA’s last three inspections.   The proposal shall discuss cleaning and changeover procedures between production of commercial biological products and pandemic influenza vaccines. For pilot facilities, the proposal shall describe the level of biocontainment and shall list products manufactured in the facilities within the past three years.

3. Organizational Experience

The proposal should describe current programs for vaccine or other biological product, evaluation, licensure, and production to document organizational capabilities to complete proposed activities, achieve regulatory approvals, and successfully produce biological products. The proposal shall describe how the Offeror will interact with A&ME firm, construction and other contractors.

4. Personnel

(a) The technical proposal should provide the name of the Principal Investigator (PI)/Project Director responsible for the overall implementation of the contract, Co-investigators and key participants for technical aspects of the project. Describe the qualifications, experience, and accomplishments of the PI, Co-investigators, and key participants. Include, in an attachment, curricula vitae of supervisors and key technical personnel, and the approximate percentage of time each will be available for this program.

(c) The technical proposal should describe the experience and qualifications of other personnel who will be assigned to work on this program. Using organizational charts, show the composition of task or work groups by project area. Document the general qualifications of work groups and recent experience with similar programs.

(c) The technical proposal should list names, titles, and proposed duties of additional personnel, if any, who will be required for full-time employment or on a subcontract or consultant basis. Indicate the technical areas, character, and extent of subcontract or consultant activities and anticipated sources. For all proposed personnel who are not currently members of Offeror's staff, provide a letter of commitment or other evidence of availability. The letter of commitment must at a minimum include (1) the specific items or expertise they will provide; (2) their availability to the project and the amount of time anticipated; (3) their willingness to act as a consultant and (4) how rights to publication and patents will be handled.

5. Timeline to licensure

The proposal shall provide a timeline for seeking FDA licensure of using the facility to manufacture influenza vaccine.

M.3. Past Performance Information

1. Offerors shall submit the following informality as part of their business proposal for both the Offeror and proposed major subcontractors:

2. The Offeror shall provide a list of the last three (3) contracts completed during the past three years and the last (3) contracts awarded currently in process that are similar in nature to the solicitation work scope. Contracts listed may include those entered into by the Federal Government, agencies of state and local governments and commercial customers. Offerors that are newly formed entities without prior contracts should list contracts as required above for all key personnel:

a. Name of Contracting Organization

b. Contract Number

c. Total Contract Value

d. Description of Requirement

e. Contract Officer's name and telephone number

f. Program Manager's name and telephone number

3. Each Offeror will be evaluated on their performance under existing and prior contracts for similar products or services. Performance information will be used for both responsibility determinations and as an evaluation factor against which the Offerors relative rankings will be compared to assure the best value to the Government. The Government will focus on information that demonstrates quality of performance relative to the size and complexity of the acquisition under consideration. The government is not required to contact all references provided by the Offeror, and references other than those identified by the Offeror may be contacted by the Government to obtain additional information that will be considered in the evaluation of the Offerors past performance.

4. An evaluation of Offeror's past performance information will be conducted subsequent to the technical evaluation.  However, this evaluation will not be conducted on any Offeror whose proposal would not be selected for award based on the results of the evaluation of factors other than past performance.

5. The evaluation will be based on information obtained from references provided by the Offeror, other relevant past performance information obtained from other sources known to the Government, and any information supplied by the Offeror concerning problems encountered on the identified contracts and corrective action taken.

The Government will assess the relative risks associated with each Offeror.  Performance risks are those associated with an Offeror's likelihood of success in performing the acquisition requirements as indicated by that Offeror's record of past performance.

The assessment of performance risk is not intended to be the product of a mechanical or mathematical analysis of an Offeror's performance on a list of contracts but rather the product of subjective judgment by the Government after it considers all available and relevant information.

When assessing performance risks, the Government will focus on the past performance of the Offeror as it relates to all acquisition requirements, such as the Offeror's record of performing according to specifications, including standards of good workmanship; the Offeror's record of controlling and forecasting costs; the Offeror's adherence to contract schedules, including the administrative aspects of performance; the Offeror's reputation for reasonable and cooperative behavior and commitment to customer satisfaction; and generally, the Offeror's business-like concern for the interest of the customer.

The Government will consider the currency and relevance of the information, source of the information, context of the data, and general trends in the Offeror's performance.

The lack of a relevant performance record may result in an unknown performance risk assessment, which will neither be used to the advantage nor disadvantage of the Offeror.

The following rating method shall be used in the evaluation of past performance information:

+2	Excellent - Based on the Offeror's performance record, no doubt exists that the Offeror will successfully perform the required effort.  Sources of information are consistently firm in stating that the Offeror's performance was superior and that they would unhesitatingly do business with the Offeror again.

+1	Good - Based on the Offeror's performance record, little doubt exists that the Offeror will successfully perform the required effort.  Sources of information state that the Offeror's performance was good, better than average, etc., and that they would do business with the Offeror again.

0 Average – Based on the Offeror’s performance record, some doubt exists that the Offeror will successfully perform the required effort.  Sources of information indicate that the Offeror’s performance is average or that favorable reports are offset by unfavorable reports.

-1	Marginal - Based on the Offeror's performance record, some doubt exists that the Offeror will successfully perform the required effort.  Sources of information make unfavorable reports about the Offeror's performance and express concern about doing business with the Offeror again.

-2	Poor - Based on the Offeror's performance record, serious doubt exists that the Offeror will successfully perform the required effort.  Sources of information consistently stated that the Offeror's performance was entirely unsatisfactory and that they would not do business with the Offeror again.

M. 4. EXTENT OF SMALL DISADVANTAGED BUSINESS PARTICIPATION

SDB participation will not be scored, but the Government’s conclusions about overall commitment and realism of the Offeror’s SDB Participation targets will be used in determining the relative merits of the Offeror’s proposal and in selecting the Offeror whose proposal is considered to offer the best value to the Government.

The extent of the Offeror’s Small Disadvantaged Business Participation Targets will be evaluated before determination of the competitive range.  Evaluation of SDB participation will be assessed based on consideration of the information presented in the Offeror’s proposal. The Government is seeking to determine whether the Offeror has demonstrated a commitment to use SDB concerns for the work that it intends to perform.

Offers will be evaluated on the following sub-factors:

Extent to which SDB concerns are specifically identified

Extent of commitment to use SDB concerns

Complexity and variety of the work SDB concerns are to perform

Realism of the proposal

Past performance of Offerors in complying with subcontracting plan goals for SDB concerns and monetary targets for SDB participation

Extent of participation of SDB concerns in terms of the value of the total acquisition.

M.5. STUDIES THAT INVOLVE HUMAN SUBJECTS

This research project involves human subjects. HHS Policy requires that women and members of minority groups and their subpopulations and children must be included in the study population of research involving human subjects, unless a clear and compelling rationale and justification is provided with respect to the health of the subjects or the purpose of the research.

Where inclusion of women, minority populations, and/or children is not feasible, a detailed rationale and justification for exclusion of one or both groups from the study population must be submitted with the technical proposal.  The HHS will review the rationale to determine if it is appropriate with respect to the health of the subjects and/or the purpose of the research.  If the rationale is not considered acceptable by the Government and you are included in the competitive range, you will be afforded the opportunity to further discuss and/or clarify your position during discussions or include women, minorities and/or children in your Final Proposal Revision (FPR).  If your exclusion position is still considered unacceptable by the Government after discussions, your proposal may not be considered further for award.

HUMAN SUBJECT EVALUATION

1. This project may involve human subjects.  HHS Policy requires:

  - Protection of Human Subjects from Research Risks

The offeror’s proposal must address the involvement of human subjects and protections from research risk relating to their participation, or provide sufficient information on the research subjects to allow a determination by Institute that a designated exemption is appropriate.

If you claim that this research should be considered exempt from coverage by the Federal Regulations at 45 CFR 46, the proposal should address why you believe it is exempt, and under which exemption it applies.

The reviewers will evaluate the proposal and provide a narrative with regard to four issues: Risks to Human Subjects, Adequacy of Protection Against Risks, Potential Benefits of the Proposed Research to the Subjects and Others, and Importance of the Knowledge to be Gained.  See Section L for a complete discussion of what is required to be addressed for each of these issues. Based on the response to this criterion, this section of the proposal may be rated “unacceptable” (i.e., concerns are identified as to the protections described against risk to human subjects or no discussion is found regarding protections against risk to human subjects) or “acceptable”.

If your discussion regarding the protection of human subjects from research risks is rated “unacceptable” and the Government includes your proposal in the competitive range (for competitive proposals), or if the Government holds discussions with the selected source (for sole source acquisitions), you will be afforded the opportunity to further discuss and/or clarify your position during such discussions and in your Final Proposal Revision (FPR).  If, after discussions, your proposed plan for the protection of human subjects from research risks is still found unacceptable,  your proposal may not be considered further for award.

  - Data and Safety Monitoring

The offeror’s proposal must include a general description of the Data and Safety Monitoring Plan for all clinical trials.  The principles of data and safety monitoring require that all biomedical and behavioral clinical trails be monitored to ensure the safe and effective conduct of human subjects research, and to recommend conclusion of the trial when significant benefits or risks are identified or if it is unlikely that the trial can be concluded successfully.  Risks associated with participation in research must be minimized to the extent practical and the method and degree of monitoring should be commensurate with risk.  Additionally, all plans must include procedures for adverse event reporting.  Finally, generally, for Phase III clinical trials, the establishment of a Data and Safety Monitoring Board (DSMB) is required, whereas for Phase I and II clinical trials, the establishment of a DSMB is optional.  The reviewers should refer to the Statement of Work and Section L in the solicitation, as well as any further technical evaluation criteria in this Section M, as applicable, for the solicitations specific requirements for data and safety monitoring.

As a part of the evaluation for proposals, the reviewers will provide a narrative that describes the acceptability of the proposed data and safety monitoring plan with respect to the potential risks to human participants, complexity of study design, and methods for data analysis.  Based on the evaluation of the response to this criterion, this section of the proposal may be rated “unacceptable” (i.e., concerns are identified as to the adequacy of the monitoring plan or no discussion can be found regarding the proposed monitoring plans) or “acceptable.”

If the information provided regarding Data and Safety Monitoring is rated “unacceptable” and the Government includes your proposal in the competitive range (for competitive proposals), or if the Government holds discussions with the selected source (for sole source acquisitions), you will be afforded the opportunity to further discuss and/or clarify your plan during such discussions and in your Final Proposal Revision (FPR).  If, after discussions, the plan is still considered “unacceptable,” your proposal may not be considered further for award.

  - Women and Minorities

Women and members of minority groups and their subpopulations must be included in the study population of research involving human subjects, unless a clear and compelling rationale and justification are provided indicating that inclusion is inappropriate with respect to the health of the subjects or the purpose of the research.  In addition, for NIH-Defined Phase III clinical trials, all proposals and/or protocols must provide a description of plans to conduct analyses, as appropriate, to detect significant differences in intervention effect (see NIH Guide , Definitions - Significant Difference) by sex/gender, racial/ethnic groups, and relevant subpopulations, if applicable, unless the Government has specified that this solicitation involves a sex/gender specific study or a single or limited number of minority population groups.  The proposal also must include one of the following plans:

- Plans to conduct valid analysis to detect significant differences in intervention effect among sex/gender and/or racial/ethnic subgroups when prior studies strongly support these significant differences among subgroups, OR

- Plans to include and analyze sex/gender and/or racial/ethnic subgroups when prior studies strongly support no significant differences in intervention effect between subgroups (representation of sex/gender and/or racial/ethnic groups as subject selection criterion is not required; however, inclusion and analyses are encouraged), OR

- Plans to conduct valid analyses of the intervention effect in sex/gender and/or racial/ethnic subgroups (without requiring high statistical power for each subgroup) when the prior studies neither support nor negate significant differences in intervention effect between subgroups.

Also, the proposal must address the proposed outreach programs for recruiting women and minorities as participants.

Reviewers will address the areas covered here and in Section L of the solicitation in narrative form in their evaluation.  Some of the issues they will evaluate include:

- whether the plan proposed includes minorities and both genders in adequate representation

- how the offeror addresses the inclusion of women and members of minority groups and their subpopulations in the development of a proposal that is appropriate to the scientific objectives of the solicitation

- the description of the proposed study populations in terms of sex/gender and racial/ethnic groups and the rationale for selection of such subjects

- if exclusion is proposed, that the rationale is appropriate with respect to the health of the subjects and/or to the purpose of the research.

- In addition, for gender exclusion, the reviewers will examine the rationale to determine if it is because:

- the purpose of the research constrains the offeror’s selection of study participants by gender (e.g., uniquely valuable stored specimens or existing datasets are single gender; very small numbers of subjects are involved; or

- overriding factors dictate selection of subjects); or

- gender representation of specimens or existing datasets cannot be accurately determined, and this does not compromise the scientific objectives of the research.

- For minority group exclusion, the reviewers will examine the rationale to determine if those minority groups are excluded because:

- inclusion of those groups would be inappropriate with respect to their health; or

- inclusion of those groups would be inappropriate with respect to the purpose of the research.

- For NIH-defined Phase III clinical trials, reviewers will also address whether there is an adequate description of plans to conduct analyses to detect significant differences of clinical or public health importance in intervention effect(s) by sex/gender and/or racial ethnic subgroups when the intervention effect(s) is expected in the primary analyses, or if there is an adequate description of plans to conduct valid analyses of the intervention effect in subgroups when the intervention effect(s) is not expected in the primary analyses.

If you determine that inclusion of women and minority populations is not feasible, you must submit a detailed rationale and justification for exclusion of one or both groups from the study population with the technical proposal.  The Government will review the rationale to determine if it is appropriate with respect to the health of the subjects and/or the purpose of the research

Based on the evaluation of the response to this criterion, this section of the proposal may be rated “unacceptable” (i.e., no discussion can be found regarding the proposed gender/minority inclusion plans, or concerns are identified as to the gender or minority representation, or the proposal does not adequately address limited representation of one gender or minority; or the plan is not in accordance with NIH policy guidelines) or “acceptable.”  See Section L of the solicitation for the requirements of women/minorities inclusion.

If the information you provide in your proposal regarding the inclusion of women and minorities is rated “unacceptable” and the Government includes your proposal in the competitive range (for competitive proposals), or if the Government holds discussions with the selected source (for sole source acquisitions), you will be afforded the opportunity to further discuss, clarify, or modify your plan during discussions and in your Final Proposal Revision (FPR).  If your plan for inclusion/exclusion of women/minorities is still considered “unacceptable” by the Government after discussions, your proposal may not be considered further for award.

  - Children

Children (i.e. individuals under the age of 21) must be included in all human subject research unless there are clear and compelling reasons not to include them.

Your proposal must include a description of plans for including children.  If you plan to exclude children from the required research, your proposal must present an acceptable justification for the exclusion.  If you determine that exclusion of a specific age range of child is appropriate, your proposal must also address the rationale for such exclusion.  Also, the plan must include a description of the expertise of the investigative team for dealing with children at the ages included, of the appropriateness of the available facilities to accommodate the children, and the inclusion of a sufficient number of children to contribute to a meaningful analysis relative to the purpose/objective of the solicitation.  Also, see Section L of the solicitation for further specific requirements on inclusion of children.

Based on the reviewers’ narrative evaluation of the offeror’s response to this evaluation criterion, this section of the proposal may be rated “unacceptable” (i.e., no discussion can be found regarding the proposed inclusion plans for children; or concerns are identified as to the offeror’s response regarding the inclusion of children; or the plan is not in accordance wit h NIH policy guidelines) or “acceptable.”

If the information provided in your proposal about the inclusion of children is rated “unacceptable” and the Government includes your proposal in the competitive range (for competitive proposals), or if the Government holds discussions with the selected source (for sole source acquisitions), you will be afforded the opportunity to further discuss, clarify or modify your plan during discussions and in your Final Proposal Revision (FPR).  If your plan for inclusion of children is still considered “unacceptable” by the Government after discussions, your proposal may not be considered further for award.

M.6. Animal Welfare

Offerors must submit a plan on how they will comply with all requirements concerning the use of animals for experimentation and be in accordance with any requirements specified and be in accordance of any requirements of the Office of Laboratory Animal Welfare: http://grants.nih.gov/grants/olaw/olaw.htm.

M.7. Relative Importance of Cost or Price and Other Evaluation Factors

All evaluation factors other than cost or price, when combined, are significantly more important than cost or price.

### M.8  52.217-5  Evaluation of Options  (July 1990)

Except when it is determined in accordance with FAR 17.206(b) not to be in the Government’s best interests, the Government will evaluate offers for award purposes by adding the total price for all options to the total price for the basic requirement. Evaluation of options will not obligate the Government to exercise the option(s).