| MVHAA: Education for Homeless Children and Youths |  |
| --- | --- |
| FY 2008 Program Performance Plan |  |
| Strategic Goal 1 |  |
| Formula |  |
| MVHAA, Title VII, Part B |  |
| CFDA | 84.196: Education for Homeless Children and Youth |

| Program Goal: | To ensure access of homeless children and youth to the same free, appropriate public education as is provided to other children and youth. |
| --- | --- |

| Objective 1 of 2: | Homeless children and youth will have greater access to a free and appropriate public education. |
| --- | --- |

| Measure 1.1 of 4: The percentage of homeless children and youth, grades three through eight, included in statewide assessments in reading, as reported by LEA subgrantees. (Desired direction: increase) 1120 |  |  |  |
| --- | --- | --- | --- |
| Year | Target | Actual (or date expected) | Status |
| 2004 |  | 16 | Measure not in place |
| 2005 | 17 | 50 | Target Exceeded |
| 2006 | 53 | 55 | Target Exceeded |
| 2007 | 60 | (January 2008) | Pending |
| 2008 | 63 | Undefined | Pending |
| 2009 | 66 | Undefined | Pending |

Frequency of Data Collection. Annual

| Measure 1.2 of 4: The percentage of homeless children and youth, grades three through eight, included in statewide assessments in mathematics, as reported by LEA subgrantees. (Desired direction: increase) 1121 |  |  |  |
| --- | --- | --- | --- |
| Year | Target | Actual (or date expected) | Status |
| 2004 |  | 15 | Measure not in place |
| 2005 | 16 | 49 | Target Exceeded |
| 2006 | 52 | 54 | Target Exceeded |
| 2007 | 60 | (January 2008) | Pending |
| 2008 | 63 | Undefined | Pending |
| 2009 | 66 | Undefined | Pending |

Frequency of Data Collection. Annual

| Measure 1.3 of 4: The percentage of homeless students, grades three through eight, who meet or exceed proficiency on state assessments in reading/language arts. (Desired direction: increase) 1122 |  |  |  |
| --- | --- | --- | --- |
| Year | Target | Actual (or date expected) | Status |
| 2002 |  | 30 | Measure not in place |
| 2004 |  | 36 | Measure not in place |
| 2005 | 34 | 42 | Target Exceeded |
| 2006 | 43 | 45 | Target Exceeded |
| 2007 | 50 | (December 2007) | Pending |
| 2008 | 52 | Undefined | Pending |
| 2009 | 55 | Undefined | Pending |

Frequency of Data Collection. Annual

| Measure 1.4 of 4: The percentage of homeless students, grades three through eight, who meet or exceed proficiency on state assessments in mathematics. (Desired direction: increase) 1123 |  |  |  |
| --- | --- | --- | --- |
| Year | Target | Actual (or date expected) | Status |
| 2002 |  | 24 | Measure not in place |
| 2004 |  | 36 | Measure not in place |
| 2005 | 26 | 41 | Target Exceeded |
| 2006 | 43 | 45 | Target Exceeded |
| 2007 | 50 | (January 2008) | Pending |
| 2008 | 52 | Undefined | Pending |
| 2009 | 55 | Undefined | Pending |

Frequency of Data Collection. Annual

| Objective 2 of 2: | Improve the operational efficiency of the program. |
| --- | --- |

| Measure 2.1 of 1: The number of days it takes the Department to send a monitoring report to States after monitoring visits. (Desired direction: decrease) 89a0cz |  |  |  |
| --- | --- | --- | --- |
| Year | Target | Actual (or date expected) | Status |
| 2005 |  | 46 | Measure not in place |
| 2006 | 44 | 43 | Did Better Than Target |
| 2007 | 41 | Undefined | Pending |
| 2008 | 40 | Undefined | Pending |
| 2009 | 40 | Undefined | Pending |

Frequency of Data Collection. Annual