STEP 3: Plan Activities

Now that you have selected activities for NIIW, it is time to begin planning.  Planning for an NIIW event can be broken down into the following components:

- Establish a Planning Committee

- Draft a Program/Agenda

- Logistics

- Publicity

- Fundraising

- Evaluation

For more information on planning an NIIW event, please join the January 24, 2008 Immunization Coalitions Technical Assistance planning call on “How to Host an NIIW Event.”  Information on the call can be found at: http://www.izta.org/confcall.cfm.

ESTABLISH A PLANNING COMMITTEE

There are many pieces to planning an event and while one person probably could do it all, it is easier to involve others in the event planning process.   Establishing a planning committee will allow your organization to focus energy and resources efficiently and allow team members to support each other.

Depending on the size and scope of your event, the committee should be created 3 – 6 months beforehand. If possible, it should have members with the following skills:

- A strong leader who can chair the committee

- Logistics experience who is very detail-oriented

- Expertise in program and agenda design for special events

- Fundraising experience

- Publicity/media relations experience

Different partners who will be involved in the event should be represented on the committee. These may include the health department, community based organizations, schools, provider organizations, or vaccine manufacturers.

You may find it is helpful to divide the committee into sub-committees assigned to specific tasks based on interest and availability.

For more information on how to run an effective committee meetings visit:  http://www.izta.org/content.cfm?id=617&subcat=55&cat=25

Once you have established your committee, it's time to make some key planning decisions.

Key Committee Decisions

Now that you’ve identified a team of people to help plan your event, it is time to make some key decisions.

- Date – NIIW is from April 19 – 26, 2008 but when during that week should you hold your event to have the biggest impact?  Pick a day and time of the week that are convenient for your target audience.  If you are hosting a media event, try to pick a slow news day, such as a Tuesday, Wednesday or Thursday.

- Venue- Where will the event be held? 
See tips about choosing a venue.

- Potential sponsors and partners- Which organizations can help you to increase the reach and profile of the event? 
Get ideas for potential sponsors and partners.

- Budget- How much money do you need? How much funding do you currently have? How big is the funding gap?
Learn more about budgeting.

- Timeline- What are the key milestones and when do they need to be accomplished? 
See a sample timeline.

DRAFT A PROGRAM/AGENDA

Now that you have a date, time, and venue it is time to create the content of the event.  This involves:

- Creating a slogan and a “take-away” message

- Identifying and recruiting speakers

- Developing the agenda

Here are some guidelines for each of these tasks:

Creating a slogan
Choose a catchy, easy-to-remember slogan for your event. Here are some examples from past immunization events:

- “Everybody Loves a Baby” (immunization event at the zoo celebrating animal babies and human babies)

- “Dine ‘N Dash” (educational seminars for physicians at restaurants)

- “The Race to Vaccinate” (vaccination campaign in conjunction with a dog sled race)

Recruiting speakers
Some events require speakers, such as luncheons, awards seminars, and educational workshops. The speakers may make opening remarks, give a keynote address, or facilitate training sessions, depending on the type of event.

Choose a speaker who will draw people to your event. This is especially important when you are targeting a busy audience like physicians. Look for a speaker who:

- Is a recognized expert on your subject

- Has name recognition (e.g., local politicians or celebrities)

- Is dynamic and funny

- Is reliable (i.e., not likely to back out at the last minute)

Some speakers may be willing to speak for free, but others may charge a fee. Some may be willing to speak for free if you cover their travel costs.

Given that immunization coalitions are non-profit entities with limited funds, it is worth the effort to negotiate with speakers about their fees. Also be sure to discuss transportation and lodging arrangements if the speaker has to travel to your event.

Developing the agenda
A draft agenda for your event should be developed no later than a month before the event. Here are some tips for developing a realistic agenda:

- Allow enough “wiggle room” in your agenda to account for late starts and unanticipated delays. For example, assume that your first session will start at least 15 minutes late and allow enough time before the second session to compensate for this.

- If your event is a seminar, training or workshop, plan for coffee or meal breaks every 2-2½ hours.

- When listing speakers and presenters on the agenda, put “tentative” or “confirmed” next to their names.

- If activities/sessions will be taking place in different rooms, be sure to list the room next to each item.

- Mark each version of the agenda with “Draft” and the date that it was revised. This will help to avoid confusions when multiple copies are circulating. Do not mark it “final” until you are absolutely sure that nothing will change.

- Assume that there will be last minute changes to your agenda and plan accordingly. For example, in your timeline, you may want to plan to print the agenda the evening before the event or even the morning of the event. Make sure that someone is available to do this at the last minute.

LOGISTICS

The “nuts and bolts” of event planning involves thinking through all aspects of your NIIW activity.  Visualize how the days leading up to the event will go, what the day of your event looks like, and try to identify places where difficulties may arise and have a back up plan prepared.

See below for a checklist of key tasks that play a role in implementing a successful event.

PUBLICITY

Now that you’ve planned your event, you need to let others know about it.  Partner organizations and the media can play a big role in publicizing your efforts.  Some key steps to publicity are:

- Identifying event spokespeople

- Creating promotional materials

- Media outreach

Remember to let national and local child health organizations know about your program.  You can submit your NIIW event information on line at www.cdc.gov/vaccines/events/niiw.

Identifying Event Spokespeople
Identify one or more spokespeople from your coalition who can talk about the event with the media and others. Ideally, the spokespeople should:

- be knowledgeable about the immunization issue you are addressing and also knowledgeable about the event.

- have prior experience interacting with the media. If your spokesperson does not have this experience, see if a local public relations firm would be willing to do “pro bono” media training.

Prepare a biosketch of your spokesperson to share with the media and other interested parties.

More information on preparing spokespeople can be found in the Public Relations Tool Section of the NIIW website, www.cdc.gov/vaccines/events/niiw, under the “Working with the Media” heading.

Promotional Materials
Creating promotional materials for your event helps reinforce your messages and sets the tone for your event. These may include:

- “Save the Date” cards

- Invitations

- Flyers

- Posters

- Fact sheets

- Collateral materials – buttons, caps, t-shirts

- Banner to hang behind the podium

- Signs to direct participants on the day of the event

To get professional quality materials, it is helpful to work with a graphic designer. See if any of your coalition members has a graphic designer within their organization who could design the materials. If not, local printers often have graphic designers for hire. Visit www.cdc.gov/vaccines/events/niiw to download and commercially print posters, banners, podium signs and other public relations materials.

Send out “Save the Date” cards 8 weeks prior to the event. Invitations should be sent 4 weeks prior to the event. An event announcement and promotional materials can be posted on your website as well as partner websites.

Whenever sending correspondence about your event to the media or community organizations, be sure to use the same letterhead. This is important for events being organized by coalitions, which consist of many different organizations. If your coalition does not have its own letterhead, then decide on one of the organizational letterheads to be used, and use it consistently. Visit www.cdc.gov/vaccines/events/niiw to download NIIW letterhead.

Media outreach is another way to publicize your event.  More information on media outreach can be found in the Public Relations Tool Section of the NIIW website, www.cdc.gov/vaccines/events/niiw, under the “Working with the Media” heading.

FUNDRAISING

Once you have determined your budget and figured out how much of a “funding gap” you are facing, you may need to consider additional sources of financial support.  More information on Fundraising can be found below.

EVALUATION

It is important to know if your event was successful or not, especially if you plan on replicating it in the future.  More information on evaluation can be found in the Planning Tools Section of the NIIW website.

Sample Checklist of Key Tasks

Before the Event

|  | Reserve the venue. If your event will take place out side, make sure that you have back-up plan in case of rain (i.e. An alternate rain date or an alternate indoor venue). |
| --- | --- |
|  | Make travel and lodging arrangements for out-of-town speakers. If you are using government funds, make sure that your speaker is aware of per diem limits. |
|  | Arrange for food and beverages. (Don’t forget to feed volunteers!) |
|  | Arrange for audio visual equipment. |
|  | Purchase office supplies that will be needed during the event (e.g. flipcharts, markers, folders, pens, notebooks). |
|  | Arrange for the production of a banner to hang behind the speaker’s podium. |
|  | Arrange for signs to guide participants to the event room/site. |
|  | Coordinate event registration. |
|  | Create name badges for participants and speakers. |

Day of the Event

|  | Set up the rooms and registration tables (one table for participants and another one for the media). |
| --- | --- |
|  | Hand out packets/materials to participants. It is preferable to distribute them as people register so that you can point out any important documents, such as evaluation forms. |
|  | Ensure that AV equipment is set up and functioning. |
|  | Supervise food distribution. |
|  | Ensure that there is water for speakers. |
|  | Staff the media table and coordinate interviews. |
|  | Escort guests/speakers to all of the events. If you are escorting them to multiple venues, bring snacks and water for them in case they do not have time to eat. |

Tips for Room Set-Up

|  | Reserve seats for speakers, dignataries and other guests near the podium. |
| --- | --- |
|  | Set aside space for the media. If radio or TV reporters will be coming, create space for video cameras and microphones near the podium. |
|  | If print journalists are coming, reserve a row of seats near the podium. |

Tips on Fundraising

Once you have determined your budget and figured out how much of a “funding gap” you are facing, the next step is to analyze your existing and potential funding sources. Consider the following sources of financial support:

Potential Sources of Financial Support

- Funding from immunization or children’s health coalition members

- State and/or local health departments

- Discretionary funds from your town/city/county council or board of supervisors

- Local hospitals and large provider groups

- Insurers and managed care organizations (e.g. Blue Cross/Blue Shield distributes small grants for health events in California)

- Local businesses

- Local universities, colleges and technical schools

- Local civic groups (e.g. Rotary and Kiwanis Clubs)

You can also ask for in-kind support to supplement your financial support. Many businesses find it easier to offer free goods or services instead of donating money. Here are a few examples:

Potential Sources of In-Kind Support

- Local printing companies may be able to print flyers at no or reduced cost.

- Local food establishments, such as pizza parlors, sandwich shops, restaurants, orchards may be able to donate food for the event participants or snacks for volunteers.

- Home supply stores, such as Home Depot or Lowes may be able to donate parking lot materials if you are doing a drive-thru clinic.

- Local community groups may be able to supply volunteers for envelope stuffing.

- Hotels or conference centers may be able to provide meeting space at reduced or no cost.

- Public relations consultants may be willing to do “pro bono” media training for your spokespeople.

You may also wish to consider a fee for participation or advertising during the event. For example:

Other Sources of Funds

- Charge vaccine manufacturers a fee for having a booth at your event. It is often easier for companies to pay a booth fee than to donate money. You may wish to charge non-profit organizations a reduced booth fee.

- Charge a nominal fee for a dinner or luncheon. Not only will you raise money, but people will be more likely to show up if they have already paid for their meal.

- If you are organizing an entertainment or sporting event (i.e. a theater performance, concert or run/walk), charge a nominal entry fee.

- Charge local pharmacies or medical supply stores a fee to advertise in the event program. If you are doing an infant immunization event, you may also wish to approach local baby supply stores about advertising.

Approaching Potential Supporters
Here are some helpful tips for approaching and recognizing your supporters:

- Work with the Publicity Committee to develop a fact sheet about the event. This can be shared with potential supporters as well as with the media.

- Create a spreadsheet of all potential sources of financial and in-kind support. Include columns to indicate the dates that they were contacted, whether or not materials were mailed to them, and how much support they ended up providing.

- Decide on a specific amount of money or a specific good/service that you will ask for from each organization.

- Develop two telephone scripts approaching potential supporters - One for the solicitation of money and the other for the solicitation of in-kind support. Be sure to mention the benefits that the funder will receive by supporting your event. For example:

  - Increased community and media visibility.

  - Recognition as a supporter of health and well being.

  - More clients/customers (i.e. for a baby store, pharmacy or health system)

- Make your initial contact via phone – This is more personal than an email or a letter, and you will be more likely to get the attention of your potential supporter. Offer to mail supporting materials after your phone call, and then follow-up to make sure that they were received.

Be sure to recognize all event supporters by putting their names in the event program and by sending them a thank you letter afterwards.