# Cincinnati Public School District

# Multi-Hazards Management:

# Creating an Emergency Management Plan

2005 - 2006

# Environmental Public Health Leadership Institute Fellow:

# Jessica L. Shelly, B.A., M.B.A., R.E.H.S., R.S.

Supervisor, Building Operations & Food Services

## Cincinnati Public Schools

2315 Iowa Ave, 2nd Floor

Cincinnati OH  45206

(513) 363-0818

Shellyj@cps-k12.org

# Mentor:

### CAPT. Craig A. Shepherd, R.S., M.P.H., D.A.A.S.

U. S. Public Health Service; Chief Environmental Health Officer

Senior Environmental Health Officer
Environmental Health Services Branch 
Division of Emergency and Environmental Health Services 
National Center for Environmental Health 
Centers for Disease Control and Prevention 
4770 Buford Highway, NE (F28)

Atlanta, GA 30341-3724 
(770) 488-7026
 cfs4@cdc.gov

# Acknowledgements:

### Thomas Gunnell, B.A., M.S.

Chief Operations Officer; Cincinnati Public Schools

# EXECUTIVE SUMMARY:

In light of current world and national events, there is recognition of the need for schools to be prepared for multiple hazards.  It is holistically implied that schools have an obligation to care for students, staff, and the community in the event of a terrorist emergency or natural disaster.  Yet, many school districts do not have an emergency management plan, have not received any preparedness training, lack coordination with local emergency agencies, and have not established an effective communication system with the community.

After evaluating Cincinnati Public Schools’s (CPS) current emergency procedures, it was determined that CPS was not prepared to manage a multi-hazard event caused by terrorist activity or natural source.  CPS faces both challenges and opportunities in meeting its obligation to provide for the safety and preservation of life of its students and staff.  CPS made the decision that it needed to strengthen and improve its Emergency Management Plan for implementation at CPS’s 79 public schools.

The Emergency Management Plan was designed to meet one of CPS’s highest priorities:  to provide for the safety and preservation of life of students and staff in Cincinnati’s school.  While CPS faces many challenges in pursuing this priority, the district has committed to developing a comprehensive strategy for emergency response and crisis management aligned with the National Incident Management System.

Two major and concurrent initiatives at CPS created a tremendous need for emergency management planning.  Together, these initiatives create a particular need for a district-wide Emergency Management Plan that can be adapted to create individualized School Response Plans that keep overall policies and procedures consistent while accounting for site-specific threats and vulnerabilities.

First, Cincinnati Public Schools is undertaking the largest restructuring in its history. The district is in its third year of a 10-year building plan that will construct dozens of new schools and fully renovate many more. Schools are being transformed from traditional, stand-alone buildings into campus-like Community Learning Centers. In some cases, larger traditional buildings are being renovated to hold two or three smaller schools.  The impact of these changes is great.  The fact that many schools are in transition creates the need for enhanced planning and coordination for emergency response.  As newer, more modern facilities are built, the potential for some hazards—like fire—will diminish. But others will be created or exacerbated—for example, as schools become community centers with campus layouts that involve more entry and exit points, chances increase for intrusion by potentially violent outsiders.

Second, the district has undertaken an aggressive, disciplined program to eliminate a $23 million deficit in a very short time frame to bring the school district in line with its budget. This has involved streamlining of departments and cutbacks in staff on all levels.  The 2005-2006 school year will be the district’s first year of staff reduction. Reduced staff necessitates better planning and coordination to mitigate, prevent and prepare for potential crises and clearer understanding of what is needed to respond to and recover from emergencies.

One of the biggest constraints identified was lack of budget for emergency preparedness; therefore, a $500,000 grant from US Department of Education for Emergency Response and Crisis Management was applied for and subsequently awarded to CPS in October 2005.

The grant monies have allowed for CPS to excel quickly in development of an emergency management plan, major equipment, supplies, and training materials purchases, and Multi-Hazard Emergency Planning for Schools training culminating in NIMS IS 700 certification for all School Incident Response Team members.

The next steps for CPS will be to conduct WMD/Hazmat Awareness training for SIRT members, complete individual School Response Plans, conduct all school site vulnerability assessments, create community awareness events, and perform a major simulation and post-assessment.

# PROJECT OBJECTIVES/DESCRIPTION/DELIVERABLES:

Program Goal:  To help prepare Cincinnati Public Schools for multi-hazard events including terrorist incidents or natural source.

Health Problem:  Cincinnati Public Schools are not prepared to manage a multi-hazard event caused by terrorist activity or natural source.  This is an exceptional problem for environmental public health since many schools throughout the country will be used as Points of Distribution for mass prophylactic and immunizations and/or as community shelter areas.

Outcome Objective: Cincinnati Public Schools are prepared to handle multi-hazards through development of emergency management plans, emergency management training, and emergency management exercises & drills.  Cincinnati Public Schools will also begin to distribute emergency management information to students/families/communities through website development, educational presentations, and other measures.

Determinant:  Cincinnati Public Schools do not have access to or understanding of emergency management fundamentals and CPS does not have the time or resources for development of an emergency management plan, training, exercises & drills, or community information.

Impact Objective:  By December 2006, CPS will have a working Emergency Management Plan that is supported by training, emergency exercises & drills, and student/family/community educational information.

Contributing Factors:

- All of the 79 CPS are within three miles of manufacturing or industrial sites

- No district-wide Emergency Response Plan in place due to the lack of resources

- CPS staff reductions are expected and will require even better planning

- CPS responded to nearly 100 incidents involving weapons such as guns and knives

- CPS is spending $890 million to rebuild or remodel every school building by 2010

- CPS budget does not allow for expenditure of supplies

Process Objectives:  The major milestones will be as follows:

- Emergency Management Plan written and approved by Board of Education by October 2005

- Major equipment, supplies, and training materials expenditures complete by December 2005

- Multi-Hazard Emergency Planning for Schools training culminating in NIMS IS 700 certification for all SIRT members by the end of March 2006

- WMD/Hazmat Awareness Training completed for SIRT members by April 2006

- School Response Plans developed and approved for all schools by May 2006

- All school site vulnerability assessments completed and evaluated by June 2006

- Community awareness events completed by October 2006

- Major simulation and post-assessment completed by October 2006

- All central office, teachers, and building support staff trained on CPS Emergency Management Plan policies and procedures by December 2006

# INTRODUCTION/BACKGROUND:

Located on the Ohio River in the southwestern-most corner of Ohio, Cincinnati is the hub of a tri-state region of Ohio, Indiana, and Kentucky.  The Ohio River joins the Licking River at Cincinnati, and the many tributaries of these streams periodically create flooding hazards throughout much of the school district.  Additionally, the valley creates what can be a deadly path for tornados, the most large-scale climatic threat for Cincinnati.  Other weather events, including severe thunderstorms and especially snow/ice storms can bring the city to a halt. Their effects are exacerbated by Cincinnati’s extremely hilly terrain, which, even without hazardous weather conditions, can hinder radio communications, making it critical for CPS and other emergency responders to have backup communications capabilities and access. Also, the 79 schools of the Cincinnati Public School district are distributed over 91.8 square miles of widely varying topography, increasing challenges to incident command and emphasizing the need for coordination and preparedness.

Cincinnati is a leading center of manufacturing, commerce and transportation in the Midwest. It is home to major chemical and industrial plants—in fact, all 79 CPS schools are within three miles of a manufacturing or industrial site—and serves as a through-center and transshipment point for chemicals and other hazardous materials originating in other parts of the nation. These materials move through the city via the rail network, the highways, the Ohio River, and the Cincinnati/Northern Kentucky International Airport. The airport is a Delta hub and is among the busiest air-cargo facilities in the nation.  In addition to commercial activity, defense activities in Cincinnati include the General Electric Aircraft Engine facility and the Fernald Uranium Enrichment Plant.  Most recently, three CPS schools were directly impacted by a Styrene tanker car leak that caused the evacuation and subsequent closure of the schools for over a week.

In particular, CPS shares the serious problems facing urban school systems and communities throughout the country—high drop-out rates, crime, violence, drug abuse, gangs, and lack of supervision for children. While CPS is believed to have an overall safe environment for students to learn, it has a comparable number of threatening incidents to other large urban districts: in the 2004-2005 school year, CPS responded to 98 incidents involving weapons, 11 of those involving guns and 61 involving knives.

As the first part of this project, a CPS Emergency Management Plan was drafted.  It includes policies and procedures to address these conditions, but the district needs training to put these policies and procedures into practice and to adapt them strategically to the individual school level.  The plan also addresses the general concerns facing the nation at large, including the potential for terrorism. Cincinnati, which composes most of Hamilton County, has been designated by the Department of Homeland Security as an Urban Area Security Initiative, allowing federal funding to flow directly to the local level. This designation was made with the understanding that urban areas are the most likely targets for terrorism.

To address potential emergencies, and to allow the CPS Emergency Management Plan to fully provide for crisis mitigation/prevention, preparedness, response and recovery, CPS needs to develop the following tasks:

- Training:  Provide appropriate content and levels of training for the district-wide Emergency Management Team, School Incident Response Teams (SIRTs), teachers and other school staff, students, and partner schools.

- Coordination:  Strengthen CPS’s coordination with emergency response partners, including Hamilton County Homeland Security Office, Cincinnati Police Department, Cincinnati Fire Department, Cincinnati Health Department, Cincinnati Community Board of Mental Health, and American Red Cross.

- Communication:  Plan for and enable effective, agreed-upon emergency response procedures among staff, first-responders, parents and guardians to ensure communication of information and safe and timely reunification of students with their parents or guardians.

Behavior Over Time Graph:  It was beneficial for CPS to graph out the different variables that affected our project.  This helped us understand what our challenges would be in accomplishing our objective.

Causal Loop Diagram and Applicable Archetype:  We also discovered how we were shifting the burden by creating a causal loop diagram.

10 Essential Environmental Health Services:  This project utilizes five of the 10 Essential Environmental Health Services1:

- Essential Environmental Health Service #4:  Inform, educate and empower people about health issues

  - Parents will receive a brochure outlining what to do in the event of an emergency at their child’s school. They will be made available in English and the main five other languages spoken in district homes. Brochures will also be made available to parents with children at non-CPS schools.

- Essential Environmental Health Service #5:  Mobilize community partnerships to identify and solve health problems

  - The CPS project design benefits from and reinforces CPS’s partner relationships with first responders: Cincinnati Fire Department, Cincinnati Police Department, Hamilton County Community Mental Health Board, Cincinnati Health Department, Hamilton County Homeland Security, and the American Red Cross. These partners are involved in every area of CPS preparedness planning, from assessment to training to practice to communication with parents and the community.

- Essential Environmental Health Service #6:  Link people to needed personal health services

  - Overall preparedness will be introduced to parents and the community-at-large through events at four schools in different parts of the district. At these events, parents and the community will be introduced to the full scope of the CPS Emergency Management Plan as well as to the larger plans of Hamilton County and Cincinnati. In particular, parents will be informed of school emergency communications and reunification procedures, i.e., where to find information in an emergency and how to use that information. The events will feature opportunities for parents and the community at large to hear from all of the CPS first responder partners as well as other supporting partners from business and industry, the Alliance for Chemical Safety and Cincinnati Youth Collaborative, which coordinates CPS’s Partners in Education program, whereby businesses sponsor programs and activities at individual schools.

- Essential Environmental Health Service #7:  Evaluate effectiveness, accessibility, and quality of personal and population based health services

  - Cincinnati Public Schools will use an evaluation process designed around the principles of learning, practicing, continuous improvement, and sustainability of results. Several levels and types of assessment will be included in an overall evaluation process conducted by CPS’s Department of Research, Evaluation & Testing.  To accomplish the scope of evaluation intended, CPS will create a project performance database in a secure area on the CPS intranet.  The database will be designed to count, track, and document progress on performance measures related to outcomes, and provide feedback to inform decisions about needed adjustments in Emergency Management Plan policies and procedures.

- Essential Environmental Health Service #9:  Develop polices and plans that support individual and community health efforts

  - CPS Emergency Management Plan includes policies and procedures to support the City of Cincinnati and federal goals of making sure all citizens are prepared for a multi-hazard emergency at any school in our district.  The plan also addresses the general concerns facing the nation at large, including the potential for terrorism.

National Goals Supported

1)  CDC 21st Century Health Protection Goals2:  This project sustains CDC’s strategy to help the public prepare for multi-hazard events such as environmental threats and terrorism through customer-centricity and leadership. CPS recognizes that we have access to a large percentage of the community and can help market to our students, staff, parents, and community at large the importance of preparing for a multi-hazard event.  Our district has an established level of trust within our community and the public is confident our leadership and direction.  Therefore, we can educate many citizens on how CPS is prepared and how their household can be prepared for an emerging health threat.

Two of the four new health protection goals are addressed in this project:  People Prepared for Emerging Health Threats, and Healthy People in Healthy Places – Schools.

- People Prepared for Emerging Health Threats: Through distributed literature, our website, and our community information events we will be able to teach our community how to prevent illness from naturally occurring health hazards and terrorist hazards.  By making the information applicable to our school community, CPS is giving our students, staff, and parents the information they want and the information the need to choose to be prepared and stay safe and healthy.

- Healthy People in Healthy Places – Schools:  By preparing every one of our schools for a multi-hazard, Cincinnati Public Schools will be safer and healthier environments.  From individualized School Response Plans for each school based on threat and vulnerability assessments to assemblies for students that explain proper Shelter-in-Place at school and at home to evacuation and lockdown drills, CPS is protecting and promoting the health and safety of not only students and staff, but the community as a whole.

2)  National Strategy to Revitalize Environmental Public Health Services3:  This project supports the CDC’s overarching goal of enhancing the environmental public health service of multi-hazard preparedness in the City of Cincinnati.  Specifically, it achieves two direct goals and their objectives:

- Goal IV:  Communicate and Market

  - CPS has worked diligently to help communicate and market the importance of emergency preparedness with their stakeholders.  CPS has attended city of Cincinnati council meetings to help support the environmental health service of multi-hazard preparedness.  We are also working with the national organization of Parents for Public Schools to have them assist in developing the strategy of distributing educational materials to students, staff, parents, and community on emergency management and preparedness.  CPS also supports other agencies and organization’s educational approaches on emergency preparedness.  For example, CPS is assisting the American Red Cross in setting up a series of Community Emergency Response Training (CERT) for all parents and staff at several CPS schools.

- Goal VI:  Create Strategic Partnerships

  - CPS is dedicated to involving all critical stakeholders in the development of the multi-hazard Emergency Management Plan for our district.  We are working in cooperation with city, county, state, and federal agencies that we have identified as influential and will assist us in our plan development and execution.  CPS has been a strong supporter of attending training programs (FEMA training in Emmetsburg, Maryland and DHS training in Anniston, Alabama, for example) with local fire, police, and city representatives so that the environmental health goal of multi-hazard preparedness can be worked on together.  CPS conducts regular quarterly meetings with all stakeholders, and all stakeholders receive monthly email updates on CPS preparedness progress so that communication lines are open and information is being shared in real-time.

Project Logic Model:  The logic model below helped develop the various inputs, outputs, and outcomes CPS expects from implementation of this project:

| Situation Statement: Cincinnati Public Schools are not prepared to manage a multi-hazard event caused by terrorist activity or natural source. This is an exceptional problem for environmental public health since many schools throughout the country will be used as Points of Distribution for mass prophylactic and immunizations and/or as community shelter areas. Outcome Summary: Cincinnati Public Schools are prepared to handle multi-hazards through development of emergency management plans, emergency management training, and emergency management exercises & drills. Cincinnati Public Schools will also begin to distribute emergency management information to students/families/communities through website development, educational presentations, and/or other measures. |
| --- |
| Inputs |  | Activities/Outputs Activities Outputs |  | Outcomes – Impact Short Term Medium Term Long Term |
| NIMS Training FEMA Training DHS Training ODP Training American Red Cross Training EPHLI support (CDC mentor support) |  | 1) Participate in multiple training classes 2) Become NIMS certified 3) Develop emergency management plan from training information 4) Collaborate with American Red cross to develop exercises & drills templates 4) Work with local EMS to develop emergency preparedness information | 1) Emergency Management Plan for CPS 2) Emergency Management Training for CPS employees 3) Emergency Management Exercises & Drills conducted at CPS 4) Emergency Preparedness Information and website link developed by CPS to distribute to students, families, & communities |  | 1) CPS increases their awareness of appropriate multi-hazard responses 2) Identification of district specific problems with preparedness and action in the event of an emergency 3) Development of strategies to address preparedness or action problems identified | 1) CPS develops their own Emergency Management Plans, Training, Exercises & Drills, and Emergency Preparedness Information 2) CPS participates in multi-hazards activities 3) Relationships developed with health, fire, police, American Red Cross, EMA, and other emergency response agencies | 1) CPS performs appropriately during an event 2) Increase in safety of students and community during an event 3) Increase in public confidence with respect to the safety and preparedness of CPS |

# METHODOLOGY:

CPS formed an Incident Management Team (IMT) in January 2005 consisting of CPS staff and representatives of the Cincinnati Police Department and Cincinnati Fire Department.  This team meets regularly, and eight members were certified in FEMA and NIMS IS 700 through training completed in March 2005. The team has met with community stakeholders, such as parents, teachers, students, the Local School Decision Making Committees (LSCMC) at each school in the CPS district, local government, non-CPS schools, and other key emergency responders. Based on these meetings, the IMT has composed an Advisory Committee that will enhance the core IMT, specifically including the coordinating partners in this proposal.  The team wrote an Emergency Management Plan using a best-practices national template and in consultation with the Hamilton County Office of Homeland Security. The plan adopts the principles and policies of the NIMS, which the district has formally recognized.

One of the biggest constraints identified was lack of budget for emergency preparedness; therefore, a $500,000 grant from US Department of Education for Emergency Response and Crisis Management was applied for and subsequently awarded to CPS in October 2005.

The overarching principle in forming CPS’s project design is the safety and preservation of life of students and staff in the schools. The goal for the proposed project is to improve and strengthen CPS’s emergency response and crisis management plans, at both district and school-building levels, in a manner that addresses the four phases of emergency management: mitigation/prevention, preparedness, response, and recovery.

This goal will be realized through the following objectives:

- Training teachers, staff, and students using materials and practices reflecting the best available knowledge and employing a train-the-trainer philosophy that ensures sustainability;

- Improving CPS’s already-strong coordination with emergency first-responders and key community partners; and

- Developing and implementing school emergency communications procedures and policies, including those for reunification of students with parents/guardians following a crisis.

The CPS’s Emergency Management Plan incorporates all four phases of Emergency Management, Mitigation/Prevention, Preparedness, Response, and Recovery.  The project design considers training, coordination, and communication in each of the four phases:

Phase One:  Mitigation/Prevention

Training – Having an accurate accounting of vulnerabilities at each school is the first step to site-specific mitigation and prevention. Included in the program design is training for staff from each school in on-going threat and vulnerability assessment. This training will be implemented through a contracted assessment firm selected in consultation with the Hamilton County Office of Homeland Security and offered on a train-the-trainer basis. Threats and vulnerabilities identified will be both general in terms of common dangers, such as fire, and specific in terms of the particular environment of the school—for example, if it is located in a floodplain or close to a chemical facility. The training will involve awareness of school-particular stresses, such as crime, gang rivalries, racial unease, etc. Prevention training will operate not as a static check-off list, but as an ongoing process involving recommendations of teachers, students and staff.  Procedures for this input are included in the draft Emergency Management Plan.

Coordination with Partners – CPS and its emergency responder partners, together comprising the IMT, will carefully align all mitigation and prevention policies and procedures with the Hamilton County Office of Homeland Security. This will involve constant communication regarding specific threats. Also, the IMT, through the expertise of its member partners, will monitor and adjust prevention/mitigation techniques and practices based on relevant local information, such as the heightened racial tension present in Cincinnati.

Communication – Emergency communication with parents and the community will be addressed through an automated telephone and email contact system and through creation of an Internet emergency information system detailing the nature of the crisis, what to do, and reunification plans. These improved communications will mitigate or prevent an emergency situation exacerbated by uninformed parents. For example, in a shelter-in-place or lockdown, response efforts would be hindered by panicked parents arriving on the scene.  Problems inherent in after-crisis reunification will be lessened through agreed-upon and practiced procedures involving students, their guardians, teachers, first-responders, and CPS staff.  Reunification areas and communication channels will be identified to lessen confusion and assist in resolution of the crisis. Also, emergency communications equipment will be installed in an Emergency Response Command Vehicle already in CPS’s possession. The equipment will allow command staff to access all databases needed for response as well as to communicate to all appropriate audiences.

Phase Two:  Preparedness

Training – The CPS Emergency Management Plan involves four levels of individuals arranged in pyramid fashion. At the top is the IMT consisting of CPS and first-responders.  The second level consists of incident teams at each school. A school incident commander, who is the principal, leads these School Incident Response Teams, or SIRTs. Teachers and other building staff constitute the third level, and students and parents, the fourth.

Each of these levels will be trained in the appropriate roles and responsibilities. For the top, this involves continual updating of the Emergency Management Plan and ensuring its compliance with the Hamilton County Emergency Operations Plan. The IMT has completed and been certified through the Multi-Hazard Training for Schools Train-the-Trainer course provided by the Emergency Management Institute of FEMA and has overall responsibility for the emergency planning for all of CPS. This team will also receive an 8-hour WMD/Hazmat Awareness Training provided by the Cincinnati Health Department.

At the school level, principals are responsible for forming 7-member School Incident Response Teams (SIRT) to direct emergency planning, mitigation, preparedness, response and recovery at their respective schools, building on a template provided by the district-wide Emergency Management Plan. SIRT members will include the principal, the assistant principal, a lead teacher, head secretary, head of security, plant supervisor, and a nurse or school counselor, if present.  All SIRT members will go through a range of training classes to prepare them for a multi-hazard emergency.  Below is a diagram of the training:

First, these individuals will undergo a one-day Multi-Hazard Emergency Planning for Schools training led by the FEMA and NIMS-certified IMT and will be certified through the IS 700 NIMS Certification Course. This one-day training for SIRTs will be conducted by geographic quadrant in Cincinnati. The SIRTs will also undergo a half-day of locally specific and district-wide emergency management training.

Two members of each SIRT will be designated as threat and vulnerability assessors and will receive 2-hour training and site-specific technical support from the contracted assessment firm for conducting assessments at their respective schools. These two SIRT members will then train other SIRT members as well as selected teachers. Three members of the SIRT – the principal, plant supervisor, and head of security – will also receive WMD/Hazmat Awareness Training.

In addition, and in terms of preparation, 200 CPS personnel received Critical Incident Stress Management Training (CISM) provided by the Southwest Ohio Critical Incident Stress Management Team in 2003.  Security personnel took a two-day course in Group Crisis Intervention, and more than 125 school psychologists, social workers, guidance counselors, and nurses took a further four days of training that will assist and support the SIRTs.

Teachers and other building staff will receive a half-day in-service training on the CPS Emergency Management Plan and how it is being adapted for implementation at their schools. Training will center on site-specific emergency potentials and procedures, use of the school’s emergency supply kit (GoKit), and around classroom emergency flip charts.

An in-house training coordinator will facilitate instruction for and by the SIRTs. Teachers, in turn, will provide age-appropriate instruction to their students regarding emergency procedures, such as evacuation routes, shelter-in-place locations, location of the emergency flip chart and how to read it, what to do in a lockdown, etc. They will be assisted by CPS-produced videos demonstrating shelter-in-place and lockdown procedures. Actual shelter locations for shelter-in-place at each CPS, private and parochial school in Cincinnati have already been identified by the fire department in school-by-school walk-throughs. Signage for CPS and partner-school shelter-in-place locations, in the form of laminated “turtle” posters, will be produced using grant funds.

Central office staff will be provided a separate overview of the Emergency Management Plan by the IMT. Each department is also required to develop its own plan.

Coordination with Partners – The CPS project design benefits from and reinforces CPS’s partner relationships with first responders: Cincinnati Fire Department, Cincinnati Police Department, Hamilton County Community Mental Health Board, Cincinnati Health Department, Hamilton County Homeland Security, and the American Red Cross. These partners are involved in every area of CPS preparedness planning, from assessment to training to practice to communication with parents and the community.

Important preparedness coordination will involve collecting and sharing assessment information on every school in the district. The fire department is developing a major computerized Cincinnati Area Geographic Information Systems (CAGIS) database of critical emergency response information for more than 54,000 buildings in the city. CPS, through its assessment of schools, will help that effort by collecting information for the district’s buildings in the format needed for the CAGIS database.

Also for the school-by-school assessments, CPS will use the threat and vulnerability assessment template recently developed by the Hamilton County Office of Homeland Security for its own use in assessing hazards in the region. By conducting the assessments on behalf of Homeland Security, CPS is both attending to the safety of its own buildings and adding to overall county homeland security.

Another example of preparedness coordination is the agreement between CPS and the Cincinnati Health Department for provision of WMD/Hazmat Awareness Training. The health department will provide training and materials, free of cost, to three individuals in each SIRT. CPS will provide facilities to the health department for its WMD/Hazmat Awareness Training and also has designated eight schools as points of distribution for emergency immunizations. Also, the Cincinnati Health Department will supply GoKits to each of the schools, pending grant funding, and the American Red Cross will provide training on their use and maintenance. Finally, CPS and the Cincinnati Police Department have long-established cooperation and coordination in security and crisis management through the provision of 11 School Resource Officers covering all of the district’s high schools, and through partnership programs such as Student Crime-Stoppers.

Communication – Overall preparedness, including training, drills and simulations, will be introduced to parents and the community-at-large through events at four schools in different parts of the district. At these events, parents and the community will be introduced to the full scope of the CPS Emergency Management Plan as well as to the larger plans of Hamilton County and Cincinnati. In particular, parents will be informed of school emergency communications and reunification procedures, i.e., where to find information in an emergency and how to use that information. The events will feature opportunities for parents and the community at large to hear from all of the CPS first responder partners, such as Cincinnati fire Department, Cincinnati Police Department, Hamilton County Emergency Management Agency, Cincinnati Health Department, and the American Red Cross, as well as other supporting partners from business and industry, the Alliance for Chemical Safety and Cincinnati Youth Collaborative, which coordinates CPS’s Partners in Education program, whereby businesses sponsor programs and activities at individual schools.

Parents will also receive a brochure outlining what to do in the event of an emergency at their child’s school. The brochures will be a concise guide reflecting the latest information on best practices as identified by CPS in conjunction with the Hamilton County Emergency Operations Plan. They will be made available in English and the main five other languages spoken in district homes. Brochures will also be made available to parents with children at non-CPS schools.

Phase Three:  Response

Training – Training in emergency response rests heavily in all parties knowing who is in charge under what circumstances. The CPS Emergency Management Plan carefully assigns responsibility according to the gravity and type of crisis and is in close alignment with NIMS lines of command.  For instance, a minor incident such as a small and contained hazardous material spill would be handled by the SIRT alone and would not activate the Emergency Management Plan. An emergency or disaster such as a building fire or tornado would activate the plan and call for transfer of overall authority from the SIRT to the district incident commander, who in the case of CPS is the chief operating officer. Once the Emergency Management Plan is activated and under the control of the district incident commander, CPS activates specific response procedures, i.e. the public information officer follows an emergency communications plan.

These response procedures, outlined in the Emergency Management Plan, will be tested through tabletop exercises and physical, on-site simulations. Two 3-hour tabletop drills will be conducted by October 2006: one for lockdown, and one for a CBRNE (chemical, biological, radioactive, or nuclear explosive) incident. The training coordinator will develop and coordinate the tabletop drills using materials (and certification) from the FEMA Multi-Hazard Training for Schools Train-the-Trainer course. The trainees will consist of the SIRTs and first-responder personnel.

These drills will include accommodation for students with disabilities and limited-English proficiency.  In addition, two simulations will test response procedures for managing multi-faceted crises. One will involve a building-compromising event in a school with children with disabilities. It will be carried out in the last two hours of a school day and will involve evacuation, transporting of students, participation of first responders, and notification of parents and reunification of students with parents. The other will be a lockdown simulation to be conducted and videotaped. Lockdown simulations require involvement of police, Homeland Security, the health department, and the mental health board.

Also, and in conjunction with the fire and health departments, a shelter-in-place drill will be conducted at each of CPS’s 79 schools and up to 35 of the Archdiocese partner schools by December 2006. Finally, CPS personnel already trained in Critical Incident Stress Management will remain an integral part of response training support.

Coordination with Partners – CPS and its first-responder partners will be the primary coordinating entities involved in the crisis. Each will have been trained and have up-to-date expertise on the Emergency Management Plan, the Hamilton County Emergency Operations Plan, and their own fields of emergency responsibilities. They will report to the overall incident commander and have operational flexibility as warranted by the local situation while also operating in the agreed-upon NIMS command structure.

Communication – Communication in time of response will involve both appropriate hardware and processes.  Hardware will include communications systems capable of mass broadcast (automated phone and email notification) and access to relevant CPS databases, such as the location and special needs of students with disabilities. Hardware will also involve equipping the Command Vehicle with these types of communications abilities.  Processes will involve who communicates what information when and to whom. CPS and its first-responder partners will speak with one voice through either the CPS public information officer or the incident commander, as outlined in the Emergency Management Plan. This information will be relayed via the Internet, automated phone systems, and the media. Information will include both general reporting on the crisis as well as actions to be taken in response.

Phase Four:  Recovery

Training – CPS staff will be trained in the importance of returning to equilibrium in terms of physical plant and educational instruction. In terms of mental health, CPS staff trained in Critical Incident Stress Management will offer this expertise to staff, students and parents. All staff, partners and students will also be apprised of what worked correctly in the response to the emergency, and what did not work correctly. This information will be added to the Emergency Management Plan and will be the subject of subsequent training.

Coordination with Partners – After an emergency incident, all partners will assess the efficacy and practicability of the policies and procedures in the Emergency Management Plan, as well as the accuracy of school-specific threat and vulnerability assessments. They will recommend changes, improvements and possible re-assessments. Also, the Hamilton County Board of Mental Health, which works in conjunction with the Red Cross and the Inter-Agency School Crisis Team, a coalition of non-profit groups—will assist CPS in meeting the mental and emotional health needs of staff, students, parents, and first-responders.

Communication – Staff, students, parents and all members responsible for the Emergency Management Plan will be apprised of the response to the crisis, and, if possible, its cause. Again, this communication will emanate from a selected “voice” or “voices” within CPS, such as the public information officer, the chief operating officer, or the superintendent. Actions, such as the re-scheduling, resumption or relocation of classes, will also be communicated via the Internet, media, and, in the case of parents, by Cincinnati Parents for Public Schools.

# NEXT STEPS:

Crisis mitigation and prevention are based on accurate knowledge of actual and potential threats on a site-specific basis.  As a result of CPS’s building plan, conditions at school sites are changing.  External threats to each location—for instance, weather events, proximity to a chemical plant or a flood-prone creek—might not change, but their potential effects might.  At present, the Cincinnati Fire Department has paper records, by quadrant of the Cincinnati area, of the location of external hazards near the schools, and is engaged in an effort to compile a Cincinnati Area Geographic Information Systems database that eventually will make such information available on a site-by-site basis for Cincinnati’s 54,000-some large buildings, including schools.  But this information now exists only on paper, and CPS has very uneven, non-systematized data for the schools.  CPS has a strategic approach to gain this site-specific knowledge and sustaining its accuracy on an ongoing basis:  the program design includes contracting, in consultation with Hamilton County Homeland Security, with a highly credentialed vulnerability assessment firm to train, supervise, and advise the IMT and staff from each school on a train-the-trainer basis to assess their site vulnerabilities.

CPS also aims to address weaknesses in its communications and coordination on three fronts:  First, at present there is no consolidated information available on the CPS website regarding the district’s Emergency Management Plan and procedures for parents and community members. With the grant assistance, CPS will create a user-friendly webpage that provides emergency response information in one place.  The webpage will also serve as one route of notification of an ongoing emergency. Second, staff time will be used to upgrade the district’s notification procedures to automated phone calling and email.  Third, Cincinnati’s hilly terrain and the spread of the school district pose special challenges in maintaining incident command communications and coordination. CPS needs to mitigate such difficulties by outfitting a Command Vehicle (already in CPS’s possession) with communications equipment, high-speed Internet capacity, backup power, and other emergency supplies.

The IMT has created a coherent, logically structured, and effective program of training for staff and students that will ensure consistency of action and command while at the same time accommodating different conditions at individual school sites.  CPS now needs to contract with a training coordinator and implement a comprehensive and coordinated training program that will include NIMS IS 700 certification for staff down to the individual school building level. The program will be based on train-the-trainer methodology to ensure sustainability.

Another gap in preparedness is actual emergency supplies for each school in the form of a crisis response kit (GoKit).  The purchase of GoKits for CPS schools will now be possible through our grant monies if the Cincinnati Health Department cannot provide them to us through their own grant monies.

While CPS currently keeps fully documented information for students with disabilities and/or language limitations, this information is not available in a single-source, easily accessible report for first responders.  CPS will support staff time for the data collection and entry needed to create this report, which will be invaluable in reunification of students with their parents following a crisis.

Finally, since CPS has only recently created its Emergency Management Plan, its policies and procedures have not been communicated to prepare parents, students, and the public at large.  The following initiatives will be undertaken:  1) four community events will be sponsored that will include all CPS responder partners as well as key members of the business community; 2) a contract with the Cincinnati chapter of Parents for Public Schools for parent involvement; and 3) production of a brochure in the several languages spoken in CPS homes providing concise information about CPS’s emergency management and actions for parents to take in the event of a crisis.

CPS and its coordinating partners have strong working relationships, and all are committed to testing emergency response procedures through practice drills and exercises.  For example, several shelter-in-place exercises have been conducted at CPS schools with the participation of the Cincinnati Fire Department and Health Department. However, funds are lacking to support the sustained level of practice required to reinforce staff training and to ensure that students, staff, and responders actually carry out procedures they have been taught.  CPS will support a series of two tabletop exercises and one major crisis simulation, as well as a shelter-in-place exercise at every CPS school in the district. Additionally, CPS will support production of laminated shelter-in-place posters designating the shelter location in each school and production of a shelter-in-place video for classroom use.

CPS has provided training in Critical Incident Stress Management (CISM) to its security personnel and advanced CISM training for 125 of its school psychologists, nurses, social workers, and counselors. These staff will serve as a resource in coordination with Cincinnati Community Mental Health Board for following up with staff, students, and parents after an emergency. Again, staff and responders are lacking in practice for crisis situations, which will be gained through the drills and simulation.

Cincinnati Public Schools will use an evaluation process designed around the principles of learning, practicing, continuous improvement, and sustainability of results. Several levels and types of assessment will be included in an overall evaluation process conducted by CPS’s Department of Research, Evaluation & Testing.

To accomplish the scope of evaluation intended, CPS proposes to create a project performance database in a secure area on the CPS intranet.  The database will be designed to 1) count track, and document progress on performance measures related to intended outcomes, and 2) provide feedback to inform decisions about needed adjustments in CPS’s emergency management policies and procedures.

The project performance database will track quantitative and process information in six areas bearing on the intended outcomes for the project:

- Vulnerability Assessment – Cincinnati Public Schools presently has only general information about risks and hazards at each school site, so establishing useful, quantitative, and accessible baseline information is a top evaluation priority. Quantitative and process measures will include:  number and dates of individuals trained; number/dates of vulnerability assessments completed; and number/dates of completed vulnerability assessments evaluated and revised.

- School Response Plans – Each SIRT is responsible for adapting a template provided in the district-wide Emergency Management Plan to prepare a School Response Plan customized to their school. Quantitative and process measures will include: number/dates of schools adapting their plans; number/dates of plans uploaded to CPS secure website for access by responders; number/dates of plans revised to reflect changes from vulnerability assessments.

- Meetings of the Emergency Management Team and Advisory Committee – The database will be used to document meeting dates, number/names of attendees, and decisions taken.

- Training and Practice – Quantitative and process measures will include: number/dates of SIRTs completing training in FEMA Multi-Hazard Training for Schools, CPS Emergency Management Plan, WMD/Hazmat, use and maintenance of GoKit; number/dates of individuals achieving NIMS IS 700 certification; number, dates, participants, and response time in tabletop exercises, drills, and simulations.

- Parent and Community Awareness – The database will be used to track number/dates of parent and community participation in the four community events; number/dates of parent, student, and community members taking American Red Cross workshops; names/date of formation of Parent Advisory Council; number/dates of parents participating in Parents for Public Schools awareness survey.

- Special Populations – The database will be used to document that information regarding students with disabilities or language challenges has been added and is accessible as needed.

Several sources of qualitative information will also be electronically captured:

- The vulnerability assessment firm will evaluate how well each school team carries out its assessment, including whether the training has been followed to ensure that all relevant hazard information is captured, whether and how successfully the team used the assessment template adapted from Hamilton County Homeland Security, the extent to which potential obstacles were identified and addressed, and whether the process needs action or improvement;

- A crisis management expert will evaluate the tabletop exercises and the simulation; key evaluation questions will include whether participants are able to identify the communication, resources, coordination, and organizational elements associated with an emergency response; whether they are able to identify policy issues that need to be considered in responding to a large-scale event, and how each individual assesses his/her own preparedness;

- The Fire Department regularly completes an evaluation for each shelter-in-place drill it conducts, following key questions in a pre-exercise packet given to the school – as examples, Are they prepared to respond? Do they have appropriate internal communications?  How will they assign tasks to individuals in the school?

- The Cincinnati chapter of Parents for Public Schools will conduct and analyze two parent perception surveys, one toward the beginning and one at end of the project.  The first survey will assess the extent to which parents understand what they should do in the event of an emergency at their child’s school. The second will be administered after 12 months to determine how much has changed in parent responses, what still needs to be done, and if there are particular populations that need outreach and education.

Both quantitative and qualitative feedback will be used by the IMT and the Advisory Committee so that appropriate actions or interventions can be taken and determinations made whether particular policies and procedures should be continued or discontinued, practiced more or less frequently, or monitored for further information. This ongoing monthly analysis and reporting will be the basis for revision and continuous improvement of CPS’s Emergency Management Plan.

In addition to the monthly reporting to project stakeholders, there will be two formal interim reports and a final report.  The two interim evaluations will analyze the quantitative and process information from the database and the qualitative information from these external sources to provide reports of progress focusing on the outcomes CPS intends. The final evaluation will include the summary of all data collected and reported through the database, “lessons learned” throughout the project, and recommended future steps to assure that vulnerability assessments are conducted routinely, plans are updated as needed, and communication around the plans to all stakeholders is ongoing.

# EXPECTED OUTCOMES:

CPS expects the following significant outcomes:

- As the result of a coherent program of training, practice, and assessment – including vulnerability assessment at each school site – CPS staff and students will have the knowledge and practical capacity to respond quickly, appropriately, and with less fear to a range of emergency situations that could arise at school.

- As the result of collaborative decision making in the Advisory Committee and joint conduct of an ambitious program of frequent drills, tabletop exercises, emergency simulation, and response assessment, CPS and its first responder and other key community partners will have a higher efficiency and deeper quality of coordination.

- As the result of carefully developed and implemented communications – including information translated into five additional languages other than English – parents and guardians will know where and how to proceed in an emergency to be reunited with their children, and the public will be aware of CPS policies and procedures for emergency response.

- As the result of CPS’s train-the-trainer strategy and its philosophy of continuous improvement through assessment and evaluation, emergency response knowledge and capacity will be increased and sustained.

- As the result of a dedicated effort to identify the locations and particular needs of students with disabilities or limited English proficiency in a single easily accessible report, CPS staff and first responders will be better able to assist these students in an emergency to mitigate any anxiety for these students and their parents easing reunification.

# LEADERSHIP DEVELOPMENT OPPORTUNITIES:

EPHLI has provided me with a valuable opportunity to take on new challenges in my career.  It has strengthened my dedication to making a difference in Environmental Health.

The participation in the Environmental Public Health Leadership Institute has been a phenomenal growth experience for me.  One of the greatest advantages I have gained is the ability to meet peers and mentors.  It has been a great honor to collaborate with other fellows who face similar problems and issues in Environmental Health.  Mentors laid the groundwork for future collaboration prospects and provided excellent leadership.  The instructors through their various activities, assignments, exercises, and lectures helped all the fellows become self-motivated to apply the new techniques they were learning and begin to make a difference immediately at their work place.

Another advantage was that EPHLI gave me the chance to gain more context knowledge and help me immediately apply new ideas and concepts to my normal day-to-day tasks.  I have been able to incorporate many of the new methods, such as critical thinking and systems modeling to name a few, into daily operations and large projects.

I believe my participation in EPHLI shows that there is no boundary for Environmental Health.  I work for a school district and under the normal umbrella of Environmental Health, I would not be invited to the table as a player.  It is a common mistake to not consider schools and private companies as groups who are stakeholders in Environmental Health and can make a positive contribution to Environmental Health advancements.  Environmental Health reaches into all aspects of our world and efforts like EPHLI will be what helps bring the importance of Environmental Health into the national spotlight where it belongs.

# ABOUT THE EPHLI FELLOW:

Jessica Miller Shelly, RS, REHS, MBA is a Supervisor of Building Operations & Food Services for Cincinnati Public Schools.  She is responsible for overseeing the daily operations at 79 schools along with serving as a core member of the Incident Management Team.

Before joining the school district, Ms. Shelly worked in local health department jurisdictions for ten years.  Most recently, she was a Senior Registered Environmental Health Specialist for the Cincinnati Health Department.  Jessica was responsible for a myriad of tasks including: serving on the Bioterrorism Public Health Response Team; teaching ServSafe® to foodservice operators; conducting internal audits of state and local mandated programs; developing inspection methodology for sanitarians; presenting environmental health issues to companies and community groups; and composing and submitting grants, position papers, and publications.

Ms. Shelly has received many accolades for her dedication and work in environmental health.  She has received three City of Cincinnati Outstanding Customer Service Awards, The Educational and Career Development Award from the City of Cincinnati, and Ms. Shelly was a City of Cincinnati Seasongood Award winner for her ServSafe® program which helped demonstrate that food safety education lead to a dramatic decease of critical violations in food establishment inspections.

Ms. Shelly was chosen to participate in the Center for Disease Control and Prevention’s 1st Annual Emerging Leaders Workshop in Atlanta in December 2003.  Ms. Shelly was also selected to be part of the 2003-2004 Ohio Public Health Leadership Institute for her “Clean Streets, Safe City” agenda.

Ms. Shelly has been a speaker at several conferences including the Ohio Environmental Health Association Southwest Conference, the Ellenbee Leggett Food Show, and most recently she was the spotlight speaker at the School Nutrition Association’s national conference in Baltimore, Maryland in July 2005.

Ms. Shelly is a member of various professional organizations including: Junior League of Cincinnati; National Environmental Health Association; International Food Safety Council; Professional Association of Code Enforcement, and National Association of Female Executives.

Ms. Shelly’s undergraduate degree in Zoology is from Miami University.  She graduated summa cum laude with her MBA in Management, International Business, and Marketing from the University of Cincinnati and was honored as the 2002 Outstanding Graduate Student of the Year.

# REFERENCES:

- 10 Essential Public Health Services, http://www.cdc.gov/nceh/ehs/home/HealthService.htm

- CDC Health Protection Goals, http://www.cdc.gov/about/goals/default.htm

- National Strategy to Revitalize Environmental Public Health Services, http://www.cdc.gov/nceh/ehs/Docs/nationalstrategy2003.pdf

# Text boxes

Emergency Preparedness

Lack of Personnel Resources

Budget Restraints

Public Awareness

Public Demand for Preparedness

School’s Involvement & Responsibility is lessened

Train schools to handle their own multi-hazard events

CPS is not prepared to respond to a

multi-hazard event

Central Office handles

all multi-hazards

VARIABLES

TIME