## PA-PWs&Dollars
Public Assistance Project Worksheets (PWs) and Dollars
Katrina Summary
Project Worksheets (PWs)/ Dollars ($s) Summary | Katrina | Changes Since Last Report | Numbers from LAST REPORT | Difference (calc'd automatically)
Projected PWs | 22750 | 0 | 22750 | 0
PWs in NEMIS | 22739 | 12 | 22727 | 12
Projects Est. to Write | 11 | -12 | 23 | -12
PW's Obligated (Paid to State) | 22520 | 1% | 22520 | 0.01
% PWs Obligated (of Projected) | 98.99% | Not Applicable | 98.99% | Not Applicable
% PWs Obligated (in NEMIS) | 99.04% | Not Applicable | 99.09% | Not Applicable
Current Estimated $s | 3598617886.15 | 0 | 3598617886.15 | 0
Total $s Eligible in NEMIS | 2973458381.38 | 6464813.66 | 2966993567.72 | 6464813.66
Projected $s Est. to Write | 625159504.77 | -6464813.66 | 631624318.43 | -6464813.66
Total $s Obligated (Paid to State) | 2867345490.26 | 0 | 2867345490.26 | 0
% $s Obligated (of Estimated) | 79.68% | Not Applicable | 79.68% | Not Applicable
% $s Obligated (in NEMIS) | 96.43% | Not Applicable | 96.64% | Not Applicable
NOTE: "Changes Since" numbers in main table will be automatically updated from the above table.

## Debris-Data
Key Counties Where Debris Clean Up Is Not Yet Complete
Overview of High Priority Counties for Katrina | [13 empty] | Total Debris Removed | Total Debris Remaining
Right of Way (ROW)* |  |  |  |  | Private Property Debris Removal (PPDR) |  |  |  | Demolitions
County | Estimated ROW (CY) | Remaining ROW (CY) | Completed ROW (CY) | Percent Complete | County | Estimated PPDRs (CY) | PPDRs Remaining (CY) | PPDRs Completed (CY) | County | Estimated Demos (#) | Remaining Demos (#) | Completed Demos (#) | Percent Complete
Hancock | 6691582 | 0.35 | 6691581.65 | 100% | Hancock | 1446733 | 0 | 1446733 | Hancock | 1825 | 0 | 1706 | 93.48% | 8138314.65 | 0.35
Harrison | 11923101 | -0.09 | 11923101.09 | 100% | Harrison | 2549204 | 0 | 2549204 | Harrison | 1923 | 0 | 1923 | 100% | 14472305.09 | -0.09
Jackson | 6922812 | -0.35 | 6922812.35 | 100% | Jackson | 1586465 | 0 | 1586465 | Jackson | 1270 | 0 | 1270 | 100% | 8509277.35 | -0.35
Total | 25537495 | -0.09 | 25537495.09 | 100% | Total | 5582402 | 0 | 5582402 | Total | 5018 | 0 | 4899 | 97.63% | 31119897.09 | -0.09
Total Debris Summary All Counties 08/27/2008
Katrina
| USACE |  | Estimate (CY) | Actual (CY) | %Complete
| Curbside |  | 15588363 | 15588363 | 100%
| PPDR |  | 3906683 | 3906683 | 100%
| DEMO |  | 820722 | 820722
Waterways and Ditches
| TOTALS |  | 20315768 | 20315768 | 100%
| Applicant |  | Estimate (CY) | Actual (CY) | %Complete
| Curbside**** |  | 25582748 | 25582748.09 | 100%
| PPDR |  | 0 | 0
| DEMO***** |  | 132440 | 132440 | 100%
| Waterways |  | 0
| TOTALS |  | 25715188 | 25715188.09 | 100%
| USCG |  | Estimate (CY) | Actual (CY) | %Complete
| Waterways |  | 400000 | 389935.42 | 97.48%
| TOTAL of Katrina |  | 46430956 | 46420891.51 | 99.98%
DATA HAS NOT CHANGED

## State_Payout_Summary
State Payout Summary,10/22/2008
1604 Summary of Funds Obligated by FEMA to the State and Paid Out by the State to Applicants By Category of Work and By High Priority Counties
Type of Work | FEMA Obligated Funds Paid to the State | State Payout (Paid to Applicants) | % Obligated Funds Paid Out By State
Emergency Work (Cat A & B) | 1083403044.58 | 1042079182 | 96.19%
Permanent Work (Cat C-G) | 1654331819.56 | 506281785 | 30.6%
Admin Costs | 129610626.12 | N/A | N/A
SUM: | 2867345490.26 | 1548360967 | 54%
High Priority Counties | FEMA Obligated Funds Paid to the State | State Payout (Paid to Applicants) | % Obligated Funds Paid Out By State
Hancock | 459755250 | 244664012 | 53.22%
Harrison | 1095677931 | 393474924 | 35.91%
Jackson | 235976870 | 127038589 | 53.84%
Description of Damage Category Codes
Emergency Work |  | Permanent Work
Category A: Debris Removal |  | Category C: Roads & Bridges
Category B: Emergency Protective Measures |  | Category D: Water Control Facilities
Category E: Public Buildings
Category F: Public Utilities
Category G: Recreational or Other

## PA_Funding-Graph
First month of reported data for Funds Disbursed from State to Applicant is July 2006.

## PA_Funding-Data
Cumulative Billions of Dollars | 2005-09-01 | 2005-10-01 | 2005-11-01 | 2005-12-01 | 2006-01-01 | 2006-02-01 | 2006-03-01 | 2006-04-01 | 2006-05-01 | 2006-06-01 | 2006-07-01 | 2006-08-01 | 2006-09-01 | 2006-10-01 | 2006-11-01 | 2006-12-12 | 2007-01-12 | 2007-01-17 | 2007-01-24 | 2007-01-31 | 2007-02-07 | 2007-02-14 | 2007-02-21 | 2007-02-28 | 2007-03-07 | 2007-03-14 | 2007-03-21 | 2007-03-28 | 2007-04-04 | 2007-04-11 | 2007-04-18 | 2007-04-25 | 2007-05-02 | 2007-05-09 | 2007-05-16 | 2007-05-23 | 2007-05-30 | 2007-06-06 | 2007-06-13 | 2007-06-20 | 2007-06-27 | 2007-07-05 | 2007-07-11 | 2007-07-18 | 2007-07-25 | 2007-08-01 | 2007-08-08 | 2007-08-15 | 2007-08-22 | 2007-08-29 | 2007-09-05 | 2007-09-12 | 2007-09-19 | 2007-09-26 | 2007-10-03 | 2007-10-17 | 2007-10-11 | 2007-10-24 | 2007-10-31 | 2007-11-14 | 2007-11-07 | 2007-11-20 | 2007-11-28 | 2007-12-05 | 2007-12-12 | 2007-12-19 | 2008-01-02 | 2008-01-09 | 2008-01-16 | 2008-01-23 | 2008-01-30 | 2008-02-06 | 2008-02-13 | 2008-02-20 | 2008-02-27 | 2008-03-06 | 2008-03-12 | 2008-03-19 | 2008-03-26 | 2008-04-02 | 2008-04-09 | 2008-04-16 | 2008-04-23 | 2008-04-30 | 2008-05-07 | 2008-05-14 | 2008-05-21 | 2008-05-29 | 2008-06-04 | 2008-06-11 | 2008-06-18 | 2008-06-25 | 2008-07-02 | 2008-07-09 | 2008-07-16 | 2008-07-23 | 2008-07-30 | 2008-08-06 | 2008-08-06 | 2008-08-20 | 2008-08-27 | 2008-09-03 | 2008-09-10 | 2008-09-17 | 2008-09-24 | 2008-10-01 | 2008-10-08 | 2008-10-15 | 2008-10-22
Federal Share of Obilgated Dollar Amount | 0.17 | 0.39 | 0.57 | 0.65 | 0.74 | 0.8 | 0.88 | 1.07 | 1.23 | 1.46 | 1.52 | 1.66 | 1.72 | 1.79 | 1.86 | 1.91 | 1.92 | 1.92 | 1.9 | 1.9 | 1.92 | 1.94 | 1.94 | 1.94 | 1.96 | 1.98 | 1.99 | 2 | 2 | 2.03 | 2.03 | 2.03 | 2.06 | 2.08 | 2.09 | 2.09 | 2.11 | 2.11 | 2.13 | 2.12 | 2.12 | 2.16 | 2.2 | 2.2 | 2.2 | 2.25 | 2.26 | 2.26 | 2.27 | 2.28 | 2.28 | 2.28 | 2.29 | 2.29 | 2.29 | 2.29 | 2.3 | 2.3 | 2.292 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.36 | 2.36 | 2.36 | 2.36 | 2.41 | 2.41 | 2.42 | 2.47 | 2.47 | 2.47 | 2.49 | 2.568 | 2.57 | 2.62 | 2.62 | 2.81 | 2.82 | 2.82 | 2.83 | 2.82 | 2.82 | 2.82 | 2.82 | 2.83 | 2.83 | 2.84 | 2.84 | 2.84 | 2.84 | 2.84 | 2.85 | 2.85 | 2.85 | 2.85 | 2.85 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87
Funds Disbursed from State to Applicant | [10 empty] | 0.63 | 0.69 | 0.77 | 0.83 | 0.89 | 0.91 | 0.96 | 0.97 | 0.98 | 0.98 | 1 | 1.02 | 1.02 | 1.03 | 1.03 | 1.03 | 1.04 | 1.04 | 1.04 | 1.04 | 1.05 | 1.06 | 1.06 | 1.06 | 1.1 | 1.1 | 1.11 | 1.11 | 1.12 | 1.13 | 1.13 | 1.14 | 1.14 | 1.15 | 1.15 | 1.16 | 1.16 | 1.18 | 1.2 | 1.2 | 1.21 | 1.22 | 1.23 | 1.24 | 1.25 | 1.26 | 1.27 | 1.27 | 1.274 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.31 | 1.32 | 1.32 | 1.33 | 1.34 | 1.34 | 1.34 | 1.34 | 1.36 | 1.36 | 1.36 | 1.365 | 1.37 | 1.37 | 1.37 | 1.39 | 1.39 | 1.39 | 1.39 | 1.39 | 1.41 | 1.42 | 1.42 | 1.42 | 1.43 | 1.44 | 1.45 | 1.46 | 1.47 | 1.48 | 1.48 | 1.49 | 1.50 | 1.50 | 1.51 | 1.51 | 1.51 | 1.51 | 1.53 | 1.53 | 1.53 | 1.54 | 1.55

## PW_Worksheets-Data
Project Worksheets Obligated
Date Obligated | Project Obligation Trend
2006-08-04 | 9741
2006-08-11 | 9819
2006-08-18 | 9964
2006-08-25 | 10086
2006-09-01 | 10012
2006-09-08 | 10138
2006-09-15 | 10257
2006-09-22 | 10485
2006-09-29 | 10493
2006-10-06 | 10575
2006-10-13 | 10649
2006-10-20 | 10819
2006-10-27 | 11033
2006-11-03 | 11033
2006-11-08 | 11074
2006-11-17 | 11285
2006-12-01 | 11521
2006-12-08 | 11554
2006-12-15 | 11632
2006-12-22 | 11792
2006-12-29 | 11792
2007-01-05 | 11803
2007-01-11 | 11827
2007-01-24 | 11994
2007-01-31 | 12013
2007-02-07 | 12088
2007-02-14 | 12111
2007-02-21 | 12111
2007-02-28 | 12161
2007-03-07 | 12204
2007-03-14 | 12213
2007-03-21 | 12271
2007-03-28 | 12307
2007-04-04 | 12345
2007-04-11 | 12402
2007-04-18 | 12633
2007-04-25 | 12660
2007-05-02 | 12693
2007-05-09 | 12725
2007-05-16 | 12763
2007-05-23 | 12811
2007-05-30 | 12830
2007-06-06 | 12868
2007-06-13 | 12885
2007-06-20 | 12891
2007-06-27 | 12842
2007-07-05 | 15816
2007-07-11 | 20228
2007-07-18 | 20535
2007-07-25 | 20535
2007-08-01 | 20599
2007-08-08 | 20617
2007-08-15 | 20617
2007-08-22 | 20705
2007-08-29 | 20723
2007-09-05 | 20775
2007-09-12 | 20828
2007-09-19 | 20878
2007-09-26 | 20884
2007-10-03 | 20956
2007-10-10 | 20956
2007-10-17 | 21032
2007-10-24 | 21052
2007-10-31 | 21101
2007-11-06 | 21101
2007-11-14 | 21145
2007-11-20 | 21175
2007-11-28 | 21225
2007-12-05 | 21254
2007-12-12 | 21261
2007-12-19 | 21261
2008-01-02 | 21352
2008-01-09 | 21352
2008-01-16 | 21352
2008-01-23 | 21352
2008-01-30 | 21385
2008-02-06 | 21385
2008-02-13 | 21452
2008-02-20 | 21494
2008-02-27 | 21559
2008-03-06 | 21559
2008-03-12 | 21682
2008-03-19 | 21773
2008-03-26 | 21777
2008-04-02 | 21806
2008-04-09 | 21821
2008-04-16 | 21827
2008-04-23 | 21871
2008-04-30 | 21878
2008-05-07 | 21940
2008-05-14 | 22011
2008-05-21 | 22011
2008-05-29 | 22051
2008-06-04 | 22051
2008-06-11 | 22146
2008-06-18 | 22146
2008-06-25 | 22172
2008-07-02 | 22172
2008-07-09 | 22227
2008-07-16 | 22227
2008-07-23 | 22227
2008-07-30 | 22249
2008-08-06 | 22249
2008-08-13 | 22249
2008-08-20 | 22249
2008-08-27 | 22365
2008-09-03 | 22389
2008-09-10 | 22389
2008-09-17 | 22447
2008-09-24 | 22447
2008-10-01 | 22520
2008-10-08 | 22520
2008-10-15 | 22520
2008-10-22 | 22520

## EXCEPTION REPORT
This Exception Report worksheet is provided for TROs to communicate significant changes to or issues with report numbers. For each exception, use a different line and be sure to clearly communicate the item. GCRO will determine whether or not to make a note of it on the actual relevant chart/graph.
*Please remove obsolete exception comments
Date | Exception Comment
2007-01-24 | ROW numbers include PPDRs and DEMOs
2007-01-24 | Applicant Curbside includes PPDR or DEMO
2007-01-24 | Applicant DEMO numbers are for debris removed since 8/31/06
2007-02-22 | Marine debris estimated CY reduced following completion of Coastline to 1/2 mile debris removal contract.
2007-03-14 | Marine debris estimated CY increased following completion of N of I-10 project.
2007-06-13 | Per NEMIS S-5, 6-9-07 - CAL- Adjusted Current 100% Estimates to reflect the 100% Cost Share change as per instructed by Bob McDonald and Carol Gruber @ the DFC for the DFSR. Cost share adjustment is equal to 141 million, with a legitimate remaining cost projection to match the existing proj's and spending plan for last cycle of 365.9 million. creating a new Rem. Cost of 507 million, which will reduce on its own once the cost share has been moved up to the 100%.
2007-06-28 | Please note on the PW_Worksheets-Graph and PW_Worksheets-Data tabs, from April 18, 2007 to June 20, 2007 the numbers reported were the Total Number of Project Worksheets in NEMIS and not the Project Worksheets Obligated in NEMIS.
2007-08-01 | Please note on the Debris Data tab from July 25, 2007 the formulas were incorrect. The report today has been updated and has correct formulas.
2007-08-08 | Please note there will be no change for State of Mississippi data. All numbers will be updated next week, August 16, 2007.
2007-09-19 | Please note there has been no change to the dry debris data since September 4, 2007.
2007-10-18 | Marine Debris totals have not changed this week due to a conflict in the data reported.
2007-10-31 | Please note there has been no change to the dry debris data since September 4, 2007.
2007-11-28 | Please note the estimated wet debris has increased from 300,000 cubic yards to 350,000.
2007-12-12 | Please note dry debris has updated (previous update 9/4/07.)
2008-01-02 | Please note projected PWs on the PA-PWs&Dollars tab have increased from 21,500 to 21,750.
2008-01-02 | Please note on the PA-PWs&Dollars tab the Changes Since Last Report Column indicates changes since 12/19/2007 (a two week period)
2008-01-23 | Please note the dry debris data is as of 1/9/08
2008-01-30 | Please note the dry debris data is as of 1/9/08
2008-02-13 | Please note the wet debris was at an estimated change of 375,000
2008-03-26 | Dry debris is currently at 100%. No updates were provided as of March 26, 2008.