Highly Qualified Teacher (HQT) Plan

Connecticut

| Requirement 1: The revised plan must provide a detailed analysis of the core academic subject classes in the State that are currently not being taught by highly qualified teachers. |  |  |
| --- | --- | --- |
| Question: Does the revised plan include an analysis of classes taught by teachers who are not highly qualified? Is the analysis based on accurate classroom level data? |  |  |
| Actions/Strategies | Timeline | Indicators of Success |
| The Connecticut State Department of Education (CSDE) will perform its highly qualified teacher (HQT) analysis at the end of the 2005-06 school year. In order to comply with the requirements resulting from the federal Title II, Part A monitoring visit, the CSDE has revised the HQT analysis criteria that will be described in detail below: - The CSDE currently collects full-time equivalent (FTE) data for each subject a teacher teaches. The CSDE has collected a stratified random sample of course rosters in order to develop a methodology whereby the FTE data can be converted into accurate classroom-level data. Based on the findings, at the elementary level, an FTE of 1.0 will be recoded as one classroom. At the secondary level, an FTE of 1.0 will be recoded as five classes. As a further example, if a teacher is teaching biology 80 percent of the time and chemistry 20 percent of the time, the biology FTE will be recoded as four classes, and the chemistry FTE will be recoded as one class. - Per the recommendations of the USDOE, CSDE recently revised our requirements for our alternate route program entitled “Durational Shortage Area Permits” (DSAP); CSDE now requires all new applicants to have successfully passed the Praxis II (or ACTFL for world languages) exam prior to being awarded a DSAP and entering the classroom. - CSDE’s high objective uniform state standard evaluation (HOUSSE) process for documenting that veteran teachers and special education teachers demonstrate content knowledge has been accepted by the USDOE; CSDE’s HOUSSE process requires all veteran teachers who do not hold a major or master’s degree in the content area(s) they teach to complete HOUSSE. All special education teachers who serve as the primary instructor of any core academic content area must demonstrate content knowledge through the HOUSSE process also. - The CSDE has collected and validated the federally mandated quality indicators that will be used in conjunction with the existing certified staff file data in the HQT analysis. In order for teachers teaching core academic subjects to be considered highly qualified, these teachers must not only hold a bachelor’s degree and be fully certified in the content area, but also must: - have a college major in the subject(s) they are teaching; or - hold a master’s degree in the content area they are teaching; or - have passed a content exam for each subject(s) they teach; or - have successfully completed HOUSSE for each subject(s) they teach. The 2005-06 HQT analysis will rely on the above quality indicators to determine the highly qualified status of veteran teachers and special education teachers who did not pass a content exam when they first obtained certification. Also in response to the Title II, Part A monitoring findings, the 2005-06 HQT analysis will automatically assign a status of not highly qualified to teachers working under Durational Shortage Area Permits (DSAPs) unless those teachers have passed a content exam. | Completed Completed HOUSSE Plan formally accepted by USDOE on June 19, 2006 By the end of the 2006-07 school year Completed Completed | Conversion formula developed and implemented and data reported to USDOE using classes taught versus full-time equivalents. Detailed analysis attached. Beginning July 1, 2006, all new DSAP applicants will be awarded a DSAP only after demonstrating successful completion of the appropriate content area Praxis II or ACTFL exam. All veteran teachers and special education teachers, who are HOUSSE candidates will complete HOUSSE by the end the 2006-07 school year HOUSSE completed for veteran teachers and special education teachers Data system rules developed to match these criteria when calculating HQT data for each district and school. Detailed analysis attached Non-HQT DSAPS factored into detailed HQT analysis |

Summary Data

Analysis of Classes Taught by Teachers Who Are Not Highly Qualified Of the 128,318 core academic classes taught in Connecticut, 4,110 (3.2%) were taught by not highly qualified teachers. Of Connecticut’s 1,049 schools, 462 (44.0%) had classes taught by not highly qualified teachers, while 587 schools (56.0%) had no classes taught by not highly qualified teachers. The CSDE has identified 234 schools (22.3% - highlighted in yellow in the attached table) that fell below the goal of 96% HQT. These schools will receive priority attention in order to meet the 100% HQT goal by the end of the 2006-2007 school year. # See attached table named “HR1 N_Classes_FTEs_NHQ by Dist_Sch with Percent/Worksheet HR1 N_Classes NHQ with Percent” for the full list of schools. The twenty schools with the highest percentage of classes taught by NHQ teachers are listed below: Total; N Core Academic; % Core Academic. Core; Classes; Classes. Academic; Taught by; Taught by. Dist; Sch; District; School; Classes; NHQ Teachers; NHQ Teachers. 281; 1; Elm City College; Elm City College; 53; 29; 54.7. 282; 60; Stamford Academy; Stamford Academy; 60; 30; 50.0. 151; 10; Waterbury; Brooklyn Elementary School; 26; 10; 39.2. 64; 11; Hartford; Kinsella School; 117; 36; 30.8. 93; 65; New Haven; Polly T. McCabe Center; 21; 6; 29.3. 15; 42; Bridgeport; Curiale School; 159; 45; 28.3. 277; 1; Highville Mustard Seed; Highville Mustard Seed Charter School; 40; 11; 27.8. 64; 19; Hartford; Milner School; 86; 23; 26.7. 270; 1; Side By Side; Side By Side Community School; 29; 8; 25.9. 93; 9; New Haven; Davis 21st Century Magnet Elementary School; 42; 10; 24.1. 93; 70; New Haven; New Haven Academy; 66; 15; 22.9. 93; 69; New Haven; Riverside Educational Academy; 95; 20; 21.1. 15; 26; Bridgeport; Roosevelt School; 123; 25; 20.3. 15; 10; Bridgeport; Luis Munoz Marin School; 197; 40; 20.3. 163; 69; Windham; Windham Academy; 25; 5; 20.0. 57; 9; Greenwich; Old Greenwich School; 60; 12; 20.0. 64; 64; Hartford; Greater Hartford Classical Magnet School; 176; 35; 19.9. 64; 53; Hartford; Dr. Joseph Bellizzi Middle School; 251; 50; 19.9. 15; 9; Bridgeport; Garfield School; 41; 8; 19.5.

| Question: Does the analysis focus on the staffing needs of schools that are not making AYP? Do these schools have high percentages of classes taught by teachers who are not highly qualified? |  |  |
| --- | --- | --- |
| The CSDE identifies schools that are not making AYP based on the Connecticut Mastery Test (CMT) scores and the Connecticut Academic Performance Test (CAPT) scores in August of each year. The CMT is administered in grades 3 through 8, and the CAPT is administered in grade 10. The percentage of classes in each school being taught by non-HQT will be determined. Then, an analysis will be performed to determine if a higher percent of classes are being taught by non-HQTs in schools not making AYP than in schools making AYP. NOTE: The CSDE obtained 2005-2006 AYP data earlier than anticipated from its testing contractor, who experienced technical difficulties in scoring the CAPT exam. Therefore, the CSDE is able to provide data to LEAs in a more timely manner. | Annual analysis, beginning with the 2005-06 data, will be completed by Oct. of each year Semi-annual Update Jan/Feb | Produce and disseminate annual HQT report to districts and schools by November of each year, as part of the State NCLB Report Cards. The HQT report will relate to the current AYP status. Districts provided HQT data twice during the year. HQT analysis focused first on districts not meeting the current (2005-06 96%, 2006-07 100%) HQT benchmark. HQT analysis report presented to State Board in November. |
| Summary Data |  |  |
| Analysis of Classes Taught by Teachers Who Are Not Highly Qualified in Schools Not Making AYP Of the 337 schools that did not make AYP, 198 (58.6%) had classes taught by not highly qualified teachers, while 139 (41.4%) had no classes taught by not highly qualified teachers. Of the 712 schools that made AYP, 264 (37.0%) had classes taught by not highly qualified teachers, while 448 (63.0%) had no classes taught by not highly qualified teachers. The CSDE has identified 114 schools (highlighted in yellow in the attached table) that did not make AYP, and fell below the goal of 96% HQT. In addition, 120 schools that made AYP have been identified as not meeting the 96% HQT goal (highlighted in green in the table below). These two groups of schools will receive priority attention in order to meet the 100% HQT goal by the end of the 2006-2007 school year. ## See attached table named “HR1 N_Classes_NHQ by Dist_Sch with Percent_AYP” |  |  |

| Question: Does the analysis identify particular groups of teachers to which the State’s plan must pay particular attention, such as special education teachers, mathematics or science teachers, or multi-subject teachers in rural schools? |  |  |
| --- | --- | --- |
| Since the 1970’s, the CSDE has collected data on an annual basis about what subjects a teacher teaches. These staff data files along with the annual fall hiring report identify the shortage areas, which include mathematics, science and special education. For the 2005-06 HQT analysis, the CSDE has also collected data about the type of classroom setting in which each special education teacher is working. That is, whether the teacher is the primary teacher in a content area, co-teaching with a content specialist, or resource/support only. If the special education teacher is responsible for instruction, the teacher must: - have a college major in the subject(s) they are teaching; or - hold a master’s degree in the content area they are teaching; or - have passed a content exam for each subject(s) they teach; or - have completed HOUSSE for each subject(s) they teach. There are several rural school districts, identified as Small Rural School Assistance (SRSA) grant recipients under the Rural Education Assistance Program (REAP), in Connecticut in which some teachers work in a departmentalized setting. The CSDE has collected data about the quality indicators listed above for all multi-subject teachers working in these rural schools. | Annual analysis, beginning with the 2005-06 data, will be completed by Nov. of each year Biannual Update Nov/ Jan | Annual analysis will focus upon particular sub-groups of teachers, including special education, mathematics and science teachers. These are all areas of shortage within our state. Produce and disseminate annual HQT report to districts and schools by November of each year as part of the State NCLB Report Cards. The HQT report will relate to the current AYP status. Districts provided HQT data twice during the year. HQT analysis focused first on districts not meeting the current (2005-06 96%, 2006-07 100%) HQT benchmark. HQT analysis report presented to State Board in November. Annual fall hiring report presented to the State Board – copy attached. Rural districts will be included in the annual analysis each year and compared to suburban and urban districts for HQT purposes. |

| Summary Data |  |  |
| --- | --- | --- |
| #### Analysis of Not Highly Qualified Teachers by Core Academic Subjects Of the 36,379.1 teacher FTEs in core academic subject areas in Connecticut, 916.3 (2.5%) teacher FTEs were not highly qualified. Priority attention will be given to all schools (highlighted in yellow in the attached table) that have not met the 96% HQT goal for all core academic subject areas, and specifically for math, science, and world languages in order to help them reach the goal of 100% HQT by the end of the 2006-2007 school year. *Special Education classes and teachers were not included in the specific subject area totals (see table) since Connecticut is currently developing a method to collect data about the specific core academic subjects these teachers teach when they are primarily responsible for instruction. Although not reported in the summary, the special education assignments were reported in the HQT data validation project conducted during the 2005-2006 school year, and have been analyzed to determine if they are HQT. ## See attached table named “HR1 N_Classes by Dist_Sch_Asg with Percent/Worksheet HR1 % Teachers NHQ” Overall, the percentage of NHQ teachers by subject areas is as follows: Total. Core; Total; Teacher; % Teacher. Academic; Teacher; FTE; FTE. Dist; Sch; District; School; Assignments; FTE; NHQ; NHQ. *State Totals by Core Academic Subject Areas; Mathematics; 3,021.4; 175.0; 5.8. World Languages; 1,804.9; 96.7; 5.4. Science; 2,882.2; 144.4; 5.0. English Language Arts; 3,393.1; 137.9; 4.1. Reading; 1,330.8; 30.9; 2.3. Music; 1,583.9; 26.5; 1.7. Social Studies; 2,697.4; 27.2; 1.0. Elementary; 11,548.1; 93.5; 0.8. Art; 1,336.0; 10.6; 0.8. |
| Question: Does the analysis identify districts and schools around the State where significant numbers of teachers do not meet HQT standards? |  |  |
| The CSDE determines the percentage of non-HQT by district and school, and by high poverty and low poverty schools. The analysis includes identifying those districts and schools who are not meeting the 2005-06 benchmark of 96 percent HQT. For those districts a semi-annual monitoring report on progress towards meeting HQT will be published. This information will continue to be published in the annual state and district report cards in November. | Annual analysis, beginning with the 2005-06 data, will be completed by October of each year Semi-annual Update Jan/Feb | Produce and disseminate annual HQT report to districts and schools by November of each year as part of the State NCLB Report Cards. The HQT report will relate to the current AYP status. Districts provided HQT data twice during the year. HQT analysis focused first on districts not meeting the current (2005-06 96%, 2006-07 100%) HQT benchmark. HQT analysis report presented to State Board in November. |
| ### Summary Data Analysis of Not Highly Qualified Teacher FTEs Of the 36,379.1 total teacher FTEs in Connecticut in core academic subjects, 916.3 (2.5%) were identified as NHQ. Of the 1,049 schools, 462 (44.0%) had teachers who were NHQ, while 587 schools (56.0%) had no teachers who were NHQ. The CSDE has identified 193 schools (18.3% - highlighted in yellow in the table below) that fell below the goal of 96% HQT. These schools will receive priority attention in order to meet the 100% HQT goal by the end of the 2006-2007 school year. See attached table named “HR1 N_Classes_FTEs_NHQ by Dist_Sch with Percent/Worksheet FTE Sums NHQ with Percent” for the full list of schools. |  |  |
| Total. Total; Teacher; % Teacher. Teacher; FTE; FTE. Dist; Sch; District; School; FTE; NHQ; NHQ. 282; 60; Stamford Academy; Stamford Academy; 12.0; 6.0; 50.0. 281; 1; Elm City College; Elm City College; 20.2; 9.0; 44.6. 93; 60; New Haven; Metropolitan Business High School; 13.0; 5.0; 38.5. 93; 65; New Haven; Polly T. McCabe Center; 4.2; 1.2; 28.9. 241; 31; CREC; Montessori Magnet School; 14.2; 4.0; 28.2. 93; 70; New Haven; New Haven Academy; 13.1; 3.0; 22.9. 277; 1; Highville Mustard Seed; Highville Mustard Seed Charter School; 13.5; 3.0; 22.2. 93; 69; New Haven; Riverside Educational Academy; 19.0; 4.0; 21.1. 163; 69; Windham; Windham Academy; 5.0; 1.0; 20.0. 64; 64; Hartford; Greater Hartford Classical Magnet School; 35.1; 7.0; 19.9. 64; 53; Hartford; Dr. Joseph Bellizzi Middle School; 50.2; 10.0; 19.9. 15; 42; Bridgeport; Curiale School; 45.8; 9.0; 19.7. 64; 11; Hartford; Kinsella School; 41.0; 8.0; 19.5. 64; 19; Hartford; Milner School; 36.4; 7.0; 19.2. 151; 10; Waterbury; Brooklyn Elementary School; 11.5; 2.0; 17.4. 64; 23; Hartford; Burr School; 31.8; 5.5; 17.3. 900; 11; CTHSS; Bullard-Havens; 38.5; 6.5; 16.9. 900; 21; CTHSS; J. M. Wright; 20.0; 3.1; 15.5. 64; 67; Hartford; University High School; 13.0; 2.0; 15.4. 64; 69; Hartford; Capital Preparatory Magnet; 13.0; 2.0; 15.4. |
| Question: Does the analysis identify particular courses that are often taught by non-highly qualified teachers? |  |  |
| The analysis does identify courses that are taught by non- HQTs. The following courses are typically of concern: mathematics, science, specifically chemistry and physics, and world languages. | Annual analysis, beginning with the 2005-06 data, will be completed by Nov. of each year Biannual Update Nov/ Jan | Annual analysis will focus upon particular courses, including mathematics, science, especially chemistry and physics, and world languages. These are areas of shortage in Connecticut. Produce and disseminate annual HQT report to districts and schools by November of each year as part of the State NCLB Report Cards. The HQT report will relate to the current AYP status. Districts provided HQT data twice during the year. HQT analysis focused first on districts not meeting the current (2005-06 96%, 2006-07 100%) HQT benchmark. HQT analysis report presented to State Board in November |
| ### Summary Data Analysis of Classes Taught by NHQ Teaches by Core Academic Subjects Of the total 128,318 core academic classes taught in Connecticut, 4,110 (3.2%) were taught by not highly qualified teachers. Priority attention will be given to all schools (highlighted in yellow) that have not met the 96% HQT goal for all core academic subject areas, and specifically for math, science, and world languages in order to help them reach the goal of 100% classes taught by HQT by the end of the 2006-2007 school year. *Special Education classes were not included in the specific subject area totals above since Connecticut is currently developing a method to collect data about the specific core academic subjects these teachers teach when they are primarily responsible for instruction. Although not reported in the summary, the special education assignments were reported in the HQT data validation project conducted during the 2005-2006 school year, and have been analyzed to determine if they are HQT. See attached table named “HR1 N_Classes by Dist_Sch_Asg with Percent/Worksheet HR1 % Classes NHQ” |  |  |
| Overall, the percentage of classes taught by NHQ teachers by subject areas is as follows: Total; N Core Academic; % Core Academic. Core; Core; Classes; Classes. Academic; Academic; Taught by; Taught by. Dist; Sch; District; School; Assignments; Classes; NHQ Teachers; NHQ Teachers. *State Totals by Core Academic Subject Areas; Mathematics; 15,077; 874; 5.8. World Languages; 8,988; 483; 5.4. Science; 14,351; 720; 5.0. English Language Arts; 16,946; 689; 4.1. Reading; 6,638; 154; 2.3. Music; 7,892; 132; 1.7. Social Studies; 13,451; 136; 1.0. Elementary; 11,557; 94; 0.8. Art; 6,671; 53; 0.8. |

| Requirement 2: The revised plan must provide information on HQT status in each LEA and the steps the SEA will take to ensure that each LEA has plans in place to assist teachers who are not highly qualified to attain HQT status as quickly as possible. |  |  |
| --- | --- | --- |
| Question: Does the plan identify LEAs that have not met annual measurable objectives for HQT? |  |  |
| Actions/Strategies | Timeline | Indicators of Success |
| - Using the information from the HQT analysis CSDE identifies those districts who have not met the 96% as of 2005-06. | Annual analysis, beginning with the 2005-06 data, will be completed by Nov. of each year | Produce and disseminate annual HQT report to districts and schools by November of each year as part of the State NCLB Report Cards. The HQT report will relate to the current AYP status. |
| Question: Does the plan include specific steps that will be taken by LEAs that have not met annual measurable objectives? |  |  |
| - Beginning with the 2005-06 data collection, CSDE will produce and disseminate an annual HQT analysis for every district. This analysis will enable districts to track their progress toward achieving the 2006-07 HQT goal of 100 percent. - CSDE state plan requires that each district incorporate specific steps, as specified in CSDE HQT designed template, in their district plans to reach the 100 percent HQT goal by the end of 2006-07. - To ensure that districts reach the 100 percent HQT goal, district plans must include the following options for getting all teachers HQT: - require that non-HQTs either successfully complete the state adopted assessment (Praxis II or ACTFL for world languages); or - complete courses to awarded a content major or master’s degree; or - transfer the non-HQT teacher into a position for which they are HQT; or - use the HOUSSE process for HQT veteran teachers and special education teachers using the exceptions presented later in this plan. - In addition, CSDE, focusing on the fact that many of the non-HQTs are teaching in the top shortage areas, will provide the following assistance to districts: - CSDE will provide periodic, regional professional development focusing on how districts can reduce the number of non-HQTs within their districts. CSDE will work with each district to assist them with achieving a 100 percent HQT force. - CSDE will work to increase the number of prepared teacher candidates in each of the top 10 shortage areas. Currently, CSDE is working with Department of Higher Education and a Regional Education Service Center (RESC) to develop an advanced alternate route program for special education for individuals who currently hold a teaching certificate in a content area. - CSDE has recently provided a grant to Southern Connecticut State University (SCSU) to work with paraprofessionals in the four largest urban centers to obtain their bachelor’s degree and become certified in special education. As part of this program, the professors will travel to the urban district to hold courses after school hours; childcare will be provided and courses paid for as part of this grant program. - CSDE is currently developing partnerships with other countries to bring in teachers under the three-year J1 Visa program in Connecticut’s top shortage areas; India is partnering to send teachers who are trained in math, science and special education. CSDE has also partnered with Spain for bilingual teachers to teach Spanish and in some cases, to serve as bilingual teachers. These teachers will be deployed to the districts having the most difficultly employing HQT teachers in these shortage areas. - CSDE is currently developing a new web-based certification system. As part of this new system, CSDE will record the applicant’s content area major and master’s degree and HQT status. | Annual analysis, beginning with the 2005-06 data, will be completed by October 15 of each year August 2006 Biannual Update Nov/ Jan Ongoing Ongoing Program developed fall 2006, Candidates recruited Jan. 2007 Phase in from 2006-2009 Ongoing Dec. 2007 | Produce and disseminate annual HQT report to districts and schools by November of each year as part of the State NCLB Report Cards. The HQT report will relate to the current AYP status. CSDE template designed. Districts provided HQT data twice during the year. HQT analysis focused first on districts not meeting the current (2005-06 96%, 2006-07 100%) HQT benchmark. November – HQT analysis report presented to State Board. Submission, review and feedback of plans from districts falling below the current (2005-06 96%, 2006-07 100%) benchmark. CSDE offered 6 professional development opportunities to assist with improving the content knowledge of teachers in academic content areas that are identified as top shortage areas. Collaborate with RESC to develop and implement a state-approved alternate route program for special education; this program will be designed to attract individuals who already hold a certificate in a content area. SCSU program implemented in fall 2006 in New Haven; by fall 2007, a cohort of paraprofessionals will begin in Hartford, fall 2008 a cohort will begin in Bridgeport, with the last cohort beginning in Waterbury in fall 2009. Partnerships developed under the three year J1Visa. On-line by Dec. 2007. |
| ### Summary Data Analysis of Schools Not Reaching 96% Goal HQT Out of 192 LEAs, the CSDE has identified 44 (22.9% - highlighted in yellow in the attached table) that failed to meet the goal of 96% HQT on any one of three indicators: percentage of NHQ teacher FTEs, percentage of core academic subject areas taught by NHQ teachers, or percentage of core academic subject areas taught by NHQ teachers in schools that did not meet AYP. These LEAs will be given priority attention in order to meet the goal of 100% HQT by the end of the 2006-2007 school year. See attached table named “HR1 Summary Statistics by Districts” See the attached NCLB Highly Qualified Teacher Progress Report, that will be provided electronically to LEAs so they can report their plans to meet the goal of 100% HQT by the end of the 2006-2007 school year and then annually report progress. |  |  |
| Question: Does the plan delineate specific steps the SEA will take to ensure that all LEAs have plans in place to assist all non-HQ teachers to become HQ as quickly as possible? |  |  |
| - CSDE will provide a template for the development of the district HQT plan (See NCLB Highly Qualified Teacher Progress Report on page 13 and attached). Technical assistance will be provided to districts regarding the development of their plan. - Beginning in 2006-07, each district in the state will develop a plan for achieving 100 percent HQT. This should be addressed as part of the school and district improvement plans. Those districts falling below the current (2005-06 96%, 2006-07 100%) benchmark must submit their plan in December to CSDE for review and feedback. Districts that are also required to submit a district improvement plan will include HQT within that plan. | August 2006 template developed Fall 2006 technical assistance December 2006 and ongoing each December | CSDE sample template developed and TA provided. Submission, review and feedback of plans from districts falling below the current (2005-06 96%, 2006-07 100%) benchmark. |

This NCLB Highly Qualified Teacher Progress Report template will be provided electronically to LEAs in October so they can report their plans to meet the goal of 100% HQT by the end of the 2006-2007 school year and then annually report progress. In addition to this template, web-based reports are available that list specific NHQ teachers/classes to help districts identify specific problems that must be addressed.

NCLB Highly Qualified Teacher Progress Report

<<DistrictName>>

Summary Statistics

| Based on 2005-2006 Data |  |
| --- | --- |
| Percentage of NHQ Teachers (FTEs): | Percentage of Students Eligible for Free or Reduced-Price Meals: |
| Percentage of Classes Taught by NHQ Teachers: | District is In Top Poverty Quartile: District is In Bottom Poverty Quartile: |
| Percentage of Classes Taught by NHQ teachers in Schools Not Making AYP: | Percentage of Minority Students: |

NOTE: the 2005-2006 data will be replaced with 2006-2007 data in February, 2007.

District Reporting

How will teachers working without a certificate become highly qualified by the end of the 2006-2007 school year? Check all that apply. - Terminate employment - Obtain DSAP after taking PRAXIS II - Take additional courses to become fully certified and pass PRAXIS II in the content area - Other: describe below

Explanation of “Other” Category: (field type Memo)

How will teachers working under Durational Shortage Area Permits (DSAPs) become highly qualified by the end of the 2006-2007 school year? (Teachers obtaining DSAPs after July 1, 2006 are required to take PRAXIS II in the content areas they are teaching.) Check all that apply. - Pass the PRAXIS II in the content area - Take additional courses to become fully certified - Report teacher as not highly qualified if coursework and PRAXIS II not completed - Terminate employment if coursework and PRAXIS II not completed - Other: describe below

Explanation of “Other” Category: (field type Memo)

How will teachers working under Interim Initial or Interim Provisional certificates become highly qualified by the end of the 2006-2007 school year? Check all that apply. - Pass the PRAXIS II in the content area - Complete all required coursework - Terminate employment if PRAXIS II not completed by expiration date of Interim certificate

How will teachers teaching out of their certification area become highly qualified by the end of the 2006-2007 school year? Check all that apply. - Transferred into a position for which they are fully certified and highly qualified - Obtain a Master’s degree in the subject area - Obtain a DSAP - Obtain appropriate certification for the content they are teaching - Other: describe below

Explanation of “Other” Category: (field type Memo)

How will veteran teachers certified prior to 1989 become highly qualified by the end of the 2006-2007 school year? Check all that apply. - Obtain a Master’s degree in the subject area - Have an undergraduate college major in the subject area - Pass the PRAXIS II in the content area - Obtain National Board Certification in the content area and level they are teaching - Successfully complete HOUSSE If a teacher does not successfully complete HOUSSE, does your district have an intervention plan for that teacher? - Yes - No - Other: describe below

Explanation of “Other” Category: (field type Memo)

How will all special education teachers who are serving or may serve in the future as the primary instructors in core academic subject areas become highly qualified by the end of the 2006-2007 school year? Check all that apply. - Successfully complete HOUSSE in at least two content areas - Pass the PRAXIS II in each content area they teach (for middle and high school) - Pass the elementary education PRAXIS II if they are teaching elementary grades - Obtain a Master’s degree in each subject area they teach - Other: describe below

Explanation of “Other” Category: (field type Memo)

Save

Cancel

Printer friendly version

| Requirement 3: The revised plan must include information on the technical assistance, programs and services that the SEA will offer to assist LEAs in successfully completing their HQT plans, particularly where large groups of teachers are not highly qualified, and the resources the LEAs will use to meet their HQT goals. |  |  |
| --- | --- | --- |
| Question: Does the plan include a description of the technical assistance the SEA will provide to assist LEAs in successfully carrying out their HQT plans? |  |  |
| Actions/Strategies | Timeline | Indicators of Success |
| CSDE will: - hold regional technical assistance, informational session workshops (fall) with State Education Resource Center (SERC) and RESC participation for development of HQT plans; - provide districts with a sample HQT plan template; - coordinate provision of technical assistance during the implementation of HQT plans to individual districts with SERC/RESCs; - provide updated biannual HQT Analysis Report of district data for tracking progress towards HQT goal. Analysis will be conducted first for those districts cited as falling below the current (2005-06 96%, 2006-07 100%) benchmark. | Sept/Oct 2006 Sept/Oct 2006 Oct/June 2006 Biannually-Nov/Jan | Technical assistance, informational session workshops held. Schedules and rosters provided. Sample HQT plan template posted and disseminated. Schedule of technical assistance developed. Districts provided HQT data twice during the year. HQT analysis focused first on districts not meeting the current (2005-06 96%, 2006-07 100%) HQT benchmark. |
| Question: Does the plan indicate that the staffing and professional development needs of schools that are not making AYP will be given high priority? |  |  |
| - High priority will be given to analyzing the HQT status of staffing for schools not making AYP; - HQT information will be provided to districts with schools not making AYP and technical assistance from SERC/RESCs will focus on districts with schools not making AYP; - emphasis will be placed on the HQT professional development needs of districts with schools not making AYP when designing and implementing school improvement activities; and - districts identified as “in need of improvement” will be required to address their HQT needs in their district improvement plans. - The CSDE School Improvement Guide will be revised to include required HQT plan information and a sample HQT plan template. - The CSDE will help to place teachers who complete the ARC program for special education and international teachers who meet our criteria into high-need districts, with large numbers of schools not making AYP. - The “grow-your-own” program will focus on the hard-to-staff schools in our four large urban districts. The CSDE has recently provided a grant to Southern Connecticut State University to work with paraprofessionals in the four largest urban centers to obtain their bachelor’s degrees and become certified in special education. As part of this program, the professors will travel to the urban districts to conduct courses after school hours; childcare will be provided and courses will be tuition-free. - Title I school districts will provide an explanation in their HQT plans on the use of their five percent HQT reservation under Title I. | November 2006 and Ongoing Ongoing Ongoing Beginning 2006 Aug/Nov & Jan December August 2006 Ongoing Phase in from 2006-2009 December 2006 | HQT status analyzed for schools not making AYP. HQT information provided to districts with schools not making AYP and technical assistance from SERC/RESCs provided. Emphasis placed on the HQT professional development needs of districts with schools not making AYP when designing and implementing school improvement activities. AYP status reported (Aug)/HQT Analysis Report provided (Nov & Jan)/HQT needs addressed in district improvement plans (Dec). The CSDE School Improvement Guide revised to include required HQT plan information and a sample HQT plan template ARC teachers and international teachers placed into high-need districts, with large numbers of schools not making AYP. SCSU program implemented in fall 2006 in New Haven; by fall 2007, a cohort of paraprofessionals will begin in Hartford, fall 2008 a cohort will begin in Bridgeport, with the last cohort beginning in Waterbury in fall 2009 HQT plans reviewed and evidence of Title I school districts’ use of five percent HQT reservation provided. |
| Question: Does the plan include a description of programs and services the SEA will provide to assist teachers and LEAs in successfully meeting HQT goals? |  |  |
| Connecticut’s teachers can become highly qualified in one of three ways: - hold an academic major/master’s degree in the content area in which they teach; or - pass Praxis II (or ACTFL for world languages), the state content test; or - successfully complete the HOUSSE procedures through the teacher evaluation process. - The CSDE will to collaborate with the Department of Higher Education and RESCs to continue to provide test preparation courses for Praxis II (or ACTFL for world languages) exams. - Veteran teachers and special education teachers who must demonstrate content knowledge through the HOUSSE process will receive individualized professional development aligned with the Guidelines for Teacher Evaluation and Professional Development. - The CSDE will provide content specific professional development including, but not limited to, those areas which the HQT analysis determines to have the greatest number of non-HQTs. - To progress through the CSDE certification continuum, teachers must achieve a master’s degree or 30 credits beyond a bachelor’s degree in a related content field. - Proposed Framework for High School Redesign: Every high school in Connecticut will have an embedded professional development program with the single purpose of improving teaching and learning. Schools will be required to ensure that a portion of each teacher’s professional development will be relevant to the academic discipline and content area in which he/she is certified. To meet this expectation, schools will be required to: - include in the annual school budget a line item for school-based professional development; and - conduct an annual analysis of each year’s professional development plan to determine the impact the plan has had on teaching and learning practices in classrooms and to ensure that designated funds were expended to support the professional staff’s needs as designed. - Proposed Recommendations for Educator Continuum: In January 2006, an Educator Continuum Steering Committee was convened and given the charge to: - Issue a comprehensive series of recommendations for consideration by the State Board of Education about how to attract and retain high quality educators to Connecticut’s public school districts. - Such recommendations will address recruitment, preparation, certification, induction, ongoing professional development and evaluation. - Four subcommittees were established to serve as work groups to explore educator continuum issues in depth and report findings and recommendations back to the Steering Committee: - Recruitment, Preparation and Certification - Focus on issues of recruitment, retention, accreditation and certification CSDE is currently in the process of updating and enhancing our Educator Continuum which includes review of our educator preparation regulations, certification regulations, teachers’/administrators’ induction programs, and professional development for all educators. As part of this undertaking, CSDE is reviewing the recruitment and retention data and making recommendations regarding how to increase the retention of teachers within Connecticut’s urban and rural districts and ensure that HQTs are distributed equitably across districts within the state. This process will continue throughout the 2006-07 year. - Induction Committee -Focus on support and assessment of beginning teachers - Teacher Evaluation and Ongoing Professional Development - Focus on policy and practice related to evaluation. Professional Development Committee reviewed research on effective teaching, professional development models, and current teacher evaluation requirements and recommended the following: - Develop standards for high quality professional development that include the context, process and content of professional development. - Develop a system that allows educators to choose from a variety of professional development approaches so that specific content and skill development is targeted. - Increase the number of hours required for professional development for recertification. - Continue to require districts to develop professional development offerings that are aligned with the Common Core of Teaching, paying close attention to the foundational skills and competencies regarding students, content and pedagogy. - Educational Leadership - Focus on preparation, pre-service, certification, induction, evaluation and professional development of administrators The work of the subcommittees has been coordinated by the CSDE to assure that they are informed of efforts throughout the state and to assure that a coherent set of recommendations emerge including recommendations that all teachers are highly qualified. Preliminary recommendations include provision of incentives for teachers to work in high-need schools and districts and the establishment of a standing State Committee on Professional Development & Learning. - Mathematics and Science Partnership Program (federal Title II, Part B funded): Provides grants to establish Leadership Training Academies that will prepare elementary, middle or high school teachers to act as school-based instructional coaches in mathematics or science who will provide individualized professional development including those teachers identified as not being highly qualified. Partnerships must include the Mathematics, Science or Engineering department of an institution of higher education, the School of Education at an institution of higher education; and a high-need district. With new state curriculum frameworks recently adopted in mathematics and science, and new state assessments to measure student progress, school districts are concentrating their efforts on adjusting their curricula and instruction to prepare greater numbers of students for high achievement in mathematics and science. In order to support these improvement efforts, especially in high-need districts (participants must include approximately 50 percent of teachers from high-need district(s)), funding will be used to develop a cohort of highly skilled instructional specialists in mathematics and science to serve as school-based coaches. Through the professional development protocols offered, elementary, middle level and high school teachers can enhance their content knowledge and pedagogical skills. The professional development model utilized must adhere to national standards established for teacher professional development in mathematics or science. - The National Governors’ Association Grant (NGA)(foundation funded): With NGA grant resources, CSDE will provide job-embedded professional development for up to 5 multi-disciplinary teams (language arts, mathematics, science, special education and technology) representing rural, suburban, and urban school districts whose participants will become teacher leaders in their districts; initiate and support classroom-based and school-based action research projects with each team; and identify, train, and support a cadre of candidates who are making mid-career transitions into education through the Alternative Route to Certification (ARC) and who are seeking teaching positions in hard-to-staff areas, including mathematics and science. - Provision of Professional Development Opportunities (state and federal funded): - The CSDE’s Bureau of Curriculum and Instruction will provide professional development opportunities to districts that focus upon increasing the subject-matter knowledge of teachers. One of the responsibilities of the Department’s content area consultants is to provide to districts across the state content specific professional development based upon the state content standards for all core academic subject areas. Priority is given to high-need districts. - Title II Part A funds provide teacher leadership academies for mathematics, science, English/language arts, social studies and elementary educators. These academies build teacher leadership skills to assist with curriculum design, analysis of assessment data and the improvement of instructional practices. Title II, Part A will continue to support principal academies which focus upon educational leadership skills and mentoring of new administrators. - Through collaborative efforts, the Regional Education Service Centers (RESCs,) the Special Education Resource Center (SERC), and a partnership with the Center for Performance Assessment (CPA) the CSDE has created a series of professional development offerings that has begun to build capacity within the state for systemic comprehensive school improvement through the Connecticut Accountability for Learning Initiative. Data-driven decision making, making standards work, effective teaching strategies and executive coaching are examples of the types of professional development provided. - Reading First, along with state Early Reading Success funds, provide targeted professional development to some of our lowest performing schools and districts on literacy modules (Phonological Awareness, Oral Language, Explicit Small Group Reading Instruction, Independent Literacy Practice, The Principal’s Role in the Instructional Process of Literacy, Comprehension, Writing and Family as Partners) and scientifically based research programs in reading. - Professional development is being expanded statewide on the literacy modules through a train-the-trainer model. The modules reflect Connecticut’s Blueprint for Reading Achievement which defines the knowledge and skills necessary for teachers to teach reading in the early grades. - With the use of Javits funding, instructional units and accompanying professional development have been created to improve elementary science and social studies instruction. - Foreign Language Assistance Program funding will be providing professional development through a summer institute in 2006 to increase foreign language instruction at the elementary level. - Special Education: - Currently, the CSDE is working with the Department of Higher Education and a RESC to develop an advanced alternate route program for special education for individuals who currently hold a teaching certificate in a content area. - The “grow-your-own” program will focus on the hard-to-staff schools in our four largest urban districts. The CSDE has recently provided a grant to Southern Connecticut State University (SCSU) to work with paraprofessionals in the four largest urban centers to obtain their bachelor’s degrees and get certified in special education. As part of this program, the professors will travel to the urban districts to hold courses after school hours. Childcare will be provided and courses paid for as part of this grant program. - To ensure that all special education teachers will be HQT in the future, CSDE is currently proposing a new certificate in which all early childhood, elementary, middle and secondary teachers would receive more training about working with all students, including students with disabilities, students from different cultures and students whose primary language is not English. Connecticut’s special education certificate would then become an advanced certificate and would require that a person complete a Master’s degree in special education and hold a content certificate prior to being certified. | Ongoing Ongoing Ongoing Ongoing 2006-07 2007-08 August of 2006 Fall of 2006 January 2007 Ongoing – new grants awarded annually March 2006-Nov. 2008 Ongoing Ongoing Ongoing Ongoing Introduced at statewide conference May 2006 PD - ongoing Summer 2006 Program developed fall 2006, candidates are recruited Jan 2007 Phased in from 2006-2009 2012 | Brochures with schedules of test preparation courses for Praxis II (or ACTFL for world languages) exams provided through collaboration between CSDE and Department of Higher Education. Individualized professional development plan developed in accordance with Guidelines for Teacher Evaluation. Content specific professional development provided. Schedules and rosters available. Teachers achieve a master’s degree or 30 credits beyond a bachelor’s degree in a related content field. Reported in staff data files. Framework disseminated. Every high school in Connecticut will have an embedded professional development program with required components. Preliminary recommendations submitted to Steering Committee. Comprehensive series of recommendations submitted to State Board of Education. Budget recommendations and policy changes sent to legislature. The Mathematics and Science Partnership Program grant funds provided to establish Leadership Training Academies. Schedule and rosters from academies available. NGA grant resources provided job-embedded professional development for up to 5 multi-disciplinary teams. Schedule and rosters from meetings available. Schedules of CSDE coaches working in schools available. Content-specific professional development opportunities provided. Schedules and rosters available. Title II, Part A funds provided support for teacher leader and principal academies. Schedules and rosters available. Professional development offerings provided. Schedules and rosters available. Targeted professional development provided to Connecticut’s lowest performing schools. Schedules and rosters available. Train-the-trainer model for professional development on literacy modules provided. Schedules and rosters available. Professional development created to improve elementary science and social studies instruction through Javits funding. Foreign Language Assistance Program funding provided professional development through a summer institute. Collaborate with RESC to develop and implement a state-approved alternate route program for special education; this program will be designed to attract individuals who already hold a certificate in a content area. SCSU program implemented in fall 2006 in New Haven; by fall 2007, a cohort of paraprofessionals will begin in Hartford, fall 2008 a cohort will begin in Bridgeport, with the last cohort beginning in Waterbury in fall 2009 Paraprofessionals in “grow-your-own” program will obtain bachelor’s degrees and became certified in special education. A new certificate is established. |
| Question: Does the plan specifically address the needs of any subgroups of teachers identified in Requirement 1? |  |  |
| The State supports activities to encourage individuals, including mid-career professionals, former military personnel, paraprofessionals, and recent college graduates to enter the teaching profession through alternative routes to state certification. - The primary Alternate Route to Certification (ARC): Administered by the Connecticut Department of Higher Education, is designed for mid-career professionals and former military personnel. This program also serves to address the shortage areas by focusing their recruitment on the areas in the top quartile of content area shortages. All ARC candidates from this program enter the classroom having completed a major (or its equivalent) in the subject area they are teaching, education preparation coursework, a student teaching experience and passed the requisite Praxis II exam. Therefore, they hold full state certification upon entering the classroom. - The Teach for America program: Requested approval in Connecticut as an alternate route for recent college graduates to teach in poor urban schools. These candidates would serve in our three major cities, Bridgeport, Hartford, and New Haven, the neediest school systems in Connecticut. - Special Education: CSDE will work to increase the number of prepared candidates in each of the top 10 shortage areas. Currently, the CSDE is working with the Department of Higher Education and a RESC to develop an advanced alternate route program for special education for individuals who currently hold a teaching certificate in a content area. - The “grow-your-own” program: CSDE has recently provided a grant to Southern Connecticut State University (SCSU) to work with paraprofessionals in the four largest urban centers to obtain their bachelor’s degree and becomes certified in special education. As part of this program, the professors will travel to the urban district to hold courses after school hours; childcare will be provided and courses paid for as part of this grant program. - Educator Continuum: CSDE is currently in the process of updating and enhancing our Educator Continuum which includes the review of Connecticut educator preparation regulations, certification regulations, teachers’/administrators’ induction programs, and professional development for all educators. As part of this undertaking, CSDE is reviewing the recruitment and retention data and making recommendations regarding how to increase the longevity of teachers within our urban and rural districts and ensure that HQTs are distributed equitably across districts within the state. This process will continue throughout the 2006-07 year. - The Mathematics and Science Partnership Program: Funded under Title II, Part B, provides grants to establish Leadership Training Academies that will prepare elementary, middle or high school teachers to act as school-based instructional coaches in mathematics or science who will provide individualized professional development to those teachers identified as not being highly qualified. Partnerships must include the Mathematics, Science or Engineering department of an institution of higher education, the School of Education at an institution of higher education; and a high-need districts. With new state curriculum frameworks recently adopted in mathematics and science, and new state assessments to measure student progress, school districts are concentrating their efforts on adjusting their curricula and instruction to prepare greater numbers of students for high achievement in mathematics and science. In order to support these improvement efforts, especially in high-need districts (participants must include approximately 50 percent of teachers from high-need district(s)), funding will be used to develop a cohort of highly-skilled instructional specialists in mathematics and science to serve as school-based coaches. Through the professional development protocols offered, elementary, middle level and high school teachers can enhance their content knowledge and pedagogical skills. The professional development model utilized must adhere to national standards established for teacher professional development in mathematics or science. | Ongoing Ongoing May 2006 Ongoing Program developed fall 2006, Candidates recruited Jan. 2007 Phase in from 2006-09 August of 2006 Fall of 2006 January 2007 Ongoing – new grants awarded annually | Activities are supported that encourage individuals, including mid-career professionals, former military personnel, paraprofessionals, and recent college graduates to enter the teaching profession through alternative routes to state certification. ARC graduates placed in shortage areas as defined by the HQT analysis. The Teach for America program implemented. Collaborate with RESC to develop and implement a state-approved alternate route program for special education; this program will be designed to attract individuals who already hold a certificate in a content area. The number of prepared candidates in each of the top 10 shortage areas will be increased. SCSU program implemented in fall 2006 in New Haven; by fall 2007, a cohort of paraprofessionals will begin in Hartford, fall 2008 a cohort will begin in Bridgeport, with the last cohort beginning in Waterbury in fall 2009. Paraprofessionals will obtain bachelor’s degrees and became certified in special education. Preliminary recommendations submitted to Steering Committee. Comprehensive series of recommendations submitted to State Board of Education. Budget recommendations and policy changes sent to legislature. The Mathematics and Science Partnership Program grant funds provided to establish Leadership Training Academies. Schedule and rosters from academies available. |
| Question: Does the plan include a description of how the State will use its available funds (e.g., Title I, Part A; Title II, Part A, including the portion that goes to the State agency for higher education; other Federal and State funds, as appropriate) to address the needs of teachers who are not highly qualified? |  |  |
| - Mathematics and Science Partnership Program (federal Title II, Part B funded): The CSDE will provide Leadership Training Academies that will prepare elementary, middle or high school teachers to act as school-based instructional coaches in mathematics or science who will provide individualized professional development to those teachers identified as not being highly qualified through the. Partnerships must include the Mathematics, Science or Engineering department of an institution of higher education, the School of Education at an institution of higher education; and a high-need district. With new state curriculum frameworks recently adopted in mathematics and science, and new state assessments to measure student progress, school districts are concentrating their efforts on adjusting their curricula and instruction to prepare greater numbers of students for high achievement in mathematics and science. In order to support these improvement efforts, especially in high-need districts (participants must include approximately 50 percent of teachers from high-need district(s)), funding will be used to develop a cohort of highly-skilled instructional specialists in mathematics and science to serve as school-based coaches. Through the professional development protocols offered, elementary, middle level and high school teachers can enhance their content knowledge and pedagogical skills. The professional development model utilized must adhere to national standards established for teacher professional development in mathematics or science. - The National Governors’ Association Grant (NGA)(foundation funded): With NGA grant resources, Connecticut will provide job-embedded professional development for up to 5 multi-disciplinary teams (language arts, mathematics, science, special education and technology) representing rural, suburban, and urban school districts whose participants will become teacher leaders in their districts; initiate and support classroom-based and school-based action research projects with each team; and identify, train, and support a cadre of candidates who are making mid-career transitions into education through the Alternative Route to Certification (ARC) and who are seeking teaching positions in hard-to-staff areas, including mathematics and science. - School Improvement (federal Title I, Part A funded): The CSDE through the Connecticut Accountability for Learning Initiative, working on school improvement initiatives: - provide executive coaching to principals in schools with the greatest need - retired exemplary principals serve as Leaders-in-Residence in the Department’s School Improvement and Literacy Unit and provide assistance to principals of high need schools (Title I schools in corrective action or restructuring) in identifying and implementing leadership practices that are proven to promote student success and an effective school culture that retains and attracts effective teachers. - a teacher-in-residence also provides assistance to teachers in high need schools regarding effective teaching practices so that they can become highly effective. - Beginning Educator Support and Training Program(BEST) (state funded) Through CSDE’s, state funded, Beginning Educator Support and Training Program (BEST), implemented in 1989, beginning teachers have opportunities to strengthen their knowledge of subject matter and instructional strategies, enhance their understanding of students as learners, and begin a process of lifelong learning and professional growth. This program has assisted special educators in becoming HQT in content areas. - District-based support in year-one of BEST is through the assignment of a mentor or support team in the teacher's own district. Many districts also conduct workshops for new teachers that focus on curriculum and instruction, classroom management and the BEST program portfolio assessment. - State-sponsored content-specific seminars: The BEST Program has developed seminars that are delivered through two different modes: "Online" (web-based) and "In-person" (regional) seminars. - Connecticut Vanguard Schools Initiative (state and federal Title I, Part A funded): The Connecticut Vanguard Schools Initiative, supported with Title I and state funds, is a public/private partnership designed to focus on school reform efforts that have demonstrated success in improving educational performance for students of all backgrounds. The CSDE, in partnership with the Connecticut Business and Industry Association, has put in place a process to identify and recognize successful schools and have them share their successful school-improvement strategies with high need schools (with emphasis on high-poverty Title I schools that have been identified as “in need of improvement”). A recognized Vanguard school has ongoing, high quality professional development that is focused and informed by research and school/classroom based assessments. Vanguard Mentoring Partnerships are established with schools that have been identified as in need of improvement in order to share best practices, including the provision of content-specific professional development for the school’s teachers (including those not highly qualified) that have resulted in improved student achievement. - Early Reading Success (state funded): State funds assisted in the development of a Blueprint for Reading Achievement a Report of the Early Reading Success Panel. The following modules have been developed and are supported by scientifically-based reading research and reflect the Blueprint: Phonological Awareness, Oral Language, Explicit Small Group Reading Instruction, Independent Literacy Practice, The Principal’s Role in the Instructional Process of Literacy, Comprehension, Writing and Family as Partners. Training on these modules has been provided to teachers in high need, priority school districts (PSD) where there are large numbers of poor and minority students to improve their effectiveness and success in teaching reading via a train the trainer model. - Provision of Professional Development Opportunities (state and federal funded): - The CSDE’s Bureau of Curriculum and Instruction will provide professional development opportunities to districts that focus upon increasing the subject-matter knowledge of teachers. One of the responsibilities of the Department’s content area consultants is to provide to districts across the state content specific professional development based upon the state content standards for all core academic subject areas. Priority is given to high-need districts. - Title II Part A Funds provide teacher leadership academies for mathematics, science, English/language arts, social studies and elementary educators. These academies build teacher leadership skills to assist with curriculum design, analysis of assessment data and the improvement of instructional practices. Title II, Part A will continue to support principal academies which focus upon educational leadership skills and mentoring of new administrators. - Reading First and state Early Reading Success Funds provide targeted professional development to some of our lowest performing schools and districts on literacy modules (Phonological Awareness, Oral Language, Explicit Small Group Reading Instruction, Independent Literacy Practice, The Principal’s Role in the Instructional Process of Literacy, Comprehension, Writing and Family as Partners) and scientifically based research programs in reading. - Professional development is being expanded statewide on the literacy modules through a train-the-trainer model. The modules reflect Connecticut’s Blueprint for Reading Achievement which defines the knowledge and skills necessary for teachers to teach reading in the early grades. - Title II Part A Grants to State Agencies for Higher Education: Connecticut teachers, including teachers teaching in our high need districts, will participate in activities at professional development programs selected for grant funds by the Connecticut Department of Higher Education. Designed by college faculty and school teachers and administrators, the projects are supported by $568,628 in Connecticut Teacher Quality Partnership Grants. The projects −mostly seminars and workshops to begin this summer and continue on into the school year –will upgrade the subject matter mastery and teaching skills of teachers in history, civics and government, science, mathematics, and reading. The projects provide teachers with the latest knowledge and skills they need to keep up with new state standards. They are designed by teachers themselves, working with experts from colleges and universities. Such partnerships are the best way of zeroing in on teacher needs and, in so doing, raising both teacher quality and student achievement. The majority of this year’s awards are in science and mathematics. Three separate panels of college faculty, teachers and curriculum specialists evaluated proposals. Priority was given to projects supporting Connecticut’s new curricular frameworks and content mastery in math, science and literacy. Selected projects include the following examples: - Connecticut Center for Science Inquiry Teaching and Learning - Summer Academy for Integrated Science and Mathematics - Hartford Elementary School Teacher Enrichment Programs (high-need district) - Hartford Elementary Science Professional Development (high-need district) | Ongoing March 2006-November 2008 Beginning Aug. 2005 and continuing Beginning Aug. 2004 and continuing Beginning 1989 ongoing Spring of 2005 - ongoing September 2005 - ongoing January 2002 and ongoing Ongoing Ongoing Ongoing Ongoing Annual grant awards – ongoing Summer 2006 | The Mathematics and Science Partnership Program grant funds provided to establish Leadership Training Academies. Schedule and rosters from academies available. . NGA grant resources provided job-embedded professional development for up to 5 multi-disciplinary teams. Schedule and rosters from meetings Schedules of CSDE coaches working in schools available. . Executive coaching provided to principals in schools with the greatest need. Listing of principals, executive coaches and schedules. Teacher-in-residence provided assistance regarding effective teaching practices to teachers in high needs schools. Schedules available. Beginning Educator Support and Training Program (BEST) provided support and training to beginning teachers. District-based support provided in year-one. State-sponsored content-specific seminars provided. Schedules and rosters available. Vanguard Schools identified. Vanguard Mentoring Partnerships established to share best practices. Presented to State Board. Module training provided, schedules available and percent trained in each PSD report presented to legislature. Content-specific professional development opportunities provided. Priority given to high-need districts. Schedules and rosters available Title II, Part A funds provided support for teacher leader and principal academies. Schedules and rosters available. Reading First and state Early Reading Success funds provided targeted professional development lowest performing schools. Train-the-trainer model for professional development on literacy modules provided. Schedules and rosters available. Teacher Quality State Grants awarded. Professional development activities held. Schedules and rosters available. |
| Question: Does the plan for the use of available funds indicate that priority will be given to the staffing and professional development needs of schools that are not making AYP? |  |  |
| - Mathematics and Science Partnership Program (federal Title II, Part B funded): The CSDE will provide Leadership Training Academies that will prepare elementary, middle or high school teachers to act as school-based instructional coaches in mathematics or science that will provide individualized professional development including those teachers identified as not being highly qualified. Partnerships must include the Mathematics, Science or Engineering department of an institution of higher education, the School of Education at an institution of higher education; and a high-need district. With new state curriculum frameworks recently adopted in mathematics and science, and new state assessments to measure student progress, school districts are concentrating their efforts on adjusting their curricula and instruction to prepare greater numbers of students for high achievement in mathematics and science. In order to support these improvement efforts, especially in high-need districts (participants must include approximately 50 percent of teachers from high-need district(s)), funding will be used to develop a cohort of highly-skilled instructional specialists in mathematics and science to serve as school-based coaches. Through the professional development protocols offered, elementary, middle level and high school teachers can enhance their content knowledge and pedagogical skills. The professional development model utilized must adhere to national standards established for teacher professional development in mathematics or science. - School Improvement (federal Title I, Part A funded): The CSDE through the Connecticut Accountability for Learning Initiative, working on school improvement initiatives: - provides executive coaching to principals in schools with the greatest need - retired exemplary principals serve as Leaders-in-Residence in the Department’s School Improvement and Literacy Unit and provide assistance to principals of high need schools (Title I schools in corrective action or restructuring) in identifying and implementing leadership practices that are proven to promote student success and an effective school culture that retains and attracts effective teachers. - a teacher-in-residence provides assistance to teachers in high need schools on effective teaching practices so they can become highly effective - Beginning Educator Support and Training Program (BEST) (state funded): Through CSDE’s, state funded, Beginning Educator Support and Training Program (BEST), implemented in 1989, beginning teachers have opportunities to strengthen their knowledge of subject matter and instructional strategies, enhance their understanding of students as learners, and begin a process of lifelong learning and professional growth. This program has assisted special educators in becoming HQT in content areas. - District-based: support in year-one of BEST is through the assignment of a mentor or support team in the teacher's own district. Many districts also conduct workshops for new teachers that focus on curriculum and instruction, classroom management and the BEST program portfolio assessment. - State-sponsored content-specific seminars: The BEST Program has developed seminars that are delivered through two different modes: "Online" (web-based) and "In-person" (regional) seminars. - Connecticut Vanguard Schools Initiative (state and federal Title I, Part A funded): The Connecticut Vanguard Schools Initiative, supported with Title I and state funds, is a public/private partnership designed to focus on school reform efforts that have demonstrated success in improving educational performance for students of all backgrounds. The CSDE, in partnership with the Connecticut Business and Industry Association and SERC, has put in place a process to identify and recognize successful schools and have them share their successful school-improvement strategies with high need schools (with emphasis on high-poverty Title I schools that have been “identified in need of improvement). A recognized Vanguard school has ongoing, high quality professional development that is focused and informed by research and school/classroom based assessments. Vanguard Mentoring Partnerships are established with schools that have been identified as in need of improvement in order to share best practices, including the provision of content-specific professional development for the school’s teachers (including those that are not highly qualified) have resulted in improved student achievement. - Early Reading Success (state funded): State funds assisted in the development of a Blueprint for Reading Achievement a Report of the Early Reading Success Panel. The following modules have been developed and are supported by scientifically-based reading research and reflects the Blueprint: Phonological Awareness, Oral Language, Explicit Small Group Reading Instruction, Independent Literacy Practice, The Principal’s Role in the Instructional Process of Literacy, Comprehension, Writing and Family as Partners. Training on these modules has been provided to teachers in high need, priority school districts where there are large numbers of poor and minority students, to improve their effectiveness and success in teaching reading via a train the trainer model. - Provision of Professional Development Opportunities (state and federal funded): - The CSDE’s Bureau of Curriculum and Instruction provides professional development opportunities to districts that focus upon increasing the subject-matter knowledge of teachers. One of the responsibilities of the Department’s content area consultants is to provide to districts across the state content specific professional development based upon the state content standards for all core academic subject areas. Priority is given to high-need (where the district itself or large numbers of schools have not met AYP) districts. - Reading First, along with state Early Reading Success funds, provide targeted professional development to our lowest performing schools and districts on literacy modules (Phonological Awareness, Oral Language, Explicit Small Group Reading Instruction, Independent Literacy Practice, The Principal’s Role in the Instructional Process of Literacy, Comprehension, Writing and Family as Partners) and scientifically based research programs in reading. - Professional development is being expanded statewide on the literacy modules through a train-the-trainer model. The modules reflect Connecticut’s Blueprint for Reading Achievement which defines the knowledge and skills necessary for teachers to teach reading in the early grades. - Improving Teacher Quality State Grants to State Agencies for Higher Education Connecticut teachers, including teachers teaching in our high need districts, will participate in activities at professional development programs selected for grant funds by the Connecticut Department of Higher Education. Designed by college faculty and school teachers and administrators, the projects are supported by $568,628 in Connecticut Teacher Quality Partnership Grants. The projects −mostly seminars and workshops to begin this summer and continue on into the school year –will upgrade the subject matter mastery and teaching skills of teachers in history, civics and government, science, mathematics, and reading. The projects provide teachers with the latest knowledge and skills they need to keep up with new state standards. They are designed by teachers themselves, working with content experts from colleges and universities. The majority of this year’s awards are in science and mathematics. Proposals were evaluated by three separate panels of college faculty, teachers and curriculum specialists. Priority was given to projects supporting Connecticut’s new curricular frameworks and content mastery in math, science and literacy. Selected projects include the following examples: - Connecticut Center for Science Inquiry Teaching and Learning - Summer Academy for Integrated Science & Mathematics - Hartford Elementary School Teacher Enrichment Programs (high-need district) - Hartford Elementary Science Professional Development (high-need district) | Ongoing Beginning Aug. 2005 and continuing Beginning Aug. 2004 and continuing Beginning 1989 ongoing March 2006-November 2008 January 2002 and ongoing Ongoing Ongoing Ongoing Annual grant award Ongoing Summer 2006 | Leadership Training Academies provided through the Mathematics and Science Partnership Program. Executive coaching provided to principals in schools with the greatest need. Listing of principals, executive coaches and schedules. Teacher-in-residence provided assistance regarding effective teaching practices to teachers in high needs schools. Schedules available. Beginning Educator Support and Training Program (BEST) provided support and training to beginning teachers. District-based support provided in year-one. State-sponsored content-specific seminars provided. Schedules and rosters available Vanguard Schools identified. Vanguard Mentoring Partnerships established to share best practices.- Presented to State Board Module training provided, schedules available and percent trained in each PSD report presented to legislature. Content-specific professional development opportunities provided. Priority given to high need districts. Schedules and rosters available. Reading First and state Early Reading Success funds provided targeted professional development lowest performing schools. Train-the-trainer model for professional development on literacy modules provided. Schedules and rosters available. Teacher Quality State Grants awarded. Professional development activities held. Schedules and rosters available. |

| Requirement 4: The revised plan must describe how the SEA will work with the LEAs that fail to reach the 100 percent HQT goal by the end of the 2006-07 school year. |  |  |
| --- | --- | --- |
| Question: Does the plan indicate how the SEA will monitor LEA compliance with the LEAs’ HQT plans described in Requirement 2 and hold LEAs accountable for fulfilling their plans? |  |  |
| Actions/Strategies | Timeline | Indicators of Success |
| - CSDE will monitor each district’s work toward achieving the 100 percent HQT goal: - CSDE will analyze and report to all districts biannually their annual HQT percentage both at the district and school level. Districts that fall below the current HQT will be monitored. High poverty schools not making AYP will be identified on this list and receive focused monitoring by CSDE; - Districts in need of improvement are required to address the needs of non-HQT within their schools in need of improvement in their district and school improvement plans. - CSDE will continue to provide each district with annual HQT reports. These reports will also be presented to the State Board of Education for further action. Connecticut General Statutes currently allows CSDE to withhold monies from districts who continue to employ people who are not certified or who are teaching out-of-field. - CSDE will hold LEAs accountable for fulfilling their plans: - LEA HQT plan progress will be a factor in the selection of LEAs for further monitoring. - LEAs who fail to meet their annual measurable objectives will be required to target a percentage of their Title II funds to support their highly qualified teacher initiatives. - A plan for corrective action will be required for LEAs that do not fulfill their plans and make sufficient progress. - Connecticut General Statutes currently allows CSDE to withhold monies from districts who continue to employ people who are not certified or who are teaching out-of-field. | November 2006 January 2007 December 2006 November 2006 Ongoing Annually/Fall Annually/Fall Annually/Fall | Districts will submit their plan for achieving the 100 percent HQT goal; CSDE will review plans from all districts and respond in writing to those who fall below the current (2005-06 96%, 2006-07 100%) benchmark; those districts below the benchmark will be monitored. All districts in need of improvement will submit their school improvement plans which must include a section on HQT. Annual HQT report presented to State Board in November 2006. HQT plan progress factored into selection process for LEA monitoring. Percentage of Title II funds targeted for HQT initiatives. Corrective action plans developed and implemented. Funds withheld as necessary. |
| Question: Does the plan show how technical assistance from the SEA to help LEAs meet the 100 percent HQT goal will be targeted toward LEAs and schools that are not making AYP? |  |  |
| - CSDE will help to place teachers who complete the ARC program for special education and international teachers who meet CSDE criteria into those districts not making AYP. Additionally, the grow-your-own paraprofessional work will focus on the hard to staff schools in our four large urban districts, which are Connecticut’s neediest school systems, who have not made AYP. - In 2005, 2006, CSDE provided targeted technical assistance in the 4 largest urban districts to beginning teachers to improve their instructional effectiveness in language arts and mathematics. This assistance resulted not only in larger numbers of beginning teachers passing the induction portfolio, but also larger numbers of teachers scoring at the excellence level. In 2006-2007, this technical assistance will continue and will expand to include differentiated instruction for culturally diverse populations, non-English speaking students and students with special needs. | Fall 2007 Fall 2006 | ARC candidates will be encouraged to seek positions in the hard-to-staff schools within districts most in need. Provide workshops to all beginning teachers in our 4 largest urban districts representing a large number of schools not making AYP and that is home to the majority of the state’s minority students about effective teaching strategies in language arts and mathematics. Expand technical assistance to include differentiated instruction to address the needs of culturally diverse, non-English speaking students and students with special needs. |
| Question: Does the plan describe how the SEA will monitor whether LEAs attain 100 percent HQT in each LEA and school: - in the percentage of highly qualified teachers at each LEA and school; and - in the percentage of teachers who are not receiving high-quality professional development to enable such teachers to become highly qualified and successful classroom teachers? |  |  |
| - CSDE will monitor each district’s work toward achieving the 100 percent HQT goal: - CSDE will analyze and report to all districts biannually their annual HQT percentage both at the district and school level. Districts that fall below the current HQT (2005-06 96%, 2006-07 100%) benchmark will be monitored. High poverty schools not making AYP will be identified on this list and receive focused monitoring by CSDE; - Districts in need of improvement are required to address the needs of non-HQT within their schools in need of improvement in their district and school improvement plans. - CSDE will continue to provide each LEA with annual HQT reports. These reports will also be presented to the State Board of Education for further action. - CSDE will help to ensure that teachers receive high-quality professional development that supports HQT goals. - The LEA Consolidated Application for Federal ESEA Grants, which includes Title II, Part A funds, is reviewed to ensure that professional development activities support LEA HQT goals. - The percentage of teachers receiving high-quality professional development is a performance indicator LEAs address in the Consolidated Application. - Every LEA’s state-required teacher evaluation and professional development plan went through a state-level peer-review process before the plan received final approval by the Department. The approved professional development plans are based on the standards clearly defined in Connecticut’s Guidelines for Comprehensive Professional Development and Teacher Evaluation and Common Core of Teaching. Professional development is provided in accordance with approved plan. - National Staff Development Council (NSDC) context, process and content for professional development standards that improve learning of all students are being investigated by the CSDE as new standards which will link to Connecticut’s Common Core of Teaching. The State Board of Education adoption of these standards will provide teachers with high-quality professional development to assist them in using effective teaching strategies that will help close the achievement gap. - Every district is required by statute to provide 18 annual hours of professional development that must aligned with the criteria defined in the Guidelines for Teacher Evaluation and Professional Development. - CSDE is investigating increasing the number of required professional development hours from 90 to 150 hours every 5 years. - LEAs currently assure in their applications for funds that their Title II, Part A needs assessments are annually conducted. CSDE will review needs assessment documents during monitoring. Information from the review of LEAs’ needs assessments will inform statewide needs. Information and feedback gathered during the provision of technical assistance by CSDE school improvement and curriculum consultants will provide additional information as to professional development needs. See attached table named “HR1 Summary Statistics by Districts” | Annual analysis, beginning with the 2005-06 data, will be completed by Nov. of each year Biannual update Nov/Jan Annually/Fall Annually/Fall Ongoing 2007-08 School Year Ongoing 2006-07 School Year Ongoing | Annual analysis will focus upon particular courses, including mathematics and science, especially chemistry and physics. These are all areas of shortage in our state Produce and disseminate annual HQT report to districts and schools by November of each year as part of the State NCLB Report Cards. The HQT report will relate to the current AYP status. Districts provided HQT data twice during the year. HQT analysis focused first on districts not meeting the current (2005-06 96%, 2006-07 100%) HQT benchmark. HQT analysis report presented to State Board in November. Consolidated Application reviewed for use of Title II funds. Consolidated Application reviewed for HQT performance indicator status. Teachers receive high-quality professional development. NSDC standards adopted by State Board of Education. District developed professional development plans. 150 professional development hours required every 5 years. Annual needs assessments are conducted and reviewed during CSDE monitoring. LEA program activities are based on the defined needs. Statewide professional development needs determined. |
| Question: Consistent with ESEA §2141, does the plan include technical assistance or corrective actions that the SEA will apply if LEAs fail to meet HQT and AYP goals? |  |  |
| The CSDE, in partnership with the Stupski Foundation and the Center for Performance Assessment, will continue to support the school improvement process through the Comprehensive Accountability For Learning Initiative. Districts that have been identified as “in need of improvement” and with schools not making AYP will receive support and technical assistance. This support will be provided by the CSDE, RESCs and SERC staff who are highly skilled educators with experience in school improvement. Priority will be given to identified districts receiving Title I funding. Guidance will be provided in the development and implementation of district improvement plans. Professional development focused on accountability for student learning will be provided. District improvement plans will be required to address the deficiencies in the district that prevented schools from achieving AYP. In addition to the required components, the improvement plan must give consideration to the complex and difficult work of the district as it relates to the leadership support for schools, governance and fiscal infrastructures, and curriculum and instruction. The CSDE will provide technical assistance regarding the identified districts’ HQT needs and will provide a HQT plan template to assist the districts in addressing their HQT needs in their improvement plans. The Comprehensive Accountability For Learning Initiative will: - focus on the district as the primary change agent; - create a culture of professional learning communities in schools, in districts, and in the state; - differentiate support based on individual district and school needs; and - increase student achievement for all students. Identified districts are required to reserve not less than 10 percent of their Title I, Part A funds for high quality professional development for instructional staff that is specifically designed to improve classroom teaching and improve content knowledge focusing on those who are non-HQT. The district must continue to reserve and use these funds for this purpose during each fiscal year that the districts are identified for improvement. High-need districts that have been identified as “in need of improvement” for two consecutive years are offered organizational audits that will focus on leadership, strategic planning, curriculum and teaching, stakeholder engagement, effective and efficient processes and accountability. Districts that have been identified as “in need of improvement” for three consecutive years and have failed to make progress toward meeting the annual measurable objectives in section 1119(b)(1) will be required to enter into a Memorandum of Agreement with the CSDE that will: - address the utilization of the professional development strategies and activities developed in accordance with section 2141(c)(1); and - address the hiring of paraprofessionals with Title I, Part A funds in accordance with section 2141(c)(2)(A,B & C) The “ED-Life Initiative” included a legislative budget request to pay an additional $3,000 per year for two years to any teacher who accepted a hard-to-staff position in an urban school. This request was not funded. In 2006-2007, CSDE will submit a similar budget proposal to the legislature. In 2006, the Connecticut State Legislature passed statutory language that allows graduates of a national corps of teachers such as Teach for America (TFA) to place teachers in the three largest urban districts; in 2006-2007, 42 TFA graduates will be teaching in New Haven Public Schools. TFA provides mentoring and technical assistance to all of its graduates during the first two years of teaching. CSDE will seek state funding for cohorts of qualified paraprofessionals to become certified teachers in our urban and priority districts. Additional state resources will allow for quicker implementation of this “grow your own” program than the original three-year implementation plan. CSDE will seek funding from the legislature to expand the alternate routes to certification programs in all shortage areas and begin an alternate route program to attract and prepare teachers of special education in our urban districts, our greatest shortage area. CSDE will seek state funding to recruit and support the most qualified teachers to serve in high poverty areas with large numbers of poor and minority students. | September 2004 and ongoing August of each year If necessary by August of 2006 after AYP determinations made Fall 2006 September 2006 November 2006 November 2006 November 2006 | Comprehensive Accountability for Learning Initiative supported school improvement process. Guidance provided in the development and implementation of district improvement plans. Professional development focused on accountability for student learning provided. District improvement plans addressed deficiencies. Identified districts reserve not less than 10 percent of their Title I, Part A funds for high quality professional development. District organizational audits conducted, feedback provided and available at CSDE. Memorandum of Agreements established. Develop and submit a legislative budget proposal to increase the incentives for teachers who accept hard-to-staff positions in urban schools. Placement of TFA candidates in New Haven Public Schools in hard-to-staff positions. Develop and submit a legislative budget request for state support of the “grow your own” paraprofessional programs to be implemented more quickly and placement of certified individuals to occur more quickly in our urban districts. Develop and submit a legislative budget request for state support to expand the alternate route to certification programs, especially in special education focused on the urban districts. Develop and submit a legislative budget request to provide state incentive bonuses and local multi-year contracts for outstanding teachers in the state’s urban and priority districts. |

| Requirement 5: The revised plan must explain how and when the SEA will complete the HOUSSE process for teachers not new to the profession who were hired prior to the end of the 2005-06 school year, and how the SEA will discontinue the use of HOUSSE procedures for teachers hired after the end of the 2005-06 school year (except for the situations described below). |  |  |
| --- | --- | --- |
| Question: Does the plan describe how and when the SEA will complete the HOUSSE process for all the teachers not new to the profession who were hired before the end of the 2005-06 school year? |  |  |
| Strategies | Timeline | Indicators of Success |
| - All districts will discontinue the use of the HOUSSE process for many teachers not new to the profession by the conclusion of the 2006-07 school year except in identified areas (English/language arts, mathematics, and science). CSDE has encouraged all districts to HOUSSE their non-HQT special education teachers in two content areas (minimally math and language arts/English) and all middle grades teachers in at least two core academic content areas by the end of 2006-07. This will allow for the maximum flexibility for involuntary transfer of teachers based on class/cohort size or based on changes created through the PPT/IEP process. - Areas for which the HOUSSE plan will continue to be used after the conclusion of the 2006-2007 year include: - Veteran teachers who return to the profession after an extended leave due to maternity/family rearing, long-term illness, etc.; - Veteran leaders who return to the classroom from an administrative position; - Veteran teachers who transfer into a new content area for which they hold an active certificate; - Special educators new to the profession who are HQT in one of the three identified content areas (English/language arts, mathematics and science) and use HOUSSE over a two year period to become HQT in other content areas; or - Teachers of multiple subjects in rural school districts who use HOUSSE over a two year period to become HQT in other content areas. | 2006-07 September 2007 | Throughout the 2006-07 year, districts must HOUSSE special education teachers, and middle grade teachers in multiple subject areas that they will be teaching. HOUSSE will be phased out in the State of Connecticut for new and veteran teachers with the exceptions of the five identified situations. |
| Question: Does the plan describe how the State will discontinue the use of HOUSSE after the end of the 2005-06 school year, except in the following situations: - Multi-subject secondary teachers in rural schools who, if HQ in one subject at the time of hire, may use HOUSSE to demonstrate competence in additional subjects within three years of the date of hire; or - Multi-subject special education teachers who are new to the profession, if HQ in language arts, mathematics, or science at the time of hire, may use HOUSSE to demonstrate competence in additional subjects within two years of the date of hire. |  |  |
| - All new teachers to the profession in the core academic content areas will be HQT due to having successfully completed a required state content knowledge assessment (Praxis II or ACTFL for world languages) for certification. Special education teachers who are serving as the primary instructor of one or more core academic content areas must be highly qualified in one content area upon hire and will then use the flexibility provision and the HOUSSE plan to become HQT in other core academic content areas that they teach. | 1990 forward | Testing teachers for content knowledge began in Connecticut in 1990. Therefore, all new teachers and those moving into Connecticut from another state must pass the state assessment prior to becoming certified with a level II certificate. |

Requirement 6: The revised plan must include a copy of the State’s written “equity plan” for ensuring that poor or minority students are not taught by inexperienced, unqualified, or out-of-field teachers at higher rates than are other students.

See attached – Connecticut’s Equity Plan