| # Meeting Title: Competitive Sourcing Monthly Team Meeting |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ### Minutes |  | #### January 19, 2006 |  | #### 9:00 – 11:00 AM |  | ##### LOcation: mib – rOOM: 5160 |  |
| Meeting called by |  |  | Donna Kalvels |  |  |  |  |
| Note taker |  |  | Marlo Allen |  |  |  |  |
| Attendees |  |  | Donna Kalvels – DOI, CCSE; Dan Ertel – CCSE; Marlo Allen-CCSE; Nancy Miller-HR; Beth Cox-USGS; Connie Rough-USGS; Michael Wright-OSM; Marcia Cash-FWS; Greg Rabida-SOL; Kathy Garrity-FWS; Michael Schwartz-FWS; Jacob Lee-FWS; Dave Morgan-FWS; Roberta Richardson-NBC; Rebecca Mack-BLM, Caroline Laiken-MMS; Diane Schmitz-OHS; VIA PHONE: Scott Morton-USGS; David Brown-BIA; Jacque Medina-BOR, Kathy Libby-BLM; Steve Schmidt-BOR |  |  |  |  |
| ## Agenda Topics: - Nancy Miller (HR) VSIP/VERA - Update on latest Appropriations language - Update on Report to Congress - FY06 FAIR Act Inventory - Update on ’06 Green Plan - Discussion with Office of the Secretary FAIR Act Inventory coordinators |  |  |  |  |  |  |  |
| #### #1 |  | #### VSIP/VERA for FTE affected by Competitive SOurcing Studies |  |  |  | ##### Nancy Miller |  |
| Discussion | - Review all positions to be studied and turn in pre-approval list to DOI. We will forward to OMB/OPM. - DOI review is approx. 2-3 weeks and OPM review is approx. 21 days. - Large number of employees to process must include Budget review. - If positions are not on pre-approval list then regular VSIP/VERA process must be done. - Each bureau has an approved VSIP/VERA number for each individual study. - You cannot add to the list after approval, it is better to add more in the beginning and not have them impacted, than to not have them at all. - You can submit request before list is approved. - Just because list is submitted doesn’t automatically mean it is approved. - DOI forwards requests to OPM. VERA is approved by OPM and VSIP must be approved by both OPM and OMB. - Plan on having request in by 3rd Quarter. - No requests for Preliminary Planning pre-approval will be considered by OPM. |  |  |  |  |  |  |
| Conclusions | - Review all positions to be studied and turn in pre-approval list to DOI. We will forward to OMB/OPM - If positions are not on pre-approval list then regular VSIP/VERA process must be done. - You can submit request before list is approved. - No requests for Preliminary Planning pre-approval will be considered by OPM. |  |  |  |  |  |  |
| Action items |  |  |  |  | Person/Office responsible |  | Deadline |
| - Plan on having request in by 3rd Quarter. |  |  |  |  | Bureaus |  |  |
| #### # 2 |  | #### Appropriation Language |  |  |  | ##### Donna Kalvels |  |
| Discussion | - The Effect of the Treasury/Transportation Bill (there are 3 key points) |  |  |  |  |  |  |
| Conclusions | - A cap set by Congress, $3.45M for DOI, Bureau must go thru their budget. (DOI Appropriations) - All agencies doing a study have to do an MEO (streamline or standard) if over 10 FTE. - No other contract other than “low cost” for FY 06’ (no Best Value, only technically acceptable, low cost. OK to use Best Value announced before Transportation/Treasury bill signed November 11, 2005). |  |  |  |  |  |  |
| Action items |  |  |  |  | Person/OFFICE responsible |  | Deadline |
| 1. All agencies doing a study have to do an MEO (standard or streamlined) if the number of FTE is over 10. |  |  |  |  | CS Team |  | n/a |
| #### #3 |  | #### Inventory |  |  |  | ##### Donna kalvels |  |
| Discussion | - Formal guidance basically the same as last year except for Function Code definitions. - Charter between DOI and Forest Service regarding Fire FTE has been signed. - Green plan-changes in 07-we need to update in August. - After the inventory is posted in the Federal Register, challenges can be submitted. We’ll send out an e-mail with the dates as soon as published. |  |  |  |  |  |  |
| Conclusions | - Changes to the Green Plan will be made in 2007 - Submit Challenges, after the inventory is posted in Federal Register |  |  |  |  |  |  |
| Action items |  |  |  |  | Person/OFFICE responsible |  | Deadline |
| 1. Send out E-mail with the dates as soon as the inventory is published in Federal Register |  |  |  |  | CCSE |  | none |

MEETING ADJOURNED AT 11:00 AM