FACILITIES DIVISION

Standard Operating Procedures

DATE: December 7, 2006

SUBJECT: CONTRACTING OFFICER AND ENGINEERING PROJECT MANAGER RESPONSIBILITIES UNDER CONSTRUCTION AND ARCHITECT-ENGINEER CONTRACTS

NUMBER: FDSOP-07-001

EFFECTIVE DATE: Immediately Until Replaced or Superseded

- 1.  Purpose

- The intent of this Standard Operating Procedure is to identify the various responsibilities of the Contracting Officer (CO) and the Engineering Project Manager (EPM) and the assistance they should provide each other during the course of construction and architect-engineer (A-E) contracts.

- 2.  References

- ARS Manual 242.4, Major Facilities Construction

- 3.  Background

- The Agricultural Research Services (ARS) utilizes a team concept to accomplish its design and construction contracts.  Members of the team include program management staff at the National Program Staff, Area and location levels, as well as contracting and engineering staff in the Facilities Division (FD).  Together, this team strives for the construction of the highest quality facilities that best meet the Agency’s needs within established scope and budget constraints.  ARS Manual 242.4, Major Facilities Construction, provides greater detail on the roles and responsibilities of all the parties involved, as well as the activities and phases involved, in the design and major construction or modernization of ARS research laboratories.

- The A-E and construction contracts awarded and administered by FD require a great deal of team work between the CO and EPM to ensure a successful conclusion.  The CO is responsible for ensuring that the terms and conditions of the contract are fulfilled and all applicable procurement laws and regulations are observed.  The EPM is responsible for ensuring that the design meets the Agency’s needs and that the resultant facilities are constructed within the project’s scope and budget and in accordance with the specifications and drawings.  Because FD’s projects originate from Congressional mandates and are highly visible, it is paramount that the CO and EPM work together and fully understand their responsibilities to facilitate successful completion of each facility.

- 4.  Procedures

- Enclosed is an outline of the activities involved in FD’s contracts and the associated responsibilities of the CO and EPM under construction and A-E contracts.

5.  Point of Contact

For further information, please contact the Office of the Director, FD, on 301-504-1151.

/s/ Patrick G. Barry

__________________________________

PATRICK G. BARRY

Director

Facilities Division

Enclosure

This page is intentionally blank.

Enclosure to FDSOP-07-

CO AND EPM RESPONSIBILITIES UNDER CONSTRUCTION AND A-E CONTRACTS

ACTION			Engineering		Contracting		REMARKS

1.	Overall Project		Responsible		Responsible		The primary project team members consists of the

Management.									Research Program Representative (RPR), CO, and EPM.

There are three distinct areas of project management

Program Management is to ensure all program

requirements are articulated and included in the

project.  Contract Management (CM) is responsible for

enforcing terms and conditions of the contract.

Engineering Project Management ensures all technical and program management issues are addressed and incorporated into the project.  The EPM is the lead point of contact.

2.	Orientation.			Responsible		Responsible		EPM and CO are responsible for coordinating and

conducting orientation sessions with the RPR, after consulting with the project team.

3.	Prepare Statement 		Responsible		Assist			EPM should coordinate this action with the CO and RPR,

of Work and schedule								to ensure adequate lead time will be available to solicit bids

of submittals.									and award a contract.

4.	Prepare independent		Responsible		Assist			EPM should prepare a cost estimate and SOW (see Step 3

Government estimate								above).  Coordinate with CO to ensure level of detail is

of A-E fee, CM fee, 								adequate.

and construction cost

estimate, when appropriate.

ACTION			Engineering		Contracting		REMARKS

5.	A-E Selection.			Responsible		Responsible		EPM shall provide CO with proposed technical evaluation

factors, sub-factors, scoring method, and scoring sheets.

EPM shall act as the A-E Evaluation Board chairperson and provide recommendations to the CO in writing, with all supporting documentation regarding A-E capability, based on project scope and rating criteria.  The CO shall make a recommendation to the selection authority for final selection (usually the FCB Chief).

6.	Conduct Design pre-start	Assist			Responsible		The CO and EPM coordinate the preparation for this

conference.									conference.  The CO, EPM, RPR, and A-E meet and

review scope, role, and administrative details.  The CO

usually leads; technical info/direction provided by EPM.

7.	Perform a review of		Responsible		Responsible		Both CO and EPM should review plans and specs to

specifications and								the extent required to fulfill their respective

drawings.									responsibilities.  CO to ensure no conflicts with contract,

FAR or other special clauses, or potentially restrictive

features are present.  EPM to ensure no ambiguities and

that quality control, closeout, and commissioning requirements are identified, as well as technical sufficiency (use Design Review and Architect-Engineer for detail review).

8.	Define any additive bid	Responsible		Assist			Coordinate with project team to ensure that the complexity

or optional line items  							and cost of alternates are compatible with base bid.  This

needed	to keep project								should occur at 50 percent submittal.

within funding limits.								(Reference PGM 03-001.)

ACTION			Engineering		Contracting		REMARKS

9.	Design Review Board.	Responsible		Responsible		The CO/EPM team will jointly prepare a one or two page

project synopsis on all aspects of the project budget.  In

addition, the team will present their report and obtain the

Board’s approval prior to implementing the next phase.

10.	Determine if liquidated	Assist			Responsible		Coordinate with project team to determine validity

damages (LD) are								of damages and impact on bidding.  (EPM to complete LD

required.									estimate and determination worksheet.)

11.	Conduct Market Research.    Assist			Responsible		Coordinate with EPM to assess the availability and size

status of potential sources.  Determine the feasibility of setting the project aside for a particular socio-economic group or conducting a full and open competition.

12.	Furnish completed design	Responsible		N/A			EPM to transmit to CO using Construction Project

criteria, specs/drawings,							Transmittal Form.  If RFP, EPM shall provide CO with

cost estimate, time schedule,							proposed technical evaluation factors, sub-factors, scoring

evaluation criteria to CO.							method, and scoring sheets, etc.

13.	Develop advanced		Assist			Responsible		Coordinate with project team to provide for compatibility

procurement plan.								with program/project requirements.

14.	Initiate appropriate		Assist			Responsible		CO coordinates with EPM to determine proper

pre-solicitation notice								requirements, descriptions, and time schedules.  CO

(FedBizOps, solicit bids/							prepares FedBizOps notice and solicits bids/proposals

proposals).									in cooperation with the EPM.

15.	Conduct pre-bid/pre-		Assist			Responsible		CO leads conference with technical support from EPM.  proposal conference.								CO to develop agenda in cooperation with EPM and ensure

the A-E prepares minutes and distributes to all attendees

and interested parties.

ACTION			Engineering		Contracting		REMARKS

16.	Issue amendments to		Assist			Responsible		EPM to furnish description of change, schedule, and

solicitations to change								the cost impacts.  CO decides on need to issue amendment

specs, performance times,							and extend bid/proposal due date.

or bid/proposal due dates.

17.	Receive and open bids/	N/A			Responsible		CO responsible for establishing time and place to receive

proposals.									and open bids/proposals.

18.	On IFB - review bids.		Assist			Responsible		Award is based on lowest price and price-related factors.

CO to review bids and make determination of

responsiveness, responsibility, and whether price is fair

and reasonable.

19.	RFP - evaluate			Responsible		Responsible		EPM responsible for evaluating technical factors; CO for

proposals and prospective							cost and price analysis.  EPM/Chairperson submits written

contractor’s qualifications.							evaluation report addressing strengths and weaknesses of

each offeror and makes recommendation on A-E short list

and final selection for negotiation and award, as well as for

construction contract award.  CO should normally accept

EPM’s recommendations in technical areas such as level

of effort, subcontracts, consultants, material quantities,

rental items, etc., but CO makes independent

recommendation to selection official for final

determination.

20.	RFP - conduct discussion/	Responsible		Responsible		Overall responsibility belongs to CO, but from a

negotiations with								practical standpoint, EPM and CO will share responsibility

contractors.									for their respective areas of expertise.

21.	Award contract. 		Assist			Responsible		CO to coordinate with EPM, but CO makes final

decision after evaluating all alternatives and potential

program, legal, and contractual consequences.

ACTION			Engineering		Contracting		REMARKS

22.	RFP - de-brief			Assist			Responsible		CO should lead, but this should be a team effort by

unsuccessful offerors.								EPM and CO in all cases.  Exceptions would include

rejection of offers based solely on contractual/legal issues.

23.	Conduct pre-construction/	Assist			Responsible		CO prepares agenda in coordination with EPM and other

post award conference. 	team members.  The CO conducts this meeting with technical support provided by EPM.  CO ensures A-E prepares minutes and distributes to all attendees and interested parties.   (Reference FDSOP 05-001.)

24.	Contract monitoring.		Responsible		Responsible		Overall legal responsibility belongs to CO.  EPM monitors

contractors effort to determine if progress is commensurate

with contract requirements.  Advises CO of any unusual

problems affecting the progress or cost of the project.  All

contractors and program personnel shall be advised of

EPM’s authority and limitations.

25.	Negotiations.			Responsible		Responsible		CO conducts negotiations.  EPM leads technical discussion.

26.	Formal contract change.	Assist			Responsible		CO executes formal document against contract reflecting

appropriate equitable adjustment.  EPM should provide

adequate specification, Government cost estimate,

time impact, and recommendation on contractor’s proposal

relative to level of effort, material types, and quantities.

27.	Issue stop-work (A-E)/	Assist			Responsible		CO has overall legal responsibility.

suspension of work

(Construction).

28.	Issue show cause/cure		Assist			Responsible		CO makes final decision after close coordination

notices and terminate	 							with Office of General Counsel and EPM.

contracts.

ACTION			Engineering		Contracting		REMARKS

29.	Final inspection.		Responsible		Responsible		CO responsible for timeliness in accordance with contract

period of performance.  EPM should participate and

coordinate development of punch list with A-E and RPR.

CO provides punch list to contractor with due date for

completion.

30.	Acceptance/Closeout.		Assist			Responsible		EPM coordinates verification with A-E and RPR that all

work is complete and sends written recommendations to

CO that project be accepted.  CO accepts and closes out

per FAR and FD policy.

31.	Warranty Phase.		Assist			Responsible		CO informs RPR of warranty contacts and obligations.

CO involvement only when RPR/location unable to get

appropriate response from contractor.

32.	Protests/Disputes.		Assist			Responsible		EPM provides technical advice and assistance to CO.

Only CO communicates with Protestor.

10/2006 Version