SCOPE OF WORK

PROJECT NAME

ROUTE AND NUMBER

### Scoping/Preliminary Design/Final Design

### Federal Highway Administration

### Central Federal Lands Highway Division

A/E Consulting Engineering Contract

Engineering Services

FIRM NAME

Task Order Number: DTFH68-0X-D-000XX/T-0X-0XX

Modification Number

Date

# GENERAL INFORMATION

## INTRODUCTION

Guideline: Provide a general description of work included with only enough detail for the Consultant/Designer to recognize generally what is included. Text below is sample only. KEEP IT SHORT!

This Scope of Work (SOW) is to perform environmental, engineering, hydraulic, geotechnical, right-of-way, surveying, mapping, and project management services towards delivery of a 30% plan set for the Federal Highway Administration, Central Federal Lands Highway Division (CFLHD) for proposed improvements to California Forest Highway 114, Hyampom Road.

## PROJECT SUMMARY

Guideline: Describe the background, location, and overall goal of the project. Provide enough historical information so the Consultant/Designer can understand the requirements and how this SOW supports the overall project goal. Identify any previously completed work that has been completed that will assist the consultant in understanding the project, including work on the environmental document. Describe the location well enough so that the Consultant/Designer can plan how to get to the project and where to stay. Also include where the project starts and stops, if applicable. Text below is sample only.

The Federal Lands Highway, Forest Highway program, provides funding for this project.  In January 1997, the Federal Highway Administration (FHWA) issued an environmental assessment that the proposed improvements would have no significant impact on the human or natural environment. This Finding of No Significant Impact (FONSI) is for the entire FH-39 route.  Project design standards were finalized in the FONSI.

Utah Forest Highway (FH) 39 begins at the intersection of FH 42 (Fremont River Road) and FH 13 (Fish Lake Road) and proceeds northward for 47.5 kilometers (29.5 miles) along Sevenmile Creek and Gooseberry Creek to its junction with Interstate 70. The junction is approximately 11.3 kilometers (7 miles) east of Salina, Utah.  The route is primarily on Federal land within the Fishlake National Forest in Sevier County. The road is maintained by Sevier County. The first phase (Phase 1) of the route provides for the reconstruction of 21.9-km (13.5 miles) of FH 39, from just south Twin Ponds Road to just south of the I-70 interchange. This project is currently under construction.

This second phase (Phase 2) will continue from Twin Ponds south toward the junction of FH-42, Fremont River Road. The second phase will cover about 14 km (9 miles). The Phase 2 segment of the route is currently funded for design and construction, with construction scheduled to begin in the Spring 2005. The third phase of the project (Phase 3) will be the completion of the route.  Phase 3 is programmed for construction in fiscal year 2007.

The proposed road reconstruction will closely follow the existing road with widening as appropriate to improve safety and minimize impacts.  The Phase 2 portion of the route includes two realignment segments, known as the Switchbacks and Salina Reservoir. The reconstruction will improve the alignment, grade, and width to appropriate current standards. The project includes grading, drainage structures, subsurface drainage, placement of crushed aggregate base and asphalt pavement, signing, striping, guardrails, and other safety-related features necessary to meet current design practice.

Under previous task order No. DTFH68-02-T0003, the design was completed to 50%.

## SCOPE

Guideline: State the project purpose and specific objectives to help the Consultant/Designer understand the size or magnitude of the anticipated effort. This will define the differences between Refuge Road, 3R, and 4R projects and let the consultants know what we want. For example in design this is where we define our expectations for “tweaking” the alignment to lay lightly on the land, fit terrain, etc on 4R projects. Identify the primary stakeholders/cooperating agencies. Text below is sample only.

The general scope of roadway improvements is programmed as recycling and overlay of surfaces on 7.2 miles of Highway 87 and 1.4 miles of the north and south access roads to the Visitor’s Center parking lot.  Guardrails are also to be upgraded to meet new standards.  The Beaver Creek Bridge is also to receive rehabilitation work in the form of installing expansion joint seals and a new wearing surface, repairing damaged and deteriorating concrete railing and curbs, repairing undermined abutments and wing walls, and installing slope protection.  These improvements will be designed and implemented in accordance with National Park Service, CFLHD, and AASHTO Highway Design Standards, in cooperation with the National Park Service, Denver Service Center and Wind Cave N.P.

# WORK REQUIRED

Remove following two paragraphs for internal work

The work shall be performed by Consultant (referred to as the A/E) or its approved designated representative. The A/E work shall be performed and/or directed by the key personnel identified in the A/E proposal. Any changes in the indicated key personnel or the A/E officer-in-charge of the work, as identified in the A/E proposal, shall be subject to review and approval by FHWA.

Subconsultants not identified in Contract DTFH68-0X-D-0000X will require approval by the FHWA Acquisitions office prior to beginning work. These subconsultants will be required to submit the same information regarding their firm as those identified in the original contract.

## PROJECT MANAGEMENT (PRMS Activity PM)

The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements.

Project Management will continue throughout the duration of the project.  It includes, but is not limited to, all work necessary to manage production efforts, coordinate with CFLHD, administer this contract and monitor progress.

While performing the work described under this task order, discussions with people from other agencies (i.e., USFS, NPS, FWS, and other personnel or consultants) as well as other CFLHD employees will be required.  Participate freely in these discussions, answer questions and respond to requests for information.  Maintain records of these discussions and keep the COTR informed of any pertinent information.  However, do not accept any direction or take additional work that is beyond the scope of this task order.  During discussions with partner agencies do not suggest performance of additional work that is beyond the scope of this task order. The FHWA Contracting Officer is the only representative that has the authority to revise or add work under the requirements of this task order.

##### Project Management oversight.  Typical activities include, but are not limited to, the following:

###### Identify the project requirements and determine complexity of the work, technical activities, schedules and resources

###### Administer project contract and monitor progress

###### Discuss and coordinate project requirements with the Contracting Officer’s Technical Representative (COTR) and designated project team contacts

###### Prepare and maintain project design files & supporting documentation for correspondence, reports, design details and calculations of quantities that are included in the plans.

###### Update Project Development Plan (PDP)

##### Develop and maintain a CPM Project Schedule (such as Microsoft Project CPM)

###### Identify the deliverable item due dates, milestones, reviews, and meetings, that ensures meeting the completion date objective

###### Identify all critical tasks in meeting the completion date

###### This schedule will be used to coordinate activities, meetings, and delivery dates

##### Contact the CFLHD COTR by phone at least every two weeks to discuss status and progress, if no meetings are scheduled within the timeframe

###### Prepare and submit discussion notes within seven days if requested.

##### Submit monthly progress reports providing a summary of:

###### Previous month’s accomplishments and activities

###### Overall progress achieved toward completion of the task order

###### Future month expectations

###### Any issues or action items that need to be resolved or addressed with CFLHD or partner agencies

###### All activities that will be undertaken during the succeeding month

###### Submit a progress report with each invoice.

##### Using the Standardized Scope of Work Sections provided by FHWA, develop a draft outline for the next Scope of Work

###### Add project specific requirements as necessary and develop a blank Task Order Fee Estimate spreadsheet following FHWA and Standard Task Order format

###### Submit the DRAFT Scope of Work and blank fee estimate spreadsheet to FHWA for review

###### Following FHWA review, incorporate all comments and submit the FINAL Scope of Work and blank fee estimate spreadsheet to the FHWA COTR.

#### Deliverables for Project Management

Add/delete deliverables to correspond to the tasks above. Coordinate number of copies with COTR. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

###### Meeting Minutes

###### Initial CPM Schedule and Revised Schedules

###### Discussion Notes

###### Monthly Progress Reports and Invoices

###### DRAFT Scope of Work and blank Estimate

###### FINAL Scope of Work and blank Estimate

## UTILITIES (PRMS Activities U1 to U3)

Refer to CFLHD Utility process

http://www.cflhd.gov/design/survey-map-row/_documents/UtilityProcess.pdf

#### Identify and Locate Utilities (U1 Activity)

Identify the type and location of existing utility facilities within the project limits legal rights or cost liability and the recommended certification level of the information as defined by the CFL Utility Data Quality Matrix

http://www.cflhd.gov/design/survey-map-row/_documents/Links/UtilityDataQualityMatrix.xls

Conduct early coordination with the cooperators and utility owners to identify potential conflicts between utilities and the project.

The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements. Revise the list below to include known (or assumed) utilities within the project limits. Discuss with FHWA PM and Utility Coordinator the desired level of research and mapping.

If R or S activities are not included they can be performed under the U1 Activity (Mapping and research of utilities)

It is assumed that the following utilities are located within the project limits:

- (List known names or types of utilities- see Project Scoping Report)

Revise steps 1 & 2 to complete this work under U1 if R1 and S1 are not included in the scope.

##### Support the research of existing utility facilities, types and interests completed under the R1 activity, Right of Way research.

###### Identify type of facility- include all physical utilities: underground, surface and aerial utilities, within the project area.

###### Determine cost liability to relocate the facilities

##### Review the existing utilities mapping completed under the S1 activity, Initial Survey and Mapping section.

##### Initiate early coordination with Cooperator, client agency and utility interests to begin identification of facilities, rights and potential conflicts.

###### Organize and attend utility/cooperator meetings to identify facilities and issues

###### Develop a list of contacts for each utility that can represent each company regarding location, design accommodation, relocation and cost liability issues associated with their facility.

##### Certify utilities at the recommended CFLHD Utility Data Quality Level

##### http://www.cflhd.gov/design/survey-map-row/_documents/Links/UtilityDataQualityLevelCertification.doc

###### Recommend to the Project Manager additional field investigation or research of utilities that would certify the presence and position of utilities at a higher Quality Level.

If meetings are required, put them in Section M. Meeting and Field Reviews

##### Develop recommendations for design modifications to accommodate utilities, as much as practical, to avoid or reduce utility impacts and relocation.  Support the development of initial drawings of potential utility conflicts (Completed under D activity).

##### Prepare Utility Summary Report containing the following:

###### Contact list for each utility showing name, address, phone, email address, and area of responsibility.

###### Recommendations for additional research or field investigation, including potholing (locating) to justify a higher Quality level

###### Utility coordination meeting minutes and “Action Item” list

###### Recommendations or modifications to roadway design and drawings showing potential utility/design conflicts (after 30% design)

###### Cost liability issues

#### Deliverables for U1 Activity

Add/delete deliverables to correspond to the tasks above. Coordinate number of copies with COTR. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

###### Copies of documents (as-built plans, third party mapping, GIS, permits, easements, agreements, etc.) obtained during research

###### CFLHD Utility Data Quality Certification

###### Utility Summary Report

#### Identify Utility/Design Conflicts (U2 Activity)

Identify utility/design or utility/construction conflicts and continue coordination with the utility companies to begin development of a Utility Resolution Plan that addresses these conflicts.  This activity may also include additional research and investigation to elevate the Quality Level.

Hidden Note: Add utility meetings if required under section M. Include costs for travel if necessary.

The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements. Revise the list below to include known (or assumed) utilities within the project limits. Discuss with FHWA PM and Utility Coordinator the desired level of research and mapping.

##### Perform additional research, field investigation and mapping to support a higher Quality Level certification, as needed.

##### Support Design to identify utility/design conflicts, develop or revise utility conflict drawings, based on intermediate design and field reviews.

##### Coordinate with cooperators and each utility company:

###### Identify conflicts and resolve design, construction and utility issues

###### Identify associated right of way requirements

###### Resolve cost liability issues

###### Discuss with utility concerns the Utility Resolution Plan

##### Develop a DRAFT Utility Resolution Plan

##### http://www.cflhd.gov/design/survey-map-row/_documents/Links/UtilityResolutionPlanTemplate.doc

#### Deliverables for U2 Activity

Add/delete deliverables to correspond to the tasks above. Coordinate number of copies with COTR. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

###### Copies of additional research and utility mapping on CFLHD coordinate and datum system

###### Updated Utility Data Quality Certification of utilities at appropriate Quality Level based on additional data collected.

###### Meeting minutes and “action item” list from conference calls

###### DRAFT Utility Resolution Plan

Including Utility Conflict Drawings if appropriate

#### Implement Utility Relocation Plan (U3 Activity)

Develop the Utility Relocation Plan, coordinating design, construction and utility issues, resolving cost liability issues, developing utility agreements and CERTIFYING that for each facility impacted by the project, the Utility Resolution Plan indicates whether the resolution will be either 1) accomplished prior to construction, 2) identified in the PS&E as a coordination requirement of the construction contractor, or (3)  included as items of work in the  PS&E for the construction contractor to perform.

The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements. Revise the list below to include known (or assumed) utilities within the project limits. Discuss with FHWA PM and Utility Coordinator the desired level of research and mapping.

##### Prepare FINAL Utility Resolution Plan

##### http://www.cflhd.gov/design/survey-map-row/_documents/Links/UtilityResolutionPlanTemplate.doc

###### Copy to be included in the SCR’s and PE Notebook

##### Support the development of construction plan sheets for the PS&E addressing each utility issue, treatment, relocation or installation that is to be constructed directly under the CFLHD contract.

###### See Sample Conflict Plan Sheet at

###### http://www.cflhd.gov/design/survey-map-row/_documents/Links/sampleConflictPlanSheet.pdf

##### Assist in the development of Special Contract Requirements (SCR’s), specifications, quantities and cost estimates for all construction related work and coordination required for the project.

##### Develop Utility Agreements as defined by the FINAL Utility Resolution Plan:

###### Agreements to resolve utility conflicts (executed by CFLHD)

###### Reimbursable agreements developed according to current CFLHD policy (executed by CFLHD)

###### Copies of each to be included in SCR’s and PE Notebook

##### Certify utilities according to CFLHD requirements

###### Utility Data Quality Level Certification signed by the designated project specific official

###### http://www.cflhd.gov/design/survey-map-row/_documents/Links/UtilityData QualityLevelCertification.doc

###### Right of Way and Utility Certification  PART 3, submitted to the designated project specific official for execution.

###### http://www.cflhd.gov/design/survey-map-row/_documents/Links/RoW-UtilityCertification.doc

###### Copies to be included in the SCR’s and PE Notebook

##### Constructability Review of proposed utility resolutions

#### Deliverables for U3 Activity

Add/delete deliverables to correspond to the tasks above. Coordinate number of copies with COTR. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

###### FINAL Utility Resolution Plan

###### Right of Way and Utility Certification, PART 3

An occurrence specific identification of each utility conflict and its resolution

Identification of when and how resolutions will be accomplished

Copies of all certifications and agreements in PE notebook (Part of D activity)

###### Utility related SCR appendices including:

            - Utility Agreements submitted for execution by CFLHD

            - Data Quality certification

PLANNING (PRMS Activity P1)

#### Project Development Planning (P1 Activity)

This activity is the starting point for all projects.  Included are the tasks related to Interdisciplinary/Environmental scoping, pre-construction work planning, scheduling and budgeting.  A good working draft of the Project Agreement is developed.

The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements. For CFL Internal Projects this activity can be done as a separate SOW (prior to completing full SOW for entire project.

##### Gather preliminary project information including as-builts, traffic counts, accident data, Road Inventory Project data, etc. as available. Submit one copy of project information to the CFLHD Project Manager when complete.

##### Prepare a Draft Project Delivery Plan (PDP) for the project. The Project Delivery Plan should include the following:

###### Design Scoping Report

Follow the FHWA Scoping Report Outline

Address all Project Development issues listed in the outline and recommend the work to be accomplished

Include recommended Utility Quality Level

###### Draft Project Agreement

Summarize the key issues associated with the work

Highlight the key elements

Show a draft schedule of all milestone activities through completion of construction.

###### Preliminary cost estimate

Show all major work items and include a minimum contingency of 25%

Recommend a project without funding limitations and a project within the program funds, if necessary. The final project to be advanced will be determined in cooperation with the Project Team.

The Comprehensive SOW and Budget is for CFL internal projects only

###### Comprehensive Statement of Work (SOW) for the entire project detailing all work tasks to be accomplished

###### Comprehensive Project Baseline Budget

###### Baseline schedule using work activities consistent with CFLHD’s Project Resource Management System (PRMS).

###### Communications Plan

Identify information needs, frequency of contact and the medium for communications.

###### Risk and Opportunity Management Plan

Summarize the potential threats and opportunities for the project

Include projected responses to each threat and opportunity.

###### Quality Control Plan

Highlight the reviews to be completed

###### Change Control Plan

Include a draft copy of the Change Control Request Form

###### Procurement Plan (if needed) for unique project situations such as Best Value, emergency situations or Design/Build

###### Draft Lessons Learned and Closeout Plan

Final Plan will be developed following completion of PS&E

###### Other Project Documents including (as applicable):

Photo Log

Culvert Summary

Sign Summary

Draft Environmental Screening Form (ESF, for NPS projects only)

Utility / ROW Cooperator Agreements

Other project specific documentation.

###### Submit to FHWA for review and comment

##### Incorporate comments and changes recommended by FHWA into the FINAL Project Delivery Plan. Produce final document for distribution to all Project Team Members.

#### Deliverables for P1 Activity

Add/delete deliverables to correspond to the tasks above. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

###### Preliminary Project Data

###### DRAFT Project Agreement

###### FINAL Project Agreement

###### DRAFT Project Scoping and Development Summary

###### FINAL Project Scoping and Development Summary

## ENVIRONMENT (PRMS Activities E0 to E4)

Note: Following Activities and Steps are for EIS and EA documents. Revise for Categorical Exclusion documents.

#### Environmental Scoping (E0 Activity)

Initiate coordination with Partner agencies, other (resource, “Cooperating”) agencies, “Participating” agencies, and the public.  Determine project classification (EA, EIS, or CatX), and determine draft purpose and need, draft alternatives, issues, and concerns.

Note: “Participating” agencies are a newer requirement by FHWA directive and/or SAFETEA-LU law. The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements. For complex 4R projects where more than one alternative alignment will be developed, specify the number of alternatives that should be studied and refined for consideration.

### Establish SEE Team

Use as much information as available from P1 deliverables (e.g., Planning and Programming Reports, traffic/accident data, preliminary Purpose and Need, preliminary environment resource data)

##### Establish Social, Economic, and Environmental (SEE) Team

###### Obtain names and addresses of agency offices

###### Write SEE Team draft letter requesting SEE Team member be identified, distribute for internal review, finalize, and send

Initial SEE Team and Interagency Meetings

##### Prepare for initial SEE Team Meeting

###### Arrange and coordinate with SEE Team members on logistics for meeting

###### Write and send SEE Team Meeting arrangements letter

###### Arrange and coordinate in-house (cross functional team) pre-SEE Team meeting

Purpose of in-house (CFT) pre-SEE Team meeting is to ensure that FHWA SEE Team co-chairs are adequately representing all functional area concerns at the meeting See Section M. Meetings and Field Reviews for assumptions on # of mtg.s as well as anticipated lengths.

###### Prepare for SEE Team meeting

###### Prepare meeting minutes/trip report for each SEE Team meeting including a decision and action register.  Submit draft to FHWA for comments.  Incorporate FHWA comments and prepare and distribute Final meeting minutes.

##### Prepare for Interagency Scoping Meeting

Note: may be held concurrently with or, typically, the day after the initial SEE Team meeting

###### Set up and coordinate with appropriate (key) Resource Agencies and SEE Team members to confirm time/date/location

###### Write and send Interagency Scoping Meeting letter

###### Prepare for Interagency Scoping Meeting and prepare agenda including an in-house Pre-Interagency Scoping Meeting.  Include the following items on the agenda:

Negotiated timeframes for the environmental review process

SAFETEA-LU “Participating Agency” responsibilities

Input from “Cooperating” and “Participating” agencies on Purpose and Need, issues, concerns, and alternatives (including methodologies to be used for alternatives analyses and the level of detail in the alternative analyses)

###### Prepare meeting minutes/trip report for each Interagency Meeting including a decision and action register.  Submit draft to FHWA for comments.  Incorporate FHWA comments and prepare and distribute Final meeting minutes.

##### Write and send “Cooperating Agency Participating Agency” request letters.

Public Involvement

##### Develop initial mailing list

###### Obtain mailing lists from Partner, Resource, and other agencies or organizations with appropriate lists

###### Obtain names and addresses of private property owners, if any, adjacent to the project (from R1 activity)

###### Obtain names/addresses from FLMA of Indian Tribes with potential interest

###### Coordinate and combine lists into appropriate FHWA-compatible database program

##### Prepare and send Letter of Intent

Letter of Intent should include a description of intent to begin project development and environmental analysis. May announce public meeting in the letter or may want to get public feedback prior to setting up public meeting

##### Perform initial Government-to-Government consultation with Indian Tribes

##### Request preliminary T&E species information from appropriate agencies

##### Perform initial coordination with SHPO to get approval of Area of Potential Effect (APE)

###### Identify APE

###### Research for known NRHP sites within the project vicinity

###### Prepare and send initial SHPO coordination letter

##### Set up Public Scoping Meetings.  For this project there will be xx public meetings located in the towns of xx and xx.

###### Make all arrangements necessary to locate and secure appropriate meeting place, times, and locations.

###### Arrange for appropriate media notification and prepare newspaper and other appropriate advertisements

###### Prepare and send Public Scoping Meeting Letter to public, agencies, etc

###### Prepare agenda, handout information, appropriate exhibits, technical and process information (including presentations)

###### Prepare reports on Public Meetings

###### Prepare meeting minutes/trip report for each Public Meeting including a decision and action register.  Submit draft to FHWA for comments.  Incorporate FHWA comments and prepare and distribute Final meeting minutes.

Purpose and Need, Alternatives, Issues & Concerns

##### Develop or refine draft statements of:  Purpose and Need (P&N), Alternatives, and Issues and Concerns.

P&N must include “a clear statement of objectives that the proposed action is intended to achieve” (SAFETEA-LU).

###### Circulate internally for review and comment

###### Revise and circulate to SEE Team, “Cooperating” agencies, and “Participating” agencies for review and comment.

###### Prepare for additional SEE Team meeting to review and obtain agreement on P&N, Alternatives, and issues and concerns.  This meeting will be held at xx.

##### Prepare and Publish Notice of Intent (NOI) in the Federal Register, and prepare and mail letter to mailing list contacts on intent to prepare an EIS.

Note: An NOI may be delayed to a later activity, if the necessity of an EIS is not yet determined. The NOI should include a summary of the transportation problems and objectives that the project is intended to address (see SAFETEA-LU guidance)

###### Prepare drafts of NOI and letter to contacts on preparing an EIS

###### Distribute drafts to appropriate CFT members for review and comment

###### Revise to FINAL draft and distribute to SEE Team members for review and comment

###### Revise to FINAL, get NOI and letter to contacts on preparing EIS signed.  Submit NOI to Federal Register for publication.  Mail letter to contacts.

##### Close out E0 Activity (schedule, budget, resources).

###### Review Project Agreement for clarifications/changes required and coordinate with PM

###### Revise/update Mailing List

###### Review Scope, Schedule, and Budget resources for next activity, E1; and coordinate any changes with PM,

###### Submit completion date of activity to scheduling system

#### Deliverables for E0 Activity

Add/delete deliverables to correspond to the tasks above. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

###### SEE Team Member request letter

###### Initial SEE Team meeting letter

###### Interagency scoping meeting letter

###### Various meeting agendas, handouts, exhibits, technical and process information, and presentations

###### Initial mailing list

###### Letter of intent to begin project development

###### Documentation of initial Government-to-Government Tribal consultation

###### Letter requesting preliminary T&E species information

###### Letter of initial coordination with SHPO

###### DRAFT Purpose and Need statement (EA and EIS)

###### DRAFT Alternatives to be studied (EA and EIS)

###### Issues and Concerns

###### Notice of Intent (NOI)

###### Letter on intent to prepare an EIS

###### E-mailed Project Agreement comments to PM

###### E0 activity completion date and E1 activity updated in scheduling system

#### Environmental Compliance Studies (E1 Activity)

Conduct required surveys for resource assessment.  Perform additional SEE Team, Interagency, and Public involvement activities.

The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements. For complex 4R projects where more than one alternative alignment will be developed, specify the number of alternatives that should be studied and refined for consideration.

Planning

##### Coordinate with “Cooperating” agencies, “Participating” agencies, and the Public on DRAFT Purpose and Need (P&N) and Alternatives identified for consideration.

SAFETEA-LU requires that we provide opportunity for these groups to offer their input on P&N and Alternatives to be considered. This task may occur at a later time in this activity and may be an iterative process of refining the P&N, alternatives, and methodologies to be used for alternative analyses. Amount of effort to be based on comments received and revisions required

###### Include opportunity for input regarding:  (1) methodologies to be used for alternative analyses, and (2) the level of detail in the alternative analyses (SAFETEA-LU).

###### Refine P&N

###### Refine alternatives to consider and alternatives to eliminate

###### Refine alternatives analyses methodologies and level of detail to consider

###### Refine issues and concerns to be addressed.

##### Develop negotiated timeframes for the environmental review process with “Cooperating” agencies, Resource agencies, and, as appropriate, “Participating” agencies.

This task may occur as an iterative process throughout the implementation of this activity

###### Coordinate with agencies for review of proposed environmental review timeframes

###### Discuss with agencies to negotiate agreeable timeframes

###### Document negotiated timeframes

##### Coordinate with USFWS, SHPO, Federal Land Management Agency resource staff, and Indian Tribes

Note: This task assumes that initial coordination/consultations have occurred under E0 activity.

###### Confirm T&E and sensitive species to be surveyed.

###### Confirm APE to be surveyed for cultural resources

###### Confirm concerns and or areas to be avoided with Tribes expressing interest. Document consultation with Tribes as part of Government-to-Government consultation.

###### Coordinate survey protocols with FLMA resource staff and invite to observe surveys

##### Obtain access permission to survey private properties and obtain any necessary FLMA permits:

###### Obtain updated property owner list and, if available, preliminary Right-of-Way Exhibit from R1 activity

###### Coordinate with functional disciplines (ROW, Geotech, etc) for who needs access

###### Prepare Access Permission Form(s) (sample can be provided by FHWA)

###### Write and send letter and Access Permission Form to property owners

###### Follow-up with non-responsive property owners

###### Identify on plan sheets, exhibit, or mapping, where access granted and denied

###### Determine if critical areas for surveys have been “denied access” and determine how to handle (i.e., obtain court ordered access, commit to survey when ROW purchased, etc.)

###### Obtain any necessary land management agency permits (e.g., Forest Service Special Use Permit)

##### Coordinate surveys/studies scope and schedule with partner agencies (FLMA resource staff, SEE Team agencies, Resource agencies (cooperating and participating agencies)).

Surveys and Studies

##### Initiate surveys/studies.

###### Review mapping of alternative alignments to be studied and confirm that survey corridor(s) identified.

###### Confirm identification of private property parcels where access allowed and denied for surveying.  Clearly denote “access denied” parcels.

Use mapping from S1 activity, when available, and use Alternatives from P1, E0, and/or D1

###### Notify private property owners of initiating surveys.

Depending on number of property owners this could be done either by a written letter (for many properties) or telephone or email (for few properties)

###### Notify land management agency SEE Team member and resource staff of initiating surveys, schedule for field work, and invite to observe surveys

###### Conduct discussion/meeting with resource surveying field personnel to review above information

###### Develop SOW for surveys and studies

##### Perform appropriate surveys/studies

Use mapping from S1 activity, when available, and use Alternatives from P1, E0, and/or D1. Detail and be specific about the type of each survey/study that needs to be completed.

###### Coordinate with FLMA resource staff

###### Conduct research and field work

###### Map resource sites using GPS

If unable to map using GPS then map in other suitable manner to obtain electronic survey data compatible with FHWA mapping

###### Monitor Survey/Studies Progress

Historic and Archeological Resources

T&E and sensitive species

Wetlands

List other Social, Economic, and Environmental areas to be addressed, as identified during Scoping activities.

##### Review survey data, upon completion of surveys, for survey adequacy and completeness for incorporation of data into environmental document.

Reporting

##### Prepare DRAFT and FINAL Reports on surveys/studies

###### Circulate DRAFTs internally and externally for review and comment

###### Revise and develop FINAL Reports

###### Distribute FINAL Reports to SEE Team and Resource agencies for review and comment

##### Provide data on resource site locations to design for input to the CADD files.

##### Review Biological Assessment from surveys

###### Review adequacy of report conclusions and recommendations

###### Identify concerns with proposed limitations of construction operations and mitigation

###### Coordinate concerns with PM and Construction and determine how to address modifications to meet needs

##### Review Cultural Resource Report with eligibility recommendations from survey

###### Review adequacy of survey results and recommendations on eligibility

###### Identify concerns with eligibility recommendations and proposed mitigation

###### Coordinate concerns of impacts with PM and Design and identify possible design revisions for avoidance or minimization of impacts

Meetings

##### Prepare for additional meetings including:

Add/delete meetings to correspond to complexity of issues, increase/decrease number and frequency of each type meeting as required in coordination with COTR/PM.

###### Monthly CFT Meetings for Project Status Updates

Hours for CFT meeting are typically accounted for under Section M, Meetings and field Reviews. Identify appropriate frequency for CFT Meetings based on complexity of project issues; at a minimum frequency shall be on major Milestones.

###### One (1) SEE Team Meeting and Field Review on P&N and Alternatives

###### One (1) Interagency (Resource agency) Team Meeting and Field Review on P&N, Alternatives, and Negotiated Timeframes.

###### Public Involvement Activities consisting of:  one (1) newsletter, one (1) public meeting, one (1) news release.

Add additional proposed meetings, as appropriate.

##### Close out of E1 activity (schedule, budget, resources)

###### Re-evaluate Project Agreement for clarifications/changes required, based on additional complexities identified from resource surveys/studies.

###### Revise/update mailing list

###### Review scope, schedule, and budget resources for next activity-E2; and coordinate any changes with PM,

###### Submit completion date of activity to scheduling system.

#### Deliverables for E1 Activity

Add/delete deliverables to correspond to the tasks above. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

###### Comments from “Cooperating” and “Participating” agencies and Public on P&N, Alternatives, and methodologies to use for alternatives analyses

###### Refined P&N, Alternatives considered and eliminated, Issues and Concerns to be addressed

###### Documented Timeframes for environmental reviews negotiated between FHWA and Resource agencies.

###### Documented confirmation of T&E species to be surveyed, including USFWS and FLMA response on T&E species and sensitive species lists.

###### Documented confirmation of APE to be surveyed for cultural resources, including SHPO response on Initial Coordination letter

###### Documented Government-to-Government consultation performed with Indian Tribes.

###### Property Access Permission Form and Letter to property owners.

###### Plan sheet, exhibit, or mapping showing area surveyed (Area of Potential Effect), and arease of survey access “granted” and “denied” for properties.

###### FLMA permits to allow surveys.

###### Response from property owners on access to survey “granted” or “denied.”

###### Documentation of notification to property owners, FLMA, other agencies of initiating surveys.

###### Various, and appropriate Surveys/Studies data and Resource Survey Reports, including mapping of resources (Draft and Final Reports).  Reports include:

To be used in Activity E2 and D1 and/or D2, and other appropriate functional areas’ activities as needed.

###### Biological Assessment

###### Cultural Resource Report, including eligibility of sites recommendations

###### Electronic data of resource site areas for submitted to Design

###### Updated mailing list

###### Additional Meetings information including:

Add/delete “meeting types,” information (e.g., agenda), and quantity of each information, as appropriate for complexity of project.

| Meeting Type | Agenda | Handouts | Exhibits |  | Newsletter | Public Notice | News Release |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SEE Team & Field Review | 1 | 1 | 1 |  |  |  |  |  |  |
| Interagency (Resource agencies) and Field Review | 1 | 1 | 1 |  |  |  |  |  |  |
| Public Involvement | 1 | 1 | 1 |  | 1 | 1 | 1 |  |  |

Note:  A DRAFT and FINAL of each meeting’s information are required.

#### Prepare Environmental Document (E2 Activity)

Perform additional studies, research, analyses, and evaluations necessary for document preparation.  Use data and analyses to prepare environmental document (draft) for signature.

The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements. For complex 4R projects where more than one alternative alignment will be developed, specify the number of alternatives that should be studied and refined for consideration.

Perform Additional Studies, Research, Analyses, and Evaluations

##### Perform cultural resource significance determination

###### Write draft letter to SHPO on “eligible” and “not eligible” sites

###### Coordinate draft SHPO eligibility letter with FLMA Resource Specialist and obtain written concurrence on determination

###### Finalize and send SHPO eligibility letter, with Final Cultural Resource Report, requesting concurrence in eligibility determination.

Typically, the FHWA Environment Section will be responsible for coordination/consultation with other Federal and/or state agencies; however, the A/E will be involved to some level as agreed to between the COTR/PM and the contractor during the development of the SOW. Revise Steps 1 and 2 appropriately for level of involvement byA/E.

##### Perform T&E species coordination/consultation.

Note: Add/Delete appropriate steps based on anticipated Affects Determination. Three (3) types of Affects Determination with different levels of consultation are possible: 1) NO EFFECT- typically only need to document to files, but may sometimes require notification to FWS; 2) MAY AFFECT BUT NOT LIKELY TO ADVERSELY AFFECT- BA sent to FWS for 30-day concurrence with appropriate coordination and consultation as necessary to receive FWS Concurrence letter; 3) ADVERSELY AFFECT- minimum of 135-day formal consultation process to receive a Biological Opinion from the FWS. Coordination/consultation of T&E species will typically follow the FHWA Environmental Guidebook’s Environmental Flow Charts process.

###### Conduct appropriate coordination with FLMA on Biological Assessment with appropriate Affects Determination:  1) No Affect, 2)  May Affect But Not Likely To Adversely Affect, and/or 3) Adversely Affect.  Include recommendations for mitigation or timing restrictions, as appropriate, for T&E and FS sensitive species.

###### Conduct appropriate consultation with Fish & Wildlife Service on Biological Assessment Determination and recommendations for mitigation and/or timing restrictions, as appropriate.

###### Coordinate with State Wildlife agency and State Wildlife Action Plans, as appropriate

##### Perform additional studies/surveys (typically those requiring greater than 1 year and/or 2 seasons).  This includes the following areas:

NOTE: Add/Delete appropriately for additional surveys that are required. Add other studies/surveys required from issues/concerns identified from Activity E1 agency and public involvement. Be specific on the anticipated type and number of studies/surveys required.

###### Verify wetland delineation with US Army Corps of Engineers (USACE)

Verification typically through report submittal to USACE with request for jurisdictional delineation determination; however, if appropriate, add field review with USACE to field-review delineation.

###### T&E species requiring longer survey timeframe protocols

###### Sensitive species requiring longer survey timeframe protocols

###### Cultural Resource Site Testing for eligibility determination

###### Additional surveys on previously denied access of private property

###### Construction activities based on most recent Alternatives’ design

###### Cumulative and Secondary effects based on most recent Alternatives’ design

###### Section 4(f) and 6(f) study

Obtain and/or confirm boundary of area from administering agency

Confirm “use” of 4(f) and 6(f) property by current Alternative(s)

Coordinate with Designers to develop Alternatives to avoid 4(f) and 6(f)

Coordination and Reporting

##### Complete all other required coordination and consultations

NOTE: The type and intensity of coordination/consultations are dependent on the complexity of the project issues, affected resources, and involvement in the project of various resource agencies, the public and local agency concerns.

###### Assist FHWA Environment Staff in performing coordination and consultation on resources or issues identified below:

NOTE: Identify the resources or issues to assist FHWA Environment Staff in performing coordination and consultation.

###### Follow the FHWA Environmental Guidebook’s Environmental Flow Charts processes.

###### Continue any necessary Government-to-Government consultation with Indian Tribes

##### Perform analyses and evaluations

###### Use information obtained from Activity E1 and above Steps in E2 and interpret and evaluate applicability of various resources to proposed project alternatives,

###### Analyze impacts to all resources identified previously from proposed alternatives,

###### Prepare information for inclusion in NEPA document.

###### Request Floodplain analysis to be performed by Hydraulics.

###### Section 4(f) and 6(f) research and analyses, as necessary:

###### Field trip to evaluate alternatives, to research area, to discuss 4(f) ramifications with administering agency

Develop specific data necessary to evaluate 4(f) and 6(f) take (e.g., acreage required, facilities in area, facilities affected, mitigation possibilities)

Obtain letters of concurrence from administering agency

Coordinate information developed for inclusion in document

##### Prepare reports on additional studies/surveys, analyses, and evaluations

NOTE: Add/Delete Reports required to adequately document any additional studies/surveys, analyses, and evaluations tasked and performed in previous Steps.

###### Reports should follow the reporting standards identified in the Environment Resource-specific SOWs

###### BA Addendum or Revision to Draft BA on T&E species requiring longer survey timeframe protocols

###### Report on Sensitive species requiring longer survey timeframe protocols

###### Report on Cultural Resource Site Testing for eligibility determination

###### Field Trip Report on findings from surveying previously denied access of private property

###### Addendum Report on Construction activities based on most recent Alternatives’ design

###### Revision to Draft Cumulative and Secondary effects Report based on most recent Alternatives’ design

###### Draft of following portions of Section 4(f) and 6(f) Evaluation:  Introduction, 4(f) and 6(f) Property(ies) Description, and Purpose and Need

NOTE: Add/delete portions of 4(f) and 6(f) Evaluation to be drafted based on information gathered in previous Steps (e.g., acreage impacted by alternatives, avoidance alternatives, etc.).

##### Begin cultural resource consultation on affected, significant sites

An FHWA Environment Staff person will be responsible for coordination/consultation with other Federal, state, or local agencies on cultural resources, unless that responsibility is delegated and tasked to the A/E.

###### Assist an FHWA Environment Staff person in performing this coordination/consultation.

###### Follow the FHWA Environmental Guidebook’s Environmental Flow Charts process and the 36CFR800, Protection of Historic Properties.

##### Coordinate with client, partner, resource, “Cooperating,” and “Participating” agencies

Add/delete types of coordination required, based on complexity of issues, concerns, and impacts identified.

###### Write and send letters/emails responding to questions and comments from agencies

Identify number of meetings and reports assumed based on complexity of issues, concerns, and impacts.

###### Prepare for SEE Team and Interagency Team meetings

###### Prepare for Field Reviews

##### Coordinate with the Public

Add/delete types of coordination required, based on complexity of issues, concerns, and impacts identified. Identify number of meetings and associated deliverables assumed to be required.

###### Write and send letters/emails responding to questions and comments from agencies

###### Prepare for Public Meeting(s)

Make all arrangements necessary to locate and secure appropriate meeting place, times, and locations.

Arrange for appropriate media notification and prepare newspaper and other appropriate advertisements

Prepare agenda, handout information, appropriate exhibits, technical and process information (including presentations)

###### Obtain input from Public on issues and concerns

###### Obtain input from Public on Purpose and Need and Alternatives to be considered

###### Perform follow-up with the Public from Public comments

###### Prepare DRAFT Newsletter(s) for review; revise, prepare FINAL Newsletter(s), and distribute to updated mailing list addressees.  Assume xx newsletters will be required for this project.

###### Prepare for briefings to state and/or local government representatives (e.g., County Commissioners, Town Council, etc.)

##### Provide information to Design, including:

Add/delete information to be provided, as appropriate.

###### Agency and Public concerns with potential to affect/change design

###### Updates to or newly identified resource locations (e.g., wetland delineations, 4(f) property, etc.)

###### Coordination on resources for which alternatives should be evaluated for avoidance, minimization, and/or mitigation of impacts.

###### Coordination on any potential construction restrictions/limitations (e.g., time period limits due to T&E species)

##### Finalize Purpose and Need (P&N) and Alternatives chapters for Environmental Document.

NOTE: The P&N must include “a clear statement of objectives that the proposed action is intended to achieve” (SAFETEA-LU).

###### Circulate internally for review and comment

###### Revise and circulate to SEE Team, “Cooperating” agencies, and “Participating” agencies for review and comment

###### Prepare for combined SEE Team-Interagency Team meeting to review and obtain agreement on Final P&N and Alternatives.

###### Request written concurrence on P&N and Alternatives from Partner, “Cooperating” and “Participating” agencies.

Prepare Environmental Document

##### Perform additional evaluations based on most recent alternatives design being considered

Add/delete evaluations as appropriate for level of additional studies/surveys performed in previous steps.

###### Review Floodplain analysis from Hydraulics and evaluate encroachments, prepare risk analysis report, prepare analysis section for inclusion in EIS.

###### Evaluate SHPO’s opinion on impacts to cultural resources for inclusion of information into EIS

###### Evaluate FWS’s concurrence on BA or Biological Opinion

###### Evaluate Section 4(f) properties’ use and determine minimization of use

##### Develop mitigation measures

###### Coordinate with Design and Construction on possible/proposed mitigation for:

Add/delete appropriate areas for which mitigation to be coordinated.

Wetlands

Cultural resources

Section 4(f),

T&E species,

Socio-economic

###### Develop proposed mitigation measures and draft proposed mitigation write-up for inclusion in EIS document

##### Coordinate mitigation measures with partner agencies and with affected resource agencies

###### Write letters/emails to agencies on proposed mitigation measures

###### Prepare for SEE Team and Interagency Team meetings/field reviews to reach consensus on mitigation measures from agencies

##### Prepare illustrations for Preliminary Draft EIS (PDEIS) document.

Illustrations consist of some or all, but are not limited to, the list shown. Add/delete illustrations as appropriate to meet the complexity of issues to be addressed in EIS.

###### Vicinity Map

###### Project and/or Study Area Map(s)

###### Existing conditions/problems photographs

###### Typical Section(s)

###### Alternatives maps

###### Visual Simulation Photographs (Before and After)

###### Floodplain map

###### Land Use map

###### Resource maps (e.g., wetlands, Section 4(f) properties)

###### Recreation Resources

###### Federal Land Management Agency Management Areas

##### Write PDEIS Document

###### Write all appropriate sections of Pre-DEIS;

###### Write Draft Section 4(f) and/or 6(f) Evaluation

##### Perform internal (FHWA) review of PDEIS document

Note: For an EIS an Environment Review Team (ERT) reviews the Pre-DEIS.

###### FHWA identifies Environment Review Team (ERT)

###### ERT conducts independent review of Pre-DEIS, with at least one member completing the DEIS Checklist

##### Perform external review of document

###### Revise Internally reviewed document to Administrative PDEIS for distribution to SEE Team and Resource agencies.

###### Distribute Administrative PDEIS to appropriate agencies

NOTE: Establish comment period of no more than 30 days from availability of the document, unless a different deadline is established by agreement of the FHWA and all participating agencies; or the deadline is extended by the FHWA for good cause (SAFETEA-LU)

###### Perform any necessary Section 4(f) and 6(f) Evaluation statement coordination or consultation

##### Prepare for interagency meeting to discuss comments/revisions to document.

###### Set up and coordinate with appropriate Resource Agencies, SEE Team members, and “Participating” agencies to confirm time/date/location

###### Write and send letter with Document for review and confirming time/date/location of meeting

###### Prepare for meeting and prepare agenda

###### Prepare for an internal cross-functional team preparation meeting.  This meeting should include the following:

Add any exhibits needed for the meeting.

Review of the document page-by-page or section-by-section and obtain comments from agencies.

A request for written comments by deadline originally set (no more than 30 days from availability of document)

Review and discuss negotiated timeframes for the environmental review process and identify if any revisions required.

##### Evaluate meeting comments and written comments received

###### Coordinate and discuss comments affecting design aspects with other disciplines

###### Develop response to comments (e.g., document to be revised per comment, additional coordination/resolution required)

###### Conduct any additional coordination required to resolve addressing of comments

###### Prepare letter to agencies on how their comments were addressed

##### Revise PDEIS document, prepare press-ready DEIS document and cover Memorandum to Signatory Authority requesting signature

Division Engineer is the Signatory for EIS.

###### Revise documents per comments received and revisions agreed upon.

###### Prepare one final revised document

###### Prepare one original Signature Page

###### Prepare Memorandum to Signatory Authority discussing:

Document has been reviewed internally and externally and comments incorporated

Attached are any appropriate resolutions to comments received

QA/QC process has been completed for this stage of the document

Document is ready for signature

##### Close out of E2 activity (schedule, budget, resources)

Update mailing list, as needed throughout the Activity, and one final time at end of activity for distribution of Environmental Document and/or Notice of Availability of Environmental Document and Public Hearing (EA and EIS)

###### Re-evaluate Project Agreement for clarifications/changes required, based on additional complexities identified during this activity

###### Revise/update Mailing List by including any new contacts (agencies, public) identified during this activity and coordinate with Right-of-Way section to obtain updates to property owner list

###### Review Scope, Schedule, and Budget resources for next activity-E3; and coordinate any changes with PM

###### Submit completion date of activity to Scheduling system

#### Deliverables for E2 Activity

Add/delete deliverables to correspond to the tasks above. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

###### Letter to SHPO on eligibility determination

###### Survey Reports from additional surveys/evaluations

Identify specific reports to be delivered. Add/delete reports as appropriate

BA Addendum or Revision to Draft BA

Sensitive Species Report

Cultural Resource Site Testing Report

Field Trip Report on findings for previously un-surveyed areas

Addendum Report on Construction activities

Revision to Draft Report on Cumulative and Secondary effects

###### Locations of any additional resources, if any, and provided to Design

###### Mitigation measures

###### Illustrations for Environmental Document

###### Internal Environmental Document for Review

###### Comments on Environmental Document from Internal review

###### External Draft Document for Review by agencies

###### Comments on Environmental Document from External review

###### Resolution to comments received on Environmental Document

###### Letter(s) to agencies on how there comments were addressed

###### Section 4(f) Evaluation

###### Press Ready Environmental Document for signature by signatory authority

###### Memo to signatory authority of Environment Document readiness for signature

###### Various meeting confirmation letters, agendas, handouts, exhibits, technical and process information, presentations, newsletters, other public involvement items

Identify numbers of each to be delivered

###### Coordination/Consultation letters/emails with agencies and Public

###### Updated mailing list(s)

###### Project Agreement comments

###### Updated or confirmed scope, schedule, and budget for next activity (E3)

###### Completion date for this Activity (E2) submitted to Scheduling system

#### Environmental Compliance Approval (E3 Activity)

Signing of, reproduction and circulation of DEIS; Public involvement (hearings) through end of official comment period.  Amending/revising/finalizing, or preparing FEIS and preparing decision document (ROD)

The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements. For complex 4R projects where more than one alternative alignment will be developed, specify the number of alternatives that should be studied and refined for consideration.

Sign, Reproduce, and Circulate DEIS Document and Conduct Appropriate Public Involvement

NOTE: FHWA sends cover Memo and DEIS to Signatory Authority and obtains appropriate signature on DEIS from Signatory Authority. FHWA gets DEIS signed. For FHWA internal projects, this is Step 1.

##### Sign and Reproduce and Mail DEIS Document

FHWA provides A/E with signed original DEIS

###### Get appropriate signatures for DEIS document

###### Prepare Federal Register Notice of Availability of DEIS and get Notice signed by appropriate FHWA Signatory Authority

###### Determine document distribution in coordination with FHWA’s PM and Environment Lead and prepare transmittal letters

###### Mail appropriate copies to EPA, DOI, FHWA Headquarters (include in EPA copy the Federal Register Notice of Availability of DEIS)

###### Mail document to appropriate agencies, public, and repositories, etc.

##### Set up and prepare for Public Hearings (PH)

###### Set up PH’s

Make all arrangements necessary to locate and secure appropriate meeting place, times, and locations

Arrange for appropriate media notification and prepare newspaper and other advertisements

Coordinate with FHWA on type of media notification to arrange

Arrange for Court Reporter to transcribe PH

###### Prepare and Distribute Public Notices for PH

Write Draft Public Notice; review internally and externally with SEE Team

Send Notice for Publication

Review “proof” version of Notice from advertiser and correct as needed

###### Send mass mailing to public and agencies on PH format, time, place, and purpose of hearing

###### Prepare agendas, handouts, presentations, and displays/exhibits for PH

Prepare drafts of materials to have at the PH

Distribute Drafts of PH materials to Cross Functional Team members and SEE/Interagency Team members and obtain comments

Coordinate with appropriate personnel for any presentations to be made

Obtain other agencies draft presentations and review and comment

Revise and finalize materials for PH

###### Conduct pre-hearing internal coordination

Set up internal Cross Functional Team meeting to discuss logistics, roles and responsibilities, and running of the PH

Coordinate with SEE Team/Interagency Team members on logistics, roles and responsibilities, presentations, running of the PH; confirm SEE/Interagency Team Meeting date prior to PH and confirm PH date.

Confirm logistics with the Court Reporter

Confirm logistics on accessing the PH Meeting Room

##### Prepare for SEE Team/Interagency Team Meeting prior to PH.

##### Review comments from PH(s)

###### Review PH transcript(s) and make necessary corrections (e.g., corrected names, misspellings, etc.)

###### Review comments received on document and at PH

###### Send copies of comments received and transcripts to SEE Team members

###### Respond to comments, requiring individual answer, by letter as appropriate with copy of responses sent to SEE Team members

Finalize Environmental Document and Prepare Decision Document

##### Amend and revise environmental document as appropriate based on comments received

###### Write summary of comments received for inclusion in final document

###### Prepare responses to substantive comments received for inclusion in final document

###### Revise and/or amend various sections of document as appropriate

###### Revise illustrations as appropriate

###### Write Final Section 4(f) and 6(f) Evaluation and Determination, as required

###### Perform any required coordination/consultation on Final Section 4(f)

##### Perform internal (FHWA) document review (includes legal sufficiency review)

###### Prepare Cover Memorandum and send Draft Pre-Final EIS (Draft PFEIS) to Legal Counsel requesting Legal Sufficiency Review

###### Reconvene Environment Review Team (ERT) to have ERT review Draft PFEIS using FEIS Checklist

###### Review ERT and Legal Counsel comments; resolve/address comments; and Revise document to Administrative Pre-Final EIS (Administrative-PFEIS) for External Agency Review

##### Perform external document Review

###### Arrange agency review meeting

###### Prepare transmittal letters

###### Distribute Administrative Pre-Final EIS (PFEIS) to SEE Team, and/or Interagency Team members for review and comment.

Set a maximum of 30-days for review time.

##### Prepare and respond to Interagency meeting to discuss comments and revisions to document

###### Revise document as appropriate

###### Summarizes substantive revisions to be made

###### Obtain written concurrence from other agency SEE Team members on Selected Alternative and Decision

###### Obtain comments from Section 4(f) and 6(f) coordination/consultation

##### Prepare Draft ROD for review

###### Write Pre-Draft ROD

###### Distribute for Internal Review; revise per comments

###### If necessary, consult with Legal Counsel for review of Pre-Draft ROD

###### Distribute Administrative Draft ROD for External Review; revise per comments

###### Prepare Draft ROD

##### Prepare press-ready document

###### Prepare original Final EIS (FEIS) signature page ready for signature

###### Prepare final document to get ready for copying

##### Get final documents signed (i.e., FEIS)

###### Prepare Cover Memorandum to Signatory Authority to request Signature

###### Get FEIS signed

###### Get transmittal letter(s) signed

###### Update mailing list and make final count for distribution of document

Coordinate with ROW Section on any changes to property ownership

Revise list based on PH sign-in sheet and property ownership changes

Revise per additional public or agencies contacts

Determine and count who to receive a copy of document; and print final mailing list, stamp with date, and file in official Environment files

###### Reproduce signed FEIS document for distribution

##### Notify agencies and the public of FEIS document availability and distribute copies

###### Write Federal Register Notice of Availability of FEIS

###### Send Federal Register Notice to EPA

###### Write and send notice of FEIS availability to newspapers

###### Write notice of FEIS availability to public and agencies

###### Distribute FEIS to repositories (i.e., Library, SEE Team members office, etc), agencies, and others as appropriate

##### Prepare and Transmit Draft Environmental Commitments Summary (ECS) to PM, Design, Construction, and others (e.g., Permits, R/W), as appropriate for review.

###### Review FEIS chapters for commitments mitigate impacts

###### Summarize commitments in a Draft ECS Table that can be used for tracking implementation of commitments

###### Distribute Draft ECS Table to PM, Design, and Construction for review and comments

##### Other Coordination and/or Consultation

###### Researching information

###### Telephone conversations, letter writing, email writing to respond to questions and concerns of the public and agencies

###### Continued government-to-government consultation with Indian Tribes

###### Field contact with agencies and/or the public and/or Indian Tribes

###### Coordination with Design on mitigation commitments, including reviews of designs, plans, specifications, and estimates to ensure the implementation of mitigation measures and commitments

##### Review comments on FEIS received from public and/or agencies

###### Review comments received on document

###### If appropriate, send copies of comments received to SEE Team members

###### Respond to comments, requiring individual answer, by letter as appropriate with copy of responses sent to SEE Team members

##### Revise and Finalize ROD

###### Prepare Pre-Final ROD, addressing any comments received on FEIS

###### Internal Review of Pre-Final ROD

###### External Review by SEE Team members of Pre-Final ROD

###### Obtain comments from SEE Team members on Pre-Final ROD

###### Obtain SEE Team members’ written concurrence on Alternative Selection Decision identified in Pre-Final ROD, if not previously obtained

###### Prepare Final ROD

##### Sign ROD, distribute ROD, Notify agencies and Public of ROD availability

###### Prepare transmittal letters for distributing ROD

###### Prepare cover Memorandum to Signatory Authority requesting ROD signature and transmittal letters signature

###### Copy signed ROD and mail to appropriate people

###### Write, get signed, and send letter of notice of  ROD to mailing list

###### Write Notice of ROD for newspaper advertisement and get notice published

###### Send ROD/FEIS to repositories (i.e., Library, FLMA District Office, etc.), and to agencies and others as appropriate

##### Transmit Final ECS Table with Cover Memorandum to internal customers.

Note: Internal customers include PM, Design, Construction, and others (e.g., Permits, R/W), as appropriate.

###### Revise Draft Commitments Memorandum to Final Commitments Memorandum and get it signed

###### Copy and distribute Commitments Memorandum

##### Close out of E3 activity (schedule, budget, resources)

###### Re-evaluate Project Agreement for clarifications/changes required, based on ROD and Commitments

###### Revise/update Mailing List

###### Review Scope, Schedule, and Budget resources for next activity-E4; and coordinate any changes with PM

###### Submit completion date of activity E3 to Scheduling system

#### Deliverables for E3 Activity

###### Cover Memorandum for:

DEIS signature

FEIS signature

ROD signature

###### PH arrangements and information including, but not limited to:

Meeting room(s)

A/V Equipment

Appropriate media notification

Newspaper advertisement

Public Notice to mailing list addressees

Court Reporter arrangements

Agenda

Handout information

Appropriate Exhibits, technical and/or process information

Presentations, as appropriate

###### Transcripts of PH and other notes, as appropriate

###### Various correspondence with agencies and Public including, but not limited to:

Transmittal of signed DEIS

Transmittal of Public Notice of PH

Confirmation of pre-hearing coordination meeting(s)

Transmittal of comments received and transcripts from PH

Transmittal of responses to comments received at PH

Confirmation of Agency document review meeting (review of Administrative  Pre-Final EIS)

Request for written concurrence on Selected Alternative Decision

Request for review of Draft ROD

###### Various meeting agendas, handouts, exhibits, technical and process information, presentations, and reports from SEE Team meetings/field reviews, interagency and cross-functional team meetings/field reviews.

Identify numbers of each to be delivered

###### Federal Register Notice of DEIS Availability

###### Response to comments on DEIS requiring individual answer by letter(s), as appropriate

###### Pre-FEIS

###### Cover Memo to Legal Counsel requesting Legal Sufficiency Review of Pre-FEIS

###### Draft ROD

###### FEIS with original signature page

###### Federal Register Notice of FEIS Availability

###### Draft Environmental Commitments Memorandum (with mitigation measures, other commitments, special contract requirements, etc.)

###### Response to comments of FEIS requiring individual answer, by letter(s) as appropriate

###### Final ROD

###### Final Environmental Commitments Memorandum from ROD/FEIS commitments (with final mitigation measures, other commitments, special contract requirements, etc.)

###### Updated mailing list(s)

###### Project Agreement comments

###### Updated or confirmed scope, schedule, and budget for next activity (E4)

###### Completion date for this Activity (E3) submitted to Scheduling system

#### Supplemental Environmental Mitigation (E4 Activity)

Implement required mitigation efforts including coordination on Environmental commitments through final design (from 30% through 100%); coordination with FLMA(s), Resource agencies, and others on mitigation work plans; implementing mitigation field work; monitoring implemented mitigation efforts; interim reporting, draft reporting, and final reporting on completed mitigations.

The following list of typical steps is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify steps to meet project specific requirements. NOTE: This activity includes the following three areas: Post-Decision Environmental Work, Pre-Construction Mitigation Efforts, and Mitigation during Construction, each of which is described below: Phase 1- Post-Decision Environmental Work including various tasks that require action after the Environmental Decision Document is completed and which are not part of any other activity, including follow-up actions on Environmental commitments through Final Design development and monitoring of mitigation efforts prior to, through, and after construction. Phase 2- Pre-Construction Mitigation Efforts, including coordination, contracting, and field work for mitigation efforts prior to construction starting Phase 3- Mitigation During Construction, including continuation of mitigation efforts from Phase 1 and additional mitigation efforts as required;

PHASE 1- POST-DECISION ENVIRONMENTAL WORK. Listed are typical Steps that are required on projects. Add/delete/revise Steps, in coordination with FHWA, to meet post-Decision Environmental Work requirements.

##### Perform re-evaluation and document re-evaluation

##### Perform additional cultural resources work and coordination

###### Monitoring

###### Reporting

List specific cultural resource work to be completed

##### Perform additional T&E species work and coordination

###### Surveys

###### Monitoring

###### Reporting

List specific T&E species work to be completed.

##### Perform additional hazardous waste work and coordination

List specific hazardous waste work to be completed.

##### Perform additional wetlands work and coordination

###### Monitoring

###### Reporting

###### Field Review

List specific wetland work to be completed.

PHASE 2, PRE-CONSTRUCTION MITIGATION EFFORTS. Portions of this phase can only be performed if either R/W has been obtained or permission granted (by private or FLMA owners) to perform the certain mitigation (particularly any invasive mitigation such as archeological data recovery). Add/delete Steps as appropriate based on status of access to property.

##### Coordination with internal and external clients

###### Ensure right-of-way or right-of-entry obtained for mitigation site(s)

###### Prepare draft mitigation approach letter, review internally, revise and send draft to client agencies for review and comment

###### Receive comments and discuss with client agencies, as necessary, and finalize mitigation approach

###### Send revised mitigation approach letter to regulatory agency

###### Revise mitigation approach in response to regulatory agency and coordinate revisions with appropriate cross-functional team members and with client and regulatory agency.

##### Obtain concurrences necessary for mitigation

If E4 activity done internally to FHWA then add Step for Contracting for work, if necessary including: Perform appropriate contracting methods as required, and, perform field trip if necessary.

##### Coordinate and monitor mitigation efforts

###### Coordinate with Land Management Agency’s appropriate Resource staff and include in monitoring

###### Coordinate with appropriate regulatory agency and include in monitoring

###### Coordinate with other cross-functional team members

##### Coordinate clearance to construction

###### Confirm appropriate mitigation field work is completed (e.g., archeological site field data recovery is done)

###### Prepare Memorandum to Construction and PM that field mitigation is complete and that area is cleared for construction.

#### Deliverables for E4 Activity

Add/delete deliverables, as needed, to meet specific work requirements above.

###### Construction Clearance Memorandum to Construction

###### Comments to Design on plans and specifications (30%, 50%, 70%, 95%)

###### Various correspondence (letters, memos, emails, telephone notes, etc.) to client and resource agencies, internal staff

###### Re-Evaluation of Document

## SURVEY (PRMS Activities S1 to S4 and M1 to M2)

#### Initial Survey and Mapping (S1 Activity)

Perform initial survey work to establish control and initial data for mapping and Right-of-Way

The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements.

##### Mobilize and reconnaissance of project site

###### Meet with agency contact or representative

###### Perform reconnaissance of project site

Identify safety, traffic and private property concerns

###### Formulate a Work Plan

##### Control Network – Set monuments, determine coordinates & elevations of primary control points

###### Research and recover existing NGS, CFLHD or other horizontal and/or vertical control points

###### Set control monuments in accordance with the Work Plan

###### Perform the required measurements

###### Analyze and adjust measurements

###### Create a Control Report and Control Data Sheet according to the requirements shown under Deliverables

List assumed utilities

##### Locate and map utilities according to ASCE Standards (ASCE 38-02);

###### Contact locate service to identify utilities to be mapped

###### Perform the required measurements to locate the utilities relative to the CFLHD control network

###### Review, edit & submit files according to the requirements shown under Deliverables

##### Locate cadastral and private property monuments and other evidence

###### Identify aliquot, right of way, property and other monumentation and evidence of possession to be mapped

###### Perform the required measurements to locate the evidence relative to the CFLHD control network

###### Review, edit & submit files according to the requirements shown under Deliverables

##### Field Reports

###### Submit progress reports

###### Submit Final Report

##### Field Mapping

###### Map area as identified in Work Plan

###### Review, edit & submit files according to the requirements shown under Deliverables

##### Office Mapping

###### Prepare TIN, map and contour files according to the requirements shown under Deliverables

Remove remote sensing step if not necessary.

##### Remote Sensing

###### Coordinate control and panel locations to provide sufficient control for the remote sensing mission

###### Prepare TIN, map and contour files according to the requirements shown under Deliverables

###### See CFLHD Remote Sensing standards and specifications

#### Deliverables for S1 Activity

All services, data and deliverables shall be to CFLHD standards and specifications. Data to be provided in the applicable digital format, when possible. The final submittal of all files shall be delivered on a CD/DVD, labeled with the Project Designation, Project Name and Final Submittal, i.e. “CA PFH 112-1(1)”, South Fork Smith River, Final Submittal”. Progress submittals shall be submitted via CD/DVD. All file names shall begin with the “Project Designation”. The remaining characters of the file name shall be descriptive of the data contained in the file. The first line of each file shall be a header describing each field and/or the contents within the file.

###### Control Data Sheet files (.xls and .dgn),

###### 3D Planimetric mapping file (.map),

###### 3D Contour mapping file (.con),

###### GEOPAK® TIN files (.tin),

###### Developed film roll in film canister for the project and labeled with the completed CFLHD film can label,

###### Current camera calibration report,

###### Digital photo index TIFF format (on the delivered CD or DVD) with one hard copy plot of the index provided,

###### Orthophoto mosaic of the Rectified Digital Imagery at 0.2’ pixel size for the entire photo covered area,

###### All files needed to accurately set and compile 3-D planimetric mapping from the supplied digital imagery in CFLHD’s current version of Socet Set ® photogrammetric suite.

###### 3-D MicroStation design file, containing space line strings and ground shots on designated levels. These space line strings and ground shots depict (in three dimensions) the topography,

###### 3-D MicroStation design Index file containing layout of all photo models and an outline of the actual compilation area,

###### An ASCII, text file listing the softcopy photogrammetric data.

The following data is to be retained by the A/E unless requested by the COTR:

###### Primary Control Point data:

Raw, unedited field data files in ASCII format,

A report of the 3D least squares analysis and adjustment of the observations made to establish coordinates for the Primary Control Points,

The final adjusted coordinates, elevations, and descriptions for the Primary Control Points in an ASCII file formatted as follows: Point Number, Northing (Y), Easting (X), Elevation (Z); Description/Comment.

###### Field Topographic Mapping Survey data and materials covering the project area:

Mapping data files shall have one point per line, utilizing the following ASCII format: “Point Number, Northing (Y), Easting (X), Elevation (or numeric placeholder), Mapping P-Code and Connect Codes; Description/Comment,”

All raw observations (GPS vector data, slope distance, zenith angle, horizontal angles and instrument and target heights) made to establish the control points and existing control checks in digital format.

The first line of each file shall be a header describing each field within the file,

The data fields shall be separated with a comma (,) the Connect Code field and the Description/Comment field shall be separated by a semi-colon (;).

###### Remote sensing data and materials covering the project area:

Two sets of color contact prints,

One set of black and white prints to be annotated with control and planimetric features.

#### Supplemental Surveys (S2 Activity)

Obtain Supplemental Survey Data and perform quality controls.

The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements. The S2 Supplemental Surveys activity is used to perform supplemental survey do to changes in alignment, obscured areas, revised scope, etc... If supplemental survey is not anticipated or known, delete this activity from the SOW. If additional survey is requested after the task order is executed the S2 should be added with a modification.

##### Mobilize and Reconnaissance of Project Site

###### Meet with agency contact or representative

###### Perform reconnaissance of project site

Identify safety, traffic and private property concerns

###### Formulate a Work Plan

##### Field Mapping

###### Map area as identified in Work Plan

###### Review, edit & submit files according to the requirements shown under Deliverables

##### Office Mapping

###### Prepare TIN, map and contour files according to the requirements shown under Deliverables

##### Locate and map Utilities according to ASCE Standards (ASCE 38-02);

###### Identify utilities to be mapped and contact locate service

###### Perform the required measurements to locate the utilities relative to the CFLHD control network

###### Review, edit & submit files according to the requirements shown under Deliverables

##### Locate cadastral and private property monuments and other evidence

###### Identify aliquot, right of way, property and other monumentation and evidence of possession to be mapped

###### Perform the required measurements to locate the evidence relative to the CFLHD control network

###### Review, edit & submit files to according to the requirements shown under Deliverables

#### Deliverables for S2 Activity

Add/delete deliverables to correspond to the tasks above. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

All services, data and deliverables shall be to CFLHD standards and specifications. Data to be provided in the applicable digital format, when possible. The final submittal of all files shall be delivered on a CD/DVD, labeled with the Project Designation, Project Name and Final Submittal, i.e. “CA PFH 112-1(1)”, South Fork Smith River, Final Submittal”. Progress submittals shall be submitted via CD/DVD. All file names shall begin with the “Project Designation”. The remaining characters of the file name shall be descriptive of the data contained in the file. The first line of each file shall be a header describing each field and/or the contents within the file.

###### 3D Planimetric mapping file (.map),

###### 3D Contour mapping file (.con),

###### GEOPAK® mapping files (.tin),

###### Developed film roll in film canister for the project and labeled with the completed CFLHD film can label,

###### Current camera calibration report,

###### One photo index including original negative and three plots on heavy weight RC paper.  If digital photo index is delivered it shall be in TIFF format (on the delivered CD or DVD) with two hard copy plots of the index provided,

###### Orthophoto mosaic of the Rectified Digital Imagery at 0.5’ pixel size for the entire photo covered area,

###### 3-D Microstation design file, containing space line strings and ground shots on designated levels. These space line strings and ground shots depict (in three dimensions) the topography,

###### 3-D Microstation design Index file containing layout of all photo models and an outline of the actual compilation area,

###### An ASCII, text file listing the softcopy photogrammetric data.

###### Utility data files shall have one point per line, utilizing the following ASCII format: “Point Number, Northing (Y), Easting (X), Elevation (or numeric placeholder), Mapping P-Code and Connect Codes; Description/Comment,”

###### Cadastral data files shall have one point per line, utilizing the following ASCII format: “Point Number, Northing (Y), Easting (X), Elevation (or numeric placeholder), Mapping P-Code and Connect Codes; Description/Comment,”

The following data is to be retained by the A/E unless requested by the COTR:

###### Field Topographic Mapping Survey data and materials covering the project area:

Mapping data files shall have one point per line, utilizing the following ASCII format: “Point Number, Northing (Y), Easting (X), Elevation (or numeric placeholder), Mapping P-Code and Connect Codes; Description/Comment,”

All raw observations (GPS vector data, slope distance, zenith angle, horizontal angles and instrument and target heights) made to establish the supplemental control points and existing control checks in digital format.

The first line of each file shall be a header describing each field within the file,

The data fields shall be separated with a comma (,) the Connect Code field and the Description/Comment field shall be separated by a semi-colon (;).

#### Alignment Staking for XX% Field Review (SCXX Activity)

Stake the Alignment for the XX% Field Review.

The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements.

##### Mobilize and Reconnaissance of Project Site

###### Meet with agency contact or representative

###### Perform reconnaissance of project site

Identify safety, traffic and private property concerns

###### Formulate a Work Plan

Work with the designers and COTR/PM to determine the appropriate number of centerline stakes required for each field review. Typical staking includes stakes at 50 feet (20 m) (25 feet and 10 m in tighter curves) along with all PC’s and PT’s. A reduced number of stakes may be appropriate for certain projects.

##### Stake Centerline Alignment

###### Perform the required measurements to confirm existing CFLHD control points

###### Set points on the alignment as directed

###### Compare elevations between set centerline points and existing TIN file

###### Review, edit & submit files according to the requirements shown under Deliverables

##### Perform measurements to confirm aerial photography

###### Identify areas to be confirmed

###### Perform the required measurements relative to the CFLHD control network

###### Review, edit & submit files according to the requirements shown under Deliverables

#### Deliverables for SCXX Activity

Add/delete deliverables to correspond to the tasks above. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

All services, data and deliverables shall be to CFLHD standards and specifications. Data to be provided in the applicable digital format, when possible. The final submittal of all files shall be delivered on a CD/DVD, labeled with the Project Designation, Project Name and Final Submittal, i.e. “CA PFH 112-1(1)”, South Fork Smith River, Final Submittal”. Progress submittals shall be submitted via CD/DVD. All file names shall begin with the “Project Designation”. The remaining characters of the file name shall be descriptive of the data contained in the file. The first line of each file shall be a header describing each field and/or the contents within the file.

###### Staked centerline coordinates data in ASCII format as follows:

Point Number,Northing,Easting,Elevation,PCode;Point Descriptor

The file shall be comma delimited and have a header record that defines the fields,

The extension shall be .nez.

The following data is to be retained by the A/E unless requested by the COTR:

###### All raw observations (GPS vector data, slope distance, zenith angle, horizontal angles and instrument and target heights) made to establish the supplemental control points and existing control checks in digital format.

###### A report of the 3D least squares analysis and adjustment of the observations made to establish coordinates for the Primary Control Points,

###### Legible copies of all field notes

#### Terrain Verification and Reference Hubbing (S4 Activity)

Verify existing ground and set reference hubs

The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements.

##### Mobilize and Reconnaissance of Project Site

###### Meet with agency contact or representative

###### Perform reconnaissance of project site

Identify safety, traffic and private property concerns

###### Formulate a Work Plan

Assume the total number of design cross sections. Additional cross sections are required for curves with radii less than 500 feet (150 m), changes in the typical section (including guardrail, drainage features, etc.), retaining walls, etc.

##### Set centerline and reference hubs

###### Perform the required measurements to confirm existing CFLHD control points

###### Set points on design centerline and reference hubs

###### Compare elevations between set centerline points and existing TIN file

###### Review, edit & submit files according to the requirements shown under Deliverables

##### Obtain ground cross-sections or topographic data

###### Identify cross-sections or areas to be mapped

###### Perform the required measurements relative to the CFLHD control network

###### Review, edit & submit files according to the requirements shown under Deliverables

##### Set supplemental control points

###### Research and recover existing NGS, CFLHD or other horizontal and/or vertical control points

###### Set supplemental control monuments in accordance with the Work Plan

###### Perform the required measurements

###### Analyze and adjust measurements according to the requirements shown under Deliverables

#### Deliverables for S4 Activity

Add/delete deliverables to correspond to the tasks above. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

All services, data and deliverables shall be to CFLHD standards and specifications. Data to be provided in the applicable digital format, when possible. The final submittal of all files shall be delivered on a CD/DVD, labeled with the Project Designation, Project Name and Final Submittal, i.e. “CA PFH 112-1(1)”, South Fork Smith River, Final Submittal”. Progress submittals shall be submitted via CD/DVD. All file names shall begin with the “Project Designation”. The remaining characters of the file name shall be descriptive of the data contained in the file. The first line of each file shall be a header describing each field and/or the contents within the file.

###### Cross-sectional data in GEOPAK® (SOE) station offset elevation format as follows:

Station,Offset,Elevation,Northing,Easting,Pcode.

Reference hubs shall be designated as RH for the p-code and centerline points shall be designated as CL.

No other p-codes are to be used.

The file shall be in ASCII format with a header record in the file that defines the fields.

The extension shall be .SOE.

###### Supplemental Control Network

Create a Control Report and revise existing CFLHD Control Data Sheet

The following data is to be retained by the A/E unless requested by the COTR:

###### MicroStation® design cross-section file with cross section and reference hub data incorporated.

###### All raw observations (GPS vector data, slope distance, zenith angle, horizontal angles and instrument and target heights) made to establish the supplemental control points and existing control checks in digital format.

###### A report of the 3D least squares analysis and adjustment of the observations made to establish coordinates for the Primary Control Points,

###### Updated MicroStation mapping file to include supplemental control.

###### Legible copies of all field notes

#### Mapping – No initial CFLHD field work involved (M1 Activity)

The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements. This activity is used when there is no initial CFLHD field work. Typically when survey is provided and needs to be translated into CFL mapping.

Compile MicroStation mapping products using data from a source other than CFLHD.

##### Research

###### Identify received data format and configuration.

###### Determine whether the data can be converted to CFLHD standards.

###### Verify that data covers the area requested.

##### Compile Mapping Product

###### Create MicroStation files

###### Merge with existing data, if applicable.

###### Review and edit Microstation files.

#### Deliverables for M1 Activity

Add/delete deliverables to correspond to the tasks above. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

The following deliverables shall be to CFLHD standards and specifications. Data to be provided in the applicable digital format, when possible. The final submittal of all files shall be delivered on a CD/DVD, labeled with the Project Designation, Project Name and Final Submittal, i.e. “CA PFH 112-1(1)”, South Fork Smith River, Final Submittal”. Progress submittals shall be submitted via CD/DVD. All file names shall begin with the “Project Designation”. The remaining characters shall be descriptive of the fieldwork contained in the file. The first line of each file shall be a header describing each field within the file.

###### Control Data Sheet files (.xls and .dgn),

###### 3D Planimetric mapping file (.map),

###### 3D Contour mapping file (.con),

###### GEOPAK® TIN files (.tin),

###### Developed film roll in film canister for the project and labeled with the completed CFLHD film can label,

###### Current camera calibration report,

###### Digital photo index TIFF format (on the delivered CD or DVD) with two hard copy plots of the index provided,

###### Orthophoto mosaic of the Rectified Digital Imagery at 0.2’ pixel size for the entire photo covered area,

###### 3-D MicroStation design file, containing space line strings and ground shots on designated levels. These space line strings and ground shots depict (in three dimensions) the topography,

###### 3-D Microstation design Index file containing layout of all photo models and an outline of the actual compilation area,

###### An ASCII, text file listing the softcopy photogrammetric data.

The following data is to be retained by the A/E unless requested by the COTR:

###### Primary Control Point data:

Raw, unedited ASCII format field data files,

A report of the 3D least squares analysis and adjustment of the observations made to establish coordinates for the Primary Control Points,

The final adjusted coordinates, elevations, and descriptions for the Primary Control Points in an ASCII file formatted as follows: Point Number, Northing (Y), Easting (X), Elevation (Z); Description/Comment.

###### Field Topographic Mapping Survey data and materials covering the project area:

Mapping data files shall have one point per line, utilizing the following ASCII format: “Point Number, Northing (Y), Easting (X), Elevation (or numeric placeholder), Mapping P-Code and Connect Codes; Description/Comment,”

The first line of each file shall be a header describing each field within the file,

The data fields shall be separated with a comma (,) the Connect Code field and the Description/Comment field shall be separated by a semi-colon (;).

###### Remote sensing data and materials covering the project area:

Two sets of color contact prints,

One set of black and white prints to be annotated with control and planimetric features.

#### Supplemental Photogrammetric Mapping (M2 Activity)

The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements.

Compile photogrammetric mapping products to extend existing mapping per request.

##### Research

###### Identify area to be mapped.

###### Verify photo coverage is available and in proper format.

###### Obtain and verify control, aerial triangulation information, workstation settings and camera calibration.

##### Compile Mapping Product

###### Create Microstation files

###### Merge with existing data.

###### Review and edit Microstation files.

#### Deliverables for M2 Activity

Add/delete deliverables to correspond to the tasks above. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

The following deliverables shall be to CFLHD standards and specifications. Data to be provided in the applicable digital format, when possible. The final submittal of all files shall be delivered on a CD/DVD, labeled with the Project Designation, Project Name and Final Submittal, i.e. “CA PFH 112-1(1)”, South Fork Smith River, Final Submittal”. Progress submittals shall be submitted via CD/DVD. All file names shall begin with the “Project Designation”. The remaining characters shall be descriptive of the fieldwork contained in the file. The first line of each file shall be a header describing each field within the file.

###### Control Data Sheet files (.xls and .dgn),

###### 3D Planimetric mapping file (.map),

###### 3D Contour mapping file (.con),

###### GEOPAK® TIN files (.tin),

###### Developed film roll in film canister for the project and labeled with the completed CFLHD film can label,

###### Current camera calibration report,

###### Digital photo index TIFF format (on the delivered CD or DVD) with two hard copy plots of the index provided,

###### Orthophoto mosaic of the Rectified Digital Imagery at 0.2’ pixel size for the entire photo covered area,

###### 3-D MicroStation design file, containing space line strings and ground shots on designated levels. These space line strings and ground shots depict (in three dimensions) the topography,

###### 3-D Microstation design Index file containing layout of all photo models and an outline of the actual compilation area,

###### An ASCII, text file listing the softcopy photogrammetric data.

The following data is to be retained by the A/E unless requested by the COTR:

###### Primary Control Point data:

Raw, unedited ASCII format field data files,

A report of the 3D least squares analysis and adjustment of the observations made to establish coordinates for the Primary Control Points,

The final adjusted coordinates, elevations, and descriptions for the Primary Control Points in an ASCII file formatted as follows: Point Number, Northing (Y), Easting (X), Elevation (Z); Description/Comment.

#### Converting the format of Microstation Files between: V7/V8, X10/X30 or English/Metric (M2c Activity)

The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements.

Convert existing Microstation files to a requested format other than the original.

##### Research

###### Identify type of conversion.

##### Comlpile Mapping Product

###### Convert files or create new ones in requested format.

###### Review and edit Microstation files for compatibility.

#### Deliverables for M2c Activity

Add/delete deliverables to correspond to the tasks above. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

###### Microstation 3D planimetric map

###### Microstation 3D contour file

###### Geopak TIN file

## ROW (PRMS Activities R1 to R5)

#### Preliminary Right of Way Studies (R1 Activity)

Perform preliminary right of way research.

The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements.

##### Perform preliminary boundary and property ownership research for the project within the limits of work.

###### Obtain Federal agency land records

###### Obtain county tax maps and ownership data

###### Obtain road and utility ownership and easement information

###### Prepare R1 ROW Preliminary research checklist

##### Assemble preliminary boundary exhibit.

###### Use available fieldwork and preliminary research

###### Show existing road and utility easements

###### Show the boundaries between public and non-public land

###### Show the boundaries of individual non-public parcels

##### Prepare exhibits for public meetings.

###### Preliminary boundary exhibits

###### Individual parcel exhibits

###### Preliminary ROW limits exhibits

##### Identify required field evidence to complete boundary exhibit.

###### Identify field evidence to complete boundary exhibit; monuments, evidence of possession.

###### Develop monument descriptions and search coordinates for field crews.

###### Prepare and submit a Preliminary ROW Summary Report to FHWA

##### Coordinate ROW, utility and railroad requirements.

###### Prepare a list of utilities, railroads, irrigation ditches, etc. affected by project with contact information.

###### Prepare a contact list for affected utilities.

#### Deliverables for R1 Activity

Add/delete deliverables to correspond to the tasks above. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

Provide data to FHWA (in a digital format where possible).

###### R1 ROW Preliminary Research Checklist

###### Documentation obtained from research

###### Preliminary Boundary Compilation

###### Monument descriptions and search coordinates for additional fieldwork.

###### Preliminary Right of Way Summary Report

###### List of utilities, railroads, irrigation ditches, etc. affected by projectwith contact information

The following data is to be retained by the A/E unless requested by FHWA:

###### GLO and BLM cadastral plats

###### Land management agency plats.

###### Any deeds obtained during research.

###### Any survey plats obtained during research.

#### Right of Way Boundary Compilation (R2 Activity)

Compile the title information and property ties into boundary plats, supplemental fieldwork, research, and ownership updates.

The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements.

##### Update preliminary boundary exhibit.

###### Integrate supplemental research ownership data into boundary exhibit.

###### Integrate supplemental fieldwork/monument ties into boundary exhibit.

##### Perform a title search to 30 years in the past and research easements to patent.

###### Research federal agency records.

###### Research private property records including court decisions and county road records.

###### Research easements to patent.

###### Research basis of prescriptive rights for the road.

###### Prepare a Property Owner Spreadsheet listing property owners and associated data.

###### Research encumbrances including easements for roads and utilities within the project limits.

##### Compile the title search results and field work into a comprehensive electronic boundary plat.

###### Prepare Right of Way Property Owner Spreadsheet

###### Resolve property boundary location based on both the record information and field ties to property evidence.

###### Update the ROW Summary Report - include ambiguities, conflicts.

###### Recommend areas that may require additional title research and/or field ties.

###### Prepare the R2 ROW Boundary Compilation Checklist.

#### Deliverables for R2 Activity

Add/delete deliverables to correspond to the tasks above. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

###### Boundary plat

###### Right of Way Property Owner Spreadsheet

###### Right of Way Summary Report

###### Electronic submittal of title information.

###### R2 ROW Boundary Compilation Checklist

The following data is to be retained by A/E unless requested by the COTR:

###### Updated county tax maps and property owner data obtained during R1

###### Updated GLO and BLM cadastral plats obtained during R1

###### One set of title records.

One copy of each parcel file, in separate folders.

###### Federal land management agency documents pertinent to the project

#### Final Right of Way Plans (R3 Activity)

Produce all documents necessary for Right of Way

The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements.

##### Coordinate with acquiring agency for document/recordation requirements.

###### Size and format

###### Type of land description

###### Drafting standards

##### Prepare and submit Process Check in accordance with R3 ROW Documents Checklist

##### Prepare DRAFT Right of Way Plans (First Submittal) according to FHWA standards and R3 ROW Documents Checklist.

###### Project proposed ROW.

###### Develop uniform corridor as much as possible.

###### Develop easements to construct and maintain road including temporary access for construction.

###### Review for adequate ROW.

###### Submit DRAFT Right of Way Plans to FHWA for review and comment

###### Provide to cooperating agencies for review

##### Incorporate FHWA comments and resubmit FINAL Right of Way Plans (Second Submittal)

##### Prepare DRAFT Legal Descriptions (First Submittal) for right of way parcels in accordance with R3 ROW Documents Checklist.

###### Descriptions for permanent acquisitions shall be either of the metes and bounds type, or centerline corridor description with offsets to the right of way as needed at the preference of the acquiring agency.

###### Temporary construction easement descriptions shall be based on station/offset relative to design alignment.

###### Submit to FHWA for review and comment

##### Incorporate FHWA comments and resubmit FINAL Legal Descriptions (Second Submittal)

##### Coordinate right of way, utility and railroad requirements.

#### Deliverables fro R3 Activity

Add/delete deliverables to correspond to the tasks above. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

###### Process Check

###### DRAFT Right of Way Documents including R3 Right of Way Documents Checklist

###### FINAL Right of Way Documents including R3 Right of Way Documents Checklist

###### Copies of transmittals of documents to affected agencies or entities

###### Electronic files of all ROW documents

#### Right of Way Acquisition (R4 Activity)

##### Transmit ROW documents to non-federal acquiring agency

##### Collaborate with CFT, acquiring agency, and landowner to develop considerations and accommodations, design modifications, and/or revisions to the ROW plans

##### Provide support and oversight to acquiring agency on all acquisition matters

##### Assure compliance with all acquisition regulations and certify project according to regulatory requirements

#### Letter of Consent (R5 Activity)

##### Transmit ROW documents and requests for Federal Land Transfer

##### Design modifications and/or revisions to ROW plans

##### Negotiate terms and stipulations

##### Coordinate with acquiring agency regarding Letter of Consent

## GEOTECHNIAL (PRMS Activities G1 to G4)

#### Preliminary Geotechnical Investigations (G1 Activity)

Conduct a preliminary geotechnical investigation, including visual and/or limited surface/subsurface investigations, pertaining to general roadway condition surveys, geotechnical hazards, anticipated excavations and structures, material sources, and general constructability issues.

Provide introductory task information, as needed, describing (1) general and/or specific site conditions and/or (2) requirements of the preliminary geotechnical investigation plan that support the following G1 work plan items. The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements. The following work elements include those commonly conducted by the CFLHD Geotechnical Group for preliminary 3R/4R geotechnical investigations on low-volume roads. Some, none, or all of these work elements, and possibly additional work elements not listed, may be appropriate for a given project. G1 work elements should also be developed to support concurrent work described in the next section under Pavement and Subsurface Investigations (V1).

##### Conduct research.  Typical research shall include but is not limited to the following:

###### Project scoping reports

###### Historical roadway work

###### Geotechnical/geological features

###### Structures

###### As-builts

###### Maintenance records

###### Preliminary design criteria

###### Also research the project setting, including regional and local geology, annual precipitation, frost depths, seismicity, soil conditions, surface and groundwater conditions, etc.

##### Develop a Preliminary Field Investigation Plan

###### Submit a copy of the plan to FHWA two weeks prior to investigation for review and approval.

##### Field investigation preparation

###### Obtain necessary permits and clearances

Right-of-Entry

Drilling/excavation permits (e.g., U.S. Forest Service Special Use Permit)

Utility clearances

Environmental clearances

Other as required

###### Procure investigation services

Auger/core drilling

Test pit excavation

Geophysical surveys

Traffic control:Provide traffic control for investigations as needed and acceptable to the local road agency and in conformance with the MUTCD

Other services as required

##### Preliminary field investigation

###### Characterize existing conditions including the roadway, pavement, structures and culverts.

###### Identify roadway geotechnical repair areas, including possible weak subgrade/subex locations, surface and groundwater problem areas, fill settlement/failures, landslide failures, etc.

###### Identify and generally characterize geological and geotechnical hazards directly or potentially impacting the roadway.

###### Investigate, sample and characterize potential cut and fill materials, noting material types, locations, and approximate quantities.

###### Conduct a comprehensive topsoil survey, noting availability and depth.

###### Identify, investigate and sample designated material sources, noting material types, locations, and approximate quantities. Coordinate with work to be completed under the Pavements section of this SOW

###### Reclaim all borings and excavations to a condition acceptable to the property owner. Coordinate with work to be complete under the Pavements section of this SOW

###### Log, stake and/or survey all exploration/sampling locations.

###### Compile field notes, field boring/test pit logs, photos, sketches, etc.  Photograph all sites of investigation, including the drill rig set up on each hole, and include photographs of all rock core and/or soil samples.  Draw a cross-sectional sketch (to be included in the G3 FINAL Geotechnical Report) showing exploration locations relative to the ditchline, centerline, or other geographical location, and a generalized subsurface profile, including water observations (as available).

Interim Geotechnical Evaluation Memoranda only required if needed to assist with preliminary design. If not required remove this step.

##### Prepare Interim Geotechnical Evaluation Memoranda

##### Procure soil/rock/water lab testing for culverts, cut/fill materials, and material sources.

##### Prepare DRAFT Preliminary Geotechnical Report summarizing findings from the aforementioned preliminary field investigation steps.  Submit to FHWA for review and comment.  Provide specific recommendations for, but not limited to, the following:

###### Subsurface drainage issues

###### Soil corrosivity and recommended culvert material types

###### Cut and fill slope ratios and construction requirements

###### Suitable/unsuitable soils and aggregates by location

###### Soil and rock shrink/swell properties, station-to-station

###### Roadway repair locations and general requirements

###### Topsoil depths and distribution

###### Anticipated structure types and foundation requirements

###### Preliminary constructability issues

##### Address FHWA comments and prepare FINAL Preliminary Geotechnical Report.  Submit to FHWA.

Based on earlier project scoping, include in this section an estimate of the quantity/locations of soil/rock sampling to be conducted, methods of sampling to be employed, and quantity/types of testing to be conducted sufficient for the development of a firm-fixed-price Independent Government Estimate by CFLHD PST staff. Include in this section additional information, as appropriate, describing such things as required federal, state, and/or county government contacts and coordination, planned drilling water sources, anticipated material source locations/providers, special requirements of proposed soil/rock sampling methods and drilling/excavation completion, special permitting needs, etc. Provide sufficient information to describe the scope of planning and task execution effort required. Depending on the nature and timing of planned fieldwork, the G1 Preliminary Geotechnical Evaluation Report may be combined with the preliminary pavements report and recommendations developed under the Pavements section. Estimates of investigation, sampling, and testing quantities provided in this TO are for project estimation purposes only. Modifications may be required at the time of the preliminary field investigation plan submittal, and/or during the field investigation, as conditions dictate. All modifications to the quantities listed in this section should be brought to the attention of the COTR/PM in a timely manner. In general, this section needs to provide enough information to (1) support the development of an Independent Government Estimate of planned work activities, (2) ensure the required scope of the project is being adequately addressed, and (3) provide a means to measure planned work performance under this task.

#### Deliverables for G1 Activity

Add/delete deliverables to correspond to the tasks above. Typically 3 copies of the DRAFT report and 8 copies of the FINAL report are submitted. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

###### Preliminary Field Investigation Plan

###### Interim Geotechnical Evaluation Memoranda

###### DRAFT Preliminary Geotechnical Report

###### FINAL Preliminary Geotechnical Report

#### Geotechnical Investigations (G2 Activity)

Conduct surface/subsurface investigations for earthwork estimation, structure/embankment foundation design, landslide assessment and mitigation, material source viability, etc.

Provide introductory task information, as needed, describing (1) general and/or specific site conditions and/or (2) requirements of the comprehensive geotechnical investigation plan that support the following G2 work plan items. The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements. The following work elements include those commonly conducted by the CFLHD Geotechnical Group for comprehensive 3R/4R geotechnical investigations on low-volume roads. Some, none, or all of these work elements, and possibly additional work elements not listed, may be appropriate for a given project. G2 work elements should also be developed to support on-going work described in the next section under Pavement and Subsurface Investigations (V2).

##### Develop a Comprehensive Geotechnical Investigation Plan

###### Submit a copy of the plan to FHWA two weeks prior to investigation.

##### Field investigation preparation

###### Obtain necessary Right-of-Entry, drilling/excavation permits (e.g., U.S. Forest Service Special Use Permit), utility clearances, environmental clearances, etc.

###### Procure investigation services, including such things as auger/core drilling, test pit excavation, geophysical surveys, traffic control, etc.  Provide traffic control for investigations as needed and acceptable to the local road agency and in conformance with the MUTCD.

##### Conduct a comprehensive subsurface investigation

###### Include cuts, fills, structures and material sources,  acquire samples, as needed, for laboratory testing.

###### Reclaim all borings and excavations to a condition acceptable to the property owner

Revise the step below based on the anticipated readings on the instrumentation

###### Log, stake and/or survey all exploration/sampling locations.

###### Compile field notes, field boring/test pit logs, photos, sketches, etc.  Photograph all sites of investigation, including the drill rig set up on each hole, and include photographs of all rock core and/or soil samples.  Draw a cross-sectional sketch (to be included in the G3 “Final Geotechnical Report”) showing exploration locations relative to the ditchline, centerline, or other geographical location, and a generalized subsurface profile, including water observations.

##### Install geotechnical instrumentation and conduct initial and scheduled readings.  It is anticipated that the following number of readings will be required:

###### example Inclonometer – 4 readings (January, March, May, July)

##### Procure soil/rock/water lab testing for culverts, cut/fill materials, and material sources.  Include tests for USCS and AASHTO classification, and material suitability for slopes, fills, walls, foundations, general earthwork, pavements, and materials.  Conduct electrochemical testing for design of MSE walls, culverts, anchors, or other buried structures.

##### Issue Interim Geotechnical Memoranda regarding preliminary findings of the field investigation, results of laboratory testing, preliminary findings regarding structure foundations (e.g., bridge foundation soil/rock profiles), constructability issues, etc.

Based on findings and recommendations from G1 preliminary geotechnical investigations, include in this section an estimate of the quantity/locations of soil/rock sampling to be conducted, methods of sampling to be employed, and quantity/types of testing to be conducted sufficient for the development of a firm-fixed-price Independent Government Estimate by CFLHD PST staff. Include in this section additional information, as appropriate, describing such things as required federal, state, and/or county government contacts and coordination, planned drilling water sources, anticipated material source locations/providers, special requirements of proposed soil/rock sampling methods and drilling/excavation completion, special permitting needs, etc. Provide sufficient information to describe the scope of planning and task execution effort required. Estimates of investigation, sampling, and testing quantities provided in this TO are for project estimation purposes only. Modifications may be required at the time of the comprehensive field investigation plan submittal, and/or during the field investigation, as conditions dictate. All modifications to the quantities listed in this section should be brought to the attention of the COTR/PM in a timely manner. In general, this section needs to provide enough information to (1) support the development of an Independent Government Estimate of planned work activities, (2) ensure the required scope of the project is being adequately addressed, and (3) provide a means to measure planned work performance under this task.

#### Deliverables for G2 Activity

Add/delete deliverables to correspond to the tasks above. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

###### Comprehensive Geotechnical Investigation Plan

###### Interim Geotechnical Memoranda

#### Geotechnical Recommendations (G3 Activity)

Conduct geotechnical analyses and prepare a draft final geotechnical report with recommendations for earthwork, structure foundations, landslides and slopes, material sources, special construction requirements, etc.

Provide introductory task information, as needed, describing requirements for conducting geotechnical analyses and final project reporting that support the following G3 work plan items. For example, specify LRFD or ASD for structure foundation design. The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements. The following work elements include those commonly conducted by the CFLHD Geotechnical Group for 3R/4R geotechnical analyses and draft final reporting for low-volume roads. Some, none, or all of these work elements, and possibly additional work elements not listed, may be appropriate for a given project. G3 work elements should also be developed to support final pavement design reporting described in the next section under Pavement and Subsurface Investigations (V2).

##### Conduct geotechnical analyses for slopes, cuts, fills, structures, landslides, etc., as required.

###### Conduct landslide and slope stability analyses and develop/evaluate slide mitigation and slope design alternatives.

###### Conduct rock slope and rockfall analyses and develop/evaluate excavation and mitigation alternatives.

###### Conduct global and external stability analysis for retaining walls and structures (sliding, bearing, overturning, and slope stability).

###### Develop temporary excavation, shoring, and dewatering alternatives for structure excavations as needed.

###### Conduct shallow foundation and embankment bearing capacity and settlement analyses, and develop/evaluate design alternatives.  Develop alternatives to eliminate or minimize excessive settlement in areas of compressible soils.

###### Conduct deep foundation analyses and settlement analyses, and develop/evaluate foundation alternatives.

###### Evaluate constructability issues pertaining to geotechnical features within the project, and develop alternative construction options as needed.

##### Prepare and issue a DRAFT Final Geotechnical Report incorporating the following:

###### Relevant findings per the G1 Preliminary Geotechnical Report, G2 Evaluation Memoranda, V1 Pavements Report, and other geotechnical information sources

###### Summary of findings from G2 field investigations

###### Specific recommendations based on G3 analyses.

It is the intent of G3 reporting to only prepare a draft final report, allowing opportunity for design alteration and revision up through the 95% PS&E review. The final report would then be updated and released prior to 100% package completion. Depending on the nature and timing of final report preparation, the G3 Draft Final Geotechnical Report may be combined with the final pavements report and related recommendations developed under the Pavements section (V2). At a minimum, the findings of the comprehensive geotechnical investigation and design analyses should be coordinated with the pavement structure design effort.

Present an interpretation of the regional and local geology, seismic conditions, and geographic setting (precipitation, frost depths, etc.).

Present details of the investigation plan procedures, methods, and results, including drilling/test pit logs and laboratory testing.  Develop interpretive tables and figures to present the field exploration and lab test data, and how the data were interpreted for analysis and design.

Present interpreted drilling/test pit explorations and geophysical results on plans, profiles, and sections.

Provide annotated site photographs, general project location maps, and investigation location maps.

Present the types and methods of analyses conducted, including tabled input values, criteria, and findings, and append relevant examples.

Provide a statement of limitations describing the potential for material type and properties variation between exploration locations, and that explorations were conducted for design purposes only.  Draw distinctions between factual and interpreted data and findings.

###### Provide specific recommendations for the following:

Suitable/unsuitable soils and aggregates by location (including wasting options/locations).

Soil and rock shrink/swell properties, station-to-station.

Topsoil depths and distribution, station-to-station.

Rock rippability.

Subsurface drainage.

Soil corrosivity and required culvert/structure materials.

Roadway subex/deep patch repair locations/designs.

Excavation requirements, including blasting and shoring.

Cut and fill slope ratios, erosion control, and construction requirements.

Embankment foundation preparation and construction specifications.

Structure foundation type, capacity, and construction/testing specifications.

Landslide mitigation requirements.

Rockfall mitigation requirements.

General constructability requirements for all geotechnical features.

Special Contract Requirements (SCR’s).

Only include the Interim Geotechnical Memoranda and Geotechnical Baseline Report in scope when required.

##### Issue Interim Geotechnical Memoranda, as needed, regarding design analyses, preliminary recommendations, technical basis for design, etc.  Prepare a Geotechnical Baseline Report, according to ASCE guidelines, for inclusion in contract documents

In general, this section needs to provide enough information to (1) support the development of an Independent Government Estimate of planned work activities, (2) ensure the required scope of the project is being adequately addressed, and (3) provide a means to measure planned work performance under this task.

#### Deliverables for G3 Activity

Add/delete deliverables to correspond to the tasks above. Typically 3 copies of the DRAFT FINAL report are submitted. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule. Also determine need/use of electronic copies.

###### DRAFT Final Geotechnical Report

###### Interim Geotechnical Memoranda

###### Geotechnical Baseline Report

#### Final Geotechnical Report (G4 Activity)

Update, revise and issue the FINAL Geotechnical Report and associated Geotechnical Advisories.

Provide introductory task information, as needed, describing requirements for completing and issuing the FINAL Geotechnical Report and Geotechnical Advisories. The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements.

##### Issue Geotechnical Advisories and plan notes for the final PS&E package.

##### Update and issue the FINAL Geotechnical Report, incorporating the latest geotechnical findings and recommendations, as well as CFLHD review comments and comments from other stakeholders.

#### Deliverables for G4 Activity

Add/delete deliverables to correspond to the tasks above. Coordinate number of copies and delivery formats with the COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

###### Geotechnical Advisories

###### FINAL Geotechnical Report

## PAVEMENTS (PRMS Activities V1 to V3)

#### Preliminary Pavement Recommendation (V1 Activity)

Complete project initiation, field investigation, materials testing, analysis, and determination of cost effective pavement material, design, and rehabilitation recommendations (as applicable).  Communication between the A/E and the CFLHD pavement engineer throughout this activity is essential for successful completion.

In addition to the mainline roads, pavement recommendations for pullouts, parking lots, and overlooks within the project must be included.  These pavement recommendations may vary from the mainline road because existing conditions and features may vary (i.e. parking lots may have curb and gutter).

Refer to Section V of this SOW and the CFLHD Website for the standard requirements, methods, and factors of the V1 activity. The following list of typical tasks is based on the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements.

##### Project Initiation

###### Gather information (archived reports/files, as-builts, scoping reports, PMS data, maintenance records, traffic data, climate data, etc)

###### Develop a Field Investigation Plan including the investigation, sampling, and testing plan, schedule, and budget.  Submit the plan, schedule, and budget to FHWA

###### Assume the following sample and data collection methods for this project:

Not all of the following sampling and data collection methods will be needed on projects. Use only the methods appropriate for the project scope.

| Sampling / Data Collection | Depth(s) | Interval (total)1 | Offset or Location |
| --- | --- | --- | --- |
| Borings |  |  |  |
| Cores |  |  |  |
| FWD2 | N/A |  |  |
| DCP |  |  |  |
| Test Pits |  |  |  |
| Other (i.e. traffic data) |  |  |  |

1Actual quantities or number of samples may go up or down based on field conditions encountered.  The task order will be modified, as necessary, to account for changes to the estimate.

2Refer to FLH FWD Testing and Analysis Guidelines.

Select only tests that are appropriate and necessary for the project. Some tests, such as the preliminary mix design evaluations, may not be determined appropriate or feasible until after the field investigation. In these cases the task order can be modified to include additional testing.

###### Assume the following tests/analyses for this project:

| Tests / Analysis | Selected Test(s) | Estimated Number of Tests3 |
| --- | --- | --- |
| Soil Strength / Stiffness -R-Value (AASHTO T 190) -CBR (AASHTO T 193) -Resilient Modulus (AASHTO T 307) -Backcalculation of FWD Data4 -Correlation of DCP Data (ASTM D 6951) |  |  |
| Soil Classification & Gradation -AASHTO M 145 -ASTM 2487 -AASHTO T 27 |  |  |
| Moisture Content of Soil (in situ) -AASHTO T 255 or T 265 |  |  |
| Moisture-Density Relation -AASHTO T 99, method C -AASHTO T 180, method D |  |  |
| Soil Stabilization (evaluate feasibility, application rate, and structural value) -Lime, Cement, and/or fly ash |  |  |
| Cold In-Place Recycling (CIPR) or Full-Depth Reclamation (FDR): Preliminary Mix Designs (evaluate feasibility, application rate, and structural value) |  |  |
| Other Testing / Analysis |  |  |

3Actual quantities or number of tests may go up or down based on field conditions encountered.  The task order will be modified, as necessary, to account for changes to the estimate.

4Refer to FLH FWD Testing and Analysis Guidelines.

##### Obtain additional investigative services (traffic control, drilling rigs, etc.)

###### Provide traffic control, as needed and acceptable to the local road agency and in conformance with the MUTCD.

##### Complete field investigation

###### Coordinate investigation, coring, and drilling access with the FHWA and the appropriate land owning/management agency.  Obtain all necessary subsurface utility clearances and access permits prior to commencing investigations.

###### Perform field investigation per the standards and guidance of the PDDM and supplements.  This includes but is not limited to: sampling and logging (including photos); surveying pavement condition and distresses (including photos); identifying potential material sources; identifying special pavement issues (i.e. frost heave); identifying areas for subexcavation, pavement drainage, or other spot repairs; identify obstacles for construction or rehabilitation (i.e. suitability of existing shoulder/bench for minor widening of the roadway).

###### Upon completion of the field investigation, submit a brief Field Investigation Summary Memo (1-page typically) or E-mail to FHWA that summarizes the investigation.

##### Review and compile field notes, logs, photos, etc.

##### Evaluate and submit samples/data for testing and analysis

###### Assure submitted samples are an adequate representation of project conditions.

On 4R projects, in coordination with the geotechnical engineer and roadway design activities, account for and integrate the soil strengths from cut and fill locations into the design soil strength value.

##### Evaluate results from lab testing, field investigation, and engineering analysis.  Determine if additional investigation, testing, or analysis is necessary.

###### Coordinate additional work with the FHWA

##### Develop Preliminary Pavement Recommendations Technical Memo.  This technical memo should include, but not be limited to, the following:

###### ESALs for the design life of the pavement

###### Effective soil resilient modulus

###### Pavement structural design

###### Design multiple alternatives, especially on pavement rehabilitation projects

###### Economic analysis on design alternatives and a recommended alternative

###### Material recommendations

###### Special recommendations, spot repairs, or other pertinent information (i.e. subexcavation locations, constructability issues, local material availability, material haul distances, pavement depth variability, steep grades, recommended follow-up investigation, etc.).

###### Submit to FHWA for review and comment.

#### Deliverables for V1 Activity

Add/delete deliverables to correspond to the tasks above. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

###### Field Investigation Plan

###### Field Investigation Summary Memo/E-mail

###### Preliminary Pavement Recommendations Technical Memo

#### Final Pavement Recommendation (V2 Activity)

Finalize the pavement recommendations within a comprehensive report.

Refer to Section V of this SOW and the CFLHD Website for the standard requirements, methods, and factors of the V2 activity. The following list of typical tasks is based on the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements.

##### Identify and/or develop needed SCRs related to the pavement structural section.

##### Finalize design recommendations

###### Pavement structural design

###### Material recommendations

###### Spot repair recommendations

###### Recommendations / information on potential material sources

###### Design exceptions.

##### Develop a DRAFT Pavement Report per the PDDM and supplements.  The activity includes, but is not limited to, the following:

###### Development of a comprehensive report that documents all information, assumptions, and calculations that were gathered and completed during the V1 and V2 tasks

###### Completing a QA review

###### Submit to FHWA for review and comment

##### Prepare FINAL Pavement Report

###### Address comments by FHWA

###### Submit to FHWA

#### Deliverables for V2 Activity

Add/delete deliverables to correspond to the tasks above. Typically 5 copies of the DRAFT report and 8 copies of the FINAL report are submitted. Also an electronic copy (pdf) should be provided. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

###### DRAFT Pavement Report

###### FINAL Pavement Report (hard and electronic copies)

#### Final Design (Support) (V3 Activity)

If there is a need to change the pavement recommendations at this stage, FHWA may request the development of a brief addendum to the pavement report that describes the change and the reasons for it.

##### Assure alignment of pavement report recommendations and PS&E.

###### Develop addendum to Pavements Report

##### Answer technical questions during the final design stage

## HYDROLOGY/HYDRAULICS (PRMS Activities H1 to H4)

#### Preliminary Hydraulics Recommendations (H1 Activity)

Initial hydrology/hydraulics survey to determine the preliminary structural requirements and water resources impact.

(Supports 15% design (D1) for 4R projects and 30% design (D2) for 3R projects and, if needed, bridge structural layout (B2, task 1) and Document Preparation (E2)). Hydraulic and Hydrologic information should be obtained at the initial site investigation. The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements.

##### Collect existing drainage related data, reports, studies, and other pertinent information.  Typical sources include:

###### Local and County agencies

###### State agencies

###### Federal agencies, including applicable land management plans

###### FEMA to determine if FEMA floodplain mapping covers the project.

##### Identify potential floodplain encroachments and channel stability issues.

##### Provide support to the NEPA process.  Support may be required in the following areas:

###### Water quality

###### Wetlands

###### Fish passage

###### Stream restoration.

##### Develop a Hydrologic and Hydraulic Criteria and Computational Methods Technical Memorandum

###### Define criteria and computational methods to be used for the hydrologic and hydraulic analyses of ditches, culverts, and bridges, including appropriate design standards and flood frequency

###### Provide proposed design criteria for other hydraulic features, e.g. storm drains and curb/gutter

Criteria and methods should be consistent with the PDDM as well as pertinent site-specific considerations.

###### Submit to CFLHD for review.  Address comments and resubmit if necessary.

###### Subsequent hydrologic and hydraulic analysis should be conducted based on the approved criteria and computational methods

##### Perform a preliminary hydraulic analysis of existing conditions

###### Use the 10-, 50-, and 100-yr events to evaluate potential encroachments and to determine water surface elevations

###### Provide recommendations regarding whether or not the potential encroachments are likely to result in undesirable floodplain effects and/or will likely require FEMA review and approval

###### Determine the existing flow rates for the 10-, 50-, and 100-yr events at the bridge locations

##### Provide support for permitting

###### Determine the ordinary high water (OHW) level and extent

In the absence of site-specific guidance, use the 2-yr event for this determination

##### Prepare a Preliminary Hydraulics Recommendations Report include, but not limited to, the following:

###### Documentation of approved criteria and methods

###### Documentation of data collection and site investigation

Examination of overall site

Existing streams and ditches

Existing culverts (size, location, and condition)

###### Identification of floodplain encroachment and channel stability issues

###### Environmental support findings in the areas of water quality, wetlands, fish passage, and stream restoration

###### Documentation of preliminary hydrologic and hydraulic computations

###### Electronic files for floodplain analysis

###### Submit to CFLHD for review.  Address comments and resubmit if necessary.

#### Deliverables for H1 Activity

Add/delete deliverables to correspond to the tasks above. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

###### Hydrologic and Hydraulic Criteria and Computational Methods Technical Memorandum  (Step 4)

###### Preliminary Hydraulics Recommendations Report (Step 7)

#### Intermediate Hydraulics Recommendations (H2 Activity)

Conduct floodplain, preliminary roadway and preliminary bridge hydraulic analyses.

Supports 30% design (D2) and, if needed, bridge TS&L (B2, task 2) The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements.

##### Perform preliminary roadway hydraulic analysis

###### Perform drainage basin delineations for all cross culvert locations that require design discharges.  Calculate peak discharges based on the design criteria and methods previously adopted for roadway drainage crossings. Recommend rehabilitation (e.g., lining), replacements, and extensions, as appropriate, considering culvert condition, hydraulic performance, and cost.

###### Design the preliminary type, size, and location of the major culverts (greater than 1200 mm (48”)).  Use HY8 or equivalent for hydraulic analysis/design.  Recommend appropriate end treatments for the major culverts

###### Design the preliminary type, size, and location of the minor cross culverts.  Use HY8 or equivalent for hydraulic analysis/design for minor culverts in critical situations such as high likelihood of ice or debris, high tailwater, low culvert barrel slope, increased risks to upstream properties, or other site-specific conditions.  Minor culverts in non-critical situations may be designed using HY8 or equivalent, inlet control nomographs, or inlet control equations.

###### Provide preliminary designs for outlet energy dissipation for all culverts.

###### Provide preliminary designs for roadside ditches, including grade control structures and/or temporary/permanent linings to prevent erosion.

##### Perform preliminary bridge waterway analysis for proposed bridge designs (TS&L).

###### Model water surface profiles using HEC-RAS or equivalent for the 10-, 50-, 100-, and 500-yr events for water surface elevation and freeboard for proposed preliminary bridge designs.  Make capacity design recommendations.

###### Characterize bed and bank materials in the vicinity of proposed bridge piers and abutments from available geotechnical data and reports.  Perform pebble counts in noncohesive materials to complete the characterization.

###### Assess scour potential at bridge locations for the overtopping, 100-yr, and 500-yr events.  Make foundation and scour countermeasure design recommendations following the guidance of HEC-18.  (Countermeasures should be avoided for piers on new or replacement bridges.)

##### Perform final floodplain analysis and delineation

###### Evaluate the effects of encroachment.

###### Model proposed conditions for the 10-, 50-, and 100-yr events.

###### Make design recommendations.

##### Prepare draft CLOMR/LOMR review package and submit to FEMA

##### Develop preliminary designs for special hydraulic features

Modify list below based on project specific conditions.

###### Fish passage

###### Storm drains and curb/gutter

###### Temporary construction related drainage features.

###### Stormwater (detention/retention) management and/or water quality measures.

###### River training/stabilization design(s).

##### Develop stream restoration and/or wetland mitigation plans in coordination with environmental specialists.

##### Prepare a Preliminary Hydraulics Report. The report will provide the necessary hydrologic and hydraulic analysis to complete the preliminary (30%) design. Contents of the report shall follow the guidance in the PDDM in a bound format.  In addition the report shall include:

###### Maps indicating the general and specific project location including the stream channel(s) to proposed structure locations and drainage basin boundaries.

###### Brief discussions, documentation, and summaries of all analysis and design activities (including any assumptions used) and results.

###### Detailed hydraulic design recommendations and conclusions.

###### Appendices containing copies of any hand or spreadsheet calculations and the input and output data from any computer models used.

###### Maps and/or exhibits showing the location and orientation of all cross-sections and cross section plots for all locations.

###### Electronic copies of computer input/output files and GIS/DEM files.

#### Deliverables for H2 Activity

Add/delete deliverables to correspond to the tasks above. Typically 3 copies of the Preliminary Hydraulics Report are submitted. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

###### Draft LOMR/CLOMR application package

###### Preliminary Hydraulics Report

#### Final Hydraulics Recommendations (H3 Activity)

Finalize the roadway, bridge and special features analysis and prepare the Final Hydraulics Report.

Supports 70% design (D3) The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements.

##### Perform final roadway hydraulic analysis

###### Design the final type, size, and location of the major culverts (greater than 1200 mm (48”)).  Finalize design of end treatments for the major culverts.

###### Design the final type, size, and location of the minor cross culverts

###### Provide final designs for outlet energy dissipation for all culverts

###### Support preparation of culvert cross-sections, including ensuring sufficient cover is provided

###### Provide final designs for roadside ditches, including needed grade control structures and protective linings

##### Finalize bridge waterway analysis for proposed bridge designs

###### Finalize modeling of water surface profiles and freeboard for proposed bridge designs

###### Finalize capacity design recommendations

###### Finalize scour assessment and foundation and countermeasure design recommendations

##### Continue FEMA coordination.

###### Finalize the CLOMR/LOMR application package and submit to FEMA.

##### Finalize channel stability analysis

##### Finalize designs for special hydraulic features

Modify list below based on project specific conditions

###### Fish passage

###### Storm drains and curb/gutter

###### Temporary construction related drainage features

###### Stormwater (detention/retention) management and/or water quality measures

###### River training/stabilization structures

##### Finalize stream restoration and/or wetland mitigation plans in coordination with environmental specialists.

##### Update the Preliminary Hydraulics Report to develop the DRAFT Hydraulics Report.  Submit to CFLHD, and other stakeholders upon request, for review.

##### Incorporate CFLHD review comments, and comments from other stakeholders, and submit a FINAL Hydraulics Report.

#### Deliverables for H3 Activity

Add/delete deliverables to correspond to the tasks above. Typically 3 copies of the DRAFT report and 5 copies of the FINAL report are submitted. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

###### Final LOMR/CLOMR Application package

###### DRAFT Hydraulics Report

###### FINAL Hydraulics Report

## HIGHWAY DESIGN (PRMS Activities D1 to D4, P2 and D5)

Some projects do not required 15% and 50% activities. Remove these activities when necessary.

#### Develop 15% Design (D1 Activity)

Develop and Distribute Conceptual Design/Alternatives Analysis.  See 15% Development Checklist for more specific details.

The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements. For complex 4R projects where more than one alternative alignment will be developed, specify the number of alternatives that should be studied and refined for consideration. 15% Activity may not be required. Remove if necessary.

##### Roadway design

###### Review survey information (contour and mapping files)

###### Develop Typical Sections for each alternative, including paved ditch, curb, retaining wall, guardrail sections, etc., as applicable.

###### Roadway Geometric Design for each alternative

Gather traffic and accident data and identify any potential problem areas

Develop horizontal and vertical alignments

Develop planimetric design features (widenings, roadside ditches, guardrail, etc.)

Refine/update roadway cross sections

##### Secondary Roadway Design

###### Approach road design

Develop geometric design for major intersections.  Show locations of all minor approach roads.

###### Develop preliminary layouts for parking areas and show locations of pullouts.

###### Identify utility conflict for each alternative.  Compare the horizontal and vertical alignments with available utility information and identify any locations of potential conflict.

##### Plan production

###### Develop preliminary title and site plan sheets

###### Develop plan and profile sheets/roll plots

###### Develop plan quantities for major pay items for each alternative

###### Print and assemble the 15% plan package accordance with the CFLHD CADD Manual and the 15% Development Checklist for each alternative.

##### Cross Functional Design Support

###### Provide highway design support for preliminary structural design and layout.  Incorporate preliminary structural recommendations.

###### Provide highway design support for hydraulics design.  Incorporate preliminary hydraulics recommendations.

###### Provide highway design support for the environmental process.

##### Engineer’s Estimate

###### Develop cost estimates for all identified items for each alternative.  Calculate quantities and unit price analysis for all identified pay items. Include a contingency for unknown items.

##### Project Documentation

###### Develop a Highway Design Standards Form

###### Develop 15% Design Technical Memorandum

###### Develop Designer’s Notebook

###### Complete the 15% Development Checklist

###### Develop the electronic file tracker

15% Peer Review (D1PRE Activity)

Pre-submittal Activity is for A/E Projects ONLY. This activity involves the submittal of the PS&E to the PM and/or select CFT members prior to the distribution to the entire CFT. If not required this activity can be removed. Peer Review Activity is for CFL Internal Projects ONLY. This activity is for a peer review by design and does not involve other disciplines.

##### Pre-submittal/Peer Review

###### Assemble, print, and distribute plans and estimate for pre-submittal/peer review.  Conduct pre-submittal/peer review and incorporate review comments into PS&E package

###### Distribute 15% plan package and estimate for an internal and external review

15% Plan Review (D1PR Activity)

This Activity/Step is for the preparation and distribution of the plans and estimate. The Activity/Step for the CFT to review the plans and estimate is in Section M. Meetings and Reviews.

##### Prepare for External/Internal Cross Functional Team Review

###### Prepare draft responses to Internal and External Reviewers

#### Deliverables for D1 Activities

Add/delete deliverables to correspond to the tasks above. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

Internal and External Distribution Deliverables

###### 15% Plans and Estimate

###### 15% Design Support Documents

15% Development Checklist

Draft Highway Design Standards Form

Design Technical Memorandum

Roll plots with horizontal and vertical alignments for all alternatives

Draft Unit Price Analysis for major pay items

15% Comment and Response Form, including draft responses to reviewers

#### Develop 30% Design (D2 Activity)

Develop and distribute the 30% design.  See 30% Development Checklist for more specific details.  Hours for incorporating 15% comments into the plans are in included in applicable items below

The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements. If there is not a 15% Activity, remove Step 1 and adjust deliverables as neded.

##### Post 15% field review

###### Prepare a Comment and Response Form for all comments received (including both redlined plan comments and type written comments).  Final responses are not required at this time.

###### Produce trip report, including decision and action register.  Submit a draft report to FHWA/CFT for comment.  Incorporate comments and finalize and distribute the 15% Trip Report.

##### Roadway Design

###### Develop/refine/update the Typical Sections for each alternative

###### Roadway geometric design for each alternative

###### Develop/refine/update horizontal and vertical alignments

###### Develop/refine/update planimetric design features (widenings, roadside ditches, guardrail, etc.)

###### Develop/refine/update roadway cross sections

##### Secondary Roadway Design

###### Develop/refine/update all geometric design for approaches, major intersection plans, cross sections and intersection safety

###### Develop/refine/update pullout and parking area design

###### Develop a preliminary erosion control design for unique and major proposed erosion control devices.

Identify locations for sediment basins, including size requirements and begin development of additional details.

###### Develop/refine/update utility resolution/conflict plans.  Compare the horizontal and vertical alignments with available utility information and determine any locations for potential conflict.

##### Develop preliminary temporary traffic control design for unique or major items.

###### Identify potential detours and road closures

###### Identify possible construction phasing.

Discuss need for IHSDM with PM and CFT

##### Use Interactive Highway Design Module (IHSDM) to evaluate the 30% design.  Analyze the generated reports and include a narrative explaining the results

##### Plan Production

###### Standards, details, Specials and project specific plan sheets

Include all applicable FLH Standard Plans and CFLHD Details

Develop project specific details and plan sheets as necessary including title and site plan sheets

###### Plan and Profile sheets

Develop plan and profile sheets

###### Develop/refine/update plan quantities, summaries and tabulations.

###### Print and assemble the 30% plan package accordance with the CFLHD CADD Manual and the 30% Development Checklist. The plan package may be numbered by hand.

##### Cross Functional Design Support

###### Provide highway design support for preliminary structural design and layout.

###### Provide highway design support for hydraulics design.

###### Provide highway design support for the environmental process.

Review the current environmental documents for the project

Become familiar with the policy, impacts, and issues associated with the project

Incorporate mitigation measures and commitments from the environmental document into the design

###### Assist with identifying and researching the need for permits.

##### Engineer’s Estimate

###### Develop/update/refine cost estimate for all identified items for each alternative.  Calculate quantities and unit price analysis for all identified pay items. Include a contingency for unknown items.

##### Construction Schedule

###### Identify the major construction bid items, develop the production rates/durations and develop the construction schedule’s calendar.

##### Project Documentation

###### Develop/update/refine Highway Design Standards Form

###### Prepare 30% Design Technical Memorandum

###### Update Designer’s Notebook

###### Complete the 30% Development Checklist

###### Update the electronic file tracker

30% Peer Review (D2PRE Activity)

Pre-submittal Activity is for A/E Projects ONLY. This activity involves the submittal of the PS&E to the PM and/or select CFT members prior to the distribution to the entire CFT. If not required this activity can be removed. Peer Review Activity is for CFL Internal Projects ONLY. This activity is for a peer review by design and does not involve other disciplines.

##### Pre-submittal/Peer Review

###### Assemble, print, and distribute PS&E package for pre-submittal/peer review.  Conduct review and incorporate review comments into PS&E package

###### Distribute 30% Plans, Specifications, and Estimate package for an in-office review by the CFT

30% Plan Review (D2PR Activity)

This Activity/Step is for the preparation and distribution of the plans and estimate. The Activity/Step for the CFT to review the plans and estimate is in Section M. Meetings and Reviews.

##### External Review

###### Update PS&E from internal review comments

###### Print and distribute the 30% package to external agencies

###### Prepare draft responses to external reviewers

#### Deliverables for D2 Activities

Add/delete deliverables to correspond to the tasks above. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

###### 15% Field Review Trip Report

Internal Distribution Deliverables

###### 30% Plans, Specifications and Estimate for Internal FHWA Distribution

###### 30% Internal FHWA Distribution Design Support Documents

30% Development Checklist

15% Comment and Response Form, including responses

Updated CPM Construction Schedule

30% Unit Price Analysis

Copy of quantity calculations and supporting documentation

Draft Highway Design Standards Form

Updated Design Technical Memorandum

Updated IHSDM Report and Narrative

External Distribution Deliverables

###### 30% Plans, Specifications and Estimate for External FHWA Distribution

###### 30% External Distribution Design Support Documents

CPM Construction Schedule

30% Internal Distribution Comment and Response Form, including responses

Draft Highway Design Standards Form

Updated Design Technical Memorandum

15% Comment and Response Form including external comments received

#### Develop 50% Design (D2.1 Activity)

Develop and distribute the 50% design.  Note:  Develop 50% Design is usually only necessary if the project is a 4R with Right-of-Way.  See 50% Development Checklist for more specific details.  Hours for incorporating 30% comments into the plans are in included in applicable items below.

The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements. The 50% Design Activity may be required. Remove if necessary.

##### Post 30% Field Review

###### Produce master redline plan set with field review comments

###### Prepare a Comment and Response Form for all comments received (including both redlined plan comments and type written comments).  Final responses are not required at this time.

###### Produce trip report, including decision and action register.  Submit a draft report to FHWA/CFT for comment.  Incorporate comments and finalize and distribute the 30% Trip Report.

##### Roadway Design

###### Refine/update the Typical Sections

###### Refine/update horizontal and vertical alignments

###### Refine/update planimetric design features (widenings, roadside ditches, guardrail, etc.)

###### Refine/update roadway cross sections

##### Secondary Roadway Design

###### Approach road design

Refine/update all geometric design for approaches, major intersection plans, cross sections and intersection safety

###### Refine/Update pullout and parking area design

###### Develop an erosion control design.  Show temporary and permanent erosion control devices in sufficient detail to identify impacts to the final footprint.

###### Refine/Update utility resolution/conflict plans.  Modify the design to avoid utility conflicts where possible.

##### Permanent and Temporary TrafficControl

###### Develop preliminary permanent traffic control signing and striping design

###### Develop preliminary temporary traffic control plans, construction phasing and/or detour plans.

Discuss need for IHSDM with PM and CFT

##### Use Interactive Highway Design Module (IHSDM) to evaluate the 50% design.  Analyze the generated reports and include a narrative explaining the results

##### Plan Production

###### Standards, details, specials and project specific plan sheets

Include all applicable FLH Standard Plans and CFLHD Details

Develop project specific details and plan sheets as necessary including title and site plan sheets

###### Refine/update plan and profile sheets

###### Refine/Update plan quantities, summaries and tabulations.

###### Print and assemble the 50% plan package accordance with the CFLHD CADD Manual and the 50% Development Checklist. The plan package may be numbered by hand.

##### Cross Functional Design Support

###### Provide highway design support for preliminary structural design and layout.  Develop layout sheets to sufficient detail to identify impact to the final footprint.

###### Provide highway design support for environmental mitigation design and commitments.

###### Assist with identifying and researching the need for permits

##### Engineer’s Estimate

###### Update/refine cost estimate.  Calculate quantities and unit price analysis for all identified pay items. Include a contingency for unknown items.

##### Construction Schedule

###### Develop the draft CPM Construction Schedule , production rates/durations for all construction items, update calendar, and written narrative discussing critical schedule elements.

##### Specifications

###### Develop draft Special Contract Requirements (SCR’s). Include all appropriate up-to-date SCR’s from the Library of Specifications. Use the Track Changes feature to highlight or redline project specific requirements to facilitate FHWA review. Incorporate recommendations from Bridge, Materials, Safety, and partner agencies.

##### Project Documentation

###### Update/refine Highway Design Standards form

###### Prepare 50% Design Technical Memorandum

###### Update Designer’s Notebook

###### Complete the 50% Development Checklist

###### Update the electronic file tracker

50% Pre-submittal/Peer Review (D2.1PRE Activity)

Pre-submittal Activity is for A/E Projects ONLY. This activity involves the submittal of the PS&E to the PM and/or select CFT members prior to the distribution to the entire CFT. If not required this activity can be removed. Peer Review Activity is for CFL Internal Projects ONLY. This activity is for a peer review by design and does not involve other disciplines.

##### Pre-submittal/Peer Review

###### Assemble, print, and distribute PS&E package for peer review.  Conduct peer review and incorporate review comments into PS&E package

###### Distribute 50% Plans, Specifications, and Estimate package for an in-office review by the CFT

External Distribution (D2.1PR Activity)

This Activity/Step is for the preparation and distribution of the plans and estimate. The Activity/Step for the CFT to review the plans and estimate is in Section M. Meetings and Reviews.

##### External Review

###### Update PS&E from internal review comments

###### Print and distribute the 50% package to external agencies

###### Prepare responses to external reviewers

#### Deliverables for D2.1 Activities

Add/delete deliverables to correspond to the tasks above. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

###### 30% Field Review Trip Report

Pre-submittal/Peer Review Distribution Deliverables

###### 50% Plans, Specifications and Estimate for Internal FHWA Distribution

###### 50% Pre-submittal Design Support Documents

30% Comment and Response Form, including responses

30% Field Review Master redlined plan set (no copy, available for meeting review only)

Draft Unit Price Analysis

Draft copy of quantity calculations

DRAFT Highway Design Standards Form

50% Design Technical Memorandum

50% IHSDM Report and Narrative

Internal Distribution Deliverables

###### 50% Plans, Specifications and Estimate for Internal FHWA Distribution

###### 50% Internal FHWA Distribution Design Support Documents

50% Development Checklist

30% Comment and Response Form, including responses

Updated CPM Construction Schedule

50% Unit Price Analysis

Copy of updated quantity calculations and supporting documentation

Updated 50% Highway Design Standards Form

Updated 50% Design Technical Memorandum

Updated 50% IHSDM Report and Narrative

External Distribution Deliverables

###### 50% Plans, Specifications and Estimate for External FHWA Distribution

###### 50% External Distribution Design Support Documents

CPM Construction Schedule

50% Internal Distribution Comment and Response Form, including responses

Updated 50% Highway Design Standards Form

Updated 50% Design Technical Memorandum

#### Develop 70% Design (D3 Activity)

Develop and distribute (70%) detailed plans specifications and estimate (PS&E) package.  See 70% Development Checklist for more specific details

The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements. If there is not a 50% Activity, revise Step 1 for Post 30% Field Review

##### Post 50% Field Review

###### Produce master redline plan set with field review comments

###### Prepare a Comment and Response Form for all comments received (including both redlined plan comments and type written comments).  Final responses are not required at this time.

###### Produce trip report, including decision and action register.  Submit a draft report to FHWA/CFT for comment.  Incorporate comments and finalize and distribute the 50% Trip Report.

##### Roadway Design

###### Finalize the Typical Sections

###### Complete horizontal and vertical alignments

###### Complete planimetric design features (widenings, roadside ditches, guardrail, etc.)

###### Complete roadway cross section

##### Secondary Roadway Design

###### Complete all geometric design for approaches, major intersection plans, cross sections and intersection safety

###### Complete pullout and parking area design

###### Update erosion control design

###### Update utility resolution/conflict plans

##### Permanent and Temporary Traffic Control

###### Update permanent traffic control signing and striping design

###### Update construction phasing and/or detour plans

###### Update temporary signing, striping, and traffic control plans

##### Plan production

###### Update/refine plan and profile sheets

###### Complete plan quantities, summaries and tabulations.

###### Verify/update all applicable FLH Standard Plans and CFLHD Details to current version

###### Complete project specific details and plan sheets including title and site plan sheets

###### Print and assemble the 70% plan package accordance with the CFLHD CADD Manual and the 70% Development Checklist. The plan package may be numbered by hand

##### Cross Functional Design Support

###### Provide highway design support for structural design and layout

###### Provide highway design support for major culvert design

###### Provide highway design support for environmental mitigation design and commitments.

###### Support/finalize all permits and requirements

###### Provide alignments for field review staking

###### Coordinate 70% field review with agencies involved

###### Prepare travel and draft field review agenda

##### Engineer’s Estimate

###### Complete the unit price analysis for all pay items and cost estimate

##### Construction Schedule

###### Update CPM construction schedule, production rates/durations for all construction items, update calendar, and written narrative discussing critical schedule elements

##### Specifications

###### Update the Special Contract Requirements (SCR’s). Include all appropriate up-to-date SCR’s from the Library of Specifications. Use the Track Changes feature to highlight or redline project specific requirements to facilitate FHWA review

##### Project Documentation

###### Complete Highway Design Standards form

###### Prepare 70% Design Technical Memorandum

###### Update Designer’s Notebook

###### Complete the 70% Development Checklist

###### Update electronic file tracker

70% Pre-submittal/Peer Review (D3PRE Activity)

Pre-submittal Activity is for A/E Projects ONLY. This activity involves the submittal of the PS&E to the PM and/or select CFT members prior to the distribution to the entire CFT. If not required this activity can be removed. Peer Review Activity is for CFL Internal Projects ONLY. This activity is for a peer review by design and does not involve other disciplines.

##### Pre-sbumittal/Peer Review

###### Assemble, print, and distribute PS&E package for peer review.  Conduct peer review and incorporate review comments into PS&E package

###### Distribute 70% Plans, Specifications, and Estimate package for an in-office review by the CFT

70% Plan Review (D3PR Activity)

This Activity/Step is for the preparation and distribution of the plans and estimate. The Activity/Step for the CFT to review the plans and estimate is in Section M. Meetings and Reviews.

##### External Review

###### Update PS&E from internal review comments

###### Print and distribute the 70% package to external agencies

###### Prepare draft responses to external reviewers

#### Deliverables for D3 Activities

Add/delete deliverables to correspond to the tasks above. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

###### 50% Field Review Trip Report

Pre-submittal/Peer Review Distribution Deliverables

###### 70% Plans, Specifications and Estimate for Internal FHWA Distribution

###### 70% Pre-submittal Design Support Documents

50% (or 30% if 50% not performed) Comment and Response Form, including responses

50% Field Review Master redlined plan set (no copy, available for meeting review only)

Draft Unit Price Analysis

Draft copy of quantity calculations

Draft Highway Design Standards Form

Draft 70% Design Technical Memorandum

Internal Distribution Deliverables

###### 70% Plans, Specifications and Estimate for Internal FHWA Distribution

###### 70% Internal FHWA Distribution Design Support Documents

70% Development Checklist

50% (or 30%, if no 50% review was held) Comment and Response Form, including responses

Updated CPM Construction Schedule

70% Unit Price Analysis

Copy of final quantity calculations and supporting documentation

Final Highway Design Standards Form

Updated 70% Design Technical Memorandum

Electronic Files and Tracking Sheet (Design files  profile at centerline and cross sections.  Updated survey topo/planimetric files when applicable.)

External Distribution Deliverables

###### 70% Plans, Specifications and Estimate for External FHWA Distribution

###### 70% External Distribution Design Support Documents

CPM Construction Schedule

70% Internal Distribution Comment and Response Form, including responses

Final Highway Design Standards Form

Updated 70% Design Technical Memorandum

#### Develop 95% Design (D4 Activity)

Develop and distribute the final design and preparation of the 95% PS&E package.  See 95% Development Checklist for more specific details.  Hours for incorporating 70% comments into the plans are in included in applicable items below

The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements.

##### Post 70% field review

###### Produce master redline plan set with field review comments

###### Prepare a Comment and Response Form for all comments received (including both redlined plan comments and type written comments).  Final responses are not required at this time.

###### Produce trip report, including decision and action register.  Submit a draft report to FHWA/CFT for comment.  Incorporate comments and finalize and distribute the 70% Trip Report.

##### Roadway Design

###### Finalize the Typical Sections

###### Finalize all horizontal and vertical alignments

###### Finalize all planimetric design features

###### Finalize all roadway cross sections

##### Secondary Road Design

###### Finalize all geometric design for approaches, major intersection plans, cross sections and intersection safety

###### Finalize pullouts and parking area design

###### Finalize erosion control design

###### Finalize utility relocation and conflict plans

##### Permanent and Temporary Traffic Control

###### Finalize permanent traffic control signing and striping design

###### Temporary Traffic Control

Finalize construction phasing and/or detour plans

Finalize temporary signing, striping and traffic control plans

##### Plan production

###### Standards, Details, Specials and project specific plan sheets

Verify/update all applicable FLH Standard Plans and CFLHD Details to current version

Finalize project Special Drawings and project specific plan sheets

###### Finalize Plan and Profile sheets

###### Finalize all plan quantities, summaries and tabulations

###### Assemble the 95% plan package according to the CFLHD CADD Manual and the 95% Development Checklist.

##### Cross Functional Design Support

###### Provide highway design support for final structural design and layout

###### Provide highway design support for final hydraulics design

###### Finalize/support environmental mitigation design and commitments

###### Support/finalize all permits and requirements

##### Engineer’s Estimate

###### Finalize the unit price analysis for all pay items and cost estimate for each bid schedule (if more than one)

##### Construction Schedule

###### Finalize CPM construction schedule, production rates/durations for all construction items, update calendar, and written narrative discussing critical schedule elements

##### Specifications

###### Finalize the Special Contract Requirements (SCR’s). Include all appropriate up-to-date SCR’s from the Library of Specifications. Use the Track Changes feature to highlight or redline project specific requirements to facilitate FHWA review

##### Project Documentation

###### Finalize Highway Design Standards Form

###### Prepare 95% Design Technical Memorandum

###### Update Designer’s Notebook

###### Complete the 95% Development Checklist

###### Update electronic file tracker

###### Prepare a draft Project Engineer’s Memo (PE Memo)

95% Pre-submittal/Peer Review (D4PRE Activity)

Pre-submittal Activity is for A/E Projects ONLY. This activity involves the submittal of the PS&E to the PM and/or select CFT members prior to the distribution to the entire CFT. If not required this activity can be removed. Peer Review Activity is for CFL Internal Projects ONLY. This activity is for a peer review by design and does not involve other disciplines.

##### Pre-submittal/Peer Review

###### Assemble, print, and distribute PS&E package for review.  Conduct peer review and incorporate review comments into PS&E package.

###### Distribute 95% Plans, Specifications, and Estimate package for an in-office review by the CFT

95% Plan Review (D4PR Activity)

This Activity/Step is for the preparation and distribution of the plans and estimate. The Activity/Step for the CFT to review the plans and estimate is in Section M. Meetings and Reviews.

##### External Review

###### Update PS&E from internal review comments

###### Print and distribute the 95% package to external agencies

###### Prepare draft responses to external reviewers

#### Deliverables for D4 Activities

###### 70% Field Review Trip Report

Pre-Submittal/Peer Review Deliverables

###### Draft 95% Plans, Specifications and Estimate for Pre-Submittal Review

###### 95% Design Support Documents

70% Comment and Response Form, including responses

70% Field review Master redlined plan set (no copy, available for meeting review only)

Draft Unit Price Analysis

Draft copy of quantity calculations

Draft Highway Design Standards Form

Draft Design Technical Memorandum

Add/delete deliverables to correspond to the tasks above. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

Internal Distribution Deliverables

###### 95% Plans, Specifications and Estimate for Internal FHWA Distribution

###### 95% Design Support Documents

95% Development Checklist

70% Comment and Response Form, including responses

Final CPM Construction Schedule

Final Unit Price Analysis

Copy of quantity calculations

Final Highway Design Standards Form

Final 95% Design Technical Memorandum

Draft Project Engineer’s memo

External Distribution Deliverables

###### 95% Plans, Specifications and Estimate for External FHWA Distribution

###### 95% Design Support Documents

95% Development Checklist

95% Internal Distribution Comment and Response Form, including draft responses

Final CPM Construction Schedule

Final Highway Design Standards Form

Final 95% Design Technical Memorandum

95% External Distribution Comment and Response Form, including draft responses

#### PS&E Approval and Contract Development (P2 Activity)

Includes revisions to the PS&E as a result of partner agency reviews and approval comments.  This is 100% design.  See 100% Development Checklist for more specific details.

The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements.

##### Finalize PS%E

###### Incorporate comments and print, compile, and deliver the final PS&E package to FHWA

##### Develop procurement documents and checklists

###### PS&E Advertisement Checklist

###### Procurement Request (PR) & 1240

###### Complete 100% Development Checklist

100% Pre-submittal/Peer Review (P2PRE Activity)

Pre-submittal Activity is for A/E Projects ONLY. This activity involves the submittal of the PS&E to the PM and/or select CFT members prior to the distribution to the entire CFT. If not required this activity can be removed. Peer Review Activity is for CFL Internal Projects ONLY. This activity is for a peer review by design and does not involve other disciplines.

##### Peer/Pre-submittal Review

###### Assemble, print, and distribute PS&E package for review.  Conduct peer review and incorporate review comments into PS&E package.

###### Distribute Final Plans, Specifications, and Estimate package for an in-office review by the CFT

##### Stamp final PS&E and prepare electronic files (PDF format)

#### Deliverables for P2 Activities

Add/delete deliverables to correspond to the tasks above. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

###### 100% Plans, Specifications and Estimate for Internal FHWA Distribution

###### 100% Design Support Documents

100% Development Checklist

95% Comment and Response Form, including responses

Final CPM Construction Schedule

Final Unit Price Analysis

Copy of quantity calculations

Designer’s Notebook

Final Highway Design Standards Form (signed)

Final Design Technical Memorandum

Draft Project Engineer’s memo

Final Electronic File Tracker

All Microstation design files (on CD)

All Excel design files (on CD)

All Geopak design files (on CD)

Geopak Earthwork reports

Contact Distribution List (on CD)

Final electronic Plans (on CD)

PS&E advertisement checklist

#### Assemble Project Engineer’s Design Package (D5 Activity)

Assemble Project Engineer’s Design Package.  See Project Engineer’s Notebook checklist for more specific details

The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements.

##### Complete the Project Engineer’s Notebook

###### Complete checklist.  See the Project Engineer’s Notebook checklist for more information

###### Finalize Project Engineer’s memo

###### Assemble Project Engineer’s Notebook according to the PE notebook checklist including project documentation.

#### Deliverables for D5 Activity

Add/delete deliverables to correspond to the tasks above. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

###### Final PE memo

###### Project Engineer’s Design Package, including two complete hard copies and three CD’s of Staking data

BRIDGE (PRMS Activities B2 to B4)

#### Structural Layout (B2 Activity)

Determine structural width, length, type, location, alternative types, typical structural section and any special details or client requests.  Structures included in this activity are bridges and concrete cantilever, soil nail (including SMSE), soldier pile and tieback retaining walls.

The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements.

Structure Selection

##### For Bridge site(s) identified in the Scoping Report, prepare a Bridge Selection Report with supporting drawings, tables, and discussion as needed.  Incorporate recommendations from Preliminary Hydraulic Recommendations and Preliminary Geotechnical Investigation.  Incorporate 30% plan and profile from Roadway Design.  Include the following:

###### Review the structure site data to determine the requirements that will control the structure size, layout, and type.

###### Propose recommended superstructure and substructure alternative(s).  Propose foundation alternative(s).  Determine the structure length, width, and span configurations that satisfy horizontal and vertical clearance criteria.  Consider hydraulic opening and potential scour requirements.

###### Propose recommended rehabilitation alternative(s) if applicable.  Consider continued use of all or parts of existing structures.

###### Consider the effects of staged construction versus realignment.

###### Consider environmental constraints.

###### Consider restrictions due to site access and transport limitations, and local material availability.

###### Recommend proposed adjustments to profile alignment and grade necessary to accommodate bridge location and freeboard requirements.

###### Include discussion on major items or issues such as future maintenance that might affect the selection of a preferred alternative.

###### Recommend a structure layout, type and rehabilitation alternative(s) as applicable.  .  State criteria used to evaluate each alternative.

###### Include a list of references of available reports, investigations, and technical memorandums used in preparation of the Bridge Selection Report.

###### Obtain acceptance by CFLHD of the Bridge Selection Report prior to beginning work on Bridge Preliminary Layout (TS&L).

##### Prepare a bridge conceptual TS&L drawing for each bridge alternative recommended.  Incorporate recommendations from Preliminary Hydraulic Recommendations and Preliminary Geotechnical Investigation.

##### Prepare bridge preliminary cost estimates for each alternative(s) based on square foot costs.

##### For retaining wall site(s) identified in the 15% design plans, prepare wall conceptual drawing(s).  Incorporate recommendations from Preliminary Hydraulic Recommendations and Preliminary Geotechnical Investigation.

###### Review the available wall site data to determine the requirements that will control the wall size, layout, and type.

###### Prepare conceptual drawings for each wall alternative showing proposed wall type and foundation alternatives.

##### Prepare preliminary cost estimates for each wall alternative based on wall face square foot costs.

Structure Preliminary Layout

##### For each approved alternative(s) identified in the Bridge Selection Report prepare a Bridge Preliminary Layout (TS&L).  Incorporate recommendations from Preliminary Hydraulic Report and Preliminary Geotechnical Investigation.  Incorporate 50% plan and profile from Roadway Design.

###### See the Federal Lands Highway Bridge Office (FLHBO) Bridge Plan Checklist, specified in Section III, for information to be included on the Bridge Preliminary Layout (TS&L) drawing(s).

###### Obtain acceptance by CFLHD on the Bridge Preliminary Layout (TS&L) prior to beginning work on Task B3 - Structure Design and Check.

##### Prepare revised bridge preliminary cost estimate for each approved alternative based on square foot costs.

##### For the approved retaining wall alternative(s) prepare typical section drawings.  Incorporate recommendations from Preliminary Hydraulic Report and Preliminary Geotechnical Investigation.

###### Evaluate wall alternatives and propose recommended wall type.

###### Consider application of FHWA CFLHD standard typical sections and details for cantilever retaining walls, soil nail walls (including SMSE), soldier pile and tieback walls.

###### Prepare wall typical sections and details, including structural railing and aesthetic treatments.

##### Prepare revised wall preliminary cost estimate based on wall face square foot cost.

#### Deliverables for B2 Activity

Add/delete deliverables to correspond to the tasks above. Typically 4 copies of the DRAFT report, 4 copies of the FINAL report, 4 copies of the DRAFT TS&L and 4 copies of the FINAL TS&L are submitted. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

###### Bridge Selection Report

###### Bridge Conceptual TS&L drawings and preliminary cost estimates (include in 30% package)

###### Wall Conceptual Drawings and preliminary cost estimates (include in 30% package)

###### Bridge Preliminary Layout (TS&L) and preliminary cost estimate (include in 50% package)

###### Wall typical section drawings and preliminary cost estimate (include in 50% package)

#### Structural Design and Check (B3 Activity)

Structural analysis, design, and check of the structure.  Draft contract plans, prepare special contract requirements, and the engineer’s estimate.  Structures included in this activity are bridges, and concrete cantilever, soil nail (including SMSE), soldier pile and tieback walls.

The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements. For Structure Preliminary Layouts (TS&Ls) prepared by the FHWA, travel to the project site with the COTR/PM or designated representative and review proposed bridge layout. Prepare and submit a trip report to the FHWA containing a summary observations and discussions.

Design Criteria

##### For the approved Bridge Preliminary Layout (TS&L) prepare a Structure Design Criteria document.

###### Follow the template referenced in Section III.

###### Obtain acceptance by CFLHD of the Structure Design Criteria prior to beginning work on Step 2 - 70% Structure Design.

###### Incorporate recommendations from Preliminary Hydraulic Report, Draft Geotechnical Report, and Geotechnical Memoranda, as available.

##### For concrete cantilever retaining walls prepare a Structure Design Criteria document.

###### Follow the template referenced in Section III.

###### Obtain acceptance by CFLHD of the Structure Design Criteria prior to beginning work on Step 2 - 70% Structure Design.

###### Incorporate recommendations from Preliminary Hydraulic Report, Draft Geotechnical Report, and Geotechnical Memoranda, as available.

70% Structure Design

##### Provide calculations for the structural design of the bridge superstructure.  Annotate design calculations with specific references to the applicable design specification.   Perform calculations for all elements of the superstructure including:

###### Girders/beams

###### Deck

###### Endwalls and wingwalls (where part of superstructure)

###### Bearings and connections

###### Expansion joints

##### Provide calculations for the structural design of retaining walls.  Annotate design calculations with specific references to the applicable design specification.  Incorporate recommendations from Final Hydraulics Report, Draft Geotechnical Report, and Geotechnical Memoranda as issued.  Include calculations for the following elements:

###### Internal stability and structural design of concrete cantilever retaining walls

###### Facing design of soil nail walls

###### Soldier pile and tieback wall structural components

70% Structure Drawings

##### Prepare plan sheets for the bridge superstructure.  Follow the format in the FLHBO Bridge Plan Checklist specified in Section III.  Incorporate recommendations from Final Hydraulics Report, Draft Geotechnical Report, and Geotechnical Memoranda as issued.  Provide plan sheets for the following:

###### Plan and elevation

###### General notes and estimate

###### Summary of boring logs (from Geotechnical Investigation)

###### Stage construction sequence

###### Endwalls and wingwalls

###### Girders/beams

###### Bearings and connections

###### Typical section

###### Deck

###### Expansion joints

###### Aesthetic treatments

###### Railing and transition railings

###### Approach slabs

##### Prepare plan sheets for the retaining walls.  Follow the format in the FLHBO Bridge Plan Checklist specified in Section III.  Incorporate recommendations from Final Hydraulics Report, Draft Geotechnical Report, and Geotechnical Memoranda as issued.  Provide plan sheets for the following:

###### General plan

###### General notes and estimate

###### Plan and profile

###### Typical sections

###### Expansion/contraction joint details

###### Drainage details

###### Aesthetic treatments

###### Excavation/backfill details

###### Shoring and min. setback/depth requirement details

###### Railing and transition railings

70% Structure Independent Check

##### Prepare independent design calculations for the bridge superstructure.  Check the structural design of all elements of the superstructure as detailed in the 70% Structure Drawings. The independent check will verify design methods, functional requirements, and conformance to the Structure Design Criteria.  Check calculations shall be annotated with specific references to the applicable design specification sections.

##### Prepare independent design calculations for the retaining walls as detailed in the 70% Structure Drawings.  The independent check will verify design methods, functional requirements, and conformance to the Structure Design Criteria.  Check calculations shall be annotated with specific references to the applicable design specification sections.

##### Check the 70% Structure Drawings for completeness and accuracy.

70% Structure Quantities and Itemized Cost Estimate

##### Prepare bridge plan item quantity calculations and document itemized cost estimate

##### Prepare wall plan item quantity calculations and document itemized cost estimate

##### Check the 70% Structure Quantities and Itemized Cost Estimate for completeness and accuracy

70% Structure Special Contract Requirements

##### Prepare Bridge Special Contract Requirements.

###### Review Structure Special Contract Requirements provided by FHWA.

###### Prepare unique Structure Special Contract Requirements required by the design.

##### Prepare Retaining Wall Special Contract Requirements.

###### Review Structure Special Contract Requirements provided by FHWA.

###### Prepare unique Structure Special Contract Requirements required by the design.

##### Check the 70% Structure Special Contract Requirements for completeness and accuracy.

95% Structure Design

##### Provide calculations for the structural design of the bridge substructure.  Annotate design calculations with specific references to the applicable design specification.  Incorporate recommendations from Final Geotechnical Report and Final Hydraulics Report.   Perform calculations for all elements of the substructure including:

###### Abutments

###### Abutment foundations

###### Piers

###### Pier foundations

##### Perform bridge load rating (NPS projects only)

###### Provide calculations, notes, and assumptions necessary to complete the load rating.

###### Complete the FHWA Load Rating form, specified in Section III.

##### Provide calculations for revised wall sections, not provided for in the 70% retaining wall design. Incorporate recommendations from Final Geotechnical Report and Final Hydraulics Report.  Annotate design calculations with specific references to the applicable design specification.

95% Structure Drawings

##### Prepare complete set of plan sheets for the bridge.  Follow the format in the FLHBO Bridge Plan Checklist specified in Section III.  Incorporate recommendations from Final Geotechnical Report and Final Hydraulics Report.  Include plan sheets for the following:

###### Revised 70% structure drawings as necessary

###### Foundation layout

###### Slope protection

###### Abutments

###### Piers

###### Reinforcing bar lists

###### Existing bridge plans

##### Prepare complete set of plan sheets for the retaining walls.  Follow the format in the FLHBO Bridge Plan Checklist specified in Section III.  Incorporate recommendations from Final Geotechnical Report and Final Hydraulics Report.  Include plan sheets for the following:

###### Revise 70% structure drawings as necessary

95% Structure Independent Check

##### Prepare independent design calculations for the bridge substructure.  Check the structural design of all elements of the substructure as detailed in the 95% Structure Drawings.  The independent check will verify design methods, functional requirements, and conformance to the Structure Design Criteria.  Check calculations shall be annotated with specific references to the applicable design specification sections.

##### Prepare independent load rating of the bridge.

###### Provide independent calculations, notes, and assumptions necessary to complete the load rating.

###### Verify the results of the FHWA Load Rating form, specified in Section III.

##### Prepare independent design calculations for the retaining walls as detailed in the 95% Structure Drawings.  The independent check will verify design methods, functional requirements, and conformance to the Structure Design Criteria.  Check calculations shall be annotated with specific references to the applicable design specification sections.

##### Check the 95% Structure Drawings for completeness and accuracy.

95% Structure Quantities and Itemized Cost Estimate

##### Revise 70% bridge plan item quantity calculations and itemized cost estimate.

##### Revise 70% wall plan item quantity calculations and itemized cost estimate.

##### Check the revised Structure Quantities and Itemized Cost Estimate for                                completeness and accuracy.

95% Structure Special Contract Requirements

##### Revise 70% Bridge Special Contract Requirements.

##### Revise 70% Wall Special Contract Requirements.

##### Check the revised Structure Special Contract Requirements for completeness and accuracy.

#### Deliverables for B3 Activity

Add/delete deliverables to correspond to the tasks above. Typically 1 copy of the site visit trip report, 1 copy of the DRAFT design criteria, and 1 copy of the FINAL design criteria, are submitted. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

###### 70% Structure Design Calculations and Independent Check

###### 70% Structure PS&E

###### 95% Structure Design Calculations and Independent Check

###### 95% Structure PS&E

#### Structural PS&E Revisions (B4 Activity)

Complete any necessary revisions to the Structure 95% PS&E package.

The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements.

##### 100% Structural PS&E Supporting Data

##### Complete any necessary revisions to the 95% Structure Design.  Provide calculations and independent check calculations for the 100% Structural Design.

##### 100% Structural PS&E

##### Revise 95% Structural Drawings.

##### Revise 95% Structural Special Contract Requirements.

##### Revise 95% Structure Quantities and Itemized Cost Estimate.

#### Deliverables for B4 Activity

Add/delete deliverables to correspond to the tasks above. Typically 1 copy of the 100% structural PS&E supporting data is submitted. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

###### 100% Structural PS&E Supporting Data

###### 100% Structural PS&E

## Permits (E4.1 Activity)

Identify environmental permitting/certification needs, coordinate with the regulatory agencies, and prepare applications.

The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements.

List the anticipated permits for the specific project below.

It is anticipated that the following permits will be required for this project:

##### Research environmental permit/certification/authorization needed for construction projects, including NEPA documents.

##### Coordinate with regulatory agencies if there is any question on the proper permitting/certification application process.  Coordination is anticipated with the following agencies:

List the agencies that it is anticipated that coordination will be needed.

##### Prepare the 404 permit application and submit to CFLHD with the required attachments including, but not limited to the following:

###### Transmittal letter

###### Environmental documents

###### Jurisdictional Determination letter from the Corps of Engineers

###### Plans (Include appropriate 8½” x 11” plans in the project description of the application)

###### Maps (Include a general location geographic map, topographic site map, and site locator map in the project description of the application)

###### Wetlands Delineation Report and Wetland Mitigation and Monitoring Plan

###### Quantification (surface area, volume) of impact areas to the jurisdictional waters in tabular form. Show wetland impacted and surface area of impact on plan sheets (plan/profile or erosion control)

###### 404 Permit Application Checklist (Note: Bill Jones is currently working on this checklist)

##### Incorporate CFLHD review comments on the 404 permit application and resubmit to CFLHD

##### Prepare 401 certification application and submit to CFLHD with any required attachments, including transmittal letter and 401 application checklist. (Note: Bill Jones is currently working on this checklist)

##### Incorporate CFLHD comments on the 401 permit application and resubmit to CFLHD.

##### Prepare NPDES Notice of Intent (NOI) or Application including, but not limited to, the following information/attachments:

###### Identify any Waters of the US on the 303 d list that may be impacted by Stormwater runoff

###### Stormwater Pollution Prevention Plan

###### Transmittal letter

###### NPDES NOI or Application checklist (Note: Bill Jones is currently working on this checklist)

##### Incorporate CFLHD comments on the NPDES NOI or Application and resubmit to CFLHD.

##### Track status of permit reviews by regulatory agencies.

#### Deliverables for E4.1 Activity

Add/delete deliverables to correspond to the tasks above. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

###### 404 Application (individual) or Preconstruction Notification (PCN) and required attachments

###### 401 Certification Application and required information/attachments

###### NPDES NOI or Application and required information/attachments

## Meetings and Field Reviews

The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements. List the assumed # of CFT mtg.s. For CFL internal projects, CFT mtg. hours will be included in each disciplines open activity.

#### Design Meetings, Plan Reviews, and Field reviews

##### Cross Functional Team (CFT) Progress Meetings (A/E Projects Only)

###### Assume xx meetings at FHWA’s Lakewood office lasting xx hours each.

###### Assume xx personnel from the A/E shall attend each meeting.

###### Discuss project status, progress and share information

###### Review the design activities and plan set status

###### The A/E should be prepared to present current technical information and overall task order status

###### Transmit any documents to be reviewed by FHWA at least one week in advance of the meeting

###### Produce Cross Functional Team meeting minutes for review, approval, and distribution by the Government of all meetings.  Provide meeting minutes to CFLHD within seven days listing all new information, action items and decisions for review.  Make all changes as directed and return the minutes within 7 days of review.  Respond in a timely manner to all inquiries, concerns and questions. (A/E projects only)

##### Attend the Scoping Meeting and Site Visit with the CFLHD Project Manager. The Consultant Project Manager and Design Engineer are required at the Scoping Meeting. It is anticipated that the Scoping Meeting will last X days including travel. The consultant is responsible for making all travel arrangements for their staff including airfare, rental car and hotel.

##### 15% CFT plan review

##### 15% CFT review meeting

##### 15% field review (preliminary line and grade review). It is anticipated that the field review will last X days including travel

##### 30% CFT plan review

##### 30% CFT review meeting

##### 30% field review. It is anticipated that the field review will last X days including travel

##### 50% CFT plan review

##### 50% CFT review meeting

##### 50% field review (final line and grade review). It is anticipated that the field review will last X days including travel

##### 70% CFT plan review

##### 70% CFT review meeting

##### 70% field review. It is anticipated that the field review will last X days including travel

##### 95% CFT plan review

##### 95% CFT review meeting

##### Environmental Meetings and Field Reviews

##### Attend SEE Team Meeting and Field Review

###### Assume xx days including travel for each meeting

###### Assume xx meetings

##### Attend Interagency Meeting

###### Assume xx days including travel for each meeting

###### Assume xx meetings

##### Attend Public Meeting

###### Assume xx days including travel for each meeting

###### Assume xx meetings

###### Set up meeting room in appropriate format (i.e., open house style, presentation style, sign-in table, court reporter location, exhibits/displays, etc.)

###### Ensure all A/V equipment operating

###### Ensure all staffing personnel know their roles and Exhibits to staff

###### Conduct close out review of PH meeting with SEE Team (what we heard, any possible problem areas, etc)

#### Deliverables for Meetings and Field Reviews

Add/delete deliverables to correspond to the tasks above. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

###### CFT Meeting Minutes

## QA/QC

Evidence that the QA/QC processes have not been performed, may initiate a Quality Assurance Audit (QAA) of the A/E’s QA/QC processes and procedures by CFLHD.  CFLHD will determine the need for a QAA based on the type and volume of deficiencies discovered.  The CFLHD Project Manager will coordinate the audit with the A/E Project Manager in the event a QAA is necessary to confirm that the required QA/QC checks and reviews have been accomplished.  The A/E will be responsible for taking action to correct the specific deficient item or condition, and taking action to prevent recurrence of the deficiencies, with the focus on prevention, not correction.  The A/E Project Manager will assemble all checking documents and a copy of all deliverables for the QA audit.  Randomly scheduled quality assurance audit(s) to review QA/QC documents will also be conducted to verify compliance with the established QA/QC procedures.  It will be necessary for the A/E to furnish a facility and assistance to facilitate the audit(s).    When requested, provide QA/QC documentation for CFLHD review, including check plans, checked computations, GEOPAK files and design notes to substantiate compliance with the QA/QC process.

##### Verify that work produced by subconsultants meet the needs of the client, complies with regulatory and contractual requirements, and that work is consistent with the design intent and can be integrated into the broader project, balancing risk between project constraints and good engineering judgment.  Provide for back checking by the subconsultant of project deliverables to assure that the technical recommendations reflect the evolution of the project and reflect the intent of the recommendations.  This work is included in the subconsultant markup and will not be paid for separately.

##### Ensure that all work is performed in accordance with the established QA/QC plan, as supplemented by a Project-specific Quality Plan (PQP)

###### Include a process whereby all documents and supporting calculations submitted for review are fully checked by a qualified individual other than the Originator before being released.  Do not release any document that does not meet an acceptable level of quality.  Complete QA/QC reviews as required to comply with the established QA/QC procedures.  Use the approved plan for the duration of the task order to ensure that all products adequately conform to accepted CFLHD design practices, comply with all CFLHD design standards, are accurate and of high quality.

###### Mark all QC review documents with a tracking stamp to create a record of the date and responsible person(s) completing the review.

###### Furnish a Quality Assurance Certificate of Compliance for each product released.  The “Quality Assurance Certificate of Compliance” for all deliverables is to contain the statement “This is to certify that the documents submitted have been produced in accordance with established QA/QC procedures and meet an acceptable quality level.”  The certification shall be signed by the Responsible Engineer (Originator), Reviewer(s), Project Manager, and approved for distribution by a management level Approving Official.  Subconsultants shall submit Certificates of Compliance meeting the same requirements as the consultant for all documents prepared by them.  The A/E firm is responsible for the formulation, implementation, and administration of their QA/QC program.

##### Develop a Project-specific Quality Plan establishing the requirements for preparation, performance, and maintenance of project specific quality activities.  The PQP in conjunction with the QA/QC plan govern project quality.

###### Provide for a QC activity schedule that lists the significant QC activities, including; reviews, management audits, QC milestones; duration of each activity; where in the process it occurs; a description of the QC activity; list of the individual(s), including title, who are assigned as reviewers of those tasks; and the persons responsible for quality assurance, including who has the authority to sign certificates of compliance.  Provide resource hours for each reviewer.

###### List subconsultants and specialists employed during execution of the task order and the QA activities necessary to ensure compliance with contractual requirements.

###### Define the technical aspects vital to the quality of the project and analyze the level of risk associated with those efforts.  Include a narrative describing the impacts for each activity identified as having a high level of risk and the measures taken to mitigate the risks.

###### Reference any written procedures for quality applicable to the project, including quality requirements defined in the various sections of task orders.

###### Provide for periodic review and updating of the QC activity and resource schedules to address changes in personnel, quality activities, and dates.

##### Conduct an evaluation of the QA/QC procedures at the conclusion of the task order to determine and document problems encountered areas for improvement, mistakes and lessons learned, outstanding features, and development of a corrective action plan to address QA/QC deficiencies.  Include an opportunity for CFLHD’s Project Manager to provide comments on the findings before finalization.   Transmit the findings to CFLHD’s Project Manager and file the findings for future quality improvement initiatives and reference.

#### Deliverables for QA/QC

###### Project-specific Quality Plan

###### Quality Assurance Certificate of Compliance for each deliverable

###### Evaluation of QA/QC procedures

## Materials and Construction Support During Design (P3 Activities C3, MAT1, and MAT2) (CFL Internal Projects Only)

The following list of typical tasks is based on and supplement the documents referenced in Section V of this SOW and the CFLHD Standard P3 Template Activities. However, it may be appropriate to add, delete, or modify tasks to meet project specific requirements. This activity is for CFL Internal Projects ONLY.

#### Materials Recommendations (MAT1 Activity)

Review (1) Interim Geotechnical Memoranda (G2 activity); (2) Pavement Field Investigation Plan; (3) Pavement Field Investigation Summary Memo; and (4) Preliminary Pavement Recommendations Technical Memo (V1 activities).  Provide Materials recommendations for incorporation into Draft Final Geotechnical Report (support of G3 activity) Pavement Field Investigation Plan (support of V1 activity) and Draft Pavement Report (support of V2 activity).

##### Review Interim Geotechnical Memoranda and make recommendations for use in DRAFT Final Geotechnical Report.

###### Review field investigations data contained in Interim Geotechnical Memoranda relative to soil/aggregate/water and electrochemical (i.e. soil corrosivity) testing for cut/fill materials, materials sources and buried structures.

###### Provide Materials recommendations for use in DRAFT Final Geotechnical Report pertaining to materials suitability as well as types of materials (i.e. cement type) and structures (i.e. culvert type) required for construction.

##### Review and make recommendations to Pavement Field Investigation Plan and Preliminary Pavement Recommendations Technical Memos for use in Draft Pavement Report.

###### Review Pavement Field Investigation Plan and provide Materials recommendations relative to sampling and testing (i.e. types of test/analysis, selected tests and estimated number of tests).

###### Review Pavement Field Investigation Summary and Preliminary Pavement Recommendations Technical Memos and provide Materials recommendations for use in Draft Pavement Report pertaining to material suitability, types of materials, materials recycling and overall constructability of the pavement structural section.

#### Deliverables for MAT1 Activities

Add/delete deliverables to correspond to the tasks above. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

###### Materials Recommendations for Draft Final Geotechnical Report.

###### Materials Recommendations for Pavement Field Investigation Plan.

###### Materials Recommendations for Draft Pavement Report.

#### Materials Final Recommendations (MAT2 Activity)

Review Draft Pavement Report (V1 activity).  Provide Materials recommendations and sign-off on the Final Pavement Report (support of V2 activities).  Identify and develop Materials Special Contract Requirements for the 70% Plans, Specifications and Estimates Package.

##### Review and sign-off of FINAL Pavements report.

###### Review Draft Pavement Report and provide Materials recommendations for use in Final Pavement Report pertaining to material suitability, types of materials, materials recycling and overall constructability of the pavement structural section.  Sign Final Pavements report.

##### Identify and/or develop special contract requirements and specifications for use in the 70% Plans, Specifications and Estimates Package relative to materials, testing, equipment and construction processes for the pavement structural section and other structures.

#### Deliverables for MAT2 Activities

Add/delete deliverables to correspond to the tasks above. Coordinate number of copies with COTR/PM. Number of copies and submittal dates shall be shown in Section IV, Deliverables and Schedule.

###### Materials Recommendations for Final Pavement Report.

###### Materials Special Contract Requirements for 70% Plans, Specifications and Estimates Package.

#### Construction Support During Design (C3 Activity)

##### Construction support during design

###### Hours for plan reviews are included in section M. Meetings and field reviews.

# FHWA FURNISHED PROPERTY/DATA

CFLHD will provide the following to facilitate successful completion of the project.  The Consultant shall notify the COTR of apparent errors and omissions discovered in the data supplied.

General Data:

###### Design Scoping Report Outline: http://www.cflhd.gov/Project_Management/scoping_outlines.cfm

###### Design Technical Memorandum Example

###### http://www.cflhd.gov/

Survey Data:

###### Aluminum caps for Control Points.

ROW Data:

Electronic Files:

###### Sample r/w documents:

R-O-W plan set

Legal descriptions

R1, R2, and R3 Checklists found on www.cflhd.gov/design/survey-map-row/

Hard copies:

###### Sample right-of-way plans and legal descriptions

Highway Design Data:

###### Project Engineer (PE) Notebook Checklist

###### CFLHD Highway Design Standards Form

Bridge/Structure Data:

###### FLH Bridge Office Microstation V8 new units Standards are located at http://www.cflhd.gov/design/_documents/structure/microstation-standards-V8-new-units.pdf

###### FLH Bridge Office Microstation V8 standards are located at http://www.cflhd.gov/design/_documents/structure/microstation-standards-V8.pdf

###### FLH Bridge Office Plan and TS&L preparation guidelines are located at http://www.cflhd.gov/design/_documents/structure/bridge_plan_checklist.pdf

###### FLH Bridge Office Load Rating form is located at http://www.cflhd.gov/design/_documents/structure/load-rating-form.pdf

###### Structure Design Criteria template is located at http://www.cflhd.gov/design/_documents/structure/structure-design-criteria.doc

# DELIVERABLES AND SCHEDULE

Below is an alternate Deliverable Schedule Table. Use one or the other.

| Task | Deliverable | # of Copies | Submittal Date | Comments Return Date |
| --- | --- | --- | --- | --- |
| Project Management |
| Project Development Planning Milestone |
| 15% Project Milestone |
| 30% Project Milestone |
| 50% Project Milestone |
| 70% Project Milestone |
| 95% Project Milestone |
| 100% Project Milestone |
| Project Engineer’s Package |

| Milestone Activity Schedule |
| --- |
| Milestone | Completion Date |
| 30% Field Review |  |
| 50% Field Review |  |
| 70% Field Review |  |
| 95% External Review |  |
| Advertisement |  |

# WORK PERFORMANCE SPECIFICATIONS, QUALITY STANDARDS AND REPORTING REQUIREMENTS

The proposal should include the information described under Section C, Article II.D and E of the contract, including a fee proposal itemized for activities listed under II. Work Required, and a discussion of methods used to accomplish any work element that is not fully understood or not adequately described in this Scope of Work (SOW).

This Task Order does not include payment for errors and/or omissions by the Consultant in the course of performing the work herein. Such errors and omissions are to be corrected at the Consultant’s expense.

Each product is expected to meet an Acceptable Quality Level (AQL) with respect to the thoroughness and appropriateness of the data collection, analysis and recommendations, the clarity of presentation, and the accuracy of the completed products.  Work conducted according to guidelines recommended in the PDDM and documents referenced below, and satisfying any specific requirements of this SOW, will meet the thoroughness, appropriateness and clarity criteria of the AQL.  Where the Standard of Practice within CFLHD currently differs from the PDDM, work should follow the current Standard of Practice.  The A/E contractor should assure work products are accurate and of high quality through an established and documented quality control and assurance (QA) process.  CFL staff will be responsible for evaluation of the quality of work throughout this project.  CFL Staff will participate in correspondence, meetings, site visits, and review of products.  CFL review is not QA of the Consultant’s work; the purpose is to understand the product and to impart CFL institutional experience with the site, customer, project features and potential construction contractors.  Also, CFL review is to evaluate the level of risk taken by the government (which is implied by the type of investigation and analysis conducted, the selected design criteria, and the quality of the A/E contractor’s products) and to evaluate if that level of risk is consistent with other similar CFL projects and/or is planned for.

Written documents to be provided to FHWA related to this project will be delivered in electronic and hard copies.  Documents will be provided in the following software formats unless specifically amended otherwise by the COTR in writing:

Application				    Software

Word Processing				Microsoft Word

Spreadsheet					Microsoft Excel

CADD						MicroStation

Highway Design				Geopak

Engineer’s Estimate			EES Program (available on FTP site)

The baseline technical standards and guidelines to be used on this project are as follows:

Geotechnical:

###### Electronic versions of geotechnical documents, if available, can be found at: http://www.fhwa.dot.gov/bridge/geopub.htm

###### FHWA-HI-97-021: Geotechnical and Foundation Engineering Module 1 - Subsurface Investigations

###### FHWA-NHI-00-043: Mechanically Stabilized Earth Walls and Reinforced Soil Slopes Design and Construction Guidelines, 2001

###### FHWA-SA-97-070: Micropile Design and Construction Guidelines – Implementation Manual, 2000

###### FHWA-IF-03-017: Geotechnical Engineering Circular No. 7 – Soil Nail Walls, 2003

###### FHWA-IF-99-015: Geotechnical Engineering Circular No. 4 – Ground Anchors and Anchored Systems, 1999

FHWA Checklist and Guidelines for Review of Geotechnical Reports and Preliminary Plans and Specifications. http://www.fhwa.dot.gov/bridge/checklist.htm

Pavements:

###### Specific Technical and Reporting Requirements: http://www.cflhd.gov/pavement_guidelines

###### AASHTO Guide For Design of Pavement Structures (1993 edition)

###### Basic Asphalt Recycling Manual, 2001 Edition, FHWA NHI 01-22

###### Techniques for Pavement Rehabilitation, FHWA-HI-98-033

Highway Design:

###### Manual on Uniform Traffic Control Devices (MUTCD).  DOT, FHWA, Latest Edition, including all errata.  http://mutcd.fhwa.dot.gov/

###### A Policy on Geometric Design of Highways and Streets, AASHTO, Latest Edition

###### Roadside Design Guide, AASHTO, Latest Edition

Bridge/Structure Design:

###### AASHTO LRFD Bridge Design Specifications –   3rd Edition, 2004, with current interim revisions.

###### AASHTO Standard Specification for Highway Bridges - 17th Edition, 2002

###### Manual for Condition and Evaluation and Load and Resistance Factor Rating (LRFR) of Highway Bridges, 2003, with current interim revisions.

###### Submit the following items in a bound format other than D-ring binders:

Structure selection report

Design notes

Independent check notes

Load rating

Structural quantities and unit cost analysis

###### Provide CADD bridge drawings on CD-ROM.  Provide drawings with true scales on 11x17 size sheets, reference files detached, and with A/E contractor logo and PE stamp on all plan sheets.

General:

###### Latest Federal Lands Highway Project Development and Design Manual (FLH PDDM)  http://www.wfl.fhwa.dot.gov/design/manual/

###### CFL division procedures available via CFLHD Project Development Home Page http://www.cflhd.gov/design/index.cfm

###### CFLHD CADD Manual and Sample Plans

###### http://www.cflhd.gov/cadd/caddStandLinks.cfm

###### Standard Specifications for the Construction of Roads and Bridges on Federal Highway Projects, FP-03

###### CFLHD Guidance for Sealing and Signing Documents

###### http://www.cflhd.gov/Project_Management/policies.cfm

###### U.S. Government references can be obtained from the National Technical Information Service (NTIS), Springfield, VA 22161, (703) 487-4650, www.ntis.gov. FHWA references are available from the FHWA Reports Center, 9701 Philadelphia Ct., Unit Q, Lanham, MD 20706, (301) 577-0818, FAX (301) 577-1421. All other references must be obtained from their respective sources. AASHTO publications can be ordered by calling 1-(800)-736-9014.

While this list is not all-inclusive, the publications listed will provide the consultant with enough information to understand this scope of work.

# PERIOD OF PERFORMANCE

Work will begin immediately after award of the task order to the A/E and all work will be completed by Month, Date, Year.

# CONTRACTING OFFICER’S TECHNICAL REPRESENTATIVE & CROSS FUNCTIONAL TEAM

Close and continuous coordination with the COTR and other FHWA personnel with special expertise will be required. All communications affecting the project will be through the COTR.

The COTR for this task order will be Mr./Ms.            .  Mr./Ms. can be reached at the following address:

FHWA-CFLHD, HFPM-16

12300 W. Dakota Ave., Suite ###

Lakewood, CO  80228

(720) 963-3###, FAX (720) 963-3###

Email: first.last@fhwa.dot.gov

FHWA-CFLHD Cross Functional Team

Project Manager:

Utilities:

Environment:

Survey:

ROW Documents:

Geotechnical:

Pavements:

Hydraulics:

Highway Design:

Bridge Design:

Construcition

QA/QC:

Safety:

# VII.  PAYMENT

See Base Contract

# Text boxes

# A/E Projects:  Use all text except Section O. Materials and Construction Support – change blue text to black

CFL Internal Projects:  Delete all blue text

Hidden Text:  To turn on/off; 1) select ¶ from the toolbar to toggle or 2)Tools>Options>View>Formatting Marks – Select/deselect hidden text.  Will not print unless Print>Options>Hidden Text is selected

******Delete this text box prior to finalizing SOW*******