## Sheet1
Attachment 2
Project Classification Index - PCI
GUIDELINES FOR CONSTRUCTION /PROJECT MANAGEMENT SUPPORT OF LEASE PROJECTS
Project |  | Tenant Improvement Tier |  | Size |  | Complexity of Construction |  | Distance from Regional Office |  | Political Sensitivity |  | Total Points
|  |  | + |  | + |  | + |  | + |  | = | 0
|  | 0=Tier 0-1 |  | 0 = Less than 10K SF |  | 0 = Basic Office |  | 0 = < 20 miles |  | 0 = Little or no sensitivity
|  | 1=Tier 2-3 |  | 1 = > 10K - 20K SF |  | 1 = Standard w/Special items |  | 1 = >20 - 50 miles |  | 1 = Moderate sensitivity
|  | 2=Tier 4-5 |  | 2 = > 20K - 50K SF |  | 2 = Complex Buildout |  | 2 = >50 - 100 miles |  | 2 = High Local Sensitivity
|  | 3=Tier 6-7 |  | 3 = > 50K + - 100K SF |  | 3 = Highly Complex Buildout |  | 3 = >100 miles |  | 3 = High Overall Sensitivity
|  |  |  | 4 - > 100K + SF |  | Plus
0 + Existing Standard Building
1+ Historic Building*
1+ New Construction
1+ Critical Seismic Zone
Level of Effort | Total Points from Above |  | Team Members Required** |  |  | Minimum Construction Management Activities
LEVEL 1 | 1 - 5 |  | Realty Specialist, Building Manager, Agency Representative, Estimator |  |  | Coordinate life safety review, evaluate lessor's pricing to verify proper separation of shell and TI costs, conduct preconstruction meeting, conduct periodic construction meetings and inspections, prepare minutes of meetings and distribute to team members, perform final inspection and accept space, prepare IGEs for lessor's TI proposal (if insufficient competitive bids) and for change orders, verify punch list items are completed. Davis Bacon interviews if new construction.
LEVEL 2 | 6 - 9 |  | Realty Specialist, Building Manager, Agency Representative, Estimator, GSA in-house professional staff (A/E) |  |  | Coordinate life safety review, evaluate lessor's pricing to verify proper separation of shell and TI costs, review DIDs, lessor's construction drawings and submittals, attend preconstruction meeting, conduct periodic construction meetings and inspections, prepare minutes of meetings and distribute to team members, perform final inspection and accept space, prepare IGEs for lessor's TI proposal (if insufficient competitive bids) and for change orders, assist in negotiating price proposals, verify punch list items are completed. Davis Bacon interviews if new construction. GSA in-house professional staff provides technical services for construction administration and advises Realty Contracting Officer.
LEVEL 3 | 10 - 13 |  | Realty Specialist, Building Manager, Agency Representative, GSA in-house professional staff (A/E) or Contract Construction Manager, Fire Safety Engineer |  |  | Coordinate life safety review, review DIDs, lessor's construction drawings and submittals, evaluate lessor's pricing to verify proper separation of shell and TI costs, attend preconstruction meeting, conduct periodic construction meetings and inspections, prepare minutes of meetings and distribute to team members, perform final inspection and accept space, prepare IGEs for lessor's TI proposal (if insufficient competitive bids) and for change orders, negotiate price proposals and prepare PNM for contracting officer review and approval, verify punch list items are completed. Davis Bacon interviews if new construction. GSA in-house professional staff or construction manager as agent for GSA attends all construction meetings and provides technical services for construction administration.
LEVEL 4 | 14 and over |  | Realty Specialist, Building Manager, Agency Representative, GSA in-house professional staff (A/E), Fire Safety Engineer, Contract Construction Manager |  |  | Coordinate life safety review, review DIDs, lessor's construction drawings and submittals, evaluate lessor's pricing to verify proper separation of shell and TI costs, attend preconstruction meeting, conduct periodic construction meetings and inspections, prepare minutes of meetings and distribute to team members, perform final inspection and accept space, prepare IGEs for lessor's TI proposal (if insufficient competitive bids) and for change orders, negotiate price proposals and prepare PNM for contracting officer review and approval, verify punch list items are completed. Davis Bacon interviews if new construction. GSA in-house professional staff or construction manager as agent for GSA attends all construction meetings and provides technical services for construction administration. Construction manager is full time assignment.
*If the lease is in a building on or eligible for the Historic Register, provide a qualified preservation architect.
** On broker contract acquisitions, the broker and its staff may provide post-award services in accordance with the broker contract.