| Monitoring Priorities and Indicators | Status of APR Data/SPP Revision Issues | OSEP Analysis/Next Steps |
| --- | --- | --- |
| - Percent of infants and toddlers with IFSPs who receive the early intervention services on their IFSPs in a timely manner. [Compliance Indicator] | VIDH’s FFY 2006 reported data for this indicator are 91%. These data represent slippage from the FFY 2005 data of 100%. VIDH did not meet its FFY 2006 target of 100%. | VIDH must review its improvement activities and revise them, if appropriate, to ensure they will enable VIDH to provide data in the FFY 2007 APR, due February 1, 2009, demonstrating that VIDH is in compliance with the timely service provision requirements in 34 CFR §§303.340(c), 303.342(e) and 303.344(f)(1), including reporting correction of the noncompliance identified in the FFY 2006 APR. |
| - Percent of infants and toddlers with IFSPs who primarily receive early intervention services in the home or programs for typically developing children. [Results Indicator] | VIDH’s FFY 2006 reported data for this indicator are 97.44%. These data represent progress from the FFY 2005 data of 96%. VIDH’s data reflect a high level of performance for this indicator. VIDH met its FFY 2006 target of 84%. | VIDH’s actual target data for provision of services to infants and toddlers in natural environments are at or greater than 95%. There is no expectation that an increase in that percentage is necessary. OSEP appreciates VIDH’s efforts to improve performance and, as noted below under Indicator 9, VIDH’s correction of noncompliance related to this indicator. OSEP expects that VIDH will continue to monitor to ensure that IFSP teams are making service setting decisions on an individualized basis and in compliance with 34 CFR §§303.12, 303.18, and 303.344(d)(1)(ii). |
| - Percent of infants and toddlers with IFSPs who demonstrate improved: A. Positive social-emotional skills (including social relationships); B. Acquisition and use of knowledge and skills (including early language/ communication); and C. Use of appropriate behaviors to meet their needs. [Results Indicator; New] | VIDH’s FFY 2006 reported progress data for this indicator are: 06-07 Infant and Toddler Outcome Progress Data; Social Emotional; Knowledge & Skills; Appropriate Behavior. a. % of infant & toddlers who did not improve functioning.; 0%; 0%; 8%. b. % of infant & toddlers who improved but not sufficient to move nearer to functioning comparable to same-aged peers.; 20%; 27%; 23%. c. % of infant & toddlers who improved to a level nearer to same-aged peers but did not reach it.; 27%; 33%; 23%. d. % of infant & toddlers who improved functioning to reach a level comparable to same-aged peers.; 40%; 27%; 15%. e. % of infant & toddlers who maintained functioning at a level comparable to same-aged peers.; 13%; 13%; 31%. VIDH provided improvement activities for this indicator through 2009. VIDH did not provide improvement activities for this indicator covering the remaining year of the SPP (through FFY 2010). | VIDH reported the required progress data but did not provide improvement activities for FFY 2010. VIDH must provide progress data and improvement activities for this indicator covering the remaining year of the SPP (through FFY 2010) in the FFY 2007 APR, due February 1, 2009, and baseline data and targets with the FFY 2008 APR, due February 1, 2010. |
| 4. Percent of families participating in Part C who report that early intervention services have helped the family: A. Know their rights; B. Effectively communicate their children's needs; and C. Help their children develop and learn. [Results Indicator] | VIDH’s reported data for this indicator are: FFY 2005 Data; FFY 2006 Data; FFY 2006 Target. A. Know their rights.; 92%; 86%; 92%. B. Effectively communicate their children’s needs.; 83%; 86%; 83%. C. Help their children develop and learn.; 92%; 86%; 92%. These data represent progress for 4B and slippage for 4A and 4C. VIDH met its FFY 2006 target for Indicator 4B and did not meet its targets for Indicator 4A and 4C. | In its description of its FFY 2006 data, VIDH did not address whether the survey response group was representative of the population in the Virgin Islands. In the FFY 2007 APR, due February 1, 2009, VIDH must address whether its FFY 2007 data are based on a survey response that is representative of its population. OSEP appreciates VIDH’s efforts to improve performance for 4B and looks forward to VIDH’s data demonstrating improvement in performance for 4A and 4C in the FFY 2007 APR, due February 1, 2009. |
| 5. Percent of infants and toddlers birth to 1 with IFSPs compared to: A. Other States with similar eligibility definitions; and B. National data. [Results Indicator] | VIDH’s FFY 2006 reported data for this indicator are 1.19%. These data represent slippage from the FFY 2005 data of 1.38%. VIDH met its revised FFY 2006 target of 1.04%. | In the FFY 2004 SPP and FFY 2005 APR, VIDH modified its targets for this indicator and OSEP approved the revisions. However, the FFY 2006 APR target did not reflect this change. VIDH must correctly report its targets in its FFY 2007 APR. OSEP appreciates the State’s efforts to improve performance. |
| 6. Percent of infants and toddlers birth to 3 with IFSPs compared to: A. Other States with similar eligibility definitions; and B. National data. [Results Indicator] | VIDH’s FFY 2006 reported data for this indicator are 2.30%. These data represent slippage from the FFY 2005 data of 2.58%. VIDH did not meet its revised FFY 2006 target of 2.43%. | In the FFY 2004 SPP and FFY 2005 APR, VIDH modified its targets for this indicator and OSEP approved the revisions. However, the FFY 2006 APR target did not reflect this change. VIDH must correctly report its targets in its FFY 2007 APR. OSEP looks forward to VIDH’s data demonstrating improvement in performance in the FFY 2007 APR, due February 1, 2009. |
| 7. Percent of eligible infants and toddlers with IFSPs for whom an evaluation and assessment and an initial IFSP meeting were conducted within Part C’s 45-day timeline. [Compliance Indicator] | VIDH’s FFY 2006 reported data for this indicator are 94.44%. These data represent slippage from the FFY 2005 data of 100%. VIDH did not meet its FFY 2006 target of 100%. VIDH did not account for untimely evaluations. | VIDH must account for untimely evaluations in the FFY 2007 APR, due February 1, 2009. VIDH must review its improvement activities and revise them, if appropriate, to ensure they will enable the State to provide data in the FFY 2007 APR, due February 1, 2009, demonstrating that the State is in compliance with the 45-day timeline requirements in 34 CFR §§303.321(e)(2), 303.322(e)(1), and 303.342, including reporting correction of the noncompliance identified in the FFY 2006 APR. |
| 8. Percent of all children exiting Part C who received timely transition planning to support the child’s transition to preschool and other appropriate community services by their third birthday including: A. IFSPs with transition steps and services; [Compliance Indicator] | VIDH’s FFY 2006 reported data for this indicator are 100%. These data remain unchanged from the FFY 2005 data of 100%. VIDH met its FFY 2006 target of 100%. | OSEP appreciates VIDH’s efforts in achieving compliance with the IFSP transition content requirements in 34 CFR §§303.148(b)(4) and 303.344(h). |
| 8. Percent of all children exiting Part C who received timely transition planning to support the child’s transition to preschool and other appropriate community services by their third birthday including: B. Notification to LEA, if child potentially eligible for Part B; and [Compliance Indicator] | VIDH’s FFY 2006 reported data for this indicator are 100%. These data remain unchanged from the FFY 2005 data of 100%. VIDH met its FFY 2006 target of 100%. | OSEP appreciates VIDH’s efforts in achieving compliance with the LEA notification requirements in 34 CFR §303.148(b)(1). |
| 8. Percent of all children exiting Part C who received timely transition planning to support the child’s transition to preschool and other appropriate community services by their third birthday including: C. Transition conference, if child potentially eligible for Part B. [Compliance Indicator] | VIDH’s FFY 2006 reported data for this indicator are 100%. These data represent progress from the FFY 2005 data of 94%. VIDH reported that the one finding of noncompliance identified in FFY 2005 related to this indicator was corrected in a timely manner. | VIDH reported that noncompliance identified in FFY 2005 with the timely transition conference requirements in 34 CFR §303.148(b)(2)(i) (as modified by IDEA section 637(a)(9)) was corrected in a timely manner. OSEP appreciates VIDH’s efforts in achieving compliance with the requirements in 34 CFR §303.148(b)(2)(i) (as modified by IDEA section 637(a)(9)). |
| 9. General supervision system (including monitoring, complaints, hearings, etc.) identifies and corrects noncompliance as soon as possible but in no case later than one year from identification. [Compliance Indicator] | VIDH’s FFY 2006 reported data for this indicator are 100%. These data represent progress from the FFY 2005 data of 76%. VIDH met its FFY 2006 target of 100%. | VIDH reported correction of all prior noncompliance for three non-priority areas and one priority area as follows: (1) IFSPs must include present levels of function as required in 34 CFR §303.344(a); (2) IFSP reviews must be conducted every six months as required in 34 CFR §303.342; (3) IFSP meetings must be held annually as required in 34 CFR §303.342(c), and (4) Justification statements must be included in IFSPs as required in 34 CFR §303.344(d)(ii). VIDH also reported timely correction of one finding identified in FFY 2005. OSEP appreciates VIDH’s efforts in timely correcting noncompliance in accordance with IDEA section 635(a)(10)(A) and 34 CFR §303.501. In responding to Indicators 1 and 7, VIDH must specifically identify and address the noncompliance identified in this table under those indicators. VIDH’s FFY 2007 Part C grant has Special Conditions (related to fiscal issues), to which OSEP will respond in VIDH’s FFY 2008 Part C grant letter. |
| 10. Percent of signed written complaints with reports issued that were resolved within 60-day timeline or a timeline extended for exceptional circumstances with respect to a particular complaint. [Compliance Indicator] | VIDH reported that it did not receive any signed written complaints during the FFY 2006 reporting period. | OSEP looks forward to reviewing VIDH’s data in the FFY 2007 APR, due February 1, 2009. |
| 11. Percent of fully adjudicated due process hearing requests that were fully adjudicated within the applicable timeline. [Compliance Indicator] | VIDH reported that it did not receive any due process hearing requests during the FFY 2006 reporting period. | OSEP looks forward to reviewing VIDH’s data in the FFY 2007 APR, due February 1, 2009. |
| 12. Percent of hearing requests that went to resolution sessions that were resolved through resolution session settlement agreements (applicable if Part B due process procedures are adopted). [Results Indicator] | Not applicable. | This indicator does not apply to VIDH because VIDH has not adopted the Part B due process procedures. |
| 13. Percent of mediations held that resulted in mediation agreements. [Results Indicator] | VIDH reported that no mediations were held during the FFY 2006 reporting period. | OSEP looks forward to reviewing VIDH’s data in the FFY 2007 APR, due February 1, 2009. |
| 14. State reported data (618 and State Performance Plan and Annual Performance Report) are timely and accurate. [Compliance Indicator] | VIDH’s FFY 2006 reported data for this indicator are 87.6%. VIDH did not meet its FFY 2006 target of 100%. | VIDH must review its improvement activities and revise them, if appropriate, to ensure they will enable VIDH to provide data in the FFY 2007 APR, due February 1, 2009, demonstrating that VIDH is in compliance with the timely and accurate data requirements in IDEA sections 616, 618, and 642 and 34 CFR §§76.720 and 303.540. |