## Cover
Operating Plans
Updated to 2006.06.01
2006

## Detail
2008 Fiscal Year Operating Plan
| MAS/ DAS | MAS/ Offc | Cooperator | # | Category | Activity: Brief Description | Destination/ Traveler(s)/ Breakdown/ Additional Description | Anticipated Start |  | Anticipated End | Cooperator's Spending | Requested Priority | Admin Funds Requested
1 | Svcs | OSI | AWA | 1 |  | Completion of new database of Chinese Widget related resources and access on AWA and Commerce websites. |  | 2005-10-01 |  | 2007-03-31 | 30000 |  | 0
1 | Svcs | OSI | AWA | 2 |  | AWA China Program Advisory Committee and Project Team Ongoing Expenses |  | 2006-10-01 |  | 2007-09-30 | 8000
|  |  | AWA | 3 |  | Export successes, evaluations, reports, case studies, interviews. |  | 2006-10-01 |  | 2007-09-30 | 22000
|  |  | AWA | 4 |  | Develop user fees, sponsorships, advertising to make program self-sustaining. |  | 2006-10-01 |  | 2007-09-30 | 30000
|  |  | AWA | 5 |  | Website development: search capacity, research on U.S. firms in China, DUNS-like reports on cities in China. |  | 2006-10-01 |  | 2007-09-30 | 48000
|  |  | AWA | 6 |  | Publicity and Advertising |  | 2006-10-01 |  | 2007-09-30 | 35000
|  |  | AWA | 7 |  | Printing and Mailing |  | 2006-10-01 |  | 2007-09-30 | 30000
|  |  | AWA | 8 |  | Demonstration projects in select strategic Chinese cities led by AWA with participation of member firms |  | 2006-10-01 |  | 2007-09-30 | 45000
|  |  | AWA | 9 |  | 2-week Training for senior China SACH delegation. | Santa Fe & Taos, NM. TL Sara Vaughan (MAS/OSI) Airfare = 700, Hotel @ 4 nights = 300, M&IE @ 4 days @ 59= 236, Transportation = 250, Total = $1,486 | 2006-10-08 |  | 2006-10-23 | 20000 | 1 | 1486
|  |  | AWA | 10 |  | MDCP 1st Quarterly Team Meeting, Washington, DC |  | 2006-10-13 |  | 2006-10-13 | 1000 |  | 0
|  |  | AWA | 11 |  | AWA 5th Annual Member Training Workshop: "Doing Business in China", Washington, DC, in conjunction with visit of Chinese delegation from State Administration of Cultural Heritage (SACH) |  | 2006-10-16 |  | 2006-10-17 | 10000 |  | 0
|  |  | AWA | 12 |  | Chinese Mayor's Training Groups to educate American Widget philosophy and showcase US Widget firms--Jiangsu & Chongqing (staff prep time and travel, honorarium, etc); Chinese mayors will visit San Francisco, San Antonio, Chicago, Minneapolis, NYC, Philadelphia, Annapolis, and Washington DC. | New York: 1 ITA team mbr: Airfare = 225, 2 nights hotel @ 274 =548, M&IE@ 2 days @ 64 =128, Transport= 100, Other = 50, Total =$1,051 | 2006-11-01 |  | 2006-11-15 | 45000 | 1 | 1051
|  |  | AWA | 13 |  | MDCP 2nd Quarterly Team Meeting, Washington, DC |  | 2007-01-15 |  | 2007-01-15 | 1000 |  | 0
|  |  | AWA | 14 |  | Organize/Recruit for Shanghai Trade Missions in May 2007 (includes Widget and marketing travel) |  | 2007-02-15 |  | 2007-04-15 | 5000 |  | 0
1 | Svcs | OSI | AWA | 15 |  | Publication in Mandarin of a quarterly periodical (similar to AWA Widget Magazine) or annual publication on Widget issues for China market. |  | 2007-03-01 |  | 2007-09-30 | 40000 |  | 0
1 | Svcs | OSI | AWA | 16 |  | Trade Mission | Shanghai : 1 ITA team mbr: Airfare = 1,500, 5 nights hotel @ 196 = 980, M&IE @ 124 @ 6 days = 744, Transportation = 200, Total = $3,424 | 2007-04-14 |  | 2007-04-18 | 30000 | 1 | 3424
1 | Svcs | OSI | AWA | 17 |  | AWA Annual Conference: sessions on China Initiative& team mtg. | Philadelphia: TL Vaughan, Team Mmbrs Mark Wells & James Fowler, U/S Lavin (keynote at mtg); Amtrak @ 80 x 4 travelers= 320, 3 nights hotel @ 138 x 4 travelers = 1,656; M&IE @ 2 days @ 64 x 4 days = 512, Transportation= 250, Total = $2,738 | 2007-04-30 |  | 2007-05-15 | 30000 | 1 | 2738
|  |  | AWA | 18 |  | AWA Member Training Workshop on Doing Business in China | Seattle: TL Sara Vaughan: Airfare = 530, 3 nights hotel @ 124 = 372, M&IE @ 4 days @ 64 = 256, Transportation = 150, Total = 1,308 | 2007-05-20 |  | 2007-05-21 | 10000 | 1 | 1308
|  |  | AWA | 19 |  | US firms to China for study tour: find export ops via meetings w/China mayors, sen. Widget officials, companies, and DOC offices. | Beijing Chongqing, Guangzhou, Nanjing, Shanghai: TL Sara Vaughan & DAS Guevara: Airfare = 2000 x 2 travelers = 4,000 total 10 nights in hotels in Beijing, @ 1,403 x 2 = 2,806; M&IE @ 11 days = 1,084 x 2 = 2,168, Transport = 400, Total = 9,374 | 2007-06-15 |  | 2007-06-30 | 30000 | 1 | 9374
|  |  | AWA | 20 |  | Chinese Mayor's Training Groups visit San Fran., San Antonio, Chicago, Minneapolis, NYC, Phil., Annapolis, DC. Showcase US Widget firms--Jiangsu & Chongqing. See American Widget philosophy. | San Francisco: 1 ITA team mbr: Airfare = 442, 2 nights hotel @ 140 =280, M&IE @ 64 @ 3 days = 192, Transportation = 100, Total = 1,014 | 2007-08-01 |  | 2007-08-15 | 45000 | 2 | 1014
|  |  | AWA | 21 |  | W/senior ITA official, brief AWA board & meet w/team. | Chicago: TL Sara Vaughan, Mark Wells & James Fowler (ITA Team Members), DAS Guevara: Airfare @ 190 x 4 = 760, 2 nights hotel @ 173 x 4 = 1,384, 2 days M&IE @ 64 x 4 = 512, Transportation = 400, Total = $3,056 | 2007-09-15 |  | 2007-09-15 | 1000 | 1 | 3056
|  |  | AWA | 22
|  |  | AWA | 23
|  |  | AWA | 24
|  |  | AWA | 25
1 | Svcs | OSI | AWA | 26
1 | Svcs | OSI | [6 empty] | - |  | 516000 |  | 23451
Note on I4: Enter dates in the traditional American format, eg. 12/01/2005, but don't be worried when it shows up in ISO format, e.g. 2005.12.01
Note on K4: Enter dates in the traditional American format, eg. 12/15/2005, but don't be worried when it shows up in abbreviated ISO format, e.g. 12.15
Note on D4: [] Choose your cooperator from this drop-down menu.
Note on F4: Use one of these eight (8) categories. - Travel - Transportation of things - Rent, communications, utilities - Prining & reproduction - Other services - Supplies & materials - Equipment - Grants, subsidies, contributions