UNITED STATES DEPARTMENT OF AGRICULTURE

__________________________________________

Office of the Chief Information Officer

Project Management Handbook Appendices

Version 1.0

TABLE OF CONTENTS

Project Charter Template

Scope Statement Template

Project Management Plan Template

Cost Management Plan Template

Earned Value Management Definitions

Scope Management Plan Template

Work Breakdown Structure Example

Quality Management Plan Template

Project Communications Plan Template

Change Management Plan Template

Risk Management Plan Template

Risk Control Form Template

Risk Management Log Template

Staffing Management Plan Template

Procurement Management Plan Template

Project Closeout Report Template

# Project Charter Template

|  | Project Charter |
| --- | --- |
|  | Project Name: |
|  | Date: |
|  | Point of Contact: |

The following are suggested sections for the Project Charter

Approvals

The signatures of the people below relay an understanding in the purpose and content of this document by those signing it.  By signing this document you agree to this as the formal Charter statement sanctioning work to begin on the project described within.

| Position/Title | Name | Date | Phone Number |
| --- | --- | --- | --- |

Purpose

Describe the purpose of the Project charter using the following guidelines.  Do not merely describe the content of the plan, but explain why a Charter is necessary for the project

The purpose of the (XYZ) project charter is to communicate the authorization for the project and the management approach to project participants and external entities.  The project charter lays the groundwork for informed decisions and planning regarding projection direction, outcomes and delivery.

Project Objective

Define the objectives of the project as they relate to the goals and objectives of the organization along the following guidelines

The [Project] will support the following [Organization] strategic goals. For each goal, [Project] objectives are identified. The project plan developed as a result of this project charter will:

Develop a project performance measurement plan to measure performance against these objectives.

Provide a project performance report to report the results.

The [external oversight committee] must approve the project performance measurement plan.

| Organization Strategic Goals | Project Objectives |
| --- | --- |

Summary Scope Statement

The level of detail in this section must be sufficient to allow for detailed scope development in the Project Plan. The Project Manager will develop a more detailed description of the project scope.

Project Authority

Describe the authority of the individual or organization initiating the project, limitations or initial checkpoint of the authorization, management oversight over the project, and the authority of the Project Manager.  Also, ensure that the project initiator has the authority to commit the appropriate resources within the organization.

Project Manager

Explicitly name the Project Manager and define his/her role and responsibility over the project. Also list the Project Manager’s skill sets, and justify their selection for this project.  Depending on the project complexities, this section may describe how the Project Manager will control matrixed organizations and employees.

Project Oversight

Describe department management control over the project. Within the project, internal control should be established to control the day-to-day activities of the project. The Project Manager should manage internal control. External oversight should be established to ensure that the organization’s resources are applied to meet the project and organization’s objectives. Describe or reference a process by which internal and external controls interact. Diagrams should be used where appropriate.

Roles and Responsibilities

Discuss the overall structure of the project organization and its roles and responsibilities throughout the project phases.  Include the roles of identified project stakeholders

Project Constraints

List and describe any identified project constraints. Typically, constraints will impact timing, cost, resources and/or quality.

Project Assumptions

List and describe any identified assumptions.  Assumptions pose a risk to the project and will need further evaluation and validation during subsequent project process phases.

Preliminary Schedule and Cost Estimates

Provide a rough estimate of dates to accomplish key project tasks.  Consider any constraints and assumptions prepared above when considering the preliminary timing. Describe key management checkpoints established by the initiating authority.  Similarly, provide a rough order of magnitude estimate of project costs.

| Management Checkpoint | Evaluation Criteria |
| --- | --- |

RECORD OF AMENDMENTS

| Version | Author | Date | Comments |
| --- | --- | --- | --- |
| 1.0 |  | 7/25/05 | Draft 1. Based on template created for project charter |

# Scope Statement Template

|  | Scope Statement |
| --- | --- |
|  | Project Name: |
|  | Date: DD Mmmm 20yy |
|  | Project Manager: |
|  | Approver: signature |
|  | Approver Name and Title |

Purpose of Scope Statement

Describe the purpose of the scope statement using the following guidelines:

The Scope Statement is distributed to all the project stakeholders for their approval.  It documents a description of the project, including the objectives, planned deliverables, and requirements.  It becomes the baseline document that can only be changed through the process outlined in the Scope Management Plan.

The Scope Statement documents a description of the project, including the objectives, planned deliverables, and requirements.  It becomes the baseline document that can only be changed through the process outlined in the Scope Management Plan.

Project Business Need

Provide the justification in terms of the problems the project will address and/or the improvements it will implement.  The business need impacts the ability to assess project alternatives.

Project History

Provide a short narrative of the events that lead up to project approval.  This helps to put the project description into context and supports the rest of the document.

Project Description/ Objectives

Describe the project in terms of strategy, timing, objectives and deliverables.

Project Product Requirements

Provide a description of the project’s product or service, its use, technical parameters, requirements, etc.

Project Deliverables

Provide the stakeholders a list of the project deliverables.

Project Assumptions and Constraints

Assumptions describe details that are considered to be true or certain that impact the success of the project.  Examples would be available critical personnel or funding.  Constraints describe factors the impact the project such as: budget limitations, organizational policies, statutes or regulations.

Assumptions

Constraints

Quality Assurance Manager Activities

Generally describe the activities of the QA manager as they relate to specific deliverables.  What will the QA manager do to supplement the testing and acceptance process?

Signature Page

The Scope Statement is distributed to all the project stakeholders for their approval.  Signature blocks should be provided for the project sponsor, the project manager and the primary resource managers from organizations such as project users, system owner, procurement, human resources, finance, enterprise architecture and others as appropriate.

RECORD OF AMENDMENTS

| Version | Author | Date | Comments |
| --- | --- | --- | --- |
| 1.0 |  | 07/25/05 | Draft 1 – Based on template created for VA IT scope statements |

# Project Management Plan Template

|  | Project Management Plan |
| --- | --- |
|  | Project Name: |
|  | Date: DD Mmmm 20xx |
|  | Project Manager: |
|  | Approver: signature |
|  | Approver name and title |

The following sections constitute the core areas of the Project Management Plan.

Introduction

Describe the purpose of the Project Management Plan using the following guidelines.

This document contains the plan for executing the xx project.  It forms the basis for all work activities and management efforts associated with the project.  The plan explains the project’s rationale, team structure, scope and objectives.

The information associated within the plan evolves as the project moves through its various stages and will be updated as new information develops about the project.  The Plan is a dynamic document and is expected to go through updates during the life of the project.  The updates will be recorded and maintained as part of the project change management process, which is a contributory portion of the overall project management plan.

Several subsidiary plans are also contained under the umbrella of the project management plan.  These describe the management practices for specific project disciplines (i.e. scope management, schedule management, risk management).  The subsidiary plans are maintained in separate documents that are also updated throughout the life of the project.  A summary description of each subsidiary plan is provided within this project management plan.

General Project Information

Project Governance Documents:

The project charter establishes the project and …

The project scope statement documents a description of the project, including the objectives, planned deliverables, and requirements.

Team Membership

The Team consists of:

Project Manager ….

The Team structure is contained in the Organizational Breakdown Structure, which is discussed elsewhere in this document.  The Team reports to xxx .

Points of Contact

A contact list of team members and other stakeholders is maintained at xxx.  The list contains names, telephone numbers, fax numbers, e-mail addresses and project roles.  The file is updated as contacts are added or removed from the project.

Executive Summary

Approach:

Provide an executive level overview of the project management plan: identify the business need or problem, identify the project goals and objectives, and define the management strategy used to implement the project.

Business Need/Problem:

State the business problem/issue the project will solve.

Project Objectives:

Provide a brief, concise list of what the project will accomplish.

Project Requirements and Scope Statement

See Project Scope Statement Template.

Work Breakdown Structure (WBS)

The project Work Breakdown Structure (WBS) organizes the project by major functions (project management, software design, quality control, etc.), continuous processes (status reporting, financial reporting, etc.), and primary deliverables. It decomposes the work to the level where the actual work is done and labor costs are tracked. These work packages are further decomposed in the schedule.

The WBS is the primary tool for managing the scope of the project.  This simply means that if the work is included within the WBS, it is considered within scope.  If work is not contained within the WBS, it is considered “out of scope” and should not be included in the project’s end product.  The WBS is used to create a time-phased project budget where actual data is collected to generate project performance measurement.

The format can be a tree diagram that resembles an organization chart or an outline format that can be accomplished in a spreadsheet format. It is extremely important to have a consistent numbering system that can tie the WBS to the budget and schedule. A typical numbering format envisions the 1.1.1.1 style, where each number represents a new level of indenture. (see sample in [WBS section])

Organizational Breakdown Structure

Provides a work package based organization chart that defines the communications channels, responsibilities, and the authority of each participating person/unit.

Create a blank ‘tree’ type diagram that looks similar to a Work Breakdown Structure, in order to prepare to assign responsibility for work packages. A spreadsheet type with all the elements of the Work Breakdown Structure listed, including work definitions, is a suggested format. (see sample in [OBS section])

The Organizational Breakdown Structure (OBS) is a diagram showing the hierarchical structure of the organization’s existing departments, units and teams.  The OBS is analyzed against the WBS to determine assignments for the work to be done.  This analysis results in a Resource Assignment Matrix (RAM), which is used to illustrate the connections between the work that needs to be done and the project team members.  Figure 2 conceptually describes how the Resource Assignment Matrix is derived from the WBS and OBS.

The OBS is the primary tool for developing the communications management plan and aids in the development of the project schedule.

Project Schedule

Following the definition of project activities, the activities are associated with time to create a project schedule. The Project Schedule provides a graphical representation of predicted tasks, milestones, dependencies, resource requirements, task duration, and deadlines. The Project Schedule should be detailed enough to show each Work Breakdown Structure task to be performed, the name of the person responsible for completing the task, the start and end date of each task, and the expected duration of the task. The Work Breakdown Structure lowest level work packages can be further decomposed into schedule tasks.(see [Project Schedule section])

A project schedule is created based on the work breakdown structure to encompass the activities associated with developing project deliverables and executing project work.  The Project Schedule contains predicted activities, milestones, dependencies, resource requirements, activity durations, and deadlines.  The Project Schedule shows each activity to be performed, the name of the person responsible for completing the activity, the start and end date of each activity, and the expected duration of the activity.

Cost Estimating

Using the OBS, WBS and the project schedule, cost estimates are developed for the lowest level of the WBS where costs are tracked (this can called the work package level or cost account level – it has also been defined as the level where the OBS intersects with the WBS, thereby identifying responsibility for a portion of the project work). The cost estimates are used during project justification briefings and become the time-phased budget used to measure cost performance (see Cost Management Plan). Additional inputs to cost estimating include resource estimates and risk assessments. Cost estimates should also incorporate a coding structure that can be applied to the organization financial tracking system.

Cost estimating is the process of calculating the cost of required resources for completing the project activities.  Cost estimating derives costs for all resources required including personnel, materials, services or equipment.  Identified risks should also be evaluated and contingencies included in the cost estimating as appropriate.

This process results in a project cost estimate, which is defined as “a quantitative assessment of the likely costs of the resources required to complete project activities” (PMBOK, 2002).  An analysis of the cost estimate provides a determination as to whether the project objectives can be achieved within the project cost constraints.

The estimating process is iterative in nature and may require several iterations to arrive at a final estimate.  Changes in the cost estimates may have impact on the scope, schedule or resource planning of the project.  Likewise, any changes in scope, schedule, quality or resource planning may impact the cost estimate.

Project Management Plan Subsidiary Documents

The following documents are developed when needed during the project life cycle and managed as subsidiary parts of the Project Management Plan. Separate templates are provided to aid development of the subsidiary documents:

The following documents are managed as subsidiary parts of the Project Management Plan.

Staffing Management Plan

The Staffing Management Plan defines the project organization, resource planning (people) and process for managing project staffing.  It describes when and how human resources will be brought onto and taken off of the project.  The Staffing Management Plan provides for orderly and efficient management of human resources within the context of the overall Project Management Plan.

Risk Management Plan

The Risk Management Plan describes how risks are identified, tracked, assessed and responded to.  The plan identifies the tools used to capture identified risks, risk categories, assigned owners, calculated probabilities, identified thresholds or triggers for instigating mitigating action and contingency plans.

Procurement Management Plan

The Procurement Management Plan discusses the scope of procurements that will exist for the EVM project, which include consultants, additional software and licenses, and employee training.  It describes the types of contracts appropriate for the procurement, the solicitation and evaluation processes, and team/stakeholder responsibilities relative to the development of procurement documents.  It discusses the timing of procurements, describing the dependencies between solicitation preparation, contract award and lead times with other aspects of the project, such as design development or deployment.  The procurement plan describes the steps required by the USDA IT acquisition approval process to initiate procurement.

Quality Management Plan

The Quality Management Plan describes the processes the project will use to accomplish project quality assurance and quality control.  The scope of Quality Management for the EVM project includes project reporting, training, contract language and EVM deliverables.  It contains the criteria used to determine acceptable products and the processes used to control quality during the development, deployment and operational phase of the project.

Communications Management Plan

The Communications Management Plan describes how project information is distributed, reviewed, updated and filed.  The plan describes the information product, how it is produced, who produces it, when it is produced and to whom it is distributed.

The plan also describes the communications forums (meetings) used to disseminate information and to escalate issues. Meeting time, purpose, attendees, sample agenda and information product(s) are all captured.

Change Control Plan

The Change Control Plan describes the processes, tools and responsibilities for controlling the necessary changes to project scope, cost and schedule.  The plan discusses change identification, submission, authorization and implementation.  The plan identifies the tools used to track, document and communicate project changes.

Cost Management Plan

The Cost Management Plan describes the process for implementing change control over cost estimates and the project time-phased cost baseline.  This covers budget preparation and maintenance. It details the process for authorizing and expending project funds.  The plan includes the steps taken when the performance measurement system identifies major or minor cost vs. budget variances.  The plan also covers the timing and distribution of cost and performance reports.

Schedule Management Plan

The Schedule Management Plan describes who owns and manages the project schedule, processes that control schedule change, reporting, updating and analysis and the process for establishing a baseline schedule.

Scope Management Plan

The Scope Management Plan discusses the development, baseline and control of the WBS, the primary scope management tool.  The Scope Management Plan also describes how scope changes will be managed and integrated into other project areas, such as cost and schedule.

RECORD OF AMENDMENTS

| Version | Author | Date | Comments |
| --- | --- | --- | --- |
| 1.0 |  | 7/25/05 | Draft 1 – Based on template created for VA IT projects |

# Cost Management Plan Template

|  | Cost Management Plan |
| --- | --- |
|  | Project Name: |
|  | Date: DD Mmmm 20yy |
|  | Project Manager |
|  | Approver: signature |
|  | Approver Name and Title |

The following are suggested sections for the Cost Management Plan:

Purpose of Cost Management Plan

Describe the purpose of the cost management plan using the following guidelines.  Do not merely describe the content of the plan, but why Cost Management is necessary for the project:

The objective of the cost management plan is to make certain that project costs are monitored and controlled and that the project is delivered within budget.

Cost changes, especially for complex projects, are common as project activities are completed and more information and detail become available.  Cost changes can be caused by several factors such as the unavailability of critical resources, material delivery, or cost of new technology.  The objective of the cost management plan is to make certain that project costs are monitored and controlled and that the project is delivered within budget.

Roles and Responsibilities

Describe how the following project participants, at a minimum, perform in the planning and execution of project cost management

Project Sponsor

Project Manager

Project Team

Project Stakeholders

Project Budget

Describe the iterative process of preparing high-level conceptual budget estimates during the project initiation phase and evolving to a detailed, time-phased, WBS based budget during the planning phase of the project. Describe the process for baselining the budget to enable performance measurement. Describe how the budget will be maintained and the process that will be followed if budget changes are required. Describe periodic budget reviews and how project stakeholders will be kept informed of their impact on the budget.

For OMB Exhibit 300 projects that involve “reimbursement” funds, be sure to describe the amounts and source of the funds, method and frequency of reporting progress towards agreed upon goals (for which the funding is intended to help achieve), mutually agreed upon ways to change the reimbursement (up or down), and mutually agreed upon decision making about disposition of year-end remainders. A senior officer(s) from the organization(s) providing the reimbursement funds should sign this plan, signifying their concurrence and approval of the portion of the plan that deals with the reimbursement funds.

Cost Performance Measures

Describe how performance reporting will be accomplished (i.e., deliverables, activity, contract, departmentally, etc.) and what performance characteristics will be reported. The reporting measures should also include a project overview of total performance to date with project completion projections. The description should include the development of financial, budget and schedule data required for the OMB Exhibit 300 process Earned Value Management System.

Cost Reports

Include a brief overview of the reporting content and format. Various reports may be used dependent upon the recipients (i.e., management reports, project team reports, contractor performance reports, etc.). At a minimum reports should include cost variances (CV), estimated at completion (EAC) and the cost performance index (CPI). Describe reporting cost data for the OMB Exhibit 300 process.

Cost Change Review and Approval Process

Describe the organization and process for evaluating and assessing project budget/cost changes. Define the authority for accepting and approving changes in cost. Include the evaluation process to assess the impact of cost changes on project scope, schedule, risk and quality. Note: the cost change review and approval process should be contained within the Integrated Change Control Management Process. Reference to that process should be included within this statement.

The integrated change management process must be followed to initiate any changes or revisions to the cost estimate.  Other aspects of the project, including scope, risks, requirements, acquisition plan etc, may impact budget changes.

Approved cost changes may or may not require re-baselining.  In other words, a change in cost may not necessarily change the budget and therefore would not require re-baselining.  In determining whether to make a cost change, consideration is given to impacts on scope, schedule, risk, quality and staffing.  The integrated change management plan should contain further explanation of the re-baselining process.  The status of all change requests is communicated to appropriate project stakeholders in accordance with the project’s communications plan.

RECORD OF AMENDMENTS

| Version | Author | Date | Comments |
| --- | --- | --- | --- |
| 1.0 |  | 7/25/05 | Draft 1. Based on template created for VA IT project cost management |

# Earned Value Management Definitions

# Scope Management Plan Template

|  | Scope Management Plan |
| --- | --- |
|  | Project Name: |
|  | Date: DD Mmmm-20yy |
|  | Project Manager: |
|  | Approver: signature |
|  | Approver Name and Title: |

The following are suggested sections for the Scope Management Plan

Purpose of Scope Management Plan

Describe the purpose of the Scope Management Plan using the following guidelines.  Do not merely describe the content of the plan, but explain why Scope Management is necessary for the project.

Scope changes are common in projects, especially complex projects, as more information and detail become available during project planning and execution.  Some changes are necessities in that the end product may not meet the project objectives if the changes are not incorporated.  Some changes are “nice to have” features that really are not essential to meeting the project end product objectives but would enhance the product.  Some changes are simply included due to a difference in approach, style or priority but are not essential at all to meeting project objectives.

A management process must to be established that will allow the evaluation and impact assessment of proposed scope changes.  Any change in scope will have some impact on cost, time or quality of the project’s end product.  Before decisions can be made regarding the proposed change the impact of that change must be known.  Therefore a scope management process must be a part of the Project Plan.  The objective of the scope management plan is to make sure the scope is delivered – no more and no less.

The scope of a project should be captured in the Work Breakdown Structure (WBS).  The WBS organizes the project by major functions (project planning, standards documentation, training etc.), continuous processes (status reporting, financial reporting, etc.), and primary deliverables.   The WBS is the primary tool for managing the scope of the project.  This simply means that if the work is included within the WBS, it is considered within scope.  If work is not contained within the WBS, it is considered “out of scope” and should not be included in the project’s end product.  The Work Breakdown Structure is the fundamental planning tool for project management.

Roles and Responsibilities

Describe how the following project participants, at a minimum, perform in the planning and execution of project communications

Project Sponsor

Project Manager

Project Team

Project Stakeholders

Work Breakdown Structure (WBS) Development

The plan should discuss the process the project will follow to develop the WBS (an outline or graphical depiction of the project scope). The development process involves deciding on an approach (usually top-down), involving team members who will accomplish the work (tasking them for inputs, meetings), creating a numbering system, including financial system codes and budgetary information, and deciding where to capture costs (work package level). A thorough understanding and buy-in of the WBS from the project team and supporting organizations is essential.

Scope Baselining

Describe the process for establishing the scope baseline (essentially freezing WBS development). The formal process to insure the project team and stakeholders understand the WBS and are supportive of its layout. The baselined WBS can then become the backbone for establishing a detailed project schedule and cost accounting system. The integrated change control process must be followed to initiate further changes or revision to the WBS (schedule, budget, risk database, requirements, acquisition plan, etc.) if rebaselining occurs. Discuss the possible use of a Change Control Board (CCB).

Scope Change Management Process

Describe the scope (WBS) change control process as it pertains to project integrated change control. Discuss the likelihood that WBS changes will be necessary. As an example, progressive elaboration of the project product can lead to changes to the WBS. Discuss the frequency of anticipated changes. Describe how scope changes will be identified classified and assessed (major cost and schedule impact, minor impact, no impact, etc). Do scope changes require changes to the scope statement, WBS, or schedule? Include a process for tracking scope changes, continuously evaluating the overall impact of changes, and reporting changes to sponsors, senior management, stakeholders, project team members (immediately, at status reviews, etc.). Discuss the triggers for rebaselining the WBS and process for revising project documents (schedule, budget, risk database, requirements, acquisition plan, etc.) if rebaselining occurs. Discuss the possible use of a Change Control Board (CCB).The integrated change management process must be followed to initiate any changes or revisions to the WBS.  Scope changes can be impacted by any aspect of the project, including schedule, budget, risks, requirements, acquisition plan etc.  The integrated change management plan is described in the document titled EVM Change Management.doc.

Change Thresholds

Submittal of a change request to the [sponsor] for approval is required if one of the two following statements is true:

- The change is estimated to reduce the cost or duration of an individual activity by x% or more, or increase the cost or duration of an individual activity by x% or more

- The change is estimated to reduce the cost or duration of the overall schedule by x% or more, or increase the cost or duration of the overall schedule by x% or more

Change requests that do not meet these threshold levels are to be submitted to the [Project Manager] for approval.

Approved scope changes may or may not require re-baselining.  In other words, a change in scope may not necessarily change the schedule or cost and therefore would not require re-baselining.  In determining whether to make a scope change, consideration will be given to impacts on schedule, cost, risk, quality and staffing.  The integrated change management plan contains further explanation of the re-baselining process.  The status of all change requests is communicated to appropriate project stakeholders in accordance with the project’s communications plan.

All change requests are documented using a change request form. The change request form is included in the integrated change management plan document  along with instructions on how to complete it.

The project Scope Statement must be reviewed for any impacts as part of a change request submission.  Any scope changes also affecting the scope statement must be noted on the request form.  The change request is then processed through the approval process with knowledge that the scope statement also requires revision.

RECORD OF AMENDMENTS

| Version | Author | Date | Comments |
| --- | --- | --- | --- |
| 1.0 |  | 7/25/05 | Draft 1. Based on template created for VA IT Scope Management |

# Work Breakdown Structure Example

# Quality Management Plan Template

|  | Quality Management Plan |
| --- | --- |
|  | Project Name: |
|  | Date: DD Mmmm 20yy |
|  | Project Manager: |
|  | Approver: signature |
|  | Approver Name and Title |

The following are suggested sections for the Quality Management Plan

Purpose of the Quality Management Plan

Describe the purpose of the Quality Management Plan using the following guidelines.  Do not merely describe the content of the plan, but why Quality Management is necessary for the project.

Quality doesn’t simply happen.  It must be planned into the project.  There must be some method of ensuring that the end result will meet the needs of the organization and the “customer” (either internal or external), as well as meeting the project objectives.  A method is needed for validating these measures.  Quality Planning, Quality Assurance and Quality Control processes developed within the Quality Management Plan are used to achieve quality goals.

Roles and Responsibilities

Describe how the following project participants, at a minimum, perform in the planning and execution of project communications

Project Sponsor

Project Manager

Project Team

Project Stakeholders

Quality Policy

Describe the organization’s quality policy or the policy adopted for the project. Quality policy might involve document preparation standards, status reporting standards, levels of communication standards for project events, contracting standards, development and testing standards, etc.

Quality Management Approach

Describe how the project team will implement the quality policy and achieve the project quality standard. Include the quality criteria identified during the quality planning process.

Quality Assurance

Describe the project quality assurance process which include the test and acceptance processes, documentation and operational support transitions, milestone checklist, the requirement verification process, schedule and communication activities, and continuous improvement processes. (see example of a Quality Management Process Model in the Quality Management Plan section)

Quality assurance is intended to “design quality into” the product.  Quality assurance is an ongoing activity that occurs in a planned and systematic way, not as a “post facto” event.  Quality assurance is focused on the quality processes that:

Organize

Design processes

Set objectives

Provide resources

Develop procedures

Quality Control

Define in-process control processes that address quality assurance activity areas. Describe how control information will be collected and how the information will be used to control processes and deliverables. Describe the periodic quality audits and reviews and how variances from acceptable criteria will be reported and resolved.

The Quality control process measures whether the project deliverables are meeting the criteria, policies, procedures and other planning steps as the project moves into the execution phase.  Quality control also analyzes the validity of the quality criteria and other outputs of the quality planning process.  Quality control is focused on quality by:

Estimating

Analyzing

Monitoring conformance

Providing quality reports

Quality Change Review and Approval Process

Describe the organization and process for evaluating and assessing proposed quality changes. Define the authority for accepting and approving changes in quality, which may include the customer. Note: the change review and approval process should be contained within the Project Integrated Change Control Process and referred to in this section.

RECORD OF AMENDMENTS

| Version | Author | Date | Comments |
| --- | --- | --- | --- |
| 1.0 |  | 7/25/05 | Draft 1 – Based on Quality Management Template created for VA IT projects |

# Project Communications Plan Template

|  | Communications Management Plan |
| --- | --- |
|  | Project Name: |
|  | Date: DD Mmmm 20yy |
|  | Project Manager: |
|  | Approver: signature |
|  | Approver Name and Title |

The following are suggested sections for the Communications Management Plan

Purpose of Communications Management Plan

Describe the purpose of the Communications Management Plan using the following guidelines.  Do not merely describe the content of the plan, but explain why Communications Management is necessary for the project:

The success of any project is heavily reliant upon the project team members and stakeholders being thoroughly informed in a timely manner.  Information such as scope, time, cost or quality changes, current project schedule status, current and projected cost data, and project decisions or issues all need to be disseminated to project members and stakeholders.  This Communications Plan establishes the project’s processes and requirements for the collection and distribution of project data.

Document accessibility and security are also key factors.  Not every project participant requires access to every project document, but some information should be available to all.  Methods need to be in place to identify security and accessibility to project information.

Roles and Responsibilities

Describe how the following project participants, at a minimum, perform in the planning and execution of project communications

Project Sponsor

Project Manager

Project Team

Project Stakeholders

Stakeholder Identification

Using the WBS and OBS identify the project stakeholders, when they will be active on the project and all the pertinent information necessary to communicate with them (organization, title, address, phone numbers, email, etc.). Further identify alternates and subordinates that will be assigned to the project and act on behalf of a stakeholder. Provide the stakeholders responsibility to the project including review and approval authority for project documentation.

Project Reports

Describe the reports to be generated in support of the project. Define the data to be collected, the frequency of collection, the responsible party for collection, compilation and analysis, the report media and format, and the distribution of the report. Some examples of reports include:

| Project Status | Open Issues/Action Items |
| --- | --- |
| Financial Data | Quality Assurance |
| Cost Variance | Resource Utilization/Projections |
| Schedule Status and Variance | Change Control |
| Updated Project Schedules |  |

The following other subsidiary project management plans also should contain information on reports:

- Cost Management Plan

- Schedule Management Plan

- Risk Management Plan

Ad-hoc or specialized report requests may arise during the project.  The plan should describe how specialized reports are accepted within the project, who approves them and how reporting changes will be communicated.

Project Meetings

Describe the meetings held on the project, their purpose, frequency, attendees and reporting requirements. This information might be held is a separate document for easier maintenance.

Project Information Accessibility

Access to project information should be planned. Centralized project files and data may not be advantageous to large projects with varied geographic locations. This section will define the project team requirements, media and locations for project information, including any document management system employed. Also consider document scanning and storage policies within the project office. The plan should also cover document security, the requirement for locked storage, passwording, etc.

RECORD OF AMENDMENTS

| Version | Author | Date | Comments |
| --- | --- | --- | --- |
| 1.0 |  | 7/25/05 | Draft 1 – Based on template developed for VA IT project communications management |

Project Name:

| Meeting Name | Frequency | Time | Location | Leader | Attendees | Purpose | Report(s) Used |
| --- | --- | --- | --- | --- | --- | --- | --- |

Project Name:

|  | Monday | Tuesday | Wednesday | Thursday | Friday |
| --- | --- | --- | --- | --- | --- |
| Week 1 |  |  |  |  |  |
| Week 2 |  |  |  |  |  |
| Week 3 |  |  |  |  |  |
| Week 4 |  |  |  |  |  |

# Change Management Plan Template

|  | Integrated Change Management Plan |
| --- | --- |
|  | Project Name: |
|  | Date: DD Mmmm 20yy |
|  | Project Manager: |
|  | Approver: signature |
|  | Approver Name and Title |

The following are suggested sections for the Integrated Change Control Plan.

Purpose of Integrated Change Management Plan

Describe the purpose of the Integrated Change Management Plan using the following guidelines.  Do not merely describe the content of the plan, but explain why Integrated Change Management is necessary for the project.

Projects are dynamic efforts and as such change is inevitable.  One of the greatest challenges to a project’s success is controlling the impact of change or managing changes to the benefit of the project objectives.  By accepting the fact that change will occur and planning for the management of change, the probability of project success is increased and enhanced.

The purpose of the Integrated Change Control Plan is to define all processes, practices, tools, review bodies, and authority necessary to monitor and control project performance, identified change and the potential impact of change on project objectives.

Roles and Responsibilities

Describe how the following project participants, at a minimum, perform in the planning and execution of project change management.

Project Sponsor

Project Manager

Project Team

Other Stakeholders

Review and Approval Process

Describe the process to identify change in the project scope, cost and budget. Describe the change approval authorities and review boards that will process project change control documents. An example may be a change control board made up of leaders in various project disciplines such as project management, cost, scheduling, configuration management, technical design, and test. Sponsors, system owners and users should also be considered. A process flow chart is appropriate for this section. (See the notional flow chart in the Change Control section of the Project Handbook Appendices)

The following text and chart comes from the VA project plan for EVM. Provided as reference only

Following are the steps involved in the change control process.  A process flow diagram at the end of this section graphically displays the steps.

- A potential change is identified by any team member or project stakeholder.

- The change request form is completed (see appendix of this document) with the assistance of the Project Manager or designee.

- The Project Team evaluates the request to make sure impacts are thoroughly discussed and identified on the form. Decision-makers should be able to clearly see the impact of change on the project (time cost, scope, quality and risks).

- If the impact of the change the thresholds outlined in this plan then the change is presented to the [Approval Body] for review.  The [Approval Body] chair has ultimate approval or denial of the change. Any changes under the threshold for [Approval Body] approval are sent to Project Manager for approval.

- If the change is denied the reason is documented and the requestor is notified.  No other action is taken.

- If the change is approved then it is documented and implemented.  The change will be reflected in all the appropriate Project Management documents. (e.g. schedule, budget, WBS, Risk management plan etc.)  Re-baselining may be appropriate (see section on re-baselining below).

- If a change request is deferred, then one of two actions is taken.  In the case where a “trigger event” which would necessitate the change is known, the Project Team will monitor the occurrence of the event. The change request will be re-visited when the event occurs. Otherwise, the Project Team will schedule a date to re-evaluate the request.

The Review and Approval Process Flow Chart is presented here

Change Thresholds

Describe the limits that trigger the change control process for scope (WBS), cost, schedule and possibly resources. An example may be critical WBS elements where costs exceed 10% of budget, or perhaps a schedule element that is falling behind and will require additional resources to meet a critical deliverable.

Change Identification, Documentation, Implementation and Reporting

Describe the initiation of a change control form and the documentation required to track a request. Describe automated tool used to manage and track changes and identify the process for entering and reporting changes. Also, if the project has a change control board, describe the process for preparing the agenda and communicating results to the stakeholders. Describe the process for updating the WBS, schedules and budget/cost documents with approved changes. If the baseline for these documents changes, describe the means for capturing the baseline change in the OMB Exhibit 300 process.

Re-baselining

Describe the reasons and procedures for re-baselining such as in the statement below:

The project WBS, schedule and costs are all baselined early in the project.  Any of these artifacts may experience enough change throughout the project to require re-baselining. The original baseline is never over-written.  Change requests submitted after re-baselining will be assessed for impacts against the revised baseline, not the original baseline.

General guidance for re-baselining includes:

- General cost overruns and schedule slippages due to performance or poor estimation are NOT sufficient reasons to re-baseline.

- As long as there is no change in scope, a project manager is able to further decompose activities that were previously recorded at a higher level.  This DOES NOT constitute a re-baselining but is considered an update.

- Requested changes to cost and/or schedule to achieve the original scope. This DOES constitute a re-baselining.

- Reductions in funding ARE an acceptable reason to re-baseline.  This should be accompanied by an explanation of how the funding cuts impact the original scope of the project.

Appendix A. – Change Request Form

The attached form is to be used for all change requests in the project affecting scope, schedule, cost and risk.

Revisions to the template should be noted in the Record of Amendments at the end of this document.

RECORD OF AMENDMENTS

| Version | Author | Date | Comments |
| --- | --- | --- | --- |
| 1.0 |  | 7/21/05 | Draft 1. Based on template created for VA IT change management |

|  | Change Request Form |
| --- | --- |
|  | Project Name: |

Refer to the last page for a diagram of the change approval process

| 1. Change Request Information – To be Completed by Requestor |
| --- |
| Requestor | Request Date |
| Proposed Change Description and References |
| Justification/Reason for Change |
| Impact of Not Implementing Proposed Change |
| Alternatives |
| Baseline(s) Affected: Scope (WBS) Schedule Cost |
| Impact on Scope |
| Impact on Schedule |
| Impact on Cost |
| Risk Analysis |
| Reference Risk Number Risk Description Change in Risk Impact From To Change in Risk Probability From To Change Impact Analysis on Risk |

2. Impact Analysis – To Be Completed by Earned Value Team

Review Date Change Control Number Comments Classification

3. Project Manager Review Results – To Be Completed by Project Manager

Review Date Comments Approved Forward to EPMC Rejected Defer Until (trigger event or future date)

Reason for Rejection/Deferral

4. [Approval Body] Review Results – To Be Completed by [Approval Body]

Review Date Comments Approved Rejected Defer Until (trigger event or future date)

Reason for Rejection/Deferral

Name Position Signature:__________________________ Name Position Signature:__________________________ Name Position Signature:__________________________ Name Position Signature:__________________________

Change Request Process Flow Diagram

# Risk Management Plan Template

|  | Risk Management Plan |
| --- | --- |
|  | Project Name: |
|  | Date: DD Mmmm 20yy |
|  | Project Manager: |
|  | Approver: signature |
|  | Approver Name and Title |

The following are suggested sections for the Risk Management Plan

Purpose of Risk Management Plan

Describe the purpose of the Risk Management Plan using the following guidelines.  Do not merely describe the content of the plan, but why Cost Management is necessary for the project.

Risk is an indicator of uncertainty about the future. The greater the investment in a project, the more one has to lose should any problems delay or derail the project. Risks on any project must be identified and analyzed so that project teams can prepare for their potential occurrence and lessen or eliminate their chance of occurring.

The Risk Management Plan provides a systematic method of identifying and analyzing the effects of uncertainties in the project and to plan for minimizing or containing the consequences of any undesired event that may impact the success of the project.

Roles and Responsibilities

Describe how the following project participants, at a minimum, perform in the planning and execution of project communications

Project Sponsor

Project Manager

Project Team

Project Stakeholders

Risk Manager

Risk Identification

During risk identification, the perception of a potential problem is documented in sufficient detail to enable effective assessment of the risk to support subsequent management decisions. Once the risk has been identified and reviewed, the risk is recorded into the risk database.

See Risk Inventory and Assessment at form end.

The project team systematically reviews the project deliverables and activities for possible risk information.  Typically, risk information is derived from:

Analysis of high-level deliverables

Analysis of the work Breakdown Structure(WBS) and Network diagram

Analysis of change requests

Project team input (experience, lessons learned etc.)

Stakeholder input (assumptions, organizational requirements etc.)

Risk Triggers

Risk triggers are events or performance characteristics that warn of the occurrence of risk events. An example of a risk trigger would be a supplier missing deliverable dates and delaying related activities and adding cost to project.

Risk triggers are determined during the risk identification process and are captured on the Risk Control Form.

Risk Analysis

The goal of risk analysis is to ensure that the risks are examined in a structured and systematic manner. The risk owner may work with the risk coordinator to formulate the initial risk assessment. Two methods of risk analysis are employed in this process – qualitative and quantitative analysis.

A qualitative risk assessment qualifies the expected impact, probability, and timeframe of a risk. The results of the risk analysis are recorded on a risk identification form. The results are used to determine Risk Management priorities.

A quantitative risk analysis is also accomplished where the impact of a risk is ranked against other risk events or in the case or performance, the risk is assessed as a percentage of reduction in performance.

Risk Severity

The results of qualitative analysis and quantitative analysis are captured on an impact/probability chart, called the Risk Severity Grid. The grid is used to determine the priority that is assigned each risk and the need to develop containment strategies.

Risk Response Planning

Risk response planning involves identifying the strategy for minimizing the effects of the risk to a level where the risk can be controlled and managed to ensure the project objectives are achieved. Risk reduction strategies include research, watch, mitigate, accept or transfer.

Each risk containment strategy will uniquely address the situation. However, strategies generally involve one of the following techniques:

| Avoidance | To avoid a risk event, the project plan may be altered. Better clarification of scope or product description may avoid the risk. The additions of resources, time, and/or the development of a different approach are also risk avoidance techniques. |
| --- | --- |
| Transference | Transferring responsibility for management of a risk may mitigate the risk. This technique is typically used when strategizing financial exposure but does not eliminate the probability of the risk event. |
| Sharing | It is at times possible to share the impact of a risk event with a customer, third party vendor, etc. This could result in an overall lessening of the risk impact and position all parties to better control, avoid or mitigate the risk event. |
| Mitigation | Mitigation attempts to reduce the probability or consequence of the risk event to an acceptable level. This could involve an early action plan to address the issue before it becomes problematic by adopting less complex processes or adding more resources or time. |
| Acceptance | Acceptance of a risk by a project team indicates that the risk is within acceptable limits or that contingency plans are sufficient to ensure project success even if the risk event occurs. Accepted risks typically require the development of a contingency plan (an alternative course of action should the risk event occur). This may include the allocation of a contingency allowance or reserve in terms of finances, time or resources. |

Risk Documentation and Reporting

Create a central repository for risk information and mitigation strategies. This is typically an automated system where risk information is available to appropriate project team members and risk owners. Typical tools include the risk register (the complete risk database) and a monthly risk status report that is part of the OMB Exhibit 300 process.

Risk Control

Define the risk control process that addresses risks on a periodic basis. Describe how risks are regularly reassessed and the risk database is updated. Describe how the risk triggers are regularly assessed and validated. Insure, on a periodic basis that new risks are being identified, assessed and captured in the database.

In order to successfully address the OMB risk categories for submission and scoring of the OMB Exhibit 300, the following Risk categories must be addressed to discuss plans, milestones and completion dates, and whether to eliminate, mitigate, or manage the risk.

| Date Identified | Area of Risk | Description | Probability of Occurrence | Strategy for Mitigation | Current Status |
| --- | --- | --- | --- | --- | --- |
|  | Schedule |  |  |  |  |
|  | Initial Cost |  |  |  |  |
|  | Life Cycle Cost |  |  |  |  |
|  | Reliability of Systems |  |  |  |  |
|  | Capability of agency to manage project |  |  |  |  |
|  | Overall risk of project failure |  |  |  |  |
|  | Technical Obsolescence |  |  |  |  |
|  | Feasibility |  |  |  |  |
|  | Dependencies and Interoperability |  |  |  |  |
|  | Risk of creating “lock-in” – a monopoly for future procurements |  |  |  |  |
|  | Organization and Change Management |  |  |  |  |
|  | Business |  |  |  |  |
|  | Data/Info |  |  |  |  |
|  | Technology |  |  |  |  |
|  | Strategic |  |  |  |  |
|  | Security |  |  |  |  |
|  | Privacy |  |  |  |  |
|  | Project Resources |  |  |  |  |
|  | Management Complexity |  |  |  |  |
|  | Departmental Reorganization |  |  |  |  |

Appendix A. - RISK IMPACT CATEGORIES

| Risk Event Impact | Schedule Slippage | Cost Increase | Performance (Scope and/or Quality) |
| --- | --- | --- | --- |
| 5 – Very High | > 20% | > 20% | End product fails to meet customer needs |
| 4 – High | 10 – 20% | 10 – 20% | Reduction in functionality or usability unacceptable to customer |
| 3 –Moderate | 5 – 10% | 5 – 10% | Major impact in functionality or usability requiring customer approval |
| 2 – Low | < 5% | < 5% | Relatively minor impact in functionality or usability |
| 1 – Very Low | ~ 0 | ~ 0 | Very minor impact in functionality or usability |

Assess the impact of each identified risk event.

Appendix B. - RISK PROBABILITY CATEGORIES

| Risk Event Probability | Likelihood of Risk Event | Response Strategy Difficulty |
| --- | --- | --- |
| 5 – Very High | > 80% – Risk event expected to occur | No strategy available to counteract the risk event occurring. |
| 4 – High | 60-80% – Risk event more likely to occur | Limited resources or strategies are available that will influence the occurrence of or contain the risk event. A high level of management attention is necessary. |
| 3 – Probable | 40-60% – Risk event may or may not to occur | A higher level of management attention is required to develop strategies that will produce an acceptable outcome. |
| 2 – Low | 20-40% – Risk event less likely to occur | With attention, normal management strategies should produce an acceptable outcome |
| 1 – Very Low | < 20% – Risk event not expected | Normal management strategies should produce an acceptable outcome. |

Assess the probability of occurrence for each identified risk event.

Appendix C. - RISK SEVERITY GRID

| Impact | 5 Very High |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 4 High |  |  |  |  |  |
|  | 3 Moderate |  |  |  |  |  |
|  | 2 Low |  |  |  |  |  |
|  | 1 Very Low |  |  |  |  |  |
|  |  | 1 Very Low | 2 Low | 3 Probable | 4 High | 5 Very High |
|  |  | Probability |

After probability and impact assessment, identify the risk severity from the chart above. Risks are then prioritized based upon the severity of event.

(Red shaded areas represent the greatest risk severity with significant potential impact to the project.)

Appendix D. - RISK CONTROL FORM

Form to be used for submitting project risks and formulating risk responses.

Appendix E. - RISK MANAGEMENT LOG

Form to be used for maintaining status of project risks.

RECORD OF AMENDMENTS

| Version | Author | Date | Comments |
| --- | --- | --- | --- |
| 1.0 |  | 7/25/05 | Draft 1 – Based on template created for VA IT risk management |

# Risk Control Form Template

|  | Risk Control Form |
| --- | --- |
|  | Project Name: |
|  | Date: |
|  | Project Manager: |

| Risk Log Number | Submittal Date | Submitted By | Assigned Owner |
| --- | --- | --- | --- |
| Brief Description of Risk Event |
| Status | Priority Level |
| Probability | Impact |
| Qualitative Analysis (Risk Severity) |
| Quantitative Analysis |
| Activity Number (WBS) | Best Case | Most Likely Case | Worst Case |
| Evaluation |
| Containment Strategy |

RECORD OF AMENDMENTS

| Version | Author | Date | Comments |
| --- | --- | --- | --- |
| 1.0 |  | 07/25/05 | Draft 1 – Based on template created for VA IT risk control |

# Risk Management Log Template

Project Name:

| Risk ID Number | Threat Event | Probability | Impact | Strategy | Follow-up Date | Responsible Team Member or Responsible Manager |
| --- | --- | --- | --- | --- | --- | --- |

# Staffing Management Plan Template

|  | Staffing Management Plan |
| --- | --- |
|  | Project Name: |
|  | Date: DD Mmmm 20yy |
|  | Project Manager: |
|  | Approver: signature |
|  | Approver Name and Title |

The following are suggested sections for the Staffing Management Plan

Purpose of the Staffing Management Plan

Describe the purpose of the Staffing Management Plan using the following guidelines.  Do not merely describe the content of the plan, but explain why Staffing Management is necessary for the project.

It takes people to run a project.  The Project Manager needs a team to produce the deliverables and maintain control over the project.  Project Team members need certain skills to become truly productive.  The Project Manager needs to ascertain when new people will be required on the project or when existing team members will be able to leave.  This Staffing Management plan provides the Project Manager with a framework to identify and justify human resource needs and provide an effective work force to accomplish the project work.

Roles and Responsibilities

Describe how the following project participants, at a minimum, perform in the planning and execution of project communications

Project Sponsor

Project Manager

Project Team

Project Stakeholders

Project Organization

Describe the project organization including the project team and stakeholders. Include the roles and responsibilities of the team members and stakeholders. An OBS may be developed indicating the responsible personnel, the department or functional area, the specific activities of responsibility and may include the associated budget allocation.

An understanding of the organization and stakeholders is also important in communications planning.  This knowledge helps identify the reporting needs and communications flow within the project.  Refer to the communications plan for a “map” of the communications channels on the project.

Resource Requirements

An outline of the resource requirements needed to execute the project. In many cases it is possible to define this based on areas of responsibility or technical capability. Identified areas such as engineering, software development, system engineering, etc. should be listed as well as the necessary skill sets and expertise required within each area

Project Managers responsible for OMB Exhibit 300 projects are required to have an extensive knowledge of project management, including all the discipline areas described in the Project Management Plan, e.g. schedule management, risk management, change management etc.

Understanding of the project background and requirements is also very important.  This includes the OMB Exhibit 300 requirements, ANSI/EIA 748 A Standards documentation and Circular A-11.  These documents can be found at xx.

All project participants are expected to have knowledge of the USDA culture, organization, policies and procedures.  Communication skills, both verbal and written, are important in any project environment.  Other soft skills, such as team dynamics, negotiation and facilitation are assets that are beneficial for any employee.

It is understood that resources may not meet all the knowledge requirements presented here.  As such, employee training has also been captured as part of this plan, and is also included in the project scope (WBS) and project schedule.  Employees are offered training as their skill levels and availability permit.

Resource Staffing Plan

Describe what resources are required and when they are required. This should be graphical in nature and indicate the time phased resource loading. This is the basis for managing resources and serves to assure that the project is resource loaded properly.

Resource Constraints

Document any known constraints regarding resources. Constraints may be project based, defining specific requirements and limitations within the project objectives, or organizationally based, defining limitations or requirements of the organization to adequately staff the project and meet project requirements and needs.

Staffing Reports

Define the reporting frequency and requirements during execution of the project. Indicate on a time phased basis what resources are required and when.

Staffing Contingency Plans

Describe the process for developing contingency plans, providing alternatives should critical resources not be available when required.

Staffing changes are common to all projects. Some of these changes can be anticipated and some cannot.  Contingencies are therefore important to ensure that project deliverables can still be met when staffing changes occur.  Contingencies should answer questions such as: What happens if the Project Manager leaves?  What if budgets are curtailed?

Training Requirements

Specialized training may be identified and required for project team members or staffing. These requirements should be defined and planned into the project.

RECORD OF AMENDMENTS

| Version | Author | Date | Comments |
| --- | --- | --- | --- |
| 1.0 |  | 7/25/05 | Draft 1 – Based on template created for VA IT Staffing Management |

# Procurement Management Plan Template

|  | Procurement Management Plan |
| --- | --- |
|  | Project Name: |
|  | Date: DD Mmmm 20yy |
|  | Project Manager: |
|  | Approver: signature |
|  | Approver Name and Title |

The following are suggested sections for the Procurement Management Plan

Purpose of the Procurement Management Plan

Describe the purpose of the Procurement Management Plan using the following guidelines.  Do not merely describe the content of the plan, but why Procurement Management is necessary for the project:

The organization is unable to create or supply all the products and services necessary to complete the project and therefore needs to use external sources that have the expertise in certain areas to assist in completing all required project deliverables.  Procurement planning gives the project team knowledge and confidence to obtain quality products and services from qualified vendors in a timely manner.

Roles and Responsibilities

Describe how the following project participants, at a minimum, perform in the planning and execution of project procurement

Project Sponsor

Project Manager

Project Team

Project Stakeholders

Contract Office Technical Representative (COTR)

Required Project Procurements and Timing

Discuss the necessity for planned procurements, including the results of alternative analyses and make or buy analyses. Discuss the best times to initiate the procurement processes to meet the detailed project schedule.

Description of Items/ Services to be acquired

Briefly describe the overall scope of the project.  What are the specific items/services/major contract deliverables that will be acquired?

IT Acquisition Process

Discuss initiating a project using the USDA IT Acquisition process. Describe the required acquisition approvals. Include the use of any tracking systems and the requirement for supporting documentation. Examples of the supporting information include: a requirements analysis, a business case justification, a cost/benefits analysis and a Statement of Work (SOW).

Solicitation Planning

Describe the responsibilities of the project team and stakeholders in developing acquisition requests, SOWs, a solicitation strategy, an evaluation strategy and evaluation criteria.

Period of Performance

Indicate the period of performance in months or years from time of award with options separately indicated.  For example:  “Three year base period with two one-year options.”

Applicable Conditions

Indicate any significant conditions, constraints, or assumptions affecting the acquisition such as the need for:

Compatibility with the enterprise architecture, existing or future systems or programs

Compliance with Section 508, privacy, security, IT investment management, and technical review and change control board requirements

Compliance with known cost, schedule or performance constraints. Also include any trade-offs that may need to be made among the various cost, schedule, and performance goals

If this is a system acquisition, describe any considerations given to build-vs.-buy decision, testing and evaluation, implementation, training, and operation and maintenance.

Background/Recent history of the procurement

If this is the first attempt to acquire the item or service, indicate “Not applicable.”  Otherwise, briefly describe the last procurement of the item or service and the results obtained.  How have lessons learned from that procurement shaped the strategy for this one?

Estimated obligations required

Include the estimated funds required for each fiscal year and total.  Describe the cost model/methodology that was used in developing the estimates.

Proposed contracting vehicle

Describe the contract vehicle(s) that will be used and the different items/services to which they will be applied.

Proposed contract type

Describe the contract types that will be used and the different items/services to which they will be applied.

Performance-based contracting

FAR 7.105 states that “Acquisition plans for service contracts must describe the strategies for implementing performance-based contracting methods or must provide a rationale for not using those methods (see Subpart 37.6).”

Modular contracting techniques

Section 5202 of The Clinger-Cohen Act as implemented in FAR 39.103 addresses the use of modular contract techniques (i.e. the use of one more contracts to acquire information technology systems in successive, interoperable increments).  If this project is a major system acquisition and such techniques will not be used, a justification should be provided.  If this project is not a major system acquisition and modular techniques were not used, indicate “Not a major systems acquisition.”

Potential sources

Indicate the prospective sources for the items or services.  Describe how competition will be sought, promoted, and sustained throughout the course of the acquisition. Include consideration of small business, veteran-owned small business, HUBZone small business, small disadvantaged business, and women-owned small businesses.  Describe the results of any market research that was conducted as well as any efforts to encourage industry participation such as draft solicitations or pre-solicitation conferences.

Source selection procedures

Describe the source selection procedures for the acquisition, to include the timing for the submission and evaluation of proposals.  Identify the major evaluation criteria and why they are needed to identify the proposals that offer the best chances for project success.  Describe how technical, past performance, and cost factors will be ranked to determine “best value.”   For example, will technical and past performance outweigh cost?  Describe whether single or multiple awards will be made.

Contract Administration

Describe who will administer the contract. Describe how the contract will be administered, including roles and responsibilities for inspection, acceptance, validation and verification of performance. Describe how invoices will be paid. Describe the process for changing the contract and controlling the changes. Describe the process for accepting contract deliverables. Describe the interaction between the project team and stakeholders with data systems used to maintain contract data.

Contract Closeout

Describe the formal acceptance of contracts and closure. Describe the alternative means for closing the contract without formal acceptance. Describe the archiving of contract documentation. Describe the use of procurement audits to identify successes and lessons learned.

RECORD OF AMENDMENTS

| Version | Author | Date | Comments |
| --- | --- | --- | --- |
| 1.0 |  | 7/25/05 | Draft 1. Based on template created for VA IT Project Procurement Management |

# Project Closeout Report Template

|  | Project Closeout Report |
| --- | --- |
|  | Project Name: |
|  | Date: DD Mmmm 20yy |
|  | Project Manager: |
|  | Approver: signature |
|  | Approver Name & Title |

The following are suggested sections for the Project Closeout Report:

Purpose of Closeout Report

Describe the purpose of the Closeout Report using the following guidelines:

The closeout report insures that personnel, contract, administrative, and financial issues are resolved, that documents are archived, and lessons learned are captured.

Administrative Closure

Were the objectives of the project met?

Review the project objectives and indicate if the objectives were met. If there were deviations from the baseline objectives and the final product, describe those here.

Archiving Project Artifacts

Describe how project documents will be collected and archived for future reference. Documentation to consider:

- Financial records

- Cost and schedule performance reports and records

- Quality data

- Correspondence

- Meeting Notes

- Status Reports

- Issue and Action Log

- Risk Log

- Contract Files

- Change Requests

- Technical documents

- Acceptance records

Lessons Learned

Conduct a lessons learned session to discuss and capture the performance (e.g., what worked well, what didn’t work well) from start to finish on the project. Capturing and incorporating lessons learned on future projects are among the most important ways in which an organization gathers information to institutionalize repeatable processes and avoid repeated mistakes.

Plans for Post Implementation Review (PIR)

Describe the plan to conduct the Post Implementation Review (PIR).

Final Customer Acceptance

Describe the achievement of final customer acceptance. Describe the final meeting with customer, who attended and what disciplines were represented (finance, contracts, quality, etc.) Discuss the documents signed. If open issues remain discuss the plan for their resolution.

Financial Records

Discuss the review of invoices, purchase orders, and final cost reporting. Describe where the final cost records are archived.

Final Project Performance Report

Summarize the project’s scope management, schedule performance, cost performance, quality achievements and a review of the risk containment performance. Discuss the reasons for cost or schedule variances.

Contract Closure

Resolution of Contract Open Issues

Describe any open contract issues and the plans to obtain closure to the issues.

Collection and Audit of Contract Documents

Contract closure is essentially a collection and audit of the contract documentation. Documentation to be collected includes but is not limited to:

- Original contracts

- Contract changes

- Schedules

- Performance reports

Describe the plan and actions for closing any contracts and associated tasks.

RECORD OF AMENDMENTS

| Version | Author | Date | Comments |
| --- | --- | --- | --- |
| 1.0 |  | 7/25/05 | Draft 1. Based on template created for VA IT Project Closure |

# Text boxes

Figure 1

Less than 2.5% schedule increase

Less than 5% schedule reduction

-------------------------------------------------

Less than 5% activity increase

Less than 10% activity reduction

Greater than 2.5% schedule increase

Greater than 5% schedule reduction

-------------------------------------------------

Greater than 5% activity increase

Greater than 10% activity reduction

DEFER

DEFER

REJECT

REJECT

APPROVE

APPROVE

Notify Project Participants of Decision

Select Trigger Event or Date to Re-visit Request

Select Trigger Event or Date to Re-visit request

Document Reason for Rejection

Document Reason for Rejection

Implement Change

Change Decision Point

Change Decision Point

Project Manager Review

[Approval Body] Review

Change Threshold Determined

Implement Change

Project Team Evaluates Request/ Finalizes Form

Complete Change Request form

Potential Change Identified

Potential Change Identified

Complete Change Request form

Project Team Evaluates Request/ Finalizes Form

Implement Change

Change Threshold Determined

[Approval Body] Review

Project Manager Review

Change Decision Point

Change Decision Point

Implement Change

Document Reason for Rejection

Document Reason for Rejection

Select Trigger Event or Date to Re-visit request

Select Trigger Event or Date to Re-visit Request

Notify Project Participants of Decision

APPROVE

APPROVE

REJECT

REJECT

DEFER

DEFER

Greater than 2.5% schedule increase

Greater than 5% schedule reduction

-------------------------------------------------

Greater than 5% activity increase

Greater than 10% activity reduction

Less than 2.5% schedule increase

Less than 5% schedule reduction

-------------------------------------------------

Less than 5% activity increase

Less than 10% activity reduction