Earned Value Management Systems

DFARS Case 2005-D006

Final Rule

PART 234—MAJOR SYSTEM ACQUISITION

* * * * *

234.005  General requirements.

See 242.1106(a) for information on the use of earned value management systems and the use of cost/schedule status reports.

* * * * *

[SUBPART 234.2—EARNED VALUE MANAGEMENT SYSTEM

234.201  Policy.

(1)  DoD applies the earned value management system requirement as follows:

(i)  For cost or incentive contracts and subcontracts valued at $20,000,000 or more, the earned value management system shall comply with the guidelines in the American National Standards Institute/Electronic Industries Alliance Standard 748, Earned Value Management Systems (ANSI/EIA-748).

(ii)  For cost or incentive contracts and subcontracts valued at $50,000,000 or more, the contractor shall have an earned value management system that has been determined by the cognizant Federal agency to be in compliance with the guidelines in ANSI/EIA-748.

(iii)  For cost or incentive contracts and subcontracts valued at less than $20,000,000—

(A)  The application of earned value management is optional and is a risk-based decision;

(B)  A decision to apply earned value management shall be documented in the contract file; and

(C)  Follow the procedures at PGI 234.201(1)(iii) for conducting a cost-benefit analysis.

(iv)  For firm-fixed-price contracts and subcontracts of any dollar value—

(A)  The application of earned value management is discouraged; and

(B)  Follow the procedures at PGI 234.201(1)(iv) for obtaining a waiver before applying earned value management.

(2)  When an offeror proposes a plan for compliance with the earned value management system guidelines in ANSI/EIA-748, follow the review procedures at PGI 234.201(2).

(3)  The Defense Contract Management Agency is responsible for determining earned value management system compliance when DoD is the cognizant Federal agency.

(4)  See PGI 234.201(4) for additional guidance on earned value management.

234.203  Solicitation provisions and contract clause.

For cost or incentive contracts valued at $20,000,000 or more, and for other contracts for which EVMS will be applied in accordance with 234.201(1)(iii) and (iv)—

(1)  Use the provision at 252.234-7001, Notice of Earned Value Management System, instead of the provisions at FAR 52.234-2, Notice of Earned Value Management System – Pre-Award IBR, and FAR 52.234-3, Notice of Earned Value Management System – Post-Award IBR, in the solicitation; and

(2)  Use the clause at 252.234-7002, Earned Value Management System, instead of the clause at FAR 52.234-4, Earned Value Management System, in the solicitation and contract.]

* * * * *

PART 242—CONTRACT ADMINISTRATION AND AUDIT SERVICES

* * * * *

242.1106  Reporting requirements.

(a)  See DoDI 5000.2, Operation of the Defense Acquisition System, for reporting requirements for defense technology projects and acquisition programs.  Table E3.T2 of DoDI 5000.2 specifies the earned value management system (EVMS) thresholds.  When an offeror proposes an EVMS plan, follow the review procedures at PGI 242.1106(a).  The Defense Acquisition Guidebook provides additional guidance on earned value management and identifies when cost/schedule status reports are applicable.

* * * * *

242.1107-70  Solicitation provisions and contract clauses.

(a)  When the Government requires contractor compliance with DoD earned value management system criteria(

(1)  Use the provision at 252.242-7001, Notice of Earned Value Management System, in solicitations; and

(2)  Use the clause at 252.242-7002, Earned Value Management System, in solicitations and contracts.

(b)  Use the clause at 252.242-7005, Cost/Schedule Status Report, in solicitations and contracts that require cost/schedule status reports (i.e., when the Contract Data Requirements List includes DI-MGMT-81467).

(c)  Use the provision at 252.242-7006, Cost/Schedule Status Report Plans, in solicitations that require cost/schedule status reports.

* * * * *

PART 252—SOLICITATION PROVISIONS AND CONTRACT CLAUSES

* * * * *

[252.234-7001  Notice of Earned Value Management System.

As prescribed in 234.203(1), use the following provision:

NOTICE OF EARNED VALUE MANAGEMENT SYSTEM (APR 2008)

(a)  If the offeror submits a proposal in the amount of $50,000,000 or more—

(1)  The offeror shall provide documentation that the Cognizant Federal Agency (CFA) has determined that the proposed Earned Value Management System (EVMS) complies with the EVMS guidelines in the American National Standards Institute/Electronic Industries Alliance Standard 748, Earned Value Management Systems (ANSI/EIA-748) (current version at time of solicitation).  The Government reserves the right to perform reviews of the EVMS when deemed necessary to verify compliance.

(2)  If the offeror proposes to use a system that has not been determined to be in compliance with the requirements of paragraph (a)(1) of this provision, the offeror shall submit a comprehensive plan for compliance with the guidelines in ANSI/EIA-748.

(i)  The plan shall—

(A)  Describe the EVMS the offeror intends to use in performance of the contract, and how the proposed EVMS complies with the EVMS guidelines in ANSI/EIA-748;

(B)  Distinguish between the offeror’s existing management system and modifications proposed to meet the EVMS guidelines;

(C)  Describe the management system and its application in terms of the EVMS guidelines;

(D)  Describe the proposed procedure for administration of the EVMS guidelines as applied to subcontractors; and

(E)  Describe the process the offeror will use to determine subcontractor compliance with ANSI/EIA-748.

(ii)  The offeror shall provide information and assistance as required by the Contracting Officer to support review of the plan.

(iii)  The offeror’s EVMS plan must provide milestones that indicate when the offeror anticipates that the EVMS will be compliant with the guidelines in ANSI/EIA-748.

(b)  If the offeror submits a proposal in an amount less than $50,000,000—

(1)  The offeror shall submit a written description of the management procedures it will use and maintain in the performance of any resultant contract to comply with the requirements of the Earned Value Management System clause of the contract.  The description shall include—

(i)  A matrix that correlates each guideline in ANSI/EIA-748 (current version at time of solicitation) to the corresponding process in the offeror’s written management procedures; and

(ii)  The process the offeror will use to determine subcontractor compliance with ANSI/EIA-748.

(2)  If the offeror proposes to use an EVMS that has been determined by the CFA to be in compliance with the EVMS guidelines in ANSI/EIA-748, the offeror may submit a copy of the documentation of such determination instead of the written description required by paragraph (b)(1) of this provision.

(c)  The offeror shall identify the subcontractors (or the subcontracted effort if subcontractors have not been selected) to whom the EVMS requirements will apply.  The offeror and the Government shall agree to the subcontractors or the subcontracted effort selected for application of the EVMS requirements.  The offeror shall be responsible for ensuring that the selected subcontractors comply with the requirements of the Earned Value Management System clause of the contract.

(End of provision)

252.234-7002  Earned Value Management System.

As prescribed in 234.203(2), use the following clause:

EARNED VALUE MANAGEMENT SYSTEM (APR 2008)

(a)  In the performance of this contract, the Contractor shall use—

(1)  An Earned Value Management System (EVMS) that complies with the EVMS guidelines in the American National Standards Institute/Electronic Industries Alliance Standard 748, Earned Value Management Systems (ANSI/EIA-748); and

(2)  Management procedures that provide for generation of timely, reliable, and verifiable information for the Contract Performance Report (CPR) and the Integrated Master Schedule (IMS) required by the CPR and IMS data items of this contract.

(b)  If this contract has a value of $50,000,000 or more, the Contractor shall use an EVMS that has been determined by the Cognizant Federal Agency (CFA) to be in compliance with the EVMS guidelines as stated in paragraph (a)(1) of this clause.  If, at the time of award, the Contractor’s EVMS has not been determined by the CFA to be in compliance with the EVMS guidelines as stated in paragraph (a)(1) of this clause, the Contractor shall apply its current system to the contract and shall take necessary actions to meet the milestones in the Contractor’s EVMS plan.

(c)  If this contract has a value of less than $50,000,000, the Government will not make a formal determination that the Contractor’s EVMS complies with the EVMS guidelines in ANSI/EIA-748 with respect to the contract.  The use of the Contractor’s EVMS for this contract does not imply a Government determination of the Contractor’s compliance with the EVMS guidelines in ANSI/EIA-748 for application to future contracts.  The Government will allow the use of a Contractor’s EVMS that has been formally reviewed and determined by the CFA to be in compliance with the EVMS guidelines in ANSI/EIA-748.

(d)  The Contractor shall submit notification of any proposed substantive changes to the EVMS procedures and the impact of those changes to the CFA.  If this contract has a value of $50,000,000 or more, unless a waiver is granted by the CFA, any EVMS changes proposed by the Contractor require approval of the CFA prior to implementation.  The CFA will advise the Contractor of the acceptability of such changes as soon as practicable (generally within 30 calendar days) after receipt of the Contractor’s notice of proposed changes.  If the CFA waives the advance approval requirements, the Contractor shall disclose EVMS changes to the CFA at least 14 calendar days prior to the effective date of implementation.

(e)  The Government will schedule integrated baseline reviews as early as practicable, and the review process will be conducted not later than 180 calendar days after (1) contract award, (2) the exercise of significant contract options, and (3) the incorporation of major modifications.  During such reviews, the Government and the Contractor will jointly assess the Contractor’s baseline to be used for performance measurement to ensure complete coverage of the statement of work, logical scheduling of the work activities, adequate resourcing, and identification of inherent risks.

(f)  The Contractor shall provide access to all pertinent records and data requested by the Contracting Officer or duly authorized representative as necessary to permit Government surveillance to ensure that the EVMS complies, and continues to comply, with the performance criteria referenced in paragraph (a) of this clause.

(g)  When indicated by contract performance, the Contractor shall submit a request for approval to initiate an over-target baseline or over-target schedule to the Contracting Officer.  The request shall include a top-level projection of cost and/or schedule growth, a determination of whether or not performance variances will be retained, and a schedule of implementation for the rebaselining.  The Government will acknowledge receipt of the request in a timely manner (generally within 30 calendar days).

(h)  The Contractor shall require its subcontractors to comply with EVMS requirements as follows:

(1)  For subcontracts valued at $50,000,000 or more, the following subcontractors shall comply with the requirements of this clause:

[Contracting Officer to insert names of subcontractors (or subcontracted effort if subcontractors have not been selected) designated for application of the EVMS requirements of this clause.]

(2)  For subcontracts valued at less than $50,000,000, the following subcontractors shall comply with the requirements of this clause, excluding the requirements of paragraph (b) of this clause:

[Contracting Officer to insert names of subcontractors (or subcontracted effort if subcontractors have not been selected) designated for application of the EVMS requirements of this clause.]

(End of clause)]

* * * * *

252.242-7001  Notice of Earned Value Management System. [Reserved]

As prescribed in 242.1107-70(a)(1), use the following provision:

NOTICE OF EARNED VALUE MANAGEMENT SYSTEM (MAR 2005)

(a)  The offeror shall provide documentation that the cognizant Administrative Contracting Officer has recognized that the proposed earned value management system (EVMS) complies with the EVMS criteria of DoDI 5000.2, Operation of the Defense Acquisition System, or that the proposed cost/schedule control system has been accepted by the Department of Defense.

(b)  If the offeror proposes to use a system that does not meet the requirements of paragraph (a) of this provision, the offeror shall submit a comprehensive plan for compliance with the EVMS criteria.

(1)  The plan shall—

(i)  Describe the EVMS the offeror intends to use in performance of the contract;

(ii)  Distinguish between the offeror's existing management system and modifications proposed to meet the criteria;

(iii)  Describe the management system and its application in terms of the 32 EVMS criteria;

(iv)  Describe the proposed procedure for administration of the criteria as applied to subcontractors; and

(v)  Provide documentation describing the process and results of any third-party or self-evaluation of the system’s compliance with EVMS criteria.

(2)  The offeror shall provide information and assistance as required by the Contracting Officer to support review of the plan.

(3)  The Government will review the offeror’s plan for EVMS before contract award.

(c)  Offerors shall identify the major subcontractors, or major subcontracted effort if major subcontractors have not been selected, planned for application of the criteria.  The prime contractor and the Government shall agree to subcontractors selected for application of the EVMS criteria.

(End of provision)

252.242-7002  Earned Value Management System. [Reserved]

As prescribed in 242.1107-70(a)(2), use the following clause:

EARNED VALUE MANAGEMENT SYSTEM (MAR 2005)

(a)  In the performance of this contract, the Contractor shall use an earned value management system (EVMS) that has been recognized by the cognizant Administrative Contracting Officer (ACO) as complying with the criteria provided in DoDI 5000.2, Operation of the Defense Acquisition System.

(b)  If, at the time of award, the Contractor’s EVMS has not been recognized by the cognizant ACO as complying with EVMS criteria (or the Contractor does not have an existing cost/schedule control system that has been accepted by the Department of Defense), the Contractor shall apply the system to the contract and shall be prepared to demonstrate to the ACO that the EVMS complies with the EVMS criteria referenced in paragraph (a) of this clause.

(c)  The Government may require integrated baseline reviews.  Such reviews shall be scheduled as early as practicable and should be conducted within 180 calendar days after (1) contract award, (2) the exercise of significant contract options, or (3) the incorporation of major modifications.  The objective of the integrated baseline review is for the Government and the Contractor to jointly assess areas, such as the Contractor’s planning, to ensure complete coverage of the statement of work, logical scheduling of the work activities, adequate resourcing, and identification of inherent risks.

(d)  Unless a waiver is granted by the ACO, Contractor-proposed EVMS changes require approval of the ACO prior to implementation.  The ACO shall advise the Contractor of the acceptability of such changes within 30 calendar days after receipt of the notice of proposed changes from the Contractor.  If the advance approval requirements are waived by the ACO, the Contractor shall disclose EVMS changes to the ACO at least 14 calendar days prior to the effective date of implementation.

(e)  The Contractor agrees to provide access to all pertinent records and data requested by the ACO or duly authorized representative.  Access is to permit Government surveillance to ensure that the EVMS complies, and continues to comply, with the criteria referenced in paragraph (a) of this clause.

(f)  The Contractor shall require the following subcontractors to comply with the requirements of this clause:

(Contracting Officer to insert names of subcontractors selected for application of EVMS criteria in accordance with 252.242-7001(c).)

(End of clause)

* * * * *

252.242-7005  Cost/Schedule Status Report.

As prescribed in 242.1107-70(b), use the following clause:

COST/SCHEDULE STATUS REPORT (MAR 2005)

(a)  The Contractor shall use management procedures in the performance of this contract that provide for—

(1)  Planning and control of costs;

(2)  Measurement of performance (value for completed tasks); and

(3)  Generation of timely and reliable information for the cost/schedule status report (C/SSR).

(b)  As a minimum, these procedures must provide for—

(1)  Establishing the time-phased budgeted cost of work scheduled (including work authorization, budgeting, and scheduling), the budgeted cost for work performed, the actual cost of work performed, the budget at completion, the estimate at completion, and provisions for subcontractor performance measurement and reporting;

(2)  Applying all direct and indirect costs and provisions for use and control of management reserve and undistributed budget;

(3)  Incorporating changes to the contract budget base for both Government directed changes and internal replanning;

(4)  Establishing constraints to preclude subjective adjustment of data to ensure that performance measurement remains realistic.  The total allocated budget may exceed the contract budget base only after consultation with the Contracting Officer.  For cost-reimbursement contracts, the contract budget base shall exclude changes for cost growth increases, other than for authorized changes to the contract scope; and

(5)  Establishing the capability to accurately identify and explain significant cost and schedule variances, both on a cumulative basis and projected at completion basis.

(c)  The Contractor may use a cost/schedule control system that has been recognized by the cognizant Administrative Contracting Officer (ACO) as complying with the earned value management system criteria provided in DoDI 5000.2, Operation of the Defense Acquisition System.

(d)  The Government may require integrated baseline reviews.  Such reviews shall be scheduled as early as practicable and should be conducted within 180 calendar days after (1) contract award, (2) the exercise of significant contract options, or (3) the incorporation of major modifications.  The objective of the integrated baseline review is for the Government and the Contractor to jointly assess areas, such as the Contractor’s planning, to ensure complete coverage of the statement of work, logical scheduling of the work activities, adequate resourcing, and identification of inherent risks.

(e)  The Contractor shall provide access to all pertinent records, company procedures, and data requested by the ACO, or authorized representative, to—

(1)  Show proper implementation of the procedures generating the cost and schedule information being used to satisfy the C/SSR contractual data requirements to the Government; and

(2)  Ensure continuing application of the accepted company procedures in satisfying the C/SSR data item.

(f)  The Contractor shall submit any substantive changes to the procedures and their impact to the ACO for review.

(g)  The Contractor shall require a subcontractor to furnish C/SSR in each case where the subcontract is other than firm-fixed-price, is 12 months or more in duration, and has critical or significant tasks related to the prime contract.  Critical or significant tasks shall be defined by mutual agreement between the Government and Contractor.  Each subcontractor's reported cost and schedule information shall be incorporated into the Contractor's C/SSR.

(End of clause)

252.242-7006  Cost/Schedule Status Report Plans.

As prescribed in 242.1107-70(c), use the following provision:

COST/SCHEDULE STATUS REPORT PLANS (MAR 2005)

(a)  The offeror shall submit a written summary of the management procedures it will establish, maintain, and use in the performance of any resultant contract to comply with the requirements of the clause at 252.242-7005, Cost/Schedule Status Report.

(b)  If the offeror proposes to use a cost/schedule control system that has been recognized by the cognizant Administrative Contracting Officer as complying with the earned value management system criteria of DoDI 5000.2, Operation of the Defense Acquisition System, the offeror may submit a copy of the documentation of such recognition instead of the written summary required by paragraph (a) of this provision.

(End of provision)