| Acquisition Process Scenario: 1. Open Market -Not Simplified Acquisition |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Roles: PO, BO, FO, OSDBU, AT, SSA, Offerors, PO/BO |  |  | Systems: C = Current, F= Future, P = Partial |  |  |  |  |  |  |
| PO | Program Office (Role performs: program management, sustainment/logistics, data, facility support, programmatics, end user) |  | #### BO |  | Buying Office (Role performs: contracting/purchasing functions) |  |  |  |  |
| FO | Finance Office (Role performs: accounting functions, budget functions) |  | #### OSDBU |  | Small Business |  |  |  |  |
| AT | Acquisition Team (Role performs: Defined by FAR 1.102-3) |  | #### SSA |  | Source Selection Authority- Determines Awardee |  |  |  |  |
| Offerors | Quoters, Bidders, or Offerors |  | #### PO/BO |  | Either or PO/ BO |  |  |  |  |
| # | Activity | #### Description | #### Role | Systems |  |  |  | Information Exchanges | Control / Business Rules |
|  |  |  |  | C |  | Name | F |  |  |
| 1. | ### Define Requirements |  |  |  |  |  |  |  |  |
| 1.1 | Determine Need | Draft requirement, establish budget, and seek budget approval. | PO |  |  |  |  |  | FAR 7.105(a), 7.107, 10.001(a) 11.002, 11.401, |
| 1.1.1 | Record Funding | Record funding. | FO |  |  |  |  |  |  |
| 1.1.2 | Combine Requirements | Explore ability to combine requirements, explore best business arrangements (contract partnering). | BO |  |  |  |  |  |  |
| 1.2 | Validate Funding | Validate funding line. This may include commitment or obligation depending on agency specific business procedures. | BO |  |  |  |  |  | OMB Circular A-11; DoD FMR Vol 2A, Chapter 2A Sec 0102; FAR 32.702 |
| 1.2.1 | Validate Funding | Validate funding line and budget restrictions. | PO |  |  |  |  |  |  |
| 1.2.2 | Validate Funding | Validate funding line and budget restrictions. | FO |  |  |  |  |  |  |
| 1.3 | Acquisition Planning | Develop acquisition plan data. | PO |  |  |  |  |  | FAR: 1.102-3, 7.103, 7.105; 7.4, 14.201(a), 15.100, 15.101, 15.201(c) FAR 19.202 11.401 |
| 1.3.1 | Acquisition Planning | Develop and Coordinate Acquisition Planning (Forecast and Acquisition Plan). | BO |  |  |  |  |  | FAR: 1.102-3, 7.103; 7.105; 7.4, 14.201(a), 15.100, 15.101, 15.201(c), 19.202 |
| 1.3.2 | Validate Goals | Validate and publish goals and agency forecast. Generally done once a year. | OSDBU | X |  | Acqnet |  | - Publish goals and forecast |  |
|  |  |  |  |  |  | FBO | X | - Publish goals and forecast |  |
| 1.4 | Purchase Request | Submit to Buying Office. Should include Statement of work/ specifications, or other requirements and evaluation criteria. | PO |  |  |  |  |  | 15, Sec 150202; FAR 32.7 |
| 1.4.1 | Communicate Purchase Request to BO | Transfer of purchase request data from PO thru FO to BO. |  |  |  |  |  |  | Agency-specific |
| 1.5 | Assigned Buyer / Contract Specialist | Buying Office analyzes requirement; assigns to buyer / contract specialist. | BO |  |  |  |  |  | Agency policy; FAR 7.102(b) OMB Cir A-11 |
| 2. | Market Research |  |  |  |  |  |  |  |  |
| 2.1 | Follow Order of Required Sources | For supplies: internal first, warehouses, UNICOR, JWOD, schedules, and open market. For services: JWOD, UNICOR, schedules, and open market. | BO |  |  |  |  |  | FAR 8.001 |
| 2.1.1 | Check Agency Excess Property | Check Agency excess property. | PO |  |  |  |  |  | FAR 8.001 |
| 2.1.2 | Check Federal Excess Property | Check Federal excess property. | PO | X |  | FEDS | X | - Check Federal excess personal property | FAR 8.001 |
| 2.1.3 | Check Required Sources | Check required sources i.e., JWOD & UNICOR sources. | BO | X |  | JWOD Website | X | - Check required source | FAR 8.7, 8.6 41 USC 46-48c; 18 USC 4121-4128 |
|  |  |  |  | X |  | UNICOR Website | X | - Check required source |  |
| 2.1.4 | Check Federal Supply Schedules/ Multiple Award Contracts / GWACs | Check Federal Supply Schedules/ Multiple Award Contracts / GWAC. | PO/ BO |  |  | eCatalog | X | - Check Supply Schedules - Check GWACs | FAR 8.4; 16.505; 41 USC 102-36.65 |
|  |  |  |  | X |  | Advantage | X | - Check Supply Schedules |  |
|  |  |  |  | X |  | Buyers.gov | X | - Reverse auction for IT against FSS and FTS contracts |  |
|  |  |  |  | X |  | FBO | X | - Check for potential combining of requirements |  |
| 2.2 | Conduct Market Survey | Determine industrial category (NAICS) and size standards. Gather market survey findings. | BO | X |  | Census Website | X | - Check for specific NAICS | FAR 6.102; 19.201; FAR 19.303 |
|  |  |  |  | X |  | CCR/BPN | X | - Use NAICS to find potential Offerors |  |
| 2.2.1 | Validate Market Survey Findings | Validate NAICS. Validate small business opportunities. | OSDBU | X |  | Census Website |  | - Check with a specific NAICS | FAR 6.102, 19.201, 19.303 |
|  |  |  |  | X |  | CCR/BPN | X | - Use NAICS to find potential Offerors |  |
| 2.3 | Issue Sources Sought Notice | Posting in newspapers, single point of government entry, trade magazines, other specialized web sites. | BO | X |  | FBO | X | - Post synopsis for sources sought | FAR 5.002, 5.101; 15 USC 637(e), 41 USC 416 |
| 2.3.1 | Establish Information Library | Drawings, specifications and other related documents. (Role may shift to PO) | BO | X |  | FBO | x | - Upload documents | FAR 15.201(f); 11.201; 5.102(b)(iii) 14.211(a) |
|  |  |  |  |  |  | FedTeds | X | - Upload documents |  |
| 2.3.2 | Assess Responses From Sources Sought | Receive responses and coordinate evaluations by the Acquisition Team. | BO | X |  | CCR/BPN | X | - Compare NAICS - Assess capabilities – Validate interest in type of requirement | FAR 15.202 14.101(a), (b) |
|  |  |  |  | X |  | ProNET |  | - Assess capabilities – Validate business size |  |
|  |  |  |  | X |  | FPDS | X | - Assess capabilities – validate experience |  |
|  |  |  |  |  |  | PPIRS | X | - Assess capabilities – validate past performance |  |
| 2.4 | Negotiate Set-aside | Prepare a position/recommendation document. | BO |  |  |  |  |  | FAR 19.5 |
| 2.4.1 | Review Recommendations | Review and resolve position/recommendation. | OSDBU |  |  |  |  |  |  |
| 3.0 | Issue Synopsis/RFQ/ RFP / Invitation for Bid (IFB) | Issue pre-solicitation synopsis advertising that requirements need to be filled. |  |  |  |  |  |  |  |
| 3.1 | Post Notice of Contract Action (Pre-solicitation Synopsis) | Post to Federal Single Point of Entry, newspapers, periodicals, trade journals, and professional journals. | BO | X |  | FBO | X | - Advertising requirement | FAR 5.201(a) |
| 3.1.1 | Post combined synopsis/solicitation | Post combined synopsis/solicitation. | BO | X |  | FBO |  | - Advertising requirement & post solicitation | FAR 12.603 |
| 3.1.2 | Process IVL | Enabling Interested Vendors List (IVL). (Optional) | BO | X |  | FBO | X | - Enable Interested Vendors List per solicitation | FAR 14.205, 13.104, 13.102 |
|  |  |  |  |  |  | BPN | X | - Use NAICS to develop potential consideration list |  |
| 3.2 | Modify Synopsis | Modify Synopsis. | BO | X |  | FBO |  | - Modify synopsis | FAR 5.201(a) |
| 3.2.1 | Amend Combined synopsis-Solicitation | Amend combined synopsis-solicitation. | BO | X |  | FBO |  | - Amend combined synopsis-solicitation | FAR: 12.102 (b), 13.105, 14.208, 15.206, |
| 3.3 | Pre-Solicitation Process | Pre-Solicitation Process. |  |  |  |  |  |  |  |
| 3.3.1 | Develop Selection Plan | Section L: Instructions to Offerors Section M: Evaluation Criteria (Price, Quality, Past Performance); Establishing evaluation factors and significant sub-factors, e.g. that would fall in to source selection plan. Coordinate with PO, FO, OSDBU, and Legal. | BO |  |  |  |  |  | FAR 12.203, 12.303, 13.106-1(a) (2), 13.106-2, 13.106-2(b), 13.106-3 (a), 14.201-5 (b) – (c), 14.201-8, 14.206-6, 15.1, 15.304, 15.305 10 USC 2305, 41 USC 253a |
| 3.3.2 | Build Solicitation | Develops and coordinates review of formal solicitation. This includes technical requirements provided and reviewed by the PO. The method of procurement (RFP, IFB, and RFQ) is determined and the Legal Office reviews for legal sufficiency. | BO | X |  | DOL –Wage Determination (Davis-Bacon) | X | - Extract wage determination (post in the solicitation for construction) | FAR 15.203-204, 14.201, 12.303, FAR 12.04, 13.106-1, 2.101 |
|  |  |  |  | X |  | NTIS / SCA Wage Determination | X | - Obtain service contract wage determinations |  |
| 3.4 | Solicitation Process |  |  |  |  |  |  |  |  |
| 3.4.1 | Pre-Solicitation Contact with Potential Offerors | Pre solicitation conferences, one-on-ones, draft solicitations, and other reviews by potential Offerors to obtain feedback and publicize. | BO | X |  | FBO | x | - Push page updates to IVs | FAR 12.102 (b), 15.201, 13.104, 14.207, 14.211 |
| 3.4.2 | Issue Solicitation | Issue solicitation. | BO | X |  | FBO | X | - Issue / post solicitation | FAR 5.003, 5.102(a), 12.102 (b), 13.106-1, 14.203, 15.205, |
|  |  |  |  |  |  | FedTEDS | X | - Upload technical drawings |  |
| 3.4.3 | Solicitation Inquiries | Post solicitation Inquiries (Vendor questions, concerns, and clarifications) obtained either by written communication or from a pre-proposal conference go through Contracting Office. | BO | X |  | FBO | X | - Post responses to inquiries | FAR 12.102 (b), 13.106-1, 14.203, 15.206, 15.201(f); 15.303(c) |
| 3.4.4 | Amend Solicitation | Amend solicitation. | BO | ### X |  | FBO | X | - Post amendments to solicitations | FAR 12.102 (b), 12.603 (b) (4), 13.105 (a), 14.208, 15.206 |
| 3.4.5 | Respond to Solicitation Protest | Can happen at any time before receipt of proposals. Solicitation protests can go to: GAO, Federal Court, Contracting Officer. | BO |  |  |  |  |  | FAR 12.102 b, 13.106-3(c), 14.408-8, 15.507, 33.1 |
| 4. | Evaluate Responses | Evaluate Responses activities based on RFP |  |  |  |  |  |  |  |
| 4.1 | Receive Response | Receive response. | BO |  |  |  | X | - Receive electronic vendor responses (use this wording for invoices) | FAR 15.207-208 |
| 4.2 | Conduct Initial Evaluation | Determine responsiveness. | BO | X |  | CCR |  | - Check for existence of registration | FAR 15.304-305 |
|  |  |  |  |  |  | BPN | X | - Validate vendor information Check far Reference for order |  |
|  |  |  |  |  |  | ORCA | X | - Retrieve representations and certifications (R&C) |  |
| 4.3 | Evaluate Business Proposal | Buying Office requests evaluators; transmit documents to evaluators, evaluates price/costs, terms and conditions. | BO |  |  |  |  |  | FAR 15.3, 15.303(a)(4), 15.305(a), 15.305(a)(3) |
| 4.4 | Evaluate Technical Proposal | Evaluate technical proposal. | PO |  |  |  |  |  | FAR 13.305(a)(1), 15.3, 15.303(a)(4), 15.305(a), 15.305(a)(3) |
| 4.4.1 | Evaluate Past Performance | Review both past and current performance utilizing online tools and telephone surveys of references | BO | x |  | PPIRS | x | - Check past performance information | FAR 15.305(a)(2) |
| 4.5 | Request Clarifications | Clarifications plus exchanges before establishment of competitive range, to determine relative ranking of Offerors absent discussion. | BO |  |  |  |  |  | FAR 15.306(a) and (b) |
| 4.6 | Determine Competitive Range | Narrow vender pool to those vendors that have a reasonable chance to receive an award. Range is determined based on outcome of evaluation. | BO |  |  |  |  |  | FAR 15.306(c): 10 USC 2305(b)(4), 41 USC 253b(d) |
| 4.6.1 | Notify Exclusions and Perform Pre-Award Debriefing | Notify vendors outside the competitive range and perform pre-award debriefing if requested. | BO |  |  |  |  |  | FAR 15.306(c)(3) & (4), 15.505 (only for negotiated) |
| 4.7 | Address Pre-Award Protests | Protests can go to GAO, Fed Court, or Contracting Officer and may occur any time before award. | BO |  |  |  |  |  | FAR 12.102 (b), 13.106-3 (c), 14.408-8, 15.507, 33.1 |
| 4.8 | Exchanges with Offerors | At request of the contracting officer. Can include: requirements, resources, cost/price, schedule, place of delivery / performance, technical approach, and provide an opportunity to correct deficiencies and make clarifications. | BO | X |  | DOL Wage Determination Web Site (Davis-Bacon) | X | - Extract wage determination from Dept of Labor and post in the solicitation for construction | FAR 15.306(d) |
|  |  |  |  | X |  | NTIS / SCA Wage Determination | X | - Obtain service contract wage determinations |  |
| 4.8.1 | Receipt of Proposal Revisions | Receive proposal revisions including final offer as a result of ongoing exchange with Offeror. | BO |  |  |  |  |  | FAR 15.306, 15.307 |
| 4.8.2 | Evaluation of Proposal Revisions |  | BO |  |  |  |  |  | FAR 15.305 |
| 4.8.2.1 | Evaluate Revised Business Proposal | Transmit revised documents to evaluators; Evaluate price/costs, and terms and conditions. | BO |  |  |  |  |  | FAR 13.305(a)(1), 15.3 |
| 4.8.2.2 | Evaluate Revised Technical Proposal | Evaluate revised technical proposal. | PO |  |  |  |  |  | FAR 13.305(a)(1), 15.3, |
| 4.8.3 | Conclusion of Exchanges | Common cut off date for final proposal revision. | BO |  |  |  |  |  | FAR 15.307(b) |
| 4.8.4 | Receipt of Final Proposal Revisions | Receive final proposal revisions as a result of conclusion of exchanges. | BO |  |  |  |  |  | FAR 15.307(b) |
| 4.9 | Pre-Award Surveys and Approvals | Verify eligibility of prospective awardee thru EEO clearance (as applicable), DCAA & DCMA | BO | X |  | DOL pre-award Website, | x | - Check vendor EEO | FAR 9.1; 9.4; 22.805(a) |
|  |  |  |  | X |  | EPLS | X | - Obtain EPLS status |  |
|  |  |  |  |  |  | BPN | X | - Obtain EPLS status |  |
|  |  |  |  |  |  | D&B | X | - Check financials |  |
| 4.10 | Source Selection Decision | Includes responsibility determination, cost technical trade offs, justification of selection, and debarred list. | SSA |  |  |  |  |  | FAR 15.308 |
| 5.0 | Issue Award |  |  |  |  |  |  |  |  |
| 5.1 | Verify Funds Availability | Ensure sufficient funds are available for proposed award value. This may include obligation depending on agency specific business procedures. | BO |  |  |  |  |  | FAR 32.702 |
| 5.2 | Prepare Award | Assemble and prepare award documentation. Execute procurement instrument. | BO |  |  |  |  |  | FAR 14.408-1, 15.204, 15.504 |
| 5.3 | Prepare Management Award Information | Develop and submit federal procurement data regarding specific current award. | BO | X |  | FPDS | X | - Report Information | FAR 4.6 |
|  |  |  |  |  |  | GWAC Index | X | - Post award data |  |
| 5.4 | Issue Award Notices | Post required notices: - Pre-award notices under set- asides this is an intent to award to vendor (only for vendors in competitive range) - Congress (as applicable), - Post award notice (FBO); - Unsuccessful Offerors - DOL (as applicable) | BO | X |  | FBO | X | - Post award notice | FAR 5.303, 12.102 (b), 13.106-3(c) 14.409-1 (b), 15.503, ; agency regs e.g. DFARS 204.6 for reports to Congress |
|  |  |  |  | X |  | ECats | X | - Post vendor data to catalogs |  |
|  |  |  |  |  |  | DOL | X | - Inform Award of service based contract performance |  |
|  |  |  |  | X |  | Sub-net |  | - Post subcontracting opportunities |  |
|  |  |  |  | X |  | FACNET |  | - EDI Transaction |  |
|  |  |  |  |  |  |  | x | - Potential for electronic transmission to Congress |  |
| 5.5 | Distribute Award Document | Send document / notification to: - Finance office - Program Office - OSDBU - Contractor - Contract Administration - DCAA - Security | BO | P |  | EDA | X | - Post all award documents to provide for internal notifications | FAR 4.201 |
|  |  |  |  |  |  | CADO | X | - Post contract award documents to provide for transparency and visibility |  |
| 5.6 | Perform Post Award Debriefing | One-on-one discussion with non-selected Offerors of the aspects of their proposal and top-level information of the winner only. Coordinate with Legal and Program Office | BO |  |  |  |  |  | FAR 14.409-1(b), 15.506 |
| 5.7 | Address Post-Award Protest | Resolve post award protests, thru Alternative Dispute resolution (ADR) or court. Rule 4 file is developed. This activity is coordinated with Legal Office. | BO | X |  | GAO website |  | - Conduct legal research | FAR 12.102(b), 13.106-3 (c), 14.408-8, 15.507, 33.1 |
|  |  |  |  | X |  | Court of Claims Web site |  | - Conduct legal research |  |
|  |  |  |  | X |  | Lexus/Nexus & Others |  | - Conduct legal research |  |
| 6. | Monitor Performance/Contract Administration |  |  |  |  |  |  |  |  |
| 6.1 | Conduct Post-Award Orientation | Conduct post award conferences exchanging information to verify baseline program performance, and to create consistent expectations between the contractor and government team. Activity may be worked in conjunction with PO and Administrative Contracting Officer (ACO). | BO |  |  |  |  |  | FAR 42.5 |
| 6.2 | Issue Notice to Proceed | Provide authority to proceed with contract performance (For Construction Contracts Only). | BO |  |  |  |  |  | FAR 36.213(e) |
| 6.3 | Monitor & Document Performance | Communication and documentation between Government and Contractor regarding quality and timeliness. Accomplished by COTR under authority of Contracting Officer (PCO or ACO). | PO | x |  | DOD CPARS | x | - Post Performance Information | FAR 42, 46.4 |
|  |  |  |  | X |  | NIH CPS | x | - Post Performance Information |  |
|  |  |  |  | X |  | NASA PPDBS | x | - Post Performance Information |  |
|  |  |  |  | X |  | Army PPMIS |  | - Post Performance Information |  |
|  |  |  |  | X |  | FDIC |  | - Post Performance Information |  |
|  |  |  |  | X |  | Education |  | - Post Performance Information |  |
| 6.3.1 | Inspect Goods and or Services | Preparation and completion of receiving documentation (e.g. DD250). | PO |  |  | PPIRS | x | - Collecting passive past performance information as it relates to timeliness quality, and delivery | FAR 46.5 |
| 6.3.2 | Accept Goods and or Services | For each contract line item number. | BO/PO |  |  |  |  |  | FAR 46.5 |
| 6.3.3 | Manage Property | Adjust agency property (includes government furnished items or equipment or contractor purchased items or equipment). | PO | X |  | FEDS or DRMO |  | - Identify disposal of excess contractor acquired property |  |
| 6.4 | Process Contract Changes | Issue modifications or change orders. Contracting Officer working in coordination with PO, ACO, FO, & Legal. | BO |  |  |  |  |  | FAR 43 |
| 6.4.1 | Verify Funding | Ensure sufficient funds are available for proposed award value. | BO |  |  |  |  |  | FAR 32.702 |
| 6.4.2 | Prepare Management Award Information | Develop and submit federal procurement data regarding specific current award. | BO | X |  | FPDS-NG | X | - Report Management Information | FAR 4.6 |
|  |  |  |  |  |  | GWAC Index | X | - Post award Management data on GWAC index as applicable |  |
| 6.4.3 | Issue Novation Agreements | Administrative modification to the contract due to changing contractor name, banking information, and addresses. ACO / PCO must approve name change. | BO |  |  | BPN | X | - Notification of name change | FAR 42.12 |
| 6.5 | Assignment of Claims | Re-designate remittance entity. | BO | P |  | CCR/BPN | X | - Change payee (EFT) | FAR 32.8 |
| 7. | Approve Payment |  |  |  |  |  |  |  |  |
| 7.1 | Receive Invoice | Must meet requirements set forth in contract. Role is dependent on how agency writes contract. | BO/ FO/ PO |  |  |  |  |  | FAR 52.232-25 |
| 7.2 | Submit Invoice to Finance Office | Communicate approved invoice to Finance Office. | BO/ PO |  |  |  |  |  | FAR 32.9 |
| 7.3 | Match Invoice to Receiving Report and Obligating Document | Ensure goods and or services have been performed satisfactory against contract requirements. | FO |  |  |  |  |  | FAR 46.502 FAR 32.702 |
| 8. | Pay Vendor |  |  |  |  |  |  |  |  |
| 8.1 | Receive Approved Invoice | Finance Office receives an approved invoice thru Buying Office. | FO |  |  |  | x | Submission of invoices from vendors | DoD FMR Vol 10, Chapter 9, Sec 0903 |
| 8.2 | Ensure Availability of Funds | Verify accounting records (matching process). | FO |  |  |  |  |  | FAR 32.702 |
| 8.3 | Verify EFT Information | Finance Office originally obtained EFT information when they received the obligating document. This information must be verified before payment. | FO | P |  | CCR/BPN | X | - Obtain EFT data | FAR 32.11 |
| 8.4 | Process Payment | Produce payment requests and create an electronic voucher that is transmitted to Treasury for disbursement. | FO |  |  |  |  |  | FAR 32.9 |
| 8.4.1 | Verify Off-sets | Verify if payment should be reduced due to amounts owed to government by contractor. | Treasury, DFAS | X |  | TOPs | X | - Verify payment e.g. TIN | Debt Collection Improvement Act PL 104-134 |
| 8.4.2 | Transfer Funds | Pay Vendor via check or EFT. | Federal Reserve, DFAS |  |  |  |  |  |  |
| 9. | Close Out |  |  |  |  |  |  |  |  |
| 9.1 | Certify All Work has been Completed | Check that all requirements under contract have been satisfactorily met and that there are no outstanding claims or judgments. | PO |  |  |  |  |  | FAR 4.804-5(a) |
| 9.2 | Settle Any Claims | Negotiate outstanding claims and obtain release of claims. | BO |  |  |  |  |  | FAR 4.804-5(a)(14) |
| 9.3 | Issue Final Past Performance Evaluation | Produce final performance evaluation identifying quality and timeliness throughout the history of the contract. | PO | X |  | DOD CPARS | X | - Update performance data for close-out | FAR 42.15 |
|  |  |  |  | x |  | NIH CPS | x | - Update performance data for close-out |  |
|  |  |  |  | x |  | NASA PPDBS | x | - Update performance data for close-out |  |
| 9.4 | Pay Final Invoice | See Pay vendor 8.1-8.42 |  |  |  |  |  |  | FAR 4.804-5(b), 52.222-7, 52.52.222-41(k) |
| 9.5 | Maintain Archival Contract Files | Maintain official contract records in accordance agency procedures and NARA requirements. | BO |  |  | FPDS-NG | X | - Report close-out information (12c FPDS-NG requirement reason for modification “closed-out”) | FAR 4.805 |
|  |  |  |  |  |  |  | X | - Record Mgt per NARA |  |