## PART Qs & Section Scoring
OMB Program Assessment Rating Tool (PART)
Research & Development Programs
Name of Program: Advanced Fuel Cycle Initiative
Section I: Program Purpose & Design (Yes,No, N/A)
Questions |  | Ans. | Explanation | Evidence/Data | Weighting | Weighted Score
1 | Is the program purpose clear? | Yes | The purpose of the Advanced Fuel Cycle Initiative (AFCI) is to reduce significantly the volume and toxicity of spent nuclear fuel generated by commercial nuclear power plants and thereby reduce the costs of waste disposal. | National Energy Policy; Appropriation Language;Secretary Abraham Statements; AFCI Report to Congress (October 2002), Report of the U.S./Russian Joint Working Group on Advanced Nuclear Technologies (July 2002); Nuclear Energy Research Advisory Committee (NERAC) Advanced Nuclear Transformation Technology (ANTT) Subcommittee meeting reports; FY 2004 Budget; and the AFCI Five-Year Program Plan. | 16.67% | 0.1667
2 | Does the program address a specific interest, problem or need? | Yes | DOE's plan addresses size and cost of repository, proliferation risk and toxicity of spent fuel. Recommended by National Energy Policy Report. Merits of initiative are debated in scientific and technical community. | National Energy Policy; Secretary Abraham Statements; AFCI Report to Congress (September 2002), Report of the U.S./Russian Joint Working Group on Advanced Nuclear Technologies (July 2002); NERAC ANTT Subcommittee meeting reports. | 16.67% | 0.1667
3 | Is the program designed to make a unique contribution in addressing the interest, problem or need (i.e., not needlessly redundant of any other Federal, state, local or private efforts)? | Yes | This is a unique initiative that does not duplicate any other Federal or non-Federal program. | AFCI Report to Congress (September 2002), Report of the U.S./Russian Joint Working Group on Advanced Nuclear Technologies (July 2002); NERAC ANTT Subcommittee meeting reports. | 16.67% | 0.1667
4 | Is the program optimally designed to address the interest, problem or need? | Yes | The program has been designed with extensive government, industry, academia and international collaboration to achieve the program objectives. | AFCI Report to Congress (September 2002); Report of the U.S./Russian Joint Working Group on Advanced Nuclear Technologies (July 2002); NERAC ANTT Subcommittee meeting reports; FY 2004 Budget Request | 16.66% | 0.1666
5 (RD 1) | Does the program effectively articulate potential public benefits? | Yes | Developing advanced fuel cycles for current and next generation nuclear reactors could significantly reduce the amount and toxicity of spent nuclear waste and thereby reduce the cost of waste disposal. Knowledge of life-cycle costs is limited. | Secretary Abraham Statements; AFCI Report to Congress (October 2002), Report of the U.S./Russian Joint Working Group on Advanced Nuclear Technologies (July 2002); NERAC Advanced Nuclear Transformation Technology (ANTT) Subcommittee meeting reports; FY 2004 Budget Request | 16.67% | 0.1667
6 (RD 2) | If an industry-related problem, can the program explain how the market fails to motivate private investment? | Yes | Private industry is unable to finance long-term, high-risk nuclear R&D programs; the potential public and environmental benefits from the program justify government sponsorship of these high-risk, leading-edge technologies. | AFCI Report to Congress (September 2002), Report of the U.S./Russian Joint Working Group on Advanced Nuclear Technologies (July 2002); NERAC ANTT Subcommittee meeting reports. | 16.66% | 0.1666
Total Section Score |  |  |  |  | 100% | 100%
Section II: Strategic Planning (Yes,No, N/A)
Questions | [5 empty] | Weighted Score
1 | Does the program have a limited number of specific, ambitious long-term performance goals that focus on outcomes and meaningfully reflect the purpose of the program? | Yes | There are four major performance goals: 1) reduce high-level nuclear waste volume, 2) reduce cost of geologic disposal, 3) reduce inventories of civilian plutonium, and 4) reduce the toxicity of high-level nuclear waste. | AFCI Report to Congress; AFCI Program Plan (September 2002) | 12% | 0.12
2 | Does the program have a limited number of annual performance goals that demonstrate progress toward achieving the long-term goals? | Yes | Annual program performance goals for 2004 include: complete UREX+ small-scale demonstrations; select iodine/technetium product storage form; complete spent fuel treatment facility pre-conceptual design study; establish final spent fuel treatment process criteria; and complete feasibility evaluation of advanced crystallization process. | AFCI Report to Congress (October 2002), the AFCI Program Plan (November 2002), and the FY 2004 Budget. | 13% | 0.13
3 | Do all partners (grantees, sub-grantees, contractors, etc.) support program planning efforts by committing to the annual and/or long-term goals of the program? | Yes | Participant performance goals and measures are established in contractors' guidance letters and work packages that support program performance goals. | AFCI Report to Congress, AFCI Program Plan (September 2002); 5-year agreements with French & Swiss; program guidance memoes and associated Statements of Work for DOE contractors. | 13% | 0.13
4 | Does the program collaborate and coordinate effectively with related programs that share similar goals and objectives? | Yes | The program is coordinated with other DOE nuclear energy and waste management programs, including the Generation IV Nuclear Energy Systems Initiative, the Nuclear Power 2010 Initiative, and the Civilian Radioactive Waste Management Program (RW). The Five-Year AFCI Program Plan clearly articulates interfaces with these programs, including RW. The Nuclear Energy (NE) program and RW worked closely on the AFCI Report to Congress and be involved in ongoing program planning and monitoring pursuant to a memorandum of understanding. | National Energy Policy; AFCI Report to Congress, NERAC ANTT Subcommittee meeting reports, FY 2004 Budget. | 12% | 0.12
5 | Are independent and quality evaluations of sufficient scope conducted on a regular basis or as needed to fill gaps in performance information to support program improvements and evaluate effectiveness? | N/A | Independent evaluations by DOE of all program participants are conducted at least semiannually. In addition, the NERAC ANTT Subcommittee conducts reviews and analysis of the program at least semiannually and reports its recommendations to DOE. Evaluations are planned as the program moves forward. | Program contracts and procedures; NERAC ANTT meeting reports | 0%
6 | Is the program budget aligned with the program goals in such a way that the impact of funding, policy, and legislative changes on performance is readily known? | No | The program budget request, goals, performance measures, and planning documents are appropriately aligned, but the budget does not show funding levels for individual projects, making potential impacts from funding changes difficult to determine. | FY 2003 and 2004 Budget Requests; Five-Year Program Plan (November 2002); AFCI Report to Congress (October 2002) | 12% | 0
7 | Has the program taken meaningful steps to address its strategic planning deficiencies? | Yes | NERAC's ANTT Subcommittee provides close review and oversight of program activities. The annual AFCI Report to Congress and AFCI program plan address specific strategic goals. | Charter for the NERAC ANTT Subcommittee and associated meeting reports; AFCI Report to Congress (September 2002); AFCI Program Plan (September 2002). | 13% | 0.13
8 (RD 1) | Is evaluation of the program's continuing relevance to mission, fields of science, and other "customer" needs conducted on a regular basis? | Yes | NERAC's ANTT Subcommittee provides close review and oversight of program activities. The annual AFCI Report to Congress and AFCI program plan address specific strategic goals. | Charter for the NERAC ANTT Subcommittee and associated meeting reports; AFCI Report to Congress (September 2002); FY 2003 and FY 2004 Budget Requests; AFCI Program Plan (September 2002) | 13% | 0.13
9 (RD 2) | Has the program identified clear priorities? | Yes | The program priorities are defined in AFCI Program Plan and the AFCI Report to Congress. The ANTT Subcommittee of NERAC provides close oversight of program activities and assists in prioritizing program activities. | Charter for the NERAC ANTT Subcommittee and associated meeting reports; AFCI Report to Congress (September 2002); AFCI Program Plan (September 2002) | 12% | 0.12
Total Section Score |  |  |  |  | 100% | 88%
Section III: Program Management (Yes,No, N/A)
Questions | [5 empty] | Weighted Score
1 | Does the agency regularly collect timely and credible performance information, including information from key program partners, and use it to manage the program and improve performance? | Yes | The Department monitors program performance on a monthly basis and uses the information to manage the program, improve performance, and determine future funding requirements. | FY 2003 and FY 2004 Budgets; Annual DOE Performance Plan and Performance Appraisal Form; Quarterly updates to the Annual Performance Plan; monthly program participant performance review; formal change control process | 12% | 0.12
2 | Are Federal managers and program partners (grantees, subgrantees, contractors, etc.) held accountable for cost, schedule and performance results? | Yes | Program performance goals are incorporated into the annual performance plans for the federal senior manager and federal program manager. Program performance goals are also incorporated into the contractor's annual performance plan and program guidance. | Annual DOE Performance Plan and Performance Appraisal Form; NE program guidance memos and associated Statements of Work | 11% | 0.11
3 | Are all funds (Federal and partners’) obligated in a timely manner and spent for the intended purpose? | Yes | Program is executed in conformance with Congressional language and established program plan. | NE program guidance memos and associated Statements of Work; NE's Monthly Obligation and Cost and Performance Tracking Report; Program Plan (September 2002) | 11% | 0.11
4 | Does the program have incentives and procedures (e.g., competitive sourcing/cost comparisons, IT improvements) to measure and achieve efficiencies and cost effectiveness in program execution? | Yes | Contractor performance is judged against project costs, schedule and technical baselines. Decisions to continue funding are based on these evaluations. Incentives are included in participants' contracts on a DOE-wide basis, not on a program-specific basis. | NE program guidance memos and associated Statements of Work; NE's Monthly Obligation and Cost and Performance Tracking Report; Program Plan (September 2002) | 11% | 0.11
5 | Does the agency estimate and budget for the full annual costs of operating the program (including all administrative costs and allocated overhead) so that program performance changes are identified with changes in funding levels? | No | Salaries, benefits, retirement funding, and other administrative expenses to support the program are included in a separate budgetary line-item ("Program Direction"). These costs are not allocated to the various programs they support. | FY 2002 Budget. | 11% | 0
6 | Does the program use strong financial management practices? | Yes | Internal controls are used in the execution of the program. | Annual Reporting for Federal Managers Financial Integrity Act | 11% | 0.11
7 | Has the program taken meaningful steps to address its management deficiencies? | Yes | Program performance goals are incorporated into staff and contractor annual performance plans and progress against these goals are monitored. The Department uses this information to evaluate contractor performance and resulting award fees. No management deficiencies have been identified. | FY 2003 and 2004 Budget Requests; Program Plan (September 2002); AFCI Report to Congress (September 2002). | 11% | 0.11
8 (RD 1) | Does the program allocate funds through a competitive, merit-based process, or, if not, does it justify funding methods and document how quality is maintained? | N/A | The program incorporates both merit-based, peer-reviewed competitive awards and national laboratory-directed awards based on technical capabilities and facilities. NE selects National Laboratories for specific AFCI R&D activities on a competitive basis. | FY 2003 and 2004 Budgets; Program Plan (September 2002); AFCI Report to Congress (September 2002); Procedure for Selection of Laboratory Contractors for AFCI R&D Activities. | 0%
9 (RD 2) | Does competition encourage the participation of new/first-time performers through a fair and open application process? | Yes | The program incorporates both merit-based, peer-reviewed competitive awards and national laboratory-directed awards based on technical capabilities and facilities. The program also has two university grant programs that competitively award ten graduate level university fellowships annually through the University of Nevada at Las Vegas and the University Research Association. f | FY 2003 and 2004 Budgets; Program Plan (September 2002); AFCI Report to Congress (September 2002);. | 11% | 0.11
10 (RD 3) | Does the program adequately define appropriate termination points and other decision points? | Yes | The AFCI Program Plan and Report to Congress identify key decision points to guide execution or termination of program activities as merited. | FY 2003 and 2004 Budgets; Program Plan (September 2002); AFCI Report to Congress (September 2002). | 11% | 0.11
11 (RD 4) | If the program includes technology development or construction or operation of a facility, does the program clearly define deliverables and required capability/performance characteristics and appropriate, credible cost and schedule goals? | N/A | Technology/facilities development not included in current budget planning scope (i.e., through 2008). | FY 2003 and 2004 Budgets; Five-Year Program Plan (November 2002); AFCI Report to Congress (October 2002) | 0%
Total Section Score |  |  |  |  | 100% | 89%
Section IV: Program Results (Yes, Large Extent, Small Extent, No)
Questions | [5 empty] | Weighted Score
1 | Has the program demonstrated adequate progress in achieving its long-term outcome goal(s)? | Small Extent | A number of near-term goals demonstrating progress on achieving the program’s long-term goals have been achieved, including an extensive systems analysis to narrow technology options to the most feasible, consistent with achieving program technical and schedule goals. From an original list of nine options, the program has selected three for detailed analysis and experimentation. Additionally, the FY 2002 goal of separating highly-radioactive isotopes from civilian spent nuclear fuel using the newly developed UREX process was fully successful. This alone has the potential to significantly reduce waste disposal costs. Furthermore, the program is on track with other planned milestones. | AFCI Report to Congress (October 2002). Five-Year Advanced Fuel Cycle Program Plan (November 2002). FY 2002 Performance and Accountability Report. | 30% | 0.099
| Long-Term Goal I: | Develop and implement technologies capable of reducing the quantity of high level nuclear waste by 2015.
| Target: | Reduce the quantity of high-level nuclear waste from commercial spent fuel requiring repository disposal by a factor of at least four.
| Actual Progress achieved toward goal: | Initial results from hot UREX test showed that separated uranium could meet current requirements for low level waste.
| Long-Term Goal II: | Develop technologies capable of reducing the radiotoxicity of high level nuclear waste by 2030.
| Target: | Reduce radiotoxicity of high level waste by a factor of 100.
| Actual Progress achieved toward goal: | Plutonium and minor actinides are the major contributors to high-level nuclear waste radiotoxicity. Analyses in the U.S. and cooperation with foreign transmutation programs have shown that light water power reactors are capable of significant plutonium destruction. Fuel development programs are underway to verify the analyses experimentally. Parallel development programs are being carried out for fuels for fast reactor and possibly accelerator-driven system transmutation of minor actinides, including experimental verification of code predictions.
| Long-Term Goal III: | Reduce the potential for release of long-lived mobile radionuclides from future repositories.
| Target: | Neptunium-237, iodine-129 and technetium-99 are the long-lived mobile radionuclides in high-level nuclear waste. The program target is to reduce their contribution to future human exposure by a factor of ten to twenty.
| Actual Progress achieved toward goal: | Neptunium-237 and its decay source, americium-241 have been fabricated into thermal reactor targets and will be irradiated and transmuted during FY 2003, with post-irradiation data available in FY 2004. The transmutation of iodine-129 has been studied in foreign countries; an experimental study will be carried out on iodine transmutation as well as technetium-99 in the U.S. in FY 2004.
| Long-Term Goal IV: | Reduce the cost of future nuclear waste repositories.
| Target: | By 2040, reduce the cost of either an expansion of the Yucca Mountain repository or a new second repository by 50%.
| Actual Progress achieved toward goal: | Analyses of the major repository cost components has shown the importance of heat load management. Experimental studies will be carried out in FY 2003 on the separation of cesium-137 and strontium-90 from nuclear waste to eliminate the short-term repository heat pulse, and minor actinide transmutation studies planned in FY 2003 will begin the effort to reduce the long-term repository heat source. Reduction in both the radiotoxicity and the mobile radionuclide constituents of the waste by transmutation will also reduce the cost of waste packages, another large contributor to repository costs.
2 | Does the program (including program partners) achieve its annual performance goals? | Large Extent | All annual performance goals have been achieved. | FY 2003 Budget Request; Performance documented in monthly performance reviews and annual contractor evaluations. | 30% | 0.201
| Key Goal I: | Begin irradiation of metallic and nitride fuel specimens in the Advanced Test Reactor, Idaho National Engineering and Environmental Laboratory.
| Performance Target: | Complete preparation of both metallic and nitride fuel elements for irradiation in August 2002.
| Actual Performance: | Metallic elements completed on schedule; nitride elements delayed until the end of September 2002.
| Key Goal II: | Perform hot experimental verification of URanium EXtraction (UREX) separations flowsheet.
| Performance Target: | Complete hot UREX tests and analyses by September 30, 2002.
| Actual Performance: | Tests were delayed approximately one week by equipment failure in the hot cells and some analytical data will not be available in time to complete all analyses by the end of FY 2002. The total delay will be approximately one month.
| Key Goal III: | Award ten competitively selected fellowships leading to masters degrees in scientific and engineering subjects closely related to the Advanced Fuel Cycle Initiative program.
| Performance Target: | Complete selection in spring of 2002 to allow summer employment of most fellows at national laboratories performing AFCI R&D.
| Actual Performance: | Selection completed on schedule, with summer employment opportunities offered to all fellows. One student resigned his fellowship, but a replacement was quickly selected.
Footnote: Performance targets should reference the performance baseline and years, e.g. achieve a 5% increase over base of X in 2000.
3 | Does the program demonstrate improved efficiencies and cost effectiveness in achieving program goals each year? | No | The program has been in operation for three years. During each year there has been a steady improvement in both management systems and technical achievements. NE is successfully leveraging its R&D funding with the international community; however, DOE contracts do not award program-specific efficiencies. | Improvements are documented in the annual contractor performance reviews and in the monthly cost and schedule performance reviews. | 20% | 0
4 | Does the performance of this program compare favorably to other programs with similar purpose and goals? | N/A | Foreign programs with very similar objectives and goals have been in operation for several decades. In three years, the U.S. program has achieved a technical maturity of sufficient stature that international interest in establishing cooperative programs with the United States has grown annually. There is no similar domestic program. | French/U.S. cooperative programs in transmutation technology were established in 2001, followed by a multinational program based in Switzerland. Opportunities for cooperation with Russia, Japan and South Korea are currently under consideration. Cooperative agreements have been signed by the French and Swiss. | 0%
5 | Do independent and quality evaluations of this program indicate that the program is effective and achieving results? | Yes | The NERAC ANTT Subcommittee chaired by Nobel Laureate Burton Richter conducts ongoing external reviews and semi-annual oversight of the program. These evaluations have confirmed that the program is effective in achieving program goals. | NERAC ANTT Subcommittee meeting reports (one in FY 2001 and one in FY 2002). | 20% | 0.2
6 (RD 1) | If the program includes construction of a facility, were program goals achieved within budgeted costs and established schedules? | N/A | Facility design/construction is planned in the future, but not within the current budget planning horizon (i.e., through 2008). | AFCI Report to Congress (September 2002); AFCI Program Plan (September 2002). | 0%
Total Section Score |  |  |  |  | 100% | 50%
Note on B6: 1. Is the program purpose clear? Purpose of the question: to determine whether the program has a focused and well-defined mission. Elements of a Yes answer: a Yes answer would require a consensus of program purpose among interested parties (e.g., Congress, Administration, public) and a clear and unambiguous mission. Considerations can include whether the program purpose can be stated succinctly. A No answer would be appropriate if the program has multiple conflicting purposes. Evidence/Data: evidence can include program authorizing legislation, program documentation or mission statement.
Note on B7: 2. Does the program address a specific interest, problem or need? Purpose of the question: to determine whether the program addresses a specific interest, problem or need that can be clearly defined and presently exists. Elements of a Yes answer: A Yes answer would require the existence of a relevant and clearly defined interest, problem or need that the program is designed to address. A Yes answer would also require that the program purpose is still relevant to current conditions (i.e., that the problem the program was created to address still exists). Considerations could include, for example, whether the program addresses a specific market failure. For research and development programs, a Yes answer would require identification of relevance to specific national needs, agency missions, fields of science or technology, or other “customer” needs. A customer may be another program at the same or another agency, an interagency initiative or partnership, or a firm or other organization from another sector or country. Evidence/Data: evidence can include documentation of the problem, interest or need that the program is designed to address. An example could be the number and income levels of uninsured individuals for a program that provides care to those without health insurance. For research and development programs, relevance to agency mission should be based on specific ways that the program addresses an important aspect of the agency mission. This question corresponds to Relevance criteria I.C and I.D of the R&D criteria.
Note on B8: 3. Is the program designed to make a unique contribution in addressing the interest, problem or need (i.e., is not needlessly redundant of any other Federal, state, local or private effort)? Purpose of the question: to determine whether the program is designed to fill a defensible gap or whether it instead duplicates or even competes with other Federal or non-federal programs. Elements of a Yes answer: a Yes answer would require that the program is not redundant or duplicative of other Federal or non-federal efforts, including the efforts of state and local governments or the private and non-profit sectors. A consideration can include whether the program serves a population not served by other programs. For credit programs, a Yes answer would require evidence of the market failure/absence or unwillingness of private sector participation and an overview of the market, including all international, Federal, local, and private sector participants. For research and development programs, a Yes answer would require justification that the program provides value beyond that of any similar efforts at the agency, efforts at other agencies, or efforts funded by state and local government, private and non-profit sectors, or other counties. Justification first requires due diligence in identifying similar efforts in the past or ongoing. Evidence/Data: evidence can include the number of separate programs and total expenditures or efforts supported by those programs that address a similar problem in a similar way as the program being evaluated. For research and development programs, this question corresponds to one aspect of Relevance criterion I.B of the R&D criteria.
Note on B9: 4. Is the program optimally designed to address the interest, problem or need? Purpose of the question: to determine whether the program design is logical given the current conditions and nature of the problem and whether the design is likely to yield the intended outcomes. This question addresses many elements. Elements of a Yes answer: in this question, the burden of proof is generally on selecting a No answer since it would not be feasible to consider all possible program design alternatives. A Yes answer would require that there be no conclusive evidence that another approach would be more efficient/effective to achieve the intended purpose. A consideration could be whether the government would get the same or better outcome expending fewer total resources through a different mechanism. For example, there may be evidence that a regulatory program to ensure public safety would be more effective as a grant program. There may be evidence that a research program to improve energy efficiency would be more effective as a tax incentive. The assessment should take into account whether the program funding and activity are roughly proportionate to the scope of the problem. This element includes whether funds are divided among so many purposes or recipients that the program is unable to use or target them effectively. In the case of formula grants and loan programs, the assessment should also consider how well funds are targeted to meet the program purpose and whether funds are protected against supplantation. The examination should also consider whether the program is optimally designed in its current form or whether the design no longer makes sense due to changes in the problem. For example, if a weapons system program was intended to combat a specific threat, the assessment should ask whether the design remains optimal when the nature or magnitude of the threat has changed. This question may also address legislative factors. For example, a mandatory program assessment could consider whether the program targets the intended beneficiaries to achieve the program goal. Evidence/Data: evidence can include cost effectiveness studies comparing alternative mechanisms such as a regulation versus a grant or data on the current form of the problem.
Note on B10: RD 1. Does the program effectively articulate potential public benefits? Purpose of the question: to determine whether the program meaningfully articulates potential benefits. Elements of a Yes answer: a Yes answer would require that the program has identified potential benefits in a meaningful, credible way. R&D benefits may include technologies and methods that could provide new options in the future, if the landscape of today’s needs and capabilities changes dramatically. While all programs should try to articulate potential benefits, basic research programs may have difficulties predicting benefits of the research. For industry-related programs, a Yes answer would also require the assessment of potential program benefits and a favorable comparison to other programs with similar goals at the agency or other agencies. Evidence/Data: evidence should include a summary of any benefit analysis and documentation of any independent reviews of the analysis. This question corresponds to Relevance criterion I.B of the R&D criteria. Additionally, for industry-related programs, evidence should include a summary of any comparative benefit analysis and documentation of any independent reviews of the analysis. This question corresponds to Industry-Specific criterion IV.A of the R&D criteria.
Note on B11: RD 2. If an industry-related program, can the program explain how the market fails to motivate private investment? Purpose of the question: to determine whether the Federal government is the most appropriate actor for the activity supported by the program. (Programs not relevant to an industry or market should set the weighting of this question to zero.) Elements of a Yes answer: a Yes answer would require that the Federal contribution and impact of the program are known and that increasing or reducing the Federal funding or intervention would have a significant impact in the context of all other factors. Important considerations include the role of state and local governments and the private and non-profit sectors, and whether the program extends its impact or reach by leveraging funds and contributions from other parties. Industry-relevant programs must identify market barriers, expectations of risk, and years to commercialization, as well as building on existing technology, complementing related research, and proposing technologically feasible projects. Evidence/Data: evidence can include the percentage of total resources and requirements directed at the problem/issue that come from the program and the relative impact of those resources and requirements. This question corresponds to Industry-Specific criterion IV.B of the R&D criteria.
Note on B18: 1. Does the program have a limited number of specific, ambitious long-term performance goals that focus on outcomes and meaningfully reflect the purpose of the program? Purpose of the question: to determine if focused, long-term performance planning is used to guide program management and performance. This question seeks to assess whether the program goals used are salient, meaningful, and capture the most important aspects of program purpose and mission. Elements of a Yes answer: a Yes answer would require identifying a limited number (e.g., two or three) of specific, easily understood program outcome goals that directly and meaningfully support the program's mission and purpose. This question relates to Section 1, Question 1 in Program Purpose and Design. The goals should focus on outcomes and may or may not be those developed to comply with the Government Performance and Results Act (GPRA). While most programs have GPRA goals, many of these goals do not meet the standards of a Yes. A Yes answer can also be given, if OMB and the agency have reached agreement on a limited number of long-term outcome goals that will be added to the FY 2004 GPRA plan. Output goals would only meet the standards of a Yes answer, if the program can produce sound justification for not adopting outcome goals. Goals should be set relative to an established baseline, have clear time frames and targets, and challenge program managers to continuously improve program performance. Programs should have at least one efficiency goal. In evaluating the goals, considerations can also include whether the program is serving the right clients, such as with certain mandatory programs. A No answer would be given for long-term goals that do not directly and meaningfully relate to the program’s mission, do not have clear time frames and targets, or are focused on outputs and lack adequate justification. In some instances, a program may have multiple or even competing goals. In these cases, there may be a problem in the program design or the articulation of the program, which may require more focused program goals or a realignment of a program through management or legislative changes. Agency goals should be listed in the evidence/data section of the PART. For credit programs, customer service benchmarks for timeliness and quality of service and utilization or participation rates may be appropriate long-term outcome goals. Evidence/Data: evidence will include the long-term outcome goals established by the program either in the GPRA plan or other program document or as agreed to by OMB and to be included in FY 2004 GPRA documents. For research and development programs, this question corresponds in part to Performance criterion III.B of the R&D criteria.
Note on B19: 2. Does the program have a limited number of annual performance goals that demonstrate progress toward achieving the long-term goals? Purpose of the question: to determine whether a limited number of annual performance goals have been identified that directly support the long-term goals evaluated in Question 1 of Section II above. Elements of a Yes answer: a Yes answer would require annual performance goals that are discrete, quantifiable, and measurable. Most importantly, these annual goals should measure the program's progress towards reaching the long-term goals evaluated in Question 1 of Section II above. The annual performance goals may focus on outputs and may or may not be those developed by the agency to comply with GPRA. A Yes answer can also be given, if OMB and the agency have reached agreement on a limited number of annual goals that will be included in the FY 2004 GPRA plan. Programs are encouraged to have at least one efficiency goal. If the program received a No in Question 1 of Section II above, an explanation of how annual performance goals contribute to desired long-term outcomes and purpose of the program must be provided to receive a Yes for this question. Agency goals should be listed in the evidence/data section of the PART. For credit programs, customer service benchmarks for timeliness and quality of service and utilization or participation rates may be appropriate annual goals. For research and development programs, a Yes answer would require that the program provides single- and multi-year R&D objectives, with annual performance outputs, to track how the program will improve scientific understanding and its application. Programs must provide schedules with annual milestones for future competitions, decisions, and termination points, highlighting changes from previous schedules. Program proposals must define what would be a minimally effective program and a successful program. Some long-term basic research programs may not be able to define meaningful annual outcome performance measures, aside from process measures. In such cases, these programs may use process-related measures, especially those that can be conceptually linked to long-term research goals. Evidence/Data: evidence will include the annual goals established by the program either in a GPRA Annual Performance Plan or other program document or as agreed to by OMB and to be included in FY 2004 GPRA documents. For research and development programs, this question corresponds in part to Performance criterion III.B of the R&D criteria.
Note on B20: 3. Do all partners (grantees, sub-grantees, contractors, etc.) support program planning efforts by committing to the annual and/or long-term goals of the program? Purpose of the question: to determine whether program efforts carried out by program partners also support the annual and long-term goals of the program. Elements of a Yes answer: a Yes answer would require that program managers strive to ensure that partners support the overall goals of the program and measure and report on their performance as it relates to accomplishing those goals. For example, a program that requires all grant applications to include performance measures that will help the program achieve its goals and monitor those measures would receive a Yes. If, however, a program does not through a requirement or some other means get program grantees to link their activities to the program’s goals, a No would be appropriate. The most obvious example of a partner is an entity receiving program funding. While a program cannot always control the activities of their partners, it can exert influence through a number of mechanisms. If the program received a No for both Questions 1 and 2 of Section II above, the program must receive a No for this question. In the case of regulatory programs, all regulated entities are not necessarily defined as program partners. Evidence/Data: evidence can include procedures the program uses to get partners to commit to, measure, and report on performance related to the program's goals.
Note on B21: 4. Does the program collaborate and coordinate effectively with related programs that share similar goals and objectives? Purpose of the question: to determine whether a Federal program that shares a common purpose or goal with another program(s) collaborates with the other program(s) in a meaningful way. Elements of a Yes answer: the question does not apply to every Federal program, but to programs that have interrelated, but separately budgeted for efforts. An example of interrelated Federal programs could include the shared efforts of Veterans Affairs and Medicare to provide care for aging veterans. A Yes answer would require the program collaborate with related Federal programs, and, to the extent appropriate or possible, with state, local and private programs that share a common purpose or goal as well. A Yes answer would require that the program show evidence of collaboration leading to meaningful actions in management and resource allocation. For example, the existence of a coordinating council would not by itself constitute meaningful collaboration. Evidence/Data: evidence of meaningful collaboration could include joint grant announcements, planning documents, or referral systems.
Note on B22: 5. Are independent and quality evaluations of sufficient scope conducted on a regular basis or as needed to fill gaps in performance information to support program improvements and evaluate effectiveness? Purpose of the question: to ensure program planning is informed by non-biased evaluations that are either conducted regularly or on an as needed basis to assess program quality and fill gaps in performance information. These evaluations should be of sufficient scope to inform program improvements and influence program planning. Elements of a Yes answer: a Yes answer would require regularly scheduled objective, independent evaluations that examine how well the program is accomplishing its mission and meeting its long-term goals. In cases where a comprehensive evaluation is unnecessary based on the known effectiveness of an intervention and performance data on the program, evaluations that fill gaps in performance information can meet the elements of a Yes answer. In addition to evaluating whether the program has achieved its goals on schedule, evaluations should include recommendations on how to improve the program's performance. To ensure the program continues to meet its goals, an evaluation may be scheduled on a periodic basis, such as every two to five years or whatever time schedule is reasonable based on the specific program, its mission, and goals. To be independent, non-biased parties with no conflict of interest would conduct the evaluation. A No answer would be appropriate for a program that has no independent evaluation or (except perhaps for basic research programs) the evaluations address process and not performance. Evidence/Data: evidence can include a plan or schedule of program evaluations and program documentation describing the type of evaluation and criteria for selecting an independent evaluator. For research and development programs, this question corresponds in part to Quality criterion II.B and Performance criterion III.C of the R&D criteria.
Note on B23: 6. Is the program budget aligned with the program goals in such a way that the impact of funding, policy, and legislative changes on performance is readily known? Purpose of the question: to establish whether or not the budget planning and performance planning processes are integrated. Elements of a Yes answer: a Yes answer would require effective program budgeting based on a determination of the level of financial resources needed to obtain annual and long-term goals. For mandatory programs, this question would assess whether the impact of specific legislative or policy changes on likely performance is readily known. If a program budget structure varies markedly from program goals, the impact of funding, policy, or legislative decisions on actual performance of a program is very difficult to estimate. A program fitting this description would receive a No. A program with budget planning that is not tied to performance or strategic planning would also receive a No. A Yes response indicates the budget reflects program goals and that annual budget requests are clearly derived by estimating what is needed to accomplish the annual performance measures and long-term goals. For capital assets and services acquisition programs, programs should be able to identify impacts of changes in quantities on performance. Evidence/Data: evidence can include documentation of how the budget structure reflects program goals or how the cost accounting system aligns the budget with program goals. Evidence could also include how budget requests clearly and directly support achieving performance measures and long-term goals.
Note on B24: 7. Has the program taken meaningful steps to address its strategic planning deficiencies? Purpose of the question: to determine whether the program has developed a system of evaluating the effectiveness of its strategic planning efforts and to correct deficiencies when they are identified. Elements of a Yes answer: a Yes answer would require that the program has a system for identifying and correcting deficiencies in its strategic planning process and whether the program has taken meaningful steps to eliminate the deficiencies. A program that does not review planning efforts or does not make corrections to eliminate identified deficiencies would receive a No. The question addresses any deficiencies identified in this section. However, particular emphasis should be placed on whether the program is working to adopt a limited number of specific, ambitious long-term performance goals and a limited number of annual performance goals that demonstrate progress toward achieving the long-term goals, if they do not already have these goals. Evidence/Data: evidence can include a description of how deficiencies in the strategic planning of a program are identified and corrected as well as examples of such changes.
Note on B25: RD 1. Is evaluation of the program's continuing relevance to mission, fields of science, and other "customer" needs conducted on a regular basis? Purpose of the question: to ensure that programs are relevant to agency-, field-, or customer-needs that motivate the program. Elements of a Yes answer: a Yes answer would require that programs undergo and pass some review of relevance to their agencies, fields of science or technology, or customers. A customer may be another program at the same or another agency, an interagency initiative or partnership, or a firm or other organization from another sector or country. Industry-relevant programs may use industry cost-sharing as an indicator of market-relevance, and they should incorporate industry in planning & prioritization. Evidence/Data: evidence can include results of external reviews or other documentation that addresses program relevance. This question corresponds in part to Relevance criterion I.E and Industry-Specific criterion IV.D of the R&D criteria.
Note on B26: RD 2. Has the program identified clear priorities? Purpose of the question: to determine whether the program has clear priorities. Elements of a Yes answer: a Yes answer would require an identified set of program priorities among goals and activities within the program and program objectives. Programs are encouraged to work with independent advisory bodies to help prioritize in ways that benefit the larger science and technology enterprise. Evidence/Data: evidence can include clear statements of program priorities in program documentation or mission statements. In combination with Question 1 of Section I, this question corresponds to Relevance criterion I.A of the R&D criteria.
Note on B32: 1. Does the agency regularly collect timely and credible performance information, including information from key program partners, and use it to manage the program and improve performance? Purpose of the question: to determine whether the program collects and reports on performance and the performance of its partners and uses the data to inform program management, resource decisions, and program performance. Program partners are other agencies or intermediaries responsible for carrying out different aspects of the program and might include partner agencies, grant recipients, participating financial institutions, regulated bodies, and contractors. Timely performance information is information that provides an accurate picture of current performance and is current enough to be useful to manage the program. Credible performance information is information that is collected through a systematic and consistent process with periodic quality controls to confirm the validity of the data. Elements of a Yes answer: a Yes answer would require that the program agency regularly collect high quality performance data relating to key program goals and use that information to adjust program priorities, make resource reallocations, or take other appropriate management actions. When key program activities are carried out by other entities, such as grantees, agencies should also consider their performance as well. A Yes also requires that the agency has collected the baseline performance data necessary to set meaningful, ambitious performance targets. For capital assets and service acquisition programs, a consideration is whether the program uses an earned value management system or similar system. Some long-term basic research programs may not be able to define meaningful annual outcome performance measures, aside from process measures. In such cases, these programs may use process-related measures, especially those that can be conceptually linked to long-term research goals. Evidence/Data: evidence can include a description of how the agency uses performance information in managing the program, as well as illustrative examples of recent management actions based on performance information. Evidence can also include steps taken by a program to enact necessary improvements cited by a specific evaluation.
Note on B33: 2. Are Federal managers and program partners (grantees, sub-grantees, contractors, etc.) held accountable for cost, schedule and performance results? Purpose of the question: to determine whether the program managers and partners are accountable for achieving program results. Elements of a Yes answer: a Yes answer would require that the program agency identify the managers who are responsible for achieving key program results and establish performance standards for those managers. When program partners contribute to the achievement of program goals, a Yes would also require those partners to achieve specific performance standards. In the case of block and formula grant programs, elements of a Yes are not confined to complying with the law. Elements of a Yes can include the presence of incentives for managers and program partners that would encourage corrections in deficient programs. For capital assets and service acquisition programs, a consideration is whether contracts include minimum performance thresholds, incentives for good performance, or other mechanisms to increase accountability. Some long-term basic research programs may not be able to define meaningful annual outcome performance measures, aside from process measures. In such cases, these programs may use process-related measures, especially those that can be conceptually linked to long-term research goals. Evidence/Data: evidence can include the use of performance management contracts with program managers, or some other mechanism for incorporating program performance into personnel performance evaluation criteria. Evidence of partners’ accountability can include requiring grant and contract awards and renewals to consider past performance.
Note on B34: 3. Are all funds (Federal and partners’) obligated in a timely manner and spent for the intended purpose? Purpose of the question: to determine whether funds are administered efficiently and obligated in accordance with planned schedules and spent for the intended purposes. Elements of a Yes answer: a Yes answer would require that the program funds be obligated consistently with the overall program plan and that a limited amount of unobligated funds remain at the end of the year. A Yes answer would also require that programs and partners establish schedules for obligations that align with the overall program plan. In addition, a Yes answer requires that adequate procedures exist for reporting actual expenditures, comparing them against the intended use, and taking timely and appropriate action to correct single audit findings when funds are not spent as intended. An important consideration for this question is whether grantees take action to address any deficiencies raised in audit reports. Evidence/Data: evidence can include periodic and year-end spending reports from the program and its partners. Evidence on expenditures can include spending reports that draw intended purpose from the Congressional Justifications, Appropriations, and program operating plans and match them against actual spending. For grantees, evidence can include grantee audit reports under the Single Audit Act, including data captured in the Federal Audit Clearinghouse, and the existence of an established procedure for reviewing actual expenditures against budgets in grant awards or appropriate Federal guidelines.
Note on B35: 4. Does the program have incentives and procedures (e.g. competitive sourcing/cost comparisons, IT improvements) to measure and achieve efficiencies and cost effectiveness in program execution? Purpose of the question: to determine whether the program has effective management procedures in place to ensure the most efficient use of each dollar spent on program execution. Elements of a Yes answer: a Yes would require that the program’s performance plans include efficiency measures and targets, such as per unit cost of outputs, timing targets, and other efficiency and productivity indicators germane to the program. A de-layered management structure that empowers front line managers and that has undergone competitive sourcing (if necessary) would also contribute to a Yes answer. For mandatory programs, a Yes could require the program to seek policies that would reduce unit costs. Evidence/Data: evidence can include performance measurements for efficiency and IT improvement plans designed to produce tangible productivity and efficiency gains, or IT business cases that document how particular projects improve efficiency.
Note on B36: 5. Does the agency estimate and budget for the full annual costs of operating the program (including all administrative costs and allocated overhead) so that program performance changes are identified with changes in funding levels? Purpose of the question: to determine whether the full costs of the program are known and are budgeted. Elements of a Yes answer: a Yes answer would require the budget estimate for the program includes all direct and indirect costs borne by the program agency, including applicable agency overhead, retirement, and other costs that might be budgeted elsewhere. While having a financial management system that fully allocates program costs and associates those costs with specific performance measures is the optimal standard, a Yes can also be achieved by having a consistent, defensible way to display the full cost of achieving performance goals. Evidence/Data: evidence can include an agency program budget estimate that identified all spending categories in sufficient detail to demonstrate that all relevant costs had been included or a report that shows the allocation of overhead and other program costs to the program.
Note on B37: 6. Does the program use strong financial management practices? Purpose of the question: to determine whether the program uses effective financial management practices in administering program funds. Elements of a Yes answer: a Yes answer would require that the program be free of material internal control weaknesses reported by auditors. Additional criteria could include whether the program has procedures in place to ensure that payments are made properly for the intended purpose to minimize erroneous payments. Evidence/Data: evidence can include recent audit reports and existence of procedures to identify and measure improper payments.
Note on B38: 7. Has the program taken meaningful steps to address its management deficiencies? Purpose of the question: to determine whether the program has developed a system of evaluating program management effectiveness and means to correct deficiencies when they are identified. Elements of a Yes answer: a Yes answer would require that the program has a system for identifying and correcting deficiencies in the various aspects of program management and implements the system to make necessary corrections. A program that does not review program management activities or does not make corrections to eliminate identified deficiencies would receive a No. Evidence/Data (if available): evidence can include a description of how deficiencies in the program management are identified and corrected as well as examples of such changes.
Note on B39: RD 1. Does the program allocate funds through a competitive, merit-based process, or, if not, does it justify funding methods and document how quality is maintained? Purpose of the question: to determine whether the program uses a clearly stated, defensible method for allocating its R&D funding. Elements of a Yes answer: a Yes answer would require that the program allocate funding using a broadly competitive process based on merit, or that it has compelling justifications for R&D funding allocated through other means. Interpretations of competition and merit review should be consistent with the definitions in Circular A-11: “…intramural and extramural research programs where funded activities are competitively awarded following review for scientific and technical merit.” All program funds allocated through means other than unlimited competition must document the processes they will use to distribute funds to each type of R&D performer (e.g., federal laboratories, federally funded research and development centers, universities, etc.). Programs are encouraged to use external assessment of the methods they use to allocate R&D and maintain program quality. Evidence/Data: evidence can include a description of the awards process, percentage of funds earmarked, percentage of funds subject to peer review. This question corresponds in part to Quality criterion II.A of the R&D criteria.
Note on B40: RD 2. Does competition encourage the participation of new/first-time performers through a fair and open application process? Purpose of the question: to determine whether or not the awards process is conducted in an open manner so that new applicants of merit will be able to compete fairly with previous grant recipients, and that long-term awardees do not monopolize the available dollars. Elements of a Yes answer: a Yes answer would require that the program operate a fair and open grant competition and provide a reasonable amount of outreach to encourage the participation of new grantees. Considerations can include whether the program tends to provide grants to the same list of grantees year after year. Evidence/Data: evidence can include the relative number of new grantees per grant cycle and technical assistance and outreach efforts of the agency.
Note on B41: RD 3. Does the program adequately define appropriate termination points and other decision points? Purpose of the question: to determine whether appropriate decision points are being defined in program planning. Elements of a Yes answer: a Yes answer would require that the program identifies decision points relevant to major program decisions, including circumstances under which the program should end. A termination point may result from a program successfully meeting its goals or from failure to meet performance or other conditions for termination. Industry-relevant programs should identify any “off ramps” in their program plans – whether, when, and how aspects of the program may be shifted to the private sector. Evidence/Data: evidence can include demonstration of meaningful decision points in program plans. This question corresponds in part to Performance criterion III.B and Industry-Specific criterion IV.E of the R&D criteria.
Note on B42: RD 4. If the program includes technology development or construction or operation of a facility, does the program clearly define deliverables, capability/performance characteristics, and appropriate, credible cost and schedule goals? Purpose of the question: to determine if the agency has defined the required capabilities and/or performance characteristics of the end product/result of the acquisition, in addition to determining whether all program costs are well understood, and whether a realistic schedule has been established. (Programs not pursuing technology development or facilities construction or operation should set the weighting of this question to zero.) Elements of a Yes answer: a Yes would require the program documented the capabilities or characteristics that are expected. A Yes answer would also require that the program is able to estimate unit costs, annual costs, and life-cycle costs. Programs should also be able to lay out detailed schedules for development and delivery of assets and services. Program should be able to demonstrate that the cost and schedule estimates are credible (e.g., by having them reviewed and validated by an independent entity outside the program). If an independent entity’s cost or schedule estimates differ from the program’s estimates, the program should defend differences. The agency should also have conducted an analysis of alternatives (AoA). The analysis should include the status quo, non-material solutions (e.g., data compression in lieu of a new data cable), and trade-offs between cost, schedule, and performance goals. Program should be able to demonstrate that the analysis is credible (e.g., by having it reviewed and validated by an independent entity outside the program.) If an independent entity’s analysis differs from the program’s analysis, the program should defend differences. Evidence/Data: evidence can include documentation from the program describing key performance characteristics and/or deliverables, as well as unit cost, acquisition cost, and life cycle cost estimates; development and/or delivery schedules; and a summary its AoA, and documentation of any independent reviews of the analysis. This question corresponds in part to Performance criterion III.B of the R&D criteria.
Note on B48: 1. Has the program demonstrated adequate progress in achieving its long-term outcome goal(s)? Purpose of the question: to determine whether the program is meeting or making measurable progress toward meeting the goals evaluated in Question 1 of Section II. The question also seeks to determine whether the program's partners are meeting long-term outcome goals evaluated in Question 3 of Section II, if partner performance is critical to the program achieving its overall goals. Examples of partners can include grantees, participating financial institutions, regulated bodies, or suppliers. Elements of a Yes answer: a Yes answer (i.e., full credit) would require that the program meet all the goals evaluated in Question 1 of Section II. A Yes answer would not be met by simply meeting any one of its goals. A Yes answer would also require that, where applicable, partners commit to long-term outcome goals and achieve them as well. Partial credit such as Large Extent or Small Extent, should be given in cases where there is partial, but notable, achievement of goals. A program could receive a No if it received a Yes for achieving its annual goals (next question), but is not making progress toward meeting its long-term goals. Space is provided in the PART worksheet to list and document goals, targets and achieved results. If adequate goals are not available and a program received a No in Question 1 of Section II, the program must receive a No answer to this question. For research and development programs, some long-term basic research programs may not be able to define meaningful annual outcome performance measures, aside from process measures. In such cases, these programs may use process-related measures, especially those that can be conceptually linked to long-term research goals. Where appropriate, these considerations should be factored into Question 5 of this Section, which should be assessed in such a way to address the relative importance of an effective process or relevance to a field of science. Evidence/Data: evidence can include data from the agency's GPRA performance report, a strategic plan, or other Administration goals and objectives. Reports detailing customer satisfaction with program performance, program reports detailing rates of utilization or participation, or independent evaluations of the program’s performance may also be considered as relevant evidence. In cases where goals are not met, additional evidence can include an explanation of the main reasons.
Note on B61: 2. Does the program (including program partners) achieve its annual performance goals? Purpose of the question: to determine whether the program is meeting the goals evaluated in Question 2 of Section II. The question also seeks to determine whether the program's partners are meeting annual goals evaluated in Question 3 of Section II, if partner performance is critical to the program achieving its overall goals. Examples of partners can include grantees, contractors, participating financial institutions, regulated bodies, or suppliers. Elements of a Yes answer: a Yes answer (i.e., full credit) would require that the program meet all the goals evaluated in Question 2 of Section II. A Yes answer would also require the program received a Yes for Questions 1 and 2 of Section II and a Yes or Not Applicable for Question 3 of Section II. A Yes answer would not be met by simply meeting any one of its goals. A Yes answer would also require that, where applicable, partners commit to annual goals and achieve them as well. Partial credit such as Large Extent or Small Extent, should be given in cases where there is partial, but notable, achievement of goals. Space is provided in the PART worksheet to list and document goals, targets and achieved results. If adequate goals are not available and a program received a No in Question 2 of Section II, the program must receive a No answer to this question. Some long-term basic research programs may not be able to define meaningful annual outcome performance measures, aside from process measures. In such cases, these programs may use process-related measures, especially those that can be conceptually linked to long-term research goals. Where appropriate, these considerations should be factored into Question 5 of this Section, which should be assessed in such a way to address the relative importance of an effective process or relevance to a field of science. Evidence/Data: evidence can include data from the agency's annual GPRA performance report, a strategic plan, or other Administration goals and objectives. In cases where goals are not met, additional evidence can include an explanation of the main reasons. For research and development programs, this question corresponds in part to Performance criterion III.C of the R&D criteria.
Note on B72: 3. Does the program demonstrate improved efficiencies and cost effectiveness in achieving program goals each year? Purpose of the question: to determine whether management practices have resulted in efficiency gains over the past year. Elements of a Yes answer: A Yes would require that the program demonstrate improved efficiency over the prior year. Program’s that have undergone a A-76 competitions would also be eligible for yes answer, independent of the outcome. A program would normally not be eligible for a Yes answer to this question if the program received a No in Question 4 of Section III. Evidence/Data: evidence can include meeting performance targets to reduce per unit costs, meeting production and schedule targets, or meeting other targets that result in tangible productivity and efficiency gains.
Note on B73: 4. Does the performance of this program compare favorably to other programs with similar purpose and goals? Purpose of the question: to determine how well the program performs relative to other Federal programs engaged in a similar activity. Elements of a Yes answer: a Yes answer would require the program compare favorably to other Federal programs in the common measures exercise. If none of the common measures relate to the program, the user should consider relevant evaluations that allow a comparison with other Federal programs with similar purpose and goals or comparable private sector activities. If no common measures relate to the program and there are no other similar Federal programs, a Not Applicable rating would be appropriate. For capital assets and service acquisition programs, review of performance should include cost/schedule adherence, quality, and quantity of deliverables. Evidence/Data: evidence can include evaluations and documentation comparing similar programs, including, if applicable, the six common measures. For research and development programs, this question corresponds in part to Performance criterion III.C of the R&D criteria.
Note on B74: 5. Do independent and quality evaluations of this program indicate that the program is effective and achieving results? Purpose of the question: to determine whether the program is effective based on independent and comprehensive evaluations. Elements of a Yes answer: a Yes answer would require that quality program evaluations such as those measured in Question 4 of Section II indicate that the program is effective. If a program is taking necessary steps to correct deficiencies uncovered by the evaluation, the user should address this effort in Question 1 of Section III, Program Management. Relevant evaluations would be at the national program level, rather than evaluations of one or more program partners, and would not focus only on process indicators such as the number of grants provided, or hits on a web site. Relevant evaluations would consider a program's impact, effectiveness, financial management, or other measurement of performance. For research and development programs, some long-term basic research programs may not be able to define meaningful annual outcome performance measures, aside from process measures. In such cases, these programs may use process-related measures, especially those that can be conceptually linked to long-term research goals. This question should be assessed in such a way to address the relative importance of an effective process or relevance to a field of science. Evidence/Data: evidence can include findings of an evaluation conducted by the General Accounting Office, Inspectors General, academic and research institutions, agency contracts or staffs, or other entities. For research and development programs, this question corresponds in part to Relevance criterion I.E and Performance criterion III.C of the R&D criteria.
Note on B75: RD. 1 If the program includes construction of a facility, were program goals achieved within budgeted costs and established schedules? Purpose of the question: to determine whether valid program goals were achieved within budgeted costs and established schedules and whether the program spends funds as planned and budgeted. Elements of a Yes answer: a Yes answer would require that the program achieved the goals evaluated in Section II on budget and on schedule. An example of a program that could receive a No rating could be an acquisition program that has experienced 60 percent cost growth and is behind schedule. Evidence/Data: evidence can include a comparison of the program's previous budget proposals for a fiscal year with its expenditures and final outcomes for that fiscal year. This question corresponds in part to Performance criterion III.C of the R&D criteria.
Note on C4: This section examines the clarity of program purpose and related program design and looks at all factors including those the program or agency may not directly control but which are within the influence of the program or agency such as legislation and market factors. A clear understanding of program purpose is essential to setting program goals, maintaining focus, and managing the program. Potential source documents and evidence for answering questions in this section include authorizing legislation, agency strategic plans, annual performance plans, and other agency reports. Options for answers are Yes, No or Not Applicable.
Note on C16: This section focuses on program planning, priority setting, and allocation of resources. Key elements in this section include an assessment of whether the program has a limited number of goals that are ambitious, yet achievable, to ensure planning is strategic and focused. Whether the program incorporates flexibility in the planning process to address problems identified through performance data and periodic monitoring is also an important element of this section. Potential source documents and evidence for answering questions include strategic planning documents, agency performance plans and reports, reports and submissions from program partners, evaluation plans, budget submissions and other documents. Options for answers are Yes, No or Not Applicable.
Note on C30: This section is focused on a variety of elements related to whether the program is effectively managed to meet program goals and objectives. Key areas include financial oversight, evaluation of program improvements, performance data collection, and program manager accountability. Additionally, specific areas of importance for each program type are also explored. There are a wide range of potential source documents and evidence for answering questions in this section including financial statements, GAO reports, IG reports, performance plans, budget execution data, IT plans, and independent program evaluations. Options for answers are Yes, No or Not Applicable.
Note on D46: This section considers whether a program is meeting its long-term and annual goals. This section also assesses how well the program compares to similar programs and how effective the program is based on independent evaluations. Potential source documents and evidence for answering questions in this section include annual performance reports, evaluations, GAO reports, IG reports and other agency documents. Assessments of program results should be based on the most recent reporting cycle or other relevant data. Answers in this section are rated as Yes, Large Extent, Small Extent, and No. Like Sections I-III, the scoring system in this section remains on a 0 to 1 point scale. Scoring for this section differs by including the option of partial credit between 0 and 1 in increments of 0, .33, .67, and 1.