(Do not fill out online. See Using forms and letters.)

NIAID Acquisition Plan

Specification Package – Template with Instructions

for

Request for Proposals

This document is the NIAID template for preparing the Specification Package for an RFP.  The Specification Package contains documents that will become Attachments to the Acquisition Plan (AP).  Attachments 1 through 7 will be developed by the Project Officer (PO) with assistance provided by the Office of Initiative Development (OID).  This may require multiple versions until an acceptable draft has been developed.  This entire Specification Package will then be forwarded to the PO and Contract Specialist (CS). The PO and CS will develop the remaining documents (Attachments 8 through 12).  Once all Attachments are completed, the entire Specification Package is attached to the Acquisition Plan.

To be developed by the Project Officer and OID:

Attachment 1:	Statement of Work (Background and Introduction, Scope, Technical Requirements)

Attachment 2:	Reporting Requirements and Deliverables

Attachment 3:	Section M - Technical Evaluation Factors

Attachment 4:	Additional Technical Proposal Instructions

Attachment 5:	Additional Business Proposal Instructions and Uniform Cost Assumptions

Attachment 6:	Advance Understandings (as needed or required)

Attachment 7:	Additional RFP-Specific Materials (as needed or required)

To be developed by the Project Officer and Contract Specialist:

Attachment 8:	Potential Source List

Attachment 9:	Sources Sought Notice

Attachment 10:	Presolicitation Notice

Attachment 11:	Independent Government Cost Estimate (IGCE)

Attachment 12:	Concept and Council (R&D) or Executive Committee (non-R&D) Minutes

Note that instructions and explanatory text are indicated by italics and colored font and should be either deleted or replaced as appropriate. All pages should include a header that identifies the draft version and date of the Specification Package.

Delete this page when complete

ATTACHMENT 1:   STATEMENT OF WORK

PROJECT TITLE

RFP NUMBER

- BACKGROUND and INTRODUCTION:

- Identify the mission of the organization and of your program or branch.

- Briefly describe the need for the requirement, and how the project’s services, resources, or products will contribute to the mission of your program or branch.

- Discuss the extent of available data, techniques, methodologies, or results of related work.

- Identify objective(s) of the requirement and the purpose of the solicitation.

For recompetitions:

- Provide the project history and contractual history of the acquisition.

- Identify the previous contract number(s) and incumbent contractor(s).

- Describe studies, activities, accomplishments of incumbent contractor(s) in the context of justification for the need of the acquisition and documentation of previous success.

- Identify any changes to the requirement from the previous competition.

- SCOPE:

- Briefly describe, in the form of a paragraph, the overall project and objective(s) in broad terms that indicate the size and magnitude of the effort.

- When appropriate, include the scope of disease, therapeutic/preventive candidate(s), type of research activity, study populations, product development activities, etc.

- Where appropriate, include definitions (i.e., ”For purposes of this contract, a candidate vaccine is defined to be …”).

- If applicable, list the programs (i.e. existing databases/computer systems, clinical study groups) and/or contractors (i.e. clinical research support services contractors) with which the Contractor will be required to collaborate.  More detailed specifications of the relationships will be delineated within the Technical Requirements. Additional RFP-specific material (which will become separate Attachments to the RFP) may be necessary to provide offerors sufficient background information on these existing programs and/or contracts.

- If applicable, identify research/service activities that are not within the scope of work, i.e. “NOTE: This contract will not provide funds to support Phase 1 clinical trials.”

- If Option(s) are planned, describe the scope of work to be performed upon the Government’s exercise of the Option(s).

- TECHNICAL REQUIREMENTS:

Independently and not as an agent of the Government, the Contractor shall furnish all the necessary services, qualified personnel, material, equipment, and facilities, not otherwise provided by the Government as needed to perform the Statement of Work below.  Specifically, the Contractor shall:

- Describe comprehensively and clearly the work that shall be required of the Contractor including any deliverable or reporting requirement resulting from completion of each particular task or activity.

- Include as appropriate, the responsibilities of the Government, i.e. “The Project Officer will review the draft protocol and provide comments to the Contractor within 15 calendar days of receipt of the draft protocol.”

- Define timelines for the Contractor and the Government in terms of either calendar days or business days and use consistently throughout the Statement of Work and in the Reporting Requirements and Deliverables section.

- Use outline format so that each item, whether a major task/category of functions or a sub-function, has a number or letter identifier to allow reference to all items in the SOW.

- Do not include instructions to offerors on what to include in the Technical Proposal; this information belongs in the “Additional Technical Proposal Instructions” section.

  - Project Management (edit as appropriate)

    - Overall Project Management

      - Provide for the overall management, integration and coordination of all contract activities, including the management and coordination of activities carried out under subcontracts.

      - Provide a technical and administrative infrastructure to ensure the efficient planning, initiation, implementation and timely completion of all projects carried out under this contract and effective communications with the Project Officer and the Contracting Officer.

      - Provide for a Principal Investigator with responsibility for overall project management and communications, tracking, monitoring and reporting on project status and progress, and recommending modifications to project requirements and timelines, including projects undertaken by subcontractors.

    - Subcontract Management and Reporting (for solicitations anticipating a significant amount of subcontracting)

      - Solicit, evaluate, award and manage subcontracts, including overseeing the technical, administrative and operational activities of subcontractors; audit subcontractor facilities, services, and financial expenditures; and track deliverables and reporting requirements.

      - Assess and provide Quarterly Technical Reports on subcontractor performance and progress toward achievement of defined tasks and responsibilities within established timelines; and identify and resolve problems with subcontractor performance.

      - Ensure that subcontractor personnel, equipment and facilities are compliant with regulatory requirements in effect throughout the contract period of performance.

      - Ensure the complete and effective transfer of technology by the subcontractors to the Contractor, the Government, or a third party designated by the Project Officer.

      - Perform all necessary transition and closeout functions on each subcontract.

    - Meetings and Teleconferences

      - Contract Initiation Meeting

Within 60 calendar days after the effective date of the contract, participate in a one-day Contract Initiation Meeting with the Project Officer, the Contracting Officer and other NIAID personnel designated by the Project Officer, to be held at the Contractor’s site.  The purpose of the Contract Initiation Meeting shall be to orient the Contractor to NIAID contract procedures.

      - Monthly Meetings/Teleconferences

        - Plan and conduct meetings at a minimum of monthly intervals, either in person or via teleconference, with the Contractor’s key personnel to review overall progress.

        - Plan and conduct meetings of the Contractor’s Principal Investigator and Project Manager with the Project Officer and Contracting Officer at a minimum of monthly intervals, either in person or via teleconference, to review protocols (proposals, etc.), the status of approved projects (protocols, etc.), and to discuss any matters relevant to the scientific and financial administration of the contract and future activities.  The schedule for those meetings will be established by the Project Officer and Contracting Officer after contract award. Prepare and distribute the agenda and meeting/teleconference materials to all participants.  Provide a summary of all meetings and teleconferences in the Semi-Annual Progress Reports.

      - Annual Site Visit

Arrange for and conduct annual site visits for NIAID contract and program staff to review and discuss:  project progress; problems and obstacles and approaches to overcoming identified problems and obstacles; recommendations for modifications in project timelines, objectives, and research approaches/methodologies based on outcomes to date; and future plans. These site visits shall be attended by the Principal Investigator, the Contractor’s business representative, and all key personnel.  The Contractor shall be responsible for:

      - Planning and submitting the agenda to the Project Officer for approval;

      - Developing written and oral presentation materials;

      - Arranging for the logistics associated with the site visits and for travel costs for all non-Government site visit attendees; and

      - Preparing and submitting Annual Site Visit reports to the Project Officer and Contracting Officer within 30 calendar days of completion of each annual site visit.

  - Intellectual Property  (if not applicable, delete)

The Contractor shall be solely responsible for the timely acquisition of all appropriate proprietary rights, including intellectual property rights, and all materials need to perform the project.  Before, during, and subsequent to the award, the U.S. Government is not required to obtain for the Contractor any proprietary rights, including intellectual property rights, or any materials needed by the Contractor to perform the project.  The Contractor is required to report to the U.S. government all inventions made in the performance of the project, as specified inn FAR 52.227-11 (Bayh-Dole Act).

  - Initial And Final Transition (edit as appropriate)

    - Initial Transition (For renewal solicitations; edit as appropriate)

In the event of transition to a new contractor, ensure an orderly, secure, and efficient transition of activities from the predecessor contractor, as follows;

List those contract activities and contract-generated data and materials that will require  transition. Include requirements for the Contractor to develop a Draft Initial Transition Plan for review by the Project Officer, and a Final Initial Transition Plan based on the Project Officer’s comments.  The Draft and Final Initial Transition plan should include not only the activities and contract-generated data and materials to be transferred, but also the timeline for completion of transition activities and the assigned staff.  Also specify the timeline for submission of both the Draft and Final Initial Transition Plans and the timeline for completion of the transition.

      - Final Transition (If applicable; edit as appropriate)

The Contractor shall ensure an orderly, secure, and efficient transition of contract-related materials and activities to the successor contractor or to the Government.  A description of transition activities, timelines, and assigned staff shall be provided in a Draft and Final Transition Plan, which will be reviewed and approved by the Project Officer.  The Draft Transition Plan shall be submitted _____ months prior to the completion date of the contract, and the Final Transition Plan (approved by the Project Officer and Contracting Officer) shall be submitted ___ months prior to the completion date of the contract.

  - Option(s)  (include only for RFPs with Options)

In addition to the services/quantities outlined above to be provided for the base requirement, Options(s) for additional services/quantities under the contract may be exercised at the discretion of the Government and are defined as follows:

Contractor requirements for Options that may be exercised by the Government are the last item in the Statement of Work.  Number each Option and delineate the scope of work to be performed for each Option.  For example:

Option 1:  Design and conduct a Phase 3 clinical trial to evaluate further the safety and efficacy of the candidate therapeutic; design and conduct additional preclinical studies for product optimization; provide statistical and data management support for additional Division-sponsored research programs involving clinical studies/trials.

Under each Option, describe the specific tasks/functions to be carried out by the Contractor in sufficient detail to ensure a meaningful and complete specification of requirements.  For some Options, this will require a fairly detailed Statement of Work to define Contractor responsibilities.

RFPs that include Options must also provide:  (1) Technical Proposal Instructions delineating what offerors are to provide in the Technical Proposal; (2) One or more Technical Evaluation Criteria to assess the merit, appropriateness and feasibility of offerors’ Technical Proposals with respect to Option(s); and (3) Additional Business Proposal Instructions and Uniform Cost Assumptions for each Option.

ATTACHMENT 2:   REPORTING REQUIREMENTS AND DELIVERABLES

PROJECT TITLE

RFP NUMBER

ARTICLE C.2.  REPORTING REQUIREMENTS

All reports required herein shall be submitted in electronic format.  In addition, one (1) hardcopy of each report shall be submitted to the Contracting Officer, unless otherwise specified.

a.	Technical Reports

In addition to those reports required by the other terms of this contract, the Contractor shall prepare and submit the following reports in the manner stated below and in accordance with the DELIVERIES ARTICLE in SECION F.

The Contractor shall submit to the Contracting Officer and to the Project Officer technical progress reports covering the work accomplished during each reporting period. These reports are subject to technical inspection and requests for clarification by the Project Officer.  These reports shall be brief and factual and prepared in accordance with the format described below.

Format of Cover page:  All reports shall include a cover page prepared in accordance with the following format:

- Contract Number and Project Title

- Period of Performance Being Reported

- Contractor’s Name and Address

- Author(s)

- Date of Submission

- Delivery Address

(Check all that apply) (The PO should provide any additional specific information to be reported under the contract for each applicable report.)

(1)	Monthly Progress Report

This report shall include a description of the activities during the reporting period, and the activities planned for the ensuing reporting period.  The first reporting period consists of the first full month of performance plus any fractional part of the initial month.  Thereafter, the reporting period shall consist of each calendar month.

(2)	Quarterly Progress Report

(a)	This report shall include a [ summation of the monthly progress reports  a description of the activities during the reporting period] and the activities planned for the ensuing reporting period.  The first reporting period consists of the first full three months of performance including any fractional part of the initial month.  Thereafter, the reporting period shall consist of three full calendar months.

(b)	A monthly report will not be submitted for the final month of a quarter.

(3)	Semi-Annual Progress Report

(a)	This report shall include a [ summation of the monthly progress reports  a description of the activities during the reporting period] and the activities planned for the ensuing reporting period.  The initial report will be submitted for the first full six months of the contract performance including any fractional part of the initial month.  Thereafter, the reporting period shall consist of six full calendar months.

(b)	Monthly and quarterly reports will not be submitted the month the semi-annual report is due.

(4)	Annual Progress Report

This report includes a summation of the results of the entire contract work for the period covered.  An Annual Progress Report will not be required for the period when the Final Report is due.  A [ Monthly  Quarterly  Semi-Annual] Report shall not be submitted when an Annual Report is due.

Use the below narrative if the Project Officer requests a draft annual report.

The Contractor shall provide the Project Officer and Contracting Officer with _____ copies of the Annual Progress Report in draft form [ in accordance with the DELIVERIES Article in SECTION F of this contract  _____ calendar days prior to the delivery date for the Final Version of the Annual Report.]  The Project Officer will review the draft report and provide the Contracting Officer with comments within _____ calendar days after receipt.  The Annual Progress Report shall be corrected by the Contractor, if necessary and the final version delivered as specified in the above paragraph.

Use in all contracts for clinical research involving human subjects:

(5)	Annual Technical Progress Report for Clinical Research Study Populations

The Contractor shall submit information about the inclusion of women and members of minority groups and their subpopulations for each study being performed under this contract.  The Contractor shall submit this information in the format indicated in the attachment entitled, "Inclusion Enrollment Report," which is set forth in Section J of the contract.  The Contractor also shall use this format, modified to indicate that it is a final report, for reporting purposes in the Final Report.

The Contractor shall submit the report in accordance with the DELIVERIES Article in SECTION F of this contract.

In addition, the NIH Policy and Guidelines on the Inclusion of Women and Minorities as Subjects in Clinical Research, Amended, October 2001, applies.  If this contract is for Phase 3 clinical trials, see II.B of these guidelines. The Guidelines may be found at the following website: .

Include a description of the plans to conduct analyses, as appropriate, by sex/gender and/or racial/ethnic groups in the clinical trial protocol as approved by the IRB, and provide a description of the progress in the conduct of these analyses, as appropriate, in the annual progress report and the final report.  If the analysis reveals no subset differences, a brief statement to that effect, indicating the subsets analyzed, will suffice.  The Government strongly encourages inclusion of the results of subset analysis in all publication submissions.  In the final report, the Contractor shall include all final analyses of the data on sex/gender and race/ethnicity.

(6)	Final Report

This report is to include a summation of the work performed and the results obtained for the entire contract period of performance. This report shall be in sufficient detail to describe comprehensively the results achieved. The Final Report shall be submitted in accordance with the DELIVERIES Article in SECTION F of the contract.  An annual report will not be required for the period when the Final Report is due.

Use the below narrative if the Project Officer requests a draft final report.

The Contractor shall provide the Project Officer and Contracting Officer with _____ copies of the Final Report in draft form [ in accordance with the DELIVERIES Article in SECTION F of this contract  _____ calendar days prior to the completion date of this contract.]  The Project Officer will review the draft report and provide the Contracting Officer with comments within _____ calendar days after receipt.  The Final Report shall be corrected by the Contractor, if necessary and the final version delivered as specified in the above paragraph.

(7)	Summary of Salient Results (required for all R&D contracts)

The Contractor shall submit, with the Final Report, a summary (not to exceed 200 words) of salient results achieved during the performance of the contract.

b.	Other Reports and Deliverables

In addition to the above reports, the following are considered other reports and deliverables under this contract and are identified in the Statement of Work.  A listing is included in the DELIVERIES Article in SECTION F.

(Check all that apply)

Human Subjects IRB Annual Report (Form OMB No. 0990-0263-formerly Optional Form 310)

Invention Report Requirement - Use when Patent Rights (FAR 52.227-11 or 52.227-13) may be included in the contract.

Source Code and Object Code - Use when software is used, produced, modified or enhanced

Unless otherwise specified herein, the Contractor shall deliver to the Government, upon the expiration date of the contract, all source code and object code developed, modified, and/or enhanced under this contract.

- SECTION D – PACKAGING, MARKING, AND SHIPPING

NOTE:  If known at the time of solicitation, this section should be tailored according to the specifications given by the Program Official in the event certain deliverables must be specially packaged and marked.  Examples of deliverables which would be included in this category could include:  tissue samples packed in dry ice, animals in special containers, infectious agents, pharmaceuticals, etc.

Checked boxes indicate that these items must be addressed in Section D of the solicitation.  The Contract Specialist should work with the Project Officer to ensure that any related clauses are also inserted into the solicitation.

Cannot be determined at this time

Temperature controlled environment is required

Shipments will be time sensitive/time critical

International shipping will apply

Shipping insurance is required

Hazardous Materials shipping is applicable

Other (list as necessary) ________________________

N/A to this solicitation

ARTICLE F - DELIVERIES

Satisfactory performance of the final contract shall be deemed to occur upon performance of the work described in the STATEMENT OF WORK Article in SECTION C of this contract and upon delivery and acceptance by the Contracting Officer, or the duly authorized representative, of the following items in accordance with the stated delivery schedule:

The items specified below as described in the REPORTING REQUIREMENTS Article in SECTION C of this contract. will be required to be delivered F.o.b. Destination as set forth in FAR 52.247-35, F.o.b. DESTINATION, WITHIN CONSIGNEES PREMISES (APRIL 1984), and in accordance with and by the date(s) specified below [and any specifications stated in SECTION D, PACKAGING, MARKING AND SHIPPING, of this contract]:

- a.	Technical Progress Reports   (SAMPLE TEMPLATE)

| - Item | ### Reports | ### Recipients | - Delivery Schedule |
| --- | --- | --- | --- |
| - 1. | - Monthly Progress Report | - 1 hard copy to PO - 1 original to CO - 1 elec. copy to PO and CO | - The first report is due on/before ________. Thereafter, each report is due on/before the 15th of each month following each reporting period. |
| - 2. | - Quarterly Progress Report | - 1 hard copy to PO - 1 original to CO - 1 elec. copy to PO and CO | - The first report is due on/before ________. Thereafter, each report is due on/before the 30th of each month following each reporting period. Monthly reports will not be submitted the month the quarterly report is due. |
| - 3. | - Semi-Annual - Progress Report | - 1 hard copy to PO - 1 original to CO - 1 elec. copy to PO and CO | - The first report is due on/before _______. Thereafter, each report is due on/before the 30th of the month following each 6-month period. Monthly and quarterly reports will not be submitted the month the semi-annual report is due. |

| - 4. | - Annual Progress Report | - 1 hard copy to PO - 1 original to CO - 1 elec. copy to PO and CO | - The first report is due on/before _______. Thereafter, each report is due on/before the 30th of the month following each anniversary date of the contract. Monthly, quarterly, and semi-annual reports will not be submitted the month the annual report is due. |
| --- | --- | --- | --- |
| - 5. | - Annual Utilization Report | - 1 copy to CO | - Due on/before the 30th of the month following each anniversary date of the contract. |
| - 6. | - Final Invention Statement | - 1 copy to CO | - Due on/before completion date of the contract. |
| - 7. | - All reports and documentation including the invention disclosure report, the confirmatory license, and the government support certification | - 1 copy to OPERA | - As required by FAR Clause 52.227-11. |
| - 8. | - Draft Final and Final Report and Summary of Salient Results | - 1 hard copy to PO - 1 original to CO - 1 elec. copy to PO and CO | - Draft Final Report is due ___ calendar days prior to the completion date of contract. - Final Report is due on/before the completion date of the contract. |

- b.	Other Reports and Deliverables (Delivery Schedule)  (SAMPLE TEMPLATE)

| - Item | ### Deliverables | ### SOW Reference | ### Recipient | - Delivery Schedule |
| --- | --- | --- | --- | --- |
| - 1. | - Draft and Final Study and Validation Protocols with SAP | - [insert SOW paragraph or task reference, i.e. 1.a.6.] | - 1 hard copy to PO - 1 elec. copy to PO | - 15 calendar days prior to initiating each study. |
| - 2. | - Working Technical Standard Operating Procedures (SOPs) | - [insert SOW paragraph or task reference] | - 1 hard copy to PO - 1 elec. copy to PO | - 15 calendar days prior to initiating each study. |
| - 3. | - Draft Study and Validation Study Reports with Statistical Analyses (SA) | - [insert SOW paragraph or task reference] | - 1 hard copy to PO - 1 elec. copy to PO | - Within 30 calendar days after completion of each study. |
| - 4. | - Draft and Final Stability Study Protocols | - [insert SOW paragraph or task reference] | - 1 hard copy to PO - 1 elec. Copy to PO | - 15 calendar days prior to initiating each study |
| - 5. | - Draft Stability Study Report | - [insert SOW paragraph or task reference] | - 1 hard copy to PO - 1 elec. Copy to PO | - Within 30 calendar days after completion of each study. |

| - 6. | - All animals as described in Section C, and progeny | - [insert SOW paragraph or task reference] | - To be specified 60 days prior to contract completion | - At contract completion |
| --- | --- | --- | --- | --- |
| - 7. | - Vaccine | - [insert SOW paragraph or task reference] | - To be specified 60 days prior to contract completion | - At contract completion |

ATTACHMENT 3:   SECTION M - TECHNICAL EVALUATION FACTORS

PROJECT TITLE

RFP NUMBER

MANDATORY QUALITIFCATION CRITERIA (if not applicable, delete)

The Mandatory Qualification Criteria establish conditions that must be met  at the time of receipt of the Original Proposal   at the time of receipt of the Final Proposal Revision submission in the Office of Acquisitions, NIAID, in order for your proposal to be considered any further for award.  (Note:  Submission at the time of Original Proposal receipt is the preferred method for NIAID.)

Listed below are the Mandatory Qualification Criteria.  The offeror must include all information that documents and/or supports the Mandatory Qualification Criteria in one clearly marked section at the front of the Technical Proposal.  Technical Proposals that are determined by the Project Officer not to meet the Mandatory Qualification Criteria will not be submitted for peer review and will not be considered any further for award.

Mandatory Qualification Criteria:

Insert the criteria here in terms that will allow Program and contract staff to easily determine whether or not the Mandatory Qualification Criteria have been met.  Do not include criteria that require a subjective or qualitative assessment. Please note that these criteria will be evaluated by Program and contract staff and NOT by peer reviewers.

Justification for Mandatory Qualification Criteria:

Provide justification for the use of Mandatory Qualification Criteria.

Documentation Required to Support Having Met the Mandatory Qualification Criteria:

Describe the documents or information that offerors must provide to demonstrate that they meet the mandatory qualification criteria.

PRE-AWARD SITE VISIT OR SITE AUDIT (if not applicable, delete; if applicable, edit as appropriate)

Offerors determined, upon completion of the scientific/technical peer review, to be in the Competitive Range may be subject to auditing of their facilities and Quality Assurance and Quality Control (QA/QC) capabilities.  The decision to audit specific facilities will be made by the Project Officer.  If audits are performed during the negotiations, the results of the audits will be a factor in final selection for award of a contract. Offerors, including proposed subcontractors, will be requested to make all non-proprietary records, including previous regulatory inspection records, and staff available in response to a pre-award site visit or audit by the NIAID or its designee.  Due to timeline requirements, pre-award site visits may be made with short notice.  Offerors are expected to guarantee the availability of key staff or other staff determined by the Government as essential for purposes of this site visit.

TECHNICAL EVALUATION CRITERIA:

The evaluation criteria are used by the technical evaluation committee when reviewing the technical proposals.  The criteria below are listed in the order of relative importance with weights assigned for evaluation purposes.

OFFERORS AND REVIEWERS ARE ADVISED TO REFER TO - Additional Technical Proposal Instructions – OF THIS SOLICITATION PACKAGE FOR GUIDANCE AND INFORMATION RELATED TO THE PREPARATION OF TECHNICAL PROPOSALS.

Edit Criteria as appropriate to mirror the corresponding sections of the Additional Technical Proposal Instructions. Unless otherwise specified, subcriteria are assumed to be of equal weight.  If appropriate, language may be added here to indicate that subcriteria are in descending order of importance. Weights are to be expressed as whole numbers (i.e., 35, 15, etc.), and not as a percentage of the total possible points (i.e., 35%, 15%, etc.).  Do not add the term “points.”

CRITERIA										WEIGHT

CRITERION 1:  TECHNICAL PLAN/APPROACH					(insert Weight) _______

Description, Factors, Sub-factors and if needed, identify relational weight of sub-factors, as appropriate:

CRITERION 2:  SCIENTIFIC AND TECHNICAL PERSONNEL		(insert Weight) _______

Include separate sub-criteria for the Principal Investigator and for Scientific and Technical Personnel.  For example:

- Principal Investigator (PI):  Appropriateness and adequacy of the education, training, experience, expertise, qualifications and effort of the proposed PI with respect to: (list the scientific/technical capabilities required of the PI)

- Scientific and Technical Personnel:  Appropriateness and adequacy of the education, training, experience, expertise, qualifications and effort for all proposed scientific and technical personnel, including proposed subcontractors, with respect to:  (list the scientific/technical areas of expertise required to carry out the functions delineated in the Statement of Work, e.g., clinical investigators, study coordinators, data entry and data management staff, information technology personnel, etc.)

CRITERION 3: FACILITIES, EQUIPMENT AND OTHER			(insert Weight) _______

RESOURCES

CRITERION 4:  PROJECT MANAGEMENT							(insert Weight) _______

An example of TEC for Project Management is provided below.

A.  Adequacy of the Project Management Plan in terms of staffing, organization, responsibilities, leadership and lines of authority.

B.  Suitability of systems proposed for tracking project activities and monitoring progress, timelines and budgets.

C.  Suitability of the plan for how the PI will communicate with the Project Officer and the Contracting Officer, as well as establish lines of communication between all performance sites and activities.

D.  Suitability of the plan for soliciting, evaluating, negotiating, awarding and managing any proposed subcontracts in accordance with Federal regulations.

E.  Adequacy of the plan to identify and remediate problems in subcontractor performance.

Additional sub-criteria may be included depending on the requirements of the project.  For example:

- Completeness of Letters of Understanding between collaborating parties to address intellectual property, facilitate development of commercialization, and resolve disputes.

- Adequacy of plan to protect and share confidential information with the External Advisory Group members.

- Suitability of plan to organize Annual Review Meetings and provide for a thorough assessment of contract status, problems and approaches to their resolution, and future plans.

TOTAL POSSIBLE WEIGHT:															_100_

EVALUATION OF OPTIONS											(insert Weight) _______

(If selected, add -- after the total weight for the Base Period -- criteria for the evaluation of each Option. Use when it is anticipated that any contract(s) awarded from this solicitation will contain Option provision(s) and period(s).)

TOTAL POSSIBLE WEIGHT (with Options):					(insert Weight) _______

Other Factors:

HUMAN SUBJECT EVALUATION

Protection of Human Subjects from Research Risks, Data and Safety Monitoring, Women and Minorities, Children

EVALUATION OF DATA SHARING PLAN

EVALUATION OF PLAN FOR SHARING MODEL ORGANISMS FOR BIOMEDICAL RESEARCH

EVALUATION OF FOREIGN CURRENCY OFFERS, FAR 52.225-17, (FEBRUARY 2000)

Use when foreign currency offers are anticipated and allowed.  This factor describes the currency conversion procedures.

PAST PERFORMANCE FACTOR

EXTENT OF SMALL DISADVANTAGED BUSINESS PARTICIPATION

SUBCONTRACTING PROGRAM EVALUATION CRITERIA

Use when additional evaluation of the offeror’s subcontracting program is warranted and desired.

ATTACHMENT 4:   ADDITIONAL TECHNICAL PROPOSAL INSTRUCTIONS,

FORMAT FOR TECHNICAL PROPOSAL, and TABLE OF CONTENTS

PROJECT TITLE

RFP NUMBER

It is strongly recommended that offerors use the following template as the Table of Contents for the Technical Proposal. All information presented in the Technical Proposal should be presented in the order specified below. These additional Technical Proposal instructions reflect the requirements of the RFP and provide specific instructions and formatting for the Technical Proposal. While Section L.2.b. of the RFP provides a generic set of Technical Proposal instructions applicable to all NIH R&D solicitations, these instructions are tailored to the specific requirements of the RFP. The information requested in these instructions should be used to format and prepare the Technical Proposal, and should be used as a Table of Contents for your Technical Proposal. Offerors should follow the instructions in Section L of the solicitation, and include the information requested here. Offerors are advised to give careful consideration to the Statement of Work, all reference materials, and attachments, the Technical Evaluation Criteria in Section M, and the RFP as a whole in the development of their Technical Proposals. Offerors proposing subcontracts to perform portions of the Statement of Work should clearly identify the specific tasks for which they plan to utilize subcontractors, as well as the method and level of integration/coordination between the prime Contractor and all proposed subcontractors, and the expected advantages of such an approach. Offerors are reminded that the total page limitation for the entire Technical Proposal is __________ pages including all appendices and attachments. Any pages in excess of this limit will be expunged from the proposal and will not be considered in the technical review.

TECHNICAL PROPOSAL – TABLE OF CONTENTS

GENERAL NOTES (if not applicable, delete)

List any uniform technical assumptions related to the requirements of the contract that will assist offerors in the preparation of their Technical Proposals.  For example, for RFPs with advanced product development requirements, it may be appropriate to indicate that NIAID is aware of the uncertainty of the regulatory pathway in terms of FDA guidance for the development of vaccines, therapeutics, etc, but that offerors are still required to address preclinical development, production, testing and characterization of candidates in compliance with existing FDA requirements.

SECTION 1:

- PROPOSAL TITLE PAGE.  Include RFP title and number, name of organization, DUNS number, proposal part, and identify if the proposal is an original or a copy.

- PROJECT OBJECTIVES, NIH FORM 1688

- GOVERNMENT NOTICE FOR HANDLING PROPOSALS

- PROPOSAL SUMMARY AND DATA RECORD (NIH-2043)

- TABLE OF CONTENTS

- MANDATORY QUALIFICATION CRITERIA  (delete if not applicable)

The Mandatory Qualification Criteria (MQC), identified in SECTION M of this solicitation, must be met  at the time of receipt of the Original Proposal   at the time of receipt of the Final Proposal Revision submission.

Documentation to support compliance with the MQC must be provided for the offeror and any proposed subcontractor(s). Include all information relevant to the MQC in this clearly marked section of your Technical Proposal.  Include copies of all materials necessary to demonstrate that you have met the MQC.

SECTION 2: TECHNICAL PROPOSAL OVERVIEW (suggested 3-page maximum)

Provide instructions to offerors to include a brief overview of the proposed program/service. For example:

Provide a brief description of the proposed project, including:

1)	A 1-2 sentence summary describing the vaccine concept the offeror is proposing to advance.

2)	A summary describing the scope of product development activities proposed.

3)	A description of the activities to be performed by the offeror and those that shall be provided by any proposed subcontractor, including the identification of the proposed subcontractors and a list of key personnel of the offeror and the proposed subcontractors with degrees and titles.

4)	A brief description of the facilities and other resources to be made available by the offeror and any proposed subcontractors.

If applicable, provide instructions to include a milestone summary and Gantt chart.

SECTION 3: TECHNICAL PLAN/APPROACH

For each major SOW function or group of functions for which potential offerors should be evaluated, provide instructions for offerors to demonstrate, describe, etc. their technical approaches, scientific rationale, proposed methodologies, proposed plans and procedures, etc. to carrying out each task.  The order of items should be presented in a manner that will provide the most meaningful presentation for reviewers to evaluate technical merit of proposals, and does not necessarily have to follow the order of items in the SOW.

It may be appropriate to include additional “Sections” of instructions for proposed plans/approaches that are tailored to the specific requirements of the solicitation.  For example, QUALITY CONTROL/QUALITY ASSURANCE SYSTEM/PLANS, and PROTOCOL IMPLEMENTATION AND OVERSIGHT might be more appropriate as individual Sections rather than as sub-sections under TECHNICAL PLAN/APPROACH.

SECTION 4: SCIENTIFIC AND TECHNICAL PERSONNEL (edit instructions as appropriate)

The Technical Proposal should include all information relevant to document individual training, education, experience, qualifications and expertise necessary for the successful completion of all contract requirements.  Proposals should include a Staffing Plan for the conduct of the Statement of Work with role descriptions and level of effort of scientific and technical personnel, including scientific and technical personnel of all proposal subcontractors.  Clearly identify who is to be assigned as Key Personnel.  Limit CVs to 2-3 pages and provide selected references for publications relevant to the scope of the RFP, and include experience with projects of similar scope, size and complexity carried out by the offer and any proposed subcontractors over the past 5 years.

In the Personnel categories below, identify specific expertise and qualifications required such as clinical trials experience, biohazard training, animal handling and training, experience with NIAID Category A-B pathogens, statistical leadership experience, etc.

1)	Principal Investigator (PI):  include experience and qualifications of the PI to plan, manage, and direct the activities to be carried out under this contract:

2)	Scientific and Technical Personnel:

SECTION 5: FACILITIES, EQUIPMENT AND OTHER RESOURCES (edit instructions as appropriate)

The Technical Proposal should document availability and adequacy of facilities, equipment, space and other resources necessary to carry out the Statement of Work, including:

- Location and features of facilities including a floor plan and a list of equipment and resources dedicated to the project for the prime contractor and any proposed subcontractors (lease or ownership information should be provided).

- Identification and description of ALL support resources (including Information Technology systems) which will be required to effectively complete the SOW.

Identify any other desired information or provide a description of requested supporting documents. This section may also include instructions to demonstrate ability to comply with safety and safety training requirements.

SECTION 6: PROJECT MANAGEMENT (edit instructions as appropriate)

1)	Provide a plan for project organization, staffing, and management in relation to the planning, initiation, implementation, conduct, monitoring and completion of tasks identified in the Statement of Work.  Describe in detail the responsibilities and level of effort for all proposed personnel who will be assigned to the contract, including proposed subcontractors and consultants.  Provide an administrative and technical framework indicating clear lines of authority and responsibility for all proposed personnel.  If consultants and/or subcontractors are proposed, include a plan to manage, coordinate, and oversee the work performed by consultants and/or subcontractor(s).  Include a chart of the proposed organizational/management structure for the project.

2)	Describe the project management systems that will be used to track activities and to keep multiple activities on time and budget.  The plan must include a description of the quality control methods that will be used to ensure the effective and efficient initiation, implementation, management, and oversight of contract requirements.

3)	Outline how the PI (or Project Manager) will communicate with the Project Officer and Contracting Officer and how the PI (or Project Manager) will communicate, monitor, and manage the project both internally and externally (at subcontractor facilities).

SECTION 7: OPTIONS (if not applicable, delete)

List each Option that the Government reserves the right to exercise, for example:

1)	to increase the services/quantities provided for in the base period of the Statement of Work;

2)	to add new services/quantities different from the base period of the Statement of Work;

3)	to extend the period of performance (either for increased or new services/quantities).

Provide instructions on what offerors are to include in the Technical Proposal to demonstrate/document capabilities and plans for the activities to be carried out under each Option, as well as personnel, project management, and facilities, equipment and other resources to perform the work under the Option(s).

SECTION 8:  OTHER CONSIDERATIONS

Section L of the RFP provides minimum documentation requirements for the following items.  The required information described in Section L should be assembled together, in the following clearly marked sections of the Technical Proposal.  Refer to Section L of the RFP for specific requirements.  Read each section below carefully.  In some cases, offerors may be asked to provide documentation which is in addition to the minimum requirements identified in Section L.

Delete all that do not apply, below.  If additional information is desired, please add below.

1)	Human Subjects

Section L of the RFP specifies the minimum documentation requirements for Human Subjects use. All related documentation should be included in the proposal in a clearly marked section.  The Technical Proposal should document all information necessary to evaluate Human Subject use.

2)	Care of Live Vertebrate Animals

Section L of the RFP specifies the minimum documentation requirements for Animal Welfare compliance. All related documentation should be included in the proposal in a clearly marked section. The Technical Proposal should document all information necessary to evaluate Animal Welfare issues.

3)	Biological Agents or Toxins

The Technical Proposal should include a plan for biohazard safety and security requirements.

4)	Obtaining and Disseminating Biomedical Research Resources

Section L of the RFP specifies the minimum documentation requirements for this element.  The Technical Proposal should document all information necessary to evaluate this issue.

5)	Sharing Research Data (Plan)

Section L of the RFP specifies the minimum documentation requirements for Data Sharing. All related documentation should be included in the proposal in this clearly marked section. The Technical Proposal should include a plan for Data Sharing as required by this RFP.

6)	Sharing of Model Organisms for Biomedical Research (Plan)

Section L of the RFP specifies the minimum documentation requirements for Model Organism sharing. All related documentation should be included in the proposal in this clearly marked section. The Technical Proposal should include a plan for sharing Model Organisms as required by this RFP.

7)	Information Technology (IT) Systems Security

Section L of the RFP specifies the minimum documentation requirements for IT Systems security. All related documentation should be included in the Technical Proposal in this clearly marked section. The Technical Proposal should include a plan for IT Systems security as required by this RFP.

ATTACHMENT 5:   ADDITIONAL BUSINESS PROPOSAL INSTRUCTIONS

AND UNIFORM COST ASSUMPTIONS

PROJECT TITLE

RFP NUMBER

In addition to the format requirements for the Business Proposal that are contained in Section L of the solicitation, the information presented in this section of the RFP is intended to provide uniform cost assumptions and business clarifications. Offerors are advised to give careful consideration to the Statement of Work, all reference material provided as attachments, the Technical Evaluation Criteria, and, the RFP as a whole, in the development of your proposal. The information requested in these instructions should be used as a guide for the development and formatting of your Business Proposal. Offerors should consider and include the information requested here, as well as any other information which will benefit the proposal.

BUSINESS PROPOSAL – TABLE OF CONTENTS

SECTION 1 – PROPOSAL COVER SHEET (use form NIH 2043 identified in Section J)

SECTION 2 – COST OR PRICE SUPPORT

Section L of the RFP specifies the minimum documentation requirements for cost data and all cost related support. All related documentation should be included in the proposal in a clearly marked section.

SECTION 3 – UNIFORM COST ASSUMPTIONS

Complete all assumptions that apply. Delete any that do not apply.  Add others as necessary.

1)  Technical Cost Assumptions

Include any assumptions specific to your technical requirement which have a cost impact that should be consistent across proposals.  For example, the number of animals to be purchased and housed in the first year and subsequent years of the contract; the number and types of clinical trials ongoing at time of contract award for which the Contractor shall assume responsibility; the number and type of new clinical trials anticipated each year of the contract period of performance; the total cost per year for subject participation in clinical trials; the number of specimens to be collected; the number of candidates to be taken into pilot lot production in any given year of the contract period of performance; the number of IND(s) submitted to the FDA; the number and type of candidate(s) to move through process development, etc.

In preparing Technical Cost Assumptions for some contract recompetitions, it is important to distinguish between technical cost assumptions for those contract activities, and associated data and contract-generated materials, that will be assumed by a new contractor on the contract effective date versus technical cost assumption for those contract activities that constitute new work.  For such recompetitions, it is often preferable to provide for two sections under the Technical Cost Assumptions – the first dealing with what will be “inherited” from the incumbent contractor and the second dealing with new work to be performed. For example:

A.  Ongoing Activities at contract award - assume responsibility for the following:

For example, assume:

- 5 Phase 2 clinical trials in development;

- 10 INDs in the preparation stage;

- 2 audits in the planning stages.

B.  New activities during the contract period of performance – assume the following:

For example, assume:

- 3 new Phase 2 clinical trials to be developed and implemented in each year of the contract period of performance;

- 5 new INDs to be prepared and submitted to regulatory authorities for each year of the contract period of performance;

- 5 audits for each year of the contract period of performance.

2)  Travel

Identify as separate items and provide uniform cost assumptions for each travel requirement, e.g., contract initiation meeting, annual progress review meetings, periodic meetings with the Project Officer, travel associated with training requirements and clinical site monitoring visits.  Include the number of trips per year, location, number of days, and the number of Contractor/subcontract staff, as well as any external advisory group members for who travel expenses will be provided by the Contractor.

Examples (edit as appropriate):

Contract Initiation Meeting: Assume one meeting in Bethesda, Maryland within three months after contract award to discuss contract initiation.  Assume that this meeting will require a two-night stay and shall be attended by all of the Contractor’s key personnel.

Training Workshops:  Assume 4 one-day training workshops per year for clinical site staff, to be held in the Bethesda, Maryland area, each requiring 4 presenters including Contractor/subcontractor staff and consultants.

Clinical Site Monitoring Visits:  Assume 15 two-day clinical site monitoring visits per year to domestic clinical trial sites, and 12 three-day clinical site monitoring visits per year to non-U.S. clinical trial sites – 7 visits in East Africa, 3 visits in South America, and 2 visits in Southeast Asia.

General Scientific Meetings: Offerors shall propose a total of $3,750 annually for the Principal Investigator and selected Contractor staff for travel to general scientific meetings for presentations of work conducted under this contract.

3)  Special Shipping and Packaging  (edit as appropriate)

Offerors should include a uniform cost assumption of ___ (number) of (insert appropriate language depending on the specific RFP, e.g., clinical specimens, study products, etc.) per year to be labeled, packaged and shipped.

Offerors should include a uniform assumption of _____ (number) domestic shipments per year.

Offerors should include a uniform assumption of _____ (number) international shipments per year.

Offerors should include a uniform assumption of _____ (number) of packaging and marking of specimens per year.

4)  Storage  (edit as appropriate)

Offerors should include a uniform assumption of _____ (number) new (insert appropriate language depending on the specific RFP, e.g., clinical specimens, study products, etc.) to be (insert appropriate language depending on the specific RFP, e.g., received, labeled, stored, inventoried, distributed, etc.) each year.

5)  Government Furnished Equipment (GFE)

Government Furnished Equipment available to be transferred from incumbent contractor.

If this initiative is a recompetition, the Contract Specialist will provide a listing of all Government Furnished Equipment that has been purchased under the incumbent contract with contract funds.  The CS will include this listing as an attachment to the RFP and potential offerors will be advised that this equipment is available to be transferred to the successful offeror.

The purchase of Government Furnished Equipment will not be authorized as a direct charge under this contract.

SECTION 4 – OPTIONS (if not applicable, delete)

A separate business proposal must be submitted for each Option.  All uniform cost assumptions associated with Options are to be delineated here.

SECTION 5 - TABLE OF CONTENTS FOR DOCUMENTATION REQUIRED UNDER SECTION L OF THE SOLICITATION  (Delete all that do not apply.)

1) Small Business Subcontracting Plan

Section L of the RFP specifies the minimum documentation requirements for completing a subcontracting plan.  This plan should be turned in with the original proposal. All related documentation should be included in the proposal in a clearly marked section.

2) Extent of Small Disadvantaged Business Participation

Section L of the RFP specifies the minimum documentation requirements for small disadvantaged business utilization.  This information should be turned in with the original proposal. All related documentation should be included in the proposal in a clearly marked section.

3) Past Performance Data, including references

Section L of the RFP specifies the minimum documentation requirements for providing past performance information.  This information should be turned in with the original proposal. All related documentation should be included in the proposal in a clearly marked section.

ATTACHMENT 6:   ADVANCE UNDERSTANDINGS

PROJECT TITLE

RFP NUMBER

There are NO Advance Understandings applicable to this solicitation.

The below Advance Understandings are applicable to this solicitation.

This section is used to specify requirements that the successful offeror must agree to before contract award.  These Advance Understandings will become part of the resulting contract. Examples include confidentiality, intellectual property, publications, and any agreements that involve third party suppliers of materials for testing/screening under the contract.  The NIAID Office of Technology Development will work with Program Divisions and DEA to develop appropriate language and requirements.

ATTACHMENT 7:   ADDITIONAL RFP-SPECIFIC MATERIALS

PROJECT TITLE

RFP NUMBER

There are NO RFP-Specific Materials applicable to this solicitation.

The below RFP-Specific Materials are applicable to this solicitation.

Additional material specific to the RFP may be necessary to provide offerors with information relevant to the preparation of technical and business proposals.  Examples include descriptions of: past, current, and planned clinical research programs, clinical studies, or clinical trials; existing research support services contractors with whom the successful offeror will be required to interact; the specifications of the computer system(s), databases, and interfacing requirements;  the current inventory of items that will be transferred from the incumbent contractor to the new Contractor; etc.

If applicable, provide titles that accurately reflect the content of the additional RFP-Specific Materials, e.g., “DMID-FUNDED CLINICAL RESEARCH SUPPORT SERVICES CONTRACTS”).  All additional RFP-Specific Materials should be included in single documents (on separate pages) with appropriate titles to distinguish each component.

STOP HERE AFTER COMPLETING ATTACHMENTS 1 thru 7

RFP SPECIFICATION PACKAGE

ATTACHMENTS 8 - 11

Upon completion of Attachments 1 through 7, STOP HERE.  Work with your Division Coordinator to arrange for internal Division review.  The Division Coordinator will then send the Specification Package to OID for review.  OID will notify the Division Coordinator and the Contract Specialist by e-mail when Attachments 1 through 7 have been completed so that you may begin development of the remaining Attachments.

Attachment 8:	Potential Source List

Attachment 9:	Sources Sought Notice

Attachment 10:	Presolicitation Notice

Attachment 11	Independent Government Cost Estimate (IGCE)

Note that instructions and explanatory text are indicated by italics and colored font and should be either deleted or replaced as appropriate. All pages should include a header that identifies the draft version and date of the Specification Package.

Delete this page when complete

ATTACHMENT 8:  POTENTIAL SOURCE LIST

PROJECT TITLE

RFP NUMBER

This requirement has an incumbent contractor (if applicable, complete the information below for each incumbent contractor; if not applicable, delete)

Name:  	____________________

Address:  	____________________

____________________

E-mail 		____________________

It is anticipated that Offerors could be any of the following organizational type(s):

(Check all that apply)

Commercial

Non-Profit

Educational

Potential Sources or offerors for this requirement are identified, below.

Provide a list of potential sources that have the requisite capabilities to submit a proposal. Include the organization name, complete address, the point of contact or Principal Investigator name and degree, telephone and fax numbers, and e-mail address.

ATTACHMENT 9:   SOURCES SOUGHT NOTICE

PROJECT TITLE

RFP NUMBER

Check as applicable

Type of Requirement

New Requirement

Re-competition (Contract No.:______________)

Expansion of (Contract/RFP No.:______________)

Place of Performance

Place of performance is unknown at this time

Place of performance is known.  Address or general location:__________________

Recompetition (if applicable)

Provide the name and address of the incumbent contractor.

#### Contracting Office Address

Department of Health and Human Services, National Institutes of Health, National Institutes of Allergy and Infectious Diseases, Office of Acquisitions, 6700-B Rockledge Drive, Room 3214, MSC 7612, Bethesda, MD, 20892-7612

Sources Sought Notice Information

Introduction

THIS NOTICE IS FOR INFORMATION AND PLANNING PURPOSES ONLY. THIS IS NOT A REQUEST FOR PROPOSAL AND DOES NOT COMMIT THE GOVERNMENT TO AWARD A CONTRACT NOW OR IN THE FUTURE. NO SOLICITATION IS AVAILABLE AT THIS TIME. BASED ON CAPABILITY STATEMENTS RECEIVED IN RESPONSE TO THIS SOURCES SOUGHT ANNOUNCEMENT THIS ACQUISITION MAY BE SOLICITED AS A 100% SMALL BUSINESS SET-ASIDE.  ALL SMALL BUSINESS ORGANIZATIONS (SB, SDB, WOSB, HUBZone, VOSB, and SDVOSB) ARE ENCOURAGED TO RESPOND TO THIS NOTICE.  SMALL BUSINESS ORGANIZATIONS MUST HAVE THEIR SIZE STATUS CERTIFIED BY THE SMALL BUSINESS ADMINISTRATION.  ALL SMALL BUSINESSES ARE ENCOURAGED TO RESPOND. THE NAICS CODE IS _________ WITH A SIZE STANDARD OF __________.

#### Description

Using the Background and Introduction section of the Statement of Work, provide two to three paragraphs which describe the supplies and/or services to be provided.  Include the estimated FTEs from the IGCE.

Potential sources must demonstrate and document the following in their capability statements:

Enter necessary capability

Capability statements submitted as a result of this announcement should demonstrate the offerors’ qualifications and experience, specifically providing evidence as to their capability to perform this requirement, with particular attention to the following:

Enter how technical capability or qualifications will be evaluated

Personnel/Management: adequacy, appropriateness and relevance of expertise, experience, qualifications, and availability of the key professional and technical staff with a project of similar size, scope, and complexity.

Past Performance:  Past performance is considered essential. In addition to demonstrating that they have met the above qualifications, interested parties must identify at least three other projects of similar size and complexity.

All capable small business organizations are encouraged to submit capability statements based on this announcement.  Interested organizations should submit two copies of their capability statement addressing each of the areas cited above.  Any proprietary information should be so marked.  Written capability statements should be received by the Contracting Officer by ____________________ (date). Please reference the solicitation number on all related correspondence.  No collect calls will be accepted. Facsimile and e-mail transmissions will be accepted.  Any proprietary information should be so marked (see Government-Wide Numbered Note 22).

ATTACHMENT 10:   PRESOLICITATION NOTICE

PROJECT TITLE

RFP NUMBER

Check as applicable

Type of Requirement

New Requirement

Re-competition (Contract No.:______________)

Expansion of (Contract/RFP No.:______________)

Place of Performance

Place of performance is unknown at this time

Place of performance is known.  Address or general location:__________________

Recompetition (if applicable)

Provide the name and address of the incumbent contractor.

#### Contracting Office Address

Department of Health and Human Services, National Institutes of Health, National Institutes of Allergy and Infectious Diseases, Office of Acquisitions, 6700-B Rockledge Drive, Room 3214, MSC 7612, Bethesda, MD, 20892-7612

Duration of contract:  ______ Years

If Options will be included, describe Options _______________________________

Anticipated award date:  _______________

Presolicitation Notice Information

Introduction

The National Institute of Allergy and Infectious Diseases (NIAID), National Institutes of Health (NIH), of the Department of Health and Human Services (DHHS) supports research related to the basic understanding of microbiology and immunology leading to the development of vaccines, therapeutics, and medical diagnostics for the prevention, treatment, and diagnosis of infectious and immune-mediated diseases.  The NIAID, [insert name of Division] has a requirement for [insert a brief description of the requirement].

#### Description

Using the Background and Introduction section of the Statement of Work, provide two to three paragraphs which describe the supplies and/or services to be provided.  Include the estimated FTEs from the IGCE.  If Mandatory Qualification Criteria are required, discuss here.

Also, include a brief description of the criteria against which the proposals will be evaluated.

It is anticipated that [one or multiple] cost reimbursement, completion type contracts will be awarded for a [fill in]-year period of performance beginning on or about [insert date].  [If Options are included, discuss here.]  It is estimated that the provision of FTEs will be approximately as follows:  [Insert FTE information.  Use total effort estimated in IGCE and convert to FTEs.]

Any responsible offeror may submit a proposal which will be considered by the Agency.   This RFP will be available electronically on/about [insert date], and may be accessed through FedBizOpps http://www.fedbizopps.gov/.  This notice does not commit the Government to award a contract.  No collect calls will be accepted.  No facsimile transmissions will be accepted. See Government-Wide Numbered Note 26.

ATTACHMENT 11:   INDEPENDENT GOVERNMENT COST ESTIMATE (IGCE)

PROJECT TITLE

RFP NUMBER

Attach a hardcopy printout of the IGCE for the official/signed AP.  Include an electronic copy of the IGCE when transmitting the Complete AP document electronically for review.  Work with your Contract Specialist to complete the IGCE Excel spreadsheet.  Use this page if needed, to explain or justify atypical or novel elements to the IGCE, (for example, if travel increases significantly in one contract out year; if a slow start-up is anticipated with significant acceleration of work in the out years).

The electronic Excel spreadsheet for the IGCE can be accessed through the Acquisition Plan SOP.

IGCE Attached

IGCE Additional Information

The following justification explains unusual, atypical, or novel elements contained in the spreadsheet.

______________________________________________________________________

______________________________________________________________________

ATTACHMENT 12:  Concept and Council (R&D) or

Executive Committee (non-R&D) Minutes

PROJECT TITLE

BAA NUMBER

Attach a hardcopy printout of the Concept and National Advisory Allergy and Infectious Diseases (NAAID) Council Minutes or NIAID Executive Committee Minutes.

A copy of the Initiative Research or Council Concept can be accessed from the Scientific Initiative Management System (SIMS):  http://ai-appiwp1/sims/list.asp

For R&D Projects, concept approval must be provided by the NIAID Council.  Minutes may be accessed at:  http://www.niaid.nih.gov/ncn/budget/default_council.htm

For non-R&D Projects, concept approval must be provided by the NIAID Executive Committee.