DEPARTMENT OF HEALTH & HUMAN SERVICES                          Office of Secretary

Washington, D.C. 20201

### ACQUISITION POLICY MEMORANDUM NO. 2008 - 02

To: 				Heads of Contracting Activity

Executive Officers

From: 				Martin J. Brown

Senior Procurement Executive

Subject: 			HHS Interim Acquisition Guidance Concerning

Earned Value Management

Effective Date: 		October 1, 2008

1. Purpose: The purpose of this memorandum is to set forth the specific implementation parameters for the application of Earned Value Management (EVM) to contracts issued by the Department of Health and Human Services (HHS), consistent with the flexibility and discretion allowed by the Federal Acquisition Regulation (FAR). Please treat this memorandum as interim acquisition guidance, pending formal incorporation in the HHS Acquisition Regulation.

2. Background: Earned value management is a program management tool and technique that facilitates systematic planning for, and monitoring of, high-value, complex projects. It integrates a project's scope of work with the related budget and schedule to permit detailed assessment of overall performance during the life of the project.

Several government-wide guidance documents govern the definition and use of EVM systems. Guidelines outlining the qualities and characteristics of an EVM system (EVMS) are set forth in American National Standards Institute/Electronic Industries Alliance (ANSIEIA) Standard-748. 1 More detailed and specific guidance and direction is contained in OMB Circular A-1 1, Preparation, Submission and Execution of the Budget, specifically in Part 7 of that Circular, Planning, Budgeting, Acquisition, and Management of Capital Assets, and its supplement, the Capital Programming Guide. Based on this collective OMB guidance, EVMS is intended to be used or those parts of acquisitions2 that will involve developmental effort. This would include not only those acquisitions designated by the agency as major systems but also those acquisitions that

include significant developmental, modificati(m, or upgrade efforts during the operational or steadystate phase of a program.

The FAR rule on EVMS became effective on July 5, 2006. Its purpose is to implement EVMS policy in accordance with OMB Circular A-II. Prior to that action, there was no specific coverage of EVMS in the FAR. Because the new FAR coverage applies throughout the executive branch and to agencies with disparate definitions of and processes and procedures for major systems acquisitions, the FAR Council decided against a "one-size-fits-all" approach and left several significant aspects of the detailed implementation up to the discretion of each covered agency. For example, the final FAR rule does not establish specific dollar-value thresholds or set universal EVMS applicability criteria. Similarly, with respect to integrated baseline reviews (IBRs)-an essential element and step in the application of EVMS at the program and/or contract level-the final rule does not mandate their use in the pre-award phase and leaves to the agency's discretion whether to pay offerors for preparation for, and participation in, pre-award IBRs conducted as part of the source selection process. Also, although the final FAR rule contains two solicitation provisions and a contract clause addressing EVMS, agencies were given the flexibility to develop provisions and clauses for their own use as long as they are substantially the same as those contained in the FAR.

3. Analysis and Discussion: EVM principles and techniques provide program managers with timely, accurate, and detailed cost, schedule, and performance status information with which to make informed decisions during the life of a program. However, using EVM on contracts involves added time, cost, and effort on the part of both vendors and the Government. For vendors, there are costs associated with establishing EVMS in accordance with the ANSI/EIA standard, setting the basic budget and schedule parameters for specific contract efforts, and preparing and submitting periodic reports of progress and status. For the Government, there are costs associated with evaluating offerors' and contractors' EVMS and with receiving, reviewing, and analyzing periodic EVM reports. Because of this workload, EVM should be used only when the benefits of applying its tools and techniques are deemed by the agency to outweigh the associated costs. To establish these parameters, the HHSAR coverage sets a contract value floor below which the application of EVM is not mandatory and any planned requirement for its use must be approved in advance by the HCA. For contracts with values exceeding the floor, this HHSAR coverage makes a distinction, also based on contract value, between contracts that require the use of EVM techniques and those that require that the successful offeror's EVMS be reviewed and approved by the Cognizant Federal Agency (CFA) as being in conformance with the full requirements of ANSI/EIA Standard-748.

Several considerations in addition to contract value should apply when determining whether to use EVM. Among the most important of these considerations are the proposed contract type and the subject matter of the underlying effort. Failure to address these considerations could result in the use of EVM to achieve results that other potentially equally effective and less costly tools and techniques could provide. Among the primary indicators of performance status that EVM provides are estimates of cost and schedule variances from the performance plans, at the detailed work package level, established during contract formation. This is done by comparing three specific values: the budgeted cost of work scheduled (BCWS); the budgeted cost of work actually

performed (BCWP); and the actual cost of work performed (ACWP). At any point, to the extent that BCWP varies from BCWS, a positive or negative schedule variance exists. Schedule deviation or variance could just as easily be determined merely by comparing planned activities with those actually performed over any time interval using tools other than EVM -e.g., Microsoft Project or a similar schedule tracking application. Similarly, to the extent that ACWP varies from BCWP, a positive or negative cost variance exists.

If the type of contract does not expose the Government to any cost risk of performance, the existence of a cost variance is of no actionable concern to the Contracting Officer's Technical Representative (COTR) or the Contracting Officer (CO). For example, under a firm-fixed-price contract, the amount the Government will pay for the supplies or services has been established at the time of contract formation, and as long as no changes are made or requested in the work to be performed, the final price to be paid will not be affected by the amount of costs the contractor incurs in performing the contract. However, if the amount the Government may pay for the contracted performance could vary or if the amount of performance actually received could be affected by the level of cost being incurred, then the existence of a cost variance is, and should be, of interest to the COTR and the CO. This would be the case if a cost-reimbursement or fixed-price-incentive type contract is being used. Also, for term form contracts (i.e., when the contracted performance is defined as a set level-of-effort), time-and-material and labor-hour contracts, and commercial contracts under FAR Part 12, the existence of a cost variance is not an actionable condition for either the COTR or CO because the contracted performance required is measured in terms of labor hours for which a fixed price, estimated cost limit, or ceiling price accompanied by fixed hourly rates has been established. Therefore, depending on the contract type, the HHSAR coverage permits either full or partial EVM. Under full EVM both the cost and schedule aspects of a contract are tracked and reported whereas, under partial EVM, tracking and reporting is limited to only the schedule aspects of the contract. The coverage also contains language prohibiting the selection of a particular contract type merely to avoid the application and use of full EVM.

The table on the following page summarizes the applicability of EVMS consistent with the specific content of the interim guidance.

|  |  |  | EVMS |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Category | Contract Value | Contract Type | Full (Cost and Schedule) EVM Required | Partial (Schedule Only) EVM Required | Not Required | Optional with HCA Prior Approval |
| Major acquisitions for development (per OMB Circular A-11) and Acquisitions for development, modernization, or upgrade (non-major) | < $ 10 million | Any Type |  |  |  |  |
|  | =/> $ 10 million to $25 million | Cost Reimbursement/Fixed Price Incentive (with incentive based on cost) | * |  |  |  |
|  | =/> $10 million to $25 million | Firm-fixed-price, Time-and-Materials, Labor-hour, and Term form |  | * |  |  |
|  | > $25 million | Cost Reimbursement/Fixed Price Incentive (with incentive based on cost) | ** |  |  |  |
|  | > $25 million | Firm-fixed-price, Time-and Materials, Labor-hour, and Term form |  | ** |  |  |
| Acquisition of non-developmental services, routine services, steady state operations, basic and applied research, or commercial items (in accordance with FAR Part 12) | Any value | Any type |  |  |  |  |

* Contractor’s EVM system must comply with ANSI/EIA Standard-748-A

** Contractor’s EVM system must be validated and accepted by the CFA.

Once a decision is made to apply EVM (whether full or partial) to a proposed contract, other related decisions will also have to be made. Among them is the choice of when to establish the performance measurement baseline (PMB). One of the first and most important steps in applying EVM techniques to an acquisition is the establishment of baseline planned schedule and/or budget parameters (the PMB) at the work package level. When the baseline has been established, all future EVM reporting of cost and/or schedule status is accomplished with respect to that plan.

The meeting to establish the PMB can take place either before award (as part of the competitive process), or after award and only with the successful offeror. In either case, it is a joint responsibility of the Project Officer (PO) (who performs technical/programmatic responsibilities in a pre-award environment), the CO, and the offeror(s)/contractor. This process is referred to as the integrated baseline review (IBR). The decision of when to conduct an IBR can have significant cost and time implications for both vendors and the Government. As a consequence, the proposed HHSAR coverage treats pre-award IBRs as an exceptional item requiring advance approval and specific funding. When pre-award IBRs are conducted, all offerors will incur added bid and

proposal costs, the cost for the Government to conduct multiple IBRs can be significant, and the source selection and award phase of the acquisition may be delayed. Government personnel will need to review and establish several baselines and also assess the compliance of several offerors' EVMS with the ANSI/EIA standard. The use and implications of pre-award IBRs in the source evaluation and selection process must be clearly set forth in both the acquisition plan and the solicitation.

The use of performance-based contracting techniques presents yet another issue with respect to preaward IBRs. In a performance-based acquisition, each offeror's submission is likely to be significantly different in areas such as approach, content, and detailed schedule, along with the expected differences in offered prices and, therefore, associated budgets. As a result, establishing an acceptable budget and/or schedule baseline with each offeror is likely to be a more resource intensive activity for the Government. Alternatively, when an IBR is conducted after contract award, it involves only the successful offeror and thus the time and cost impact will be reduced. In fact, even when pre-award IBRs have been conducted, a post-award IBR is often still necessary to incorporate any changes that may have resulted from negotiations with the successful offeror. Also, the use of pre-award IBRs may adversely affect the desire or ability of small business concerns to compete effectively for business opportunities.

Therefore, the interim HHSAR coverage places significant limitations on the decision to use preaward IBRs and requires that offerors be compensated for preparing for and participating in them.

4. Impact on HHSAR: This interim acquisition guidance has an impact on two parts of the HHSAR:

HHSAR 334.2-Earned Value Management System (EVMS): It adds a new subpart that addresses the implementation of earned value management within HHS. This new subpart sets forth the contract value thresholds for EVMS use, establishes criteria for applying either full or partial EVMS based upon the contract type used, states policy with respect to the decision to use pre-award IBRs, and prescribes the use of two solicitation provisions and two contract clauses addressing EVMS.

HHSAR 352. 234-X-Solicitation Provisions and Contract Clauses: It adds two solicitation provisions-one to be used in contract solicitations when pre-award IBRs are contemplated and one to be used when only a post-award IBR is contemplated. Further, it adds two contract clauses to be used in solicitations and contracts that, depending upon contract type, will require the use of either full or partial EVM. The FAR provisions and contract clause are not used because of unique HHS EVM applicability and implementation issues, which can be addressed more effectively and efficiently using the HHSAR-specific provisions and clauses.

5. Regulatory Language: Attached is the interim regulatory language to address EVM.

cc: ASRT/OCIO (Phil Clark)

ASAM/OFMP (Diane Stewart)

ASPRIBARDA (Michael Blumenfeld)

Attachment

Attachment

Interim HHSAR Guidance -Earned Value Management

- Add a new subpart at HHSAR 334.2, as/allows:

Part 334-Major System Acquisition

[Subpart 334.2-Earned Value Management System

334.200 Definitions

As used in this subpart –

"Full EVMS" means tracking and reporting of both the cost and schedule aspects of a contract using the principles and guidelines described in ANSIIEIA Standard-748, Earned Value Management Systems (using the version of the Standard that is in effect at the time of the solicitation).

"Partial EVMS" means tracking and reporting of only the schedule aspects of a contract using the principles and guidelines described in ANSI/EIA Standard-748, Earned Value Management Systems (using the version of the Standard that is in effect at the time of the solicitation).

334.201 Policy

- For acquisitions for development designated as major in accordance with both OMB Circular A-II and HHS policy on major acquisitions; for acquisitions that involve substantial development, modification or enhancement; or for acquisitions that involve significant upgrade of operational or steady state systems or programs, use of an Earned Value Management System (EVMS) is required as follows:

- For individual cost-reimbursement or fixed-price-incentive contracts (with incentive based on cost) valued at $10 million to $25 million, including options, full EVMS (as defined in 334.200) is required and the contractor's EVMS shall comply with the guidelines in ANSIIEIA Standard-748.

- For individual firm-fixed-price, term form (level-of-effort) of any type, time-andmaterials, or labor-hour contracts valued at $10 million to $25 million, including options, partial EVMS (as defined in 334.200) is required and the contractor's EVMS shall comply with the guidelines in ANSI/EIA Standard-748.

- For individual cost-reimbursement or fixed-price-incentive contracts (with incentive based on cost) valued at more than $25 million, including options, full EVMS (as defined in 334.200) is required and the contractor's EVMS must be formally validated and accepted by the Government (i.e., the contractor's Cognizant Federal Agency (CFA), as defined in FAR 2.101 and described in FAR 42.003).

- For individual firm-fixed-price, term form (level-of-effort) of any type, time-andmaterials, or labor-hour contracts valued at more than $25 million, including options, partial EVMS (as defined in 334.200) is required and the contractor's EVMS must be formally validated and accepted by the Government (i.e., the contractor's CFA).

- For individual contracts of any type valued at less than $10 million, including options, full or partial EVM application, as appropriate to the contract type involved, is optional. The recommendation to use EVM should be based upon a risk analysis by the program manager/Project Officer (PO). A decision to use EVM at this level requires the prior approval of the cognizant Head of the Contracting Activity (HCA).

- EVM is not required, but may be applied with prior written approval of the HCA, on contracts of any dollar amount meeting either of the following criteria:

- The acquisition is for non-developmental support services (e.g., program office support, Independent Verification & Validation services), steady state operations, basic and applied research, and routine services (e.g., building maintenance, help-desk services, landscaping services); or

- The contract is for a commercial item(s) under FAR Part 12.

- When full EVM is required on a prime contract, it applies to subcontracts issued thereunder if those subcontracts have a value and are of a type and subject matter that would have required the use of full EVM had they been prime contracts. However, if the prime contract requires the use of only partial EVM, any subcontracts to which EVM is made applicable, because of dollar value, contract type or subject matter, shall require only partial EVM.

- When offerors are required to provide an EVMS plan as part of their proposals, the contracting officer shall request the assistance of the PO (and/or an appropriate HHSdesignated third party) in determining the adequacy of such proposed EVMS plans.

- The selection or use of a particular contract type, if done only or primarily to avoid the application of full EVM to the acquisition is prohibited.

334.202 Integrated Baseline Reviews (IBRs).

- An IBR normally should be conducted as a post-award activity. A pre-award IBR may be conducted only if:

- The acquisition plan contains documentation that demonstrates the need and rationale for a pre-award IBR, including an assessment of the impact on the source selection schedule and the expected benefits;

- The use of a pre-award IBR is approved in writing by the cognizant HCA prior to the issuance of the solicitation;

- The source selection plan specifically addresses how the results of a pre-award IBR will be used during source selection, including any weight to be given to it in source evaluation, and that same or similar rationale is clearly set forth in the solicitation; and,

- Specific arrangements are made, and budget authority is provided, to compensate all offerors who prepare for or participate in a pre-award IBR; and the solicitation informs prospective offerors of the means for and conditions of such compensation.

334.203 Solicitation provisions and contract clauses.

The FAR EVMS solicitation provisions and contract clause will not be used in HHS contracts. See 334.203-70 for the HHS solicitation provisions and contract clauses.

334.203-70 HHS solicitation provisions and contract clauses.

As provided in 334.201(a) and 334.202, the Contracting Officer (CO) shall insert

- The provision at 352.234-1, Notice of Earned Value Management System-Pre-Award IBR, in solicitations for contracts that will require the contractor to use an Earned Value Management System (EVMS), whether full or partial, when the Government requires an Integrated Baseline Review (IBR) prior to award.

- The provision at 352.234-2, Notice of Earned Value Management System-Post-Award IBR, in solicitations for contracts that will require the contractor to use an EVMS, whether full or partial, when the Government requires an IBR after contract award.

- The clause at 352.234-3, Full Earned Value Management System, in solicitations and contracts that will: be either cost-reimbursement or fixed-price-incentive (where the incentive is based on cost), have an expected value, including options, equal to or greater than $25 million, and require a contractor to use full EVMS. The CO shall use the clause with its Alternate I when the contract value, including options, is equal to or greater than $10 million but less than $25 million.

- The clause at 352.234-4, Partial Earned Value Management System, in solicitations and contracts that will be firm-fixed-price, time-and-materials, labor-hour, or term form; have an expected value, including options, equal to or greater than $25 million; and require a contractor to use partial EVMS. The CO shall use the clause with its Alternate I when the contract value, including options, is equal to or greater than $10 million but less than $25 million.]

- Add sections 352.234-1, 352.234-2, and 352.234-3 to read as follows:

[352.234-1 Notice of Earned Value Management System – Pre-Award IBR.

As prescribed in 334.203-70(a), use the following provision:

NOTICE OF EARNED VALUE MANAGEMENT SYSTEM -PRE-AWARD IBR (OCT 2008)

- The offeror shall provide documentation that its proposed Earned Value Management System (EVMS) complies with the EVMS guidelines in ANSI/EIA Standard-748 (current version at time of solicitation).

- If the offeror proposes to use a system that currently does not meet the requirements of paragraph (a) of this provision, the offeror shall submit a comprehensive plan for compliance with the guidelines.

(1)	 The plan shall

  - Describe the EVMS the offeror intends to use in performance of the contract;

  - Distinguish between the offeror's existing management system and modifications proposed to meet the guidelines;

  - Describe the management system and its application in terms of the EVMS guidelines;

  - Describe the proposed procedure for application of the EVMS requirements to subcontractors;

  - Provide documentation describing the process and results, including Government participation if applicable, of any third-party evaluation or self-evaluation of the system's compliance with the EVMS guidelines;

  - Provide a schedule of events leading up to formal validation and Government acceptance of the offeror's EVMS, if the value of the offeror's proposal, including options, is $25 million or more.

- The offeror shall provide information and assistance, as required by the Contracting Officer,  to support review of the plan.

- The Contracting Officer will review the offeror's EVMS implementation plan prior to   contract award.

- The offeror's EVMS plan must provide milestones indicating when the offeror anticipates that the EVMS will be compliant with the ANSVEIS Standard-748 guidelines.

- The offeror shall identify in its offer the subcontractors, or subcontracted effort if subcontractors have not been identified, to which the requirements of EVMS will be applied. Prior to contract award, the offeror and HHS shall agree on the subcontractors, or subcontracted effort, subject to the EVMS requirement.

- HHS will conduct an Integrated Baseline Review (IBR) prior to contract award. The offeror shall be compensated as set forth elsewhere in this solicitation for its preparation for and participation in the IBR.

(End of provision)

352.234-2 Notice of Earned Value Management System -Post-Award IBR.

As prescribed in 334.203-70(b), use the following provision:

NOTICE OF EARNED VALUE MANAGEMENT SYSTEM -POST-AWARD IBR (OCT 2008)

- The offeror shall provide documentation that its proposed Earned Value Management System (EVMS) complies with the EVMS guidelines in ANSI/EIA Standard-748 (current version in effect at time of solicitation).

- If the offeror proposes to use a system that currently does not meet the requirements of paragraph (a) of this provision, the offeror shall submit a comprehensive plan for compliance with the guidelines.

- The plan shall

- Describe the EVMS the offeror intends to use in performance of the contract;

- Distinguish between the offeror's existing management system and modifications proposed to meet the guidelines;

- Describe the management system and its application in terms of the EVMS guidelines;

- Describe the proposed procedure for application of the EVMS requirements to subcontractors;

- Provide documentation describing the process and results, including Government participation if applicable, of any third-party evaluation or self-evaluation of the system's compliance with the EVMS guidelines;

- Provide a schedule of events leading up to formal validation and Government acceptance of the offeror's EVMS, if the value of the offeror's proposal, including options, is $25 million or more.

- The offeror shall provide information and assistance, as required by the Contracting Officer, to support review of the plan.

- The Contracting Officer will review the offeror's EVMS implementation plan prior to contract award.

- The offeror's EVMS plan must provide milestones indicating when the offeror anticipates that the EVM system will be compliant with the ANSI/EIA Standard-748 guidelines.

- The offeror shall identify in its offer the subcontractors, or subcontracted effort if subcontractors have not been identified, to which the requirements of EVMS will be applied. Prior to contract award, the offeror and HHS shall agree on the subcontractor:-, ')r subcontracted effort, subject to the EVMS requirement.

(End of provision)

352.234-3 Full Earned Value Management System.

As prescribed in 334.302-70(c), insert the following clause:

FULL EARNED VALUE MANAGEMENT SYSTEM (OCT 2008)

- The Contractor shall use an Earned Value Management System (EVMS) that has been validated and accepted by the Cognizant Federal Agency (CFA) as being compliant with the guidelines in ANSI/EIA Standard-748 (current version at the time of award) to manage this contract. If the Contractor's current EVMS has not been validated and accepted by the CFA at the time of award, see paragraph (b) of this clause. The Contractor shall submit EVM reports in accordance with the requirements of this contract.

- If, at the time of award, the Contractor's EVM system has not been validated and accepted by the CFA as complying with EVMS guidelines in ANSI/EIA Standard-748 (current version at time of award), the Contractor shall

- Apply the current system to the contract; and

- Take necessary and timely actions to meet the milestones in the Contractor's EVMS plan approved by the Contracting Officer.

- HHS requires the Contractor to obtain validation and acceptance of its EVM system by the CFA during the base period of performance of this contract. The Contracting Officer or designee will conduct a Compliance Review to assess the Contractor's compliance with its approved plan. If the Contractor does not follow the approved implementation schedule or correct all resulting system deficiencies noted during the Compliance Review within a reasonable time, the Contracting Officer may take remedial action, which may include, but is not limited to, suspension of or reduction in progress payments, or a reduction in fee.

- HHS will conduct an Integrated Baseline Review (IBR). If a pre-award IBR has not been conducted, a post-award IBR will be conducted by HHS as early as practicable, but no later than ninety (90) days after contract award. The Contracting Officer may also require an IBR as pari of the exercise of an option or the incorporation of a major modification.

- Unless a waiver is granted by the CFA, Contractor-proposed EVMS changes require approval of the CFA prior to implementation. The CFA will advise the Contractor of the acceptability of such changes within 30 calendar days after receipt of the notice of proposed changes from the Contractor. If the advance approval requirements are waived by the CFA, the Contractor shall disclose EVMS changes to the CFA at least 14 calendar days prior to the effective date of implementation.

- The Contractor shall provide access to all pertinent records and data requested by the Contracting Officer or a duly authorized representative as necessary to permit Government surveillance to ensure that the EVMS conforms, and continues to conform, with the requirements referenced in paragraph (a) of this clause.

- The Contractor shall require the subcontractors specified below to comply with the requirements of the clause: (Insert list of applicable subcontractors.)

(End of clause)

(Alternate I) (OCT 2008)

As prescribed in 334.203-70(c), substitute the following paragraphs (a), (b), and (c) for paragraphs (a), (b), and (c) of the basic clause and delete paragraph (e) of the basic clause:

  - The Contractor shall use an Earned Value Management System (EVMS) that is compliant with the guidelines in ANSI/EIA Standard-748 (current version at the time of award) to manage this contract. If the Contractor's current EVMS is not compliant at the time of award, see paragraph (b) of this clause. The Contractor shall submit EVM reports in accordance with the requirements of this contract.

  - If, at the time of award, the Contractor's EVM system is not in compliance with the EVMS guidelines in ANSI/EIA Standard-748 (current version at time of award), the Contractor shall

- Apply the current system to the contract; and

- Take necessary and timely actions to meet the milestones in the Contractor's EVMS plan approved by the Contracting Officer.

  - HHS will not formally validate or accept the Contractor's EVMS with respect to this contract. The use of the Contractor's EVMS for this contract does not imply HHS acceptance of the Contractor's EVMS for application to future contracts. The Contracting Officer or designee will conduct a Compliance Review to assess the Contractor's compliance with its approved plan. If the Contractor does not follow the approved implementation schedule or correct all resulting system deficiencies noted during the Compliance Review within a reasonable time, the Contracting Officer may take remedial action that may include, but is not limited to, suspension of or reduction in progress payments, or a reduction in fee.

352.234-4 Partial Earned Value Management System.

As prescribed in 334.203-70(d), insert the following clause:

PARTIAL EARNED VALUE MANAGEMENT SYSTEM (OCT 2008)

  - The Contractor shall use an Earned Value Management System (EVMS) that has been validated and accepted by the Cognizant Federal Agency (CFA) as being compliant with the schedule-related guidelines in ANSI/EIA Standard-748 (current version at the time of award) to manage this contract. If the Contractor's current EVMS has not been validated and accepted by the CFA at the time of award, see paragraph (b) of this clause. The Contractor shall submit EVM reports in accordance with the requirements of this contract.

  - If, at the time of award, the Contractor's EVM system has not been validated and accepted by the CFA as complying with the schedule-related EVMS guidelines in ANSI/EIA Standard-748 (current version at time of award), the Contractor shall

- Apply the current system to the contract; and

- Take necessary and timely actions to meet the milestones in the Contractor's EVMS plan approved by the Contracting Officer.

  - HHS requires the Contractor to obtain validation and acceptance of the schedule-related portions of its EVM system by the CFA during the base period of performance of this contract. The Contracting Officer or designee will conduct a Compliance Review to assess the Contractor's compliance with its approved plan. If the Contractor does not follow the approved implementation schedule or correct all resulting system deficiencies noted during the Compliance Review within a reasonable time, the Contracting Officer may take remedial action, which may include, but is not limited to, suspension of or reduction in progress payments, or a reduction in fee.

  - HHS will conduct an Integrated Baseline Review (IBR). If a pre-award IBR has not been conducted, a post-award IBR will be conducted by HHS as early as practicable, but no later than ninety (90) days after contract award. The Contracting Officer may also require an IBR as part of the exercise of an option or the incorporation of a major modification.

  - Unless a waiver is granted by the CFA, Contractor-proposed EVMS changes require approval of the CFA prior to implementation. The CFA will advise the Contractor of the acceptability of such changes within 30 calendar days after receipt of the notice of proposed changes from the Contractor. If the advance approval requirements are waived by the CFA, the Contractor shall disclose EVMS changes to the CFA at least 14 calendar days prior to the effective date of implementation.

  - The Contractor shall provide access to all pertinent records and data requested by the Contracting Officer or a duly authorized representative as necessary to permit Government surveillance to ensure that the EVMS conforms, and continues to conform, with the requirements referenced in paragraph (a) of this clause.

  - The Contractor shall require the subcontractors specified below to comply with the requirements of the clause: (Insert list of applicable subcontractors.)

(End of clause)

(Alternate I) (OCT 2008)

As prescribed in 334.203-70(d), substitute the following paragraphs (a), (b), and (c) for paragraphs (a), (b), and (c) of the basic clause and delete paragraph (e) of the basic clause:

  - The Contractor shall use an Earned Value Management System (EVMS) that is compliant with the schedule-related guidelines in ANSI/EIA Standard-748 (current version at the time of award) to manage this contract. If the Contractor's current EVMS is not compliant at the time of award, see paragraph (b) of this clause. The Contractor shall submit EVM reports in accordance with the requirements of this contract.

  - If, at the time of award, the Contractor's schedule-related EVM system is not in compliance with the schedule-related EVMS guidelines in ANSI/EIA Standard-748 (current version at time of award), or the Contractor does not have an existing schedule control system that is compliant with such guidelines, the Contractor shall –

- Apply the current system to the contract; and

- Take necessary and timely actions to meet the milestones in the Contractor's EVMS plan approved by the Contracting Officer.

  - HHS will not formally validate or accept the Contractor's schedule-related EVMS with respect to this contract. The use of the Contractor's EVMS for this contract does not imply HHS acceptance of the Contractor's EVMS for application to future contracts. The Contracting Officer or designee will conduct a Compliance Review to assess the Contractor's compliance with its approved plan. If the Contractor does not follow the approved implementation schedule or correct all resulting system deficiencies noted during the Compliance Review within a reasonable time, the Contracting Officer may take remedial action, that may include, but is not limited to, suspension of or reduction in progress payments, or a reduction in fee.]

3 The final FAR rule (in case 2004-019) was issued as a part of Federal Acquisition Circular (FAC) 2005-11. The full text Qfthe final version of the rule can be found at: httpJ!www,acgnet.gov!fARlFAC!fac2005-11 federal register.pdf