# Committee Name:  Violence Prevention Technical Advisory Committee ____________________		Chair: _Linda Belton / Michael Hodgson_

Annual Briefing: ______________________

## Semi-annual update: _XX

| - Committee Membership | Unchanged from last time |
| --- | --- |
| - Purpose | Review existing violence programs and plans, identify weaknesses, develop short- and long-term strategies for improvement |
| - Goals and accomplish-ments | 2003 Goals (as presented at the last annual meeting) and status •FY 2003 Performance monitor Completion –Training network: all facilities trained 2 trainers for hands-on training –Training plan: 15 of 142 facilities developed plans that failed to meet all of the pre-determined criteria for acceptability. This plan was to address high risk occupations (nursing) and high risk areas (geriatrics, mental health, emergency departments). Those facilities have been asked to revise their plans •FY2004 Performance monitor: Flagging and Training --The FY2004 Performance Monitor consists of two parts: implementation of patient record flags, with the formation of a Disruptive Behavior Committee under senior clinical leadership with appropriate training and progress on the training plan --10N supported the implementation of the Patient Record Flags, with M Hodgson identified as a stakeholder. Software has been released. -- An introductory clinical tape was developed (in addition to the originally planned IO training tape) for roll-out. An initial version of the clinical tape was withdrawn because of a recognized --A curriculum for formal threat assessment is under development. A set of training calls for the PRF Committees have been scheduled starting January 2004. Four satellite broadcasts are planned for mid to late 2004. -- Supporting educational materials were sent out to all committees •Process evaluation (NIOSH) - Field work completed but progress on receiving a report •Development of Post incident f/u -- The National Center for PTSD (Dr Ruzek) received funding to develop this manual and is reportedly making progress. ## •Violence prevention through environmental design Slide show and text completed and presented to Engineering Advisory Board for consideration. The goal is to make this mandatory for all engineers and before any renovation Identification of causes -- The project “Violence Assessment and Management Program” (VAMP), by Drs Zeiss (Palo Alto) and Lanza (Bedford) is underway in Bedford, Marion (VISN 11), and San Antonio, as planned. Additional projects •Data summary -- A manuscript on assaults in VHA was written, cleared with OQP and 10, and is under final review (after revisions) at a peer-reviewed journal. •Dom Task Force: -- The project “Violence Assessment and Management Program” (VAMP), by Drs Zeiss (Palo Alto) and Lanza (Bedford -- The Dom Task Force requested help from the Violence Prevention Task force to develop and implement a violence prevention strategy in the Domiciliaries as part of the Dom task force work. A formative and summative tool was developed and implemented, after piloting, through a series of meetings, site visits, and a satellite broadcast. The National Dom Program will develop a formal report which will be shared with the HR Committee • New EES Training Modules -- EES is working with Jim Scaringi, Dan Kowalski, and an NSF-funded group to develop scenario-based anti-aggression training modules. |
| - Status/Accomplishments | See 3. |
| - Areas requiring HR Committee Support | None at present |
| - Next Steps | Discussions for next years performance monitor are under way Planning on how to use committee minutes from the DBC are under way Discussions with two private sector organizations on developing innovative training materials for threat assessment are under way. |