INDIAN HEALTH SERVICE

Business Office Coordinators, HIPAA Coordinators,

Information System Coordinators and Headquarters

Minutes for September 16, 2004

HIPAA Business Transactions Awareness Conference Call

Present

ITSC:	Dyanne Leyba, Catherine Thompkins, Yolanda Trent

Headquarters:	Frank Martin

Aberdeen:	Ray Granbois, Marie Baker

Alaska:	No Response

Albuquerque:	No Response

Bemidji:	Julie Heisler, Steve Bird, Jan Thunder

Billings:	No Response

California:	No Response

Nashville:	No Response

Navajo:	Brenda Tahe

Oklahoma:	No Response

Portland:	David Battese

Phoenix:	Violet Kenney, Charolett Melcher

Tucson:	Kurt Priessman

Meeting Began at 10:00 AM

Roll Call

Minutes	The Conference Call Minutes for 8/19/04 were approved. They will be posted to the IHS website.

AGENDA ITEMS ADDRESSED

# Items of follow up from ITSC Business Transactions Training held in February 2004 – UPDATE STATUS REPORTS.

# Item # 1 -- National Training Online Modules –Funding Issued-Getting proposal from Company. Frank Martin Sandra Lahi/Kurt Priessman

Per Frank, Larry Pope is working on the proposal-hopefully will complete this week. These modules will include information for 837 and 835 testing. Frank also stated that he has updated the website Training Tool for new employees for HIPAA compliance.

# Item # 2 -- Indian Health Service CMS representation – Elmer Brewster/Sandra Lahi-Waiting for CMS to respond.

Per Frank, work still continues to obtain the CMS contact, Elmer has made contact and is working on arrangements with CMS.  I H S needs to become involved with the CMS workgroup for HIPAA.

Reports from Area Office Leads/ITSC – (1) Is there progress with testing the HIPAA transactions for your Area or Facility?  (2) Are there any major issues that you need I H S to address regarding RPMS software?

Aberdeen	Marie reported that they are testing the 837 format with ND Medicaid. Have began testing Medicare part A claims at Bradford City. Not working on 835 currently.

Alaska	No Report Provided

Albuquerque	No Report Provided

Bemidji	Red Lake is looking good with Part A and B. 835 is also good. Will begin testing with Medicaid this week.

Billings	No report provided

California	No Report Provided

Nashville	No Report Provided

Navajo 	Brenda stated that the area is in production with Medicare A&B. They have had some provider number problems since release of patch 6. Should be in full production with AHCCCS and NM Medicaid by end of month. They are successful with the 835 from AHCCCS. Tuba City will take the lead on Quovadx testing.

Oklahoma	No report provided

Portland	David reports that their 835 for Medicare Part B is not working. He attended the Trailblazer meeting in Dallas and notes that there are some updates needed to the 837 files due to more data requirements. He is having problems with the form locator override for Colville.

Phoenix	Violet stated that they are in full production with Medicare and Medicaid. PIMC will be testing the 835 for the next two weeks. Elko and Ft Duchesne remain to test.

Tucson	Per Kurt, Sells testing 837D with BCBSAZ.  835 files with AHCCCS are missing remark codes. They will process first 835 for Blue Cross through PNC today. Santa Rosa and San Xavier are testing.

ITSC

Sandra Lahi	1.  837 ABM Version 2.6 to be assigned for development-Sandra

No update provided.

Catherine

Thompkins	2.  835 PNC Bank Project- Catherine Thompkins

Per Catherine, the Phoenix area almost complete. PNC is working to get 	MN Medicaid running, as well as last details for MediCal and NV 	Medicaid. Lawton has begun processing files from OK Medicaid. Red 	Lake is processing Medicare Part B. We have been notified that NM 	Medicaid will not have an 835 format available until the summer of 2005.

Sandra Lahi	3.  Patient Registration Clean up Report. Task Order approved and waiting to 	be assigned for development.- Sandra

No update provided.

Catherine	4.  2005 ICD 9 Code Set Updates

Thompkins		PIMC is now testing-do not have an update yet.

Follow up Items:

1.  Status of National Clearinghouse Contract Discussion.

The RFP is due to go out before the end of September. Status Quo.

QUESTIONS/CONCERNS/DISCUSSION

David from Portland area wants to have the Secondary 837 files pull the Payment/Adjustment info directly from the Primary 835 files.

NEXT CONFERENCE CALL

The next call is scheduled for Thursday, October 14, 2004 at 10:00 AM (MDST).  The conference call-in number is:  (888) 531-9517 (Passcode:  46879).