AIP Project Schedule

2008-2010

FAA Airports Division, Alaskan Region

(Last saved:  Friday, October 3, 2008)

STATE OF ALASKA - CENTRAL REGION

ANCHORAGE (Stevens Int’l)								ANC

Project:	Two projects: 1)Reconstruct runway 7R-25L including widening to 200 ft., Design Group VI Aircraft, 2) Runway extension pending Environmental Assessment (EA)

* MAJOR RUNWAY PROJECT

Construction Start:	April 2010

Likely Completion:	October 2010

Sponsor/POC:	AKDOT/Gary Lincoln, 269-0606

Airports POC:	Eric Helms, 271-5202

ATO POC:	Suzanne Lee-Pang (425)917-6673, Mike Edelman 271-3823

Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts: 	GS, IM, ALSF, RVR, ASOS, ASDE, NDB, PAPI, REIL, cables

AVN Impacts:	Runway Extension will require revision of all approaches to Runway 7R

AT Impacts:	Long term (7 month) shutdown of Runway 7R-25L. Ongoing coordination between Airport Ops & ATCT

Reimbursable Agreement Info:	Initial ATO design support Reimbursable Agreement (RA) in place. Additional RA required for ATO support during Runway Widening and Runway Extension.

ATKA	AKA

Project:	Extend, Reconstruct, and Realign Runway

Rotate Runway 15/33 3 degrees (Also being redesignated due to magnetic declination from Runway 16/34).  Extending runway to 4500’.  Construct new apron, SREB, Rotating Beacon, Lighted Wind Cone, Pads and Conduit for future REILs and PAPIs.  Relocate electrical and telephone services to existing AWOS.

Construction Start:	July 2008

Likely Completion:	Fall 2009

Sponsor/POC:	AKDOT Aviation Construction Project Manager/Steve Frey, 269-0450

Airports POC:	Krisjon Tabisola, 271-3785

FAA Tech Ops Engineering POC:	Jose Echeveria, 271-2366

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts: 	Constructing pads and installing conduit for future PAPI’s.  Potential temporary impact to existing AWOS during electrical and telephone relocation/reconnection.

AVN Impacts:	Chart Date July 2, 2009

Reimbursable Agreement Info:	None

BETHEL  	BET

Project:  	Construct Parallel Runway Phase II —Project will complete construction  and paving of the runway 1R/19L

Construction Start:	July 2008

Likely Completion:	August 1, 2009

Sponsor/POC:	AKDOT/Harold Henderson, 269-0446

Airports POC:	Krisjon Tabisola, 271-3785

ATO POC: 	Tom Ondra, 271-2427

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts: 	PAPI’s/REIL’s—Construct pads.  Tom Ondra working with DOT on PAPI’s.  Equipment is available.

AVN Impacts:	Chart Date is 11/2008.  Construction will not be complete until Summer 2009.  NOTAM’s will be used to clarify.  Upon completion of the runway the runway numbers for the primary runway and this new parallel runway will be painted simultaneously and the NOTAM’s deleted or changed accordingly.

Reimbursable Agreement Info:	None

CHEFORNAK	TM10

Project:	Construct New Airport –Phase II

Construction Start:	Summer 2009

Likely Completion:	Fall 2010/11

Sponsor/POC:	AKDOT/Gary Lincloln

Airports POC:	John Lovett, 271-5446

ATO POC:		Suzanne Lee-Pang (425)917-6673

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts:	(low priority for PAPI/REILS)

AVN Impacts:	New airport will be open at completion of Phase II

Reimbursable Agreement Info:

CROOKED CREEK	CIX

Project:	Realign/Extend Runway

Construction Start:	?

Likely Completion:	?

Sponsor POC: 	Morgan Merritt 269-

Airports POC:	John Lovett, 271-5446

ATO POC:	Suzanne Lee-Pang (425)917-6673

NAS Impacts:

AVN Impacts: (low priority for PAPI/REILS)

Reimbursable Agreement Info:

# DILLINGHAM	DLG

Project:	Construct RSA/Parallel Taxiway

Construction Start:	2010

Likely Completion:	2011

Sponsor/POC:  	AKDOT/ Tom Schmidt, 269-0612

FAA Airports:	John Lovett, 271-5446

ATO POC:	Suzanne Lee-Pang (425)917-6673

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts:  TBD

AVN Impacts:  TBD

Reimbursable Agreement Info:

GOODNEWS	GNU

Project:	Reconstruct/Realign Runway

Construction Start:	2009

Likely Completion:	2010

Sponsor/POC:	AKDOT/Gary Lincoln, 269-0606

Airports POC:	John Lovett, 271-5446

ATO POC:	Robert Yerkes, 271-5800

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts:	Install PAPI/REILS

AVN Impacts:

Reimbursable Agreement Info:

KING SALMON	AKN

Project:  	RELOCATE RUNWAY 29 THRESHOLD (400’), RESURFACE RUNWAY 18/36, CONSTRUCT GA TAXIWAY, RELOCATE RUNWAY 29 PAPI, MARK POFZ (PRECISION OBSTACLE FREE ZONE, CHANGE RUNWAY 11/29 TO 12/30 (MAGN. DECL.)

Construction Start:	July 2008

Likely Completion:	September 25, 2008 for Runway 18/36 work (Complete as of 10/3/08)

October 2008 for remaining work

Sponsor/POC:	AKDOT/Bob Lundell, 269-0448

Airports POC:	Krisjon Tabisola, 271-3785

ATO POC:	David Yee, __________

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts: 	Will need to turn Localizer and Glide Slope off during threshold relocation.  (Expect Flight Check August 15, 2008.)

AVN Impacts:	9/25/08 Chart Date.

After 8/15/08 flight check can Loc & G.S. be operational for RWY 11?

Can numbers be re-marked then NOTAM’d, or covered with temp marking?

Reimbursable Agreement Info:	Signed? DOT needs to sign ASAP, and overnight the check to FAA OKC…

Randy Swartz, SSC, (246-3424) needs to hear ASAP from DOT Construction with confirmation of 7/15/08 start date.

KIPNUK	IIK

Project:	Construct Airport (Phase II)

Construction Start:	2009

Likely Completion:	2011

Sponsor/POC:	AKDOT/Gary Lincoln, 269-0606

Airports POC:	John Lovett, 271-5446

ATO POC:	Robert Yerkes, 271-5800

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts:  PAPI/REILS

AVN Impacts:	New airport will be completed under PhaseII

Reimbursable Agreement Info:

KODIAK	ADQ

Project:	Construct RSA 7/25&18/36, 	Pavement Rehabilitation

Construction Start:	2010 (7/25), 2011 (18/36) (EIS underway)

Likely Completion:	2012, 2014

Sponsor/POC:	AKDOT/Gary Lincoln, 269-0606

Airports POC:	John Lovett, 271-5446

ATO POC:	Suzanne Lee-Pang (425)917-6673

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts: 	TBD

AVN Impacts:	TBD

Reimbursable Agreement Info:

KONGIGANAK	DUY

Project:	Rehabilitate/Extend Runway

Construction Start:	Ongoing

Likely Completion:	2009

Sponsor/POC:	AKDOT/ Bob Lundell, 269-0448

Airports POC:	Krisjon Tabisola, 271-3785

ATO POC:	Ed Vey, 271-3056

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS/AVN Impacts:	None.

Reimbursable Agreement Info:	None

KWIGILLINGOK	A85

Project:	Rehabilitate/Extend Runway

Construction Start:	UNKN

Likely Completion:	UNKN

Sponsor/POC:	AKDOT/Gary Lincoln, 269-0606

Airports POC:	Krisjon Tabisola, 271-3785

ATO  POC:	Suzanne Lee-Pang (425)917-6673

FAA Flight Procedures POC:    Kyle Christiansen, 271-5187

NAS Impacts:

AVN Impacts:

Reimbursable Agreement Info:

MANAKOTAK	17G

Project:	Construct New Airport

Construction Start:	Summer 2007

Likely Completion:	Fall 2008

Sponsor/POC:	AKDOT/Gary Lincoln, 269-0606

Airports POC:	Pat Oien, 271-5445

ATO POC:

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts: 	AWOS relocation

AVN Impacts:	PAPI/REILS, New airport

Reimbursable Agreement Info:

McGRATH	MCG

Project:	Realign runway 7/25 (GA runway)

Construction Start:	 Summer 2008

Likely Completion:	Fall 2008

Sponsor/POC:	AKDOT/Gary Lincoln, 269-0606

Airports POC:	Pat Oien, 271-5445

FAA Tech Ops Engineering POC:	Charlie Bader, 271-5395

NAS Impacts: 	None known

AVN Impacts:	New X-wind alignment

Reimbursable Agreement Info:

# NIGHTMUTE	IGT

Project:	Airport Reconstruction

Construction Start:	2008

Likely Completion:	2010

Sponsor/POC:	AKDOT/Gary Lincoln 269-0606

Airports POC:	John Lovett, 271-5446

ATO POC:	Suzanne Lee-Pang (425)917-6673

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts:	(low priority for PAPI/REILS) - Via IAG (Inter-Agency Agreement)

AVN Impacts:	None.

Reimbursable Agreement Info:

NUNAPITCHUK	16A

Project:	Extend and Rehab Runway

Construction Start:	2008

Likely Completion:	2009

Sponsor/POC:	AKDOT/ Morgan Merritt, 269-0614

Airports POC:	John Lovette, 271-5446

ATO POC:	Charlie Bader, 271-5395

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts:	PAPI/REILS – Via IAG

AVN Impacts:	TBD

Reimbursable Agreement Info:

OUZINKIE	4K5

Project:	Construct Airport

Construction Start:	2009?

Likely Completion	2010?

Sponsor/POC:	AKDOT/Gary Lincoln, 269-0606

Airports POC:	John Lovett, 271-5446

ATO POC:	Suzanne Lee-Pang (425)917-6673

FAA Flight Procedures POC:   Kyle Christiansen, 271-5187

NAS Impacts:	(medium priority for PAPI/REILS)

AVN Impacts:

Reimbursable Agreement Info:

PLATINUM	PTU

Project:	Relocate Airport

Construction Start:	2009

Likely Completion:	2010

Sponsor/POC:	AKDOT/Gary Lincoln, 269-0606

FAA Airports:	John Lovett, 271-5446

ATO POC:	Tom Ondra, 271-2427

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts:	PAPI/REILS – Via IAG

AVN Impacts:	2009 Chart date not valid any more…

Reimbursable Agreement Info:

STONY RIVER	SRV

Project:	Relocate Airport

Construction Start:	2013

Likely Completion 	2015

Sponsor/POC:	AKDOT/Gary Lincoln, 269-0606

FAA Airports:	John Lovett, 271-5446

ATO  POC:	Suzanne Lee-Pang (425)917-6673

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts:	(low priority for PAPI/REILS)

AVN Impacts:	TBD

Reimbursable Agreement Info:

# TAKOTNA	TCT

Project:	Construct Airport

Construction Start:	2009?

Likely Completion:	2010?

Sponsor/POC:	AKDOT/Morgan Merritt, 269-0614

Airports POC:	John Lovett, 271-5446

ATO POC:

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts:	(low priority for PAPI/REILS)

AVN Impacts:

Reimbursable Agreement Info:

# TULUKSAK	TLT

Project:	Construct Airport

Construction Start:	2010

Likely Completion 	2012

Sponsor/POC:	AKDOT/Morgan Merritt, 269-0614

Airports POC:	Pat Oien, 271-5445

ATO POC:

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts:	(low priority for PAPI/REILS)

AVN Impacts:

Reimbursable Agreement Info:

TUNTUTULIAK	A61

Project:	Construct Airport Phase 2-New Airport

Construction Start:	Ongoing

Likely Completion:	2008 (Needs to be confirmed)

Sponsor/POC:	AKDOT/ Bob Lundell, 269-0448

Airports POC:	Krisjon Tabisola, 271-3785

ATO POC:

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts:	No FAA facilities are in Tuntutuliak.  None anticipated for near future.

AVN Impacts:	No known approaches for Tuntutuliak at this time.

Reimbursable Agreement Info:	None

TUNUNAK	4KA

Project:	Reconstruct Runway?

Construction Start:	UNKN

Likely Completion 	UNKN

Sponsor/POC:	AKDOT/?

Airports POC:		John Lovett, 271-5445

ATO POC:

FAA Flight Procedures POC: Kyle Christiansen, 271-5187

NAS Impacts:	(low priority for PAPI/REILS)???

AVN Impacts:

Reimbursable Agreement Info:

STATE OF ALASKA - NORTHERN REGION

ALAKANUK	TM08

Project:	Project constructs new airport: Phase 3 Install electrical and gravel surface for runway (4000’x75), apron, taxiway, access road, PAPI, REIL, and AWOS pad

Construction Start:	Embankment settling; Electrical installation starting Summer 2010.

Likely Completion Date: Fall 2010

Sponsor/POC:	AKDOT/Ryan Anderson, 451-5129

Airports POC:	Matt Freeman, 271-5455

ATO POC:	Kerwin Faciane, 271-5563

FAA Flight Procedures POC:	 Kyle Christiansen, 271-5187

NAS Impacts: 	PAPI/REIL installation ready Fall 2008

AVN Impacts:	TBD

Reimbursable Agreement Info:

ALLAKAKET	6A8

Project:	Resurface runway.

Construction Start:	2009

Likely Completion Date:	2010

Sponsor/POC:	AKDOT/Cindie Little, 451-2284

Airports POC:	Matt Freeman, 271-5455

ATO POC:	Kerwin Faciane, 271-5563

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts: 	PAPI, REIL, AWOS pads will be installed.

AVN Impacts:	TBD

Reimbursable Agreement Info:

AMBLER	AFM

Project:	Extend primary and crosswind runways, clear runway visibility zone, expand runway safety areas, construct new apron, construct new SREB, and relocate airport access road.  Dealing with naturally occurring asbestos in the ground.

Construction Start:	2011

Likely Completion Date: 2013

Sponsor/POC:	AKDOT Cindie Little 451-2284

Airports POC:	Matt Freeman, 271-5455

ATO POC:	Ed Vey, 271-3056

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts: 	Existing VASI’s.

AVN Impacts:	Update all IAP’s.  Need new runway data by end of 2006.

Reimbursable Agreement Info:

ANVIK	ANV

Project:	Reconstruct runway, relocate runway thresholds and elevations

Construction Start:	Under Construction –

Likely Completion Date: August, 2008

Sponsor/POC:	AKDOT Sig Strandberg 443-3423

Airports POC:	Matt Freeman, 271-5455

ATO POC:	Jose Echevarria 271-2366

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts: 	VASI, AWOS, NDB, RCO, & DME.  NDB was moved.

AVN Impacts:	Update all approaches and airways due to new NDB location.

Reimbursable Agreement Info:

BARROW	BRW

Project:  	Project shifts runway 6/24 approximately 250-feet south with changes to runway elevation.  Relocates localizer antenna, VASI/PAPI, REIL, and approach lights.  Paving on new runway starts July 10, 2008 for the first lift, final lift Summer 2009.  New runway available Fall 2009..

.

Construction Start:	Under construction

Likely Completion Date: 2010

Sponsor/POC:	AKDOT/Cindie Little, 451-2284

Airports POC:	Matt Freeman, 271-5455

ATO POC:	Mike Edelman, 271-3823

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts: 	Relocates MALSR. replaces VASIs w/ PAPIs, relocates ASOS windbird.

AVN Impacts:	Update all approaches including ILS.  Need runway end and ILS data 10-months before the new approaches are ready for publication.

Reimbursable Agreement Info:

Notes:

CORDOVA (MUDHOLE) SMITH	CDV

Project:  	Runway Safety Area Drainage.

Construction Start:	2012

Likely Completion Date:

Sponsor/POC:	AKDOT/Cindie Little, 451-2284

Airports POC:	Matt Freeman, 271-5455

ATO POC:	Tom Ondra, 271-2427

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts: 	Remove or plug point drains and drainage structures, regrade runway safety area for sheet flow.

AVN Impacts:	TBD

Reimbursable Agreement Info:

Notes:  The subsurface drainage piping structures are corroding and eroding the runway safety area embankment.  The drainage structures will either be grouted in place or excavated and removed, then the runway safety area graded for sheet flow.  This may change the grade in front of the glide slope antenna.

CORDOVA (MUDHOLE) SMITH	CDV

Project:	Construct new apron, extend taxiway, and general aviation improvements.

Construction Start:	2011

Proposed Completion Date:

Sponsor/POC:	AKDOT/ Cindie Little, 451-2284

Airports POC:	Matt Freeman, 271-5455

ATO POC:	Tom Ondra, 271-2427

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts: 	Relocate fence and parking lot in front of the FSS building.

AVN Impacts:	TBD

Reimbursable Agreement Info:

CORDOVA (MUDHOLE) SMITH	CDV

Project:  	Replace MIRL’s with HIRL’s & RVR.  FAA will provide the equipment and installation for the replacement RVR.

Construction Start:	Summer 2008

Proposed Completion Date:	Fall 2008

Sponsor/POC:	AKDOT/ Cindie Little, 451-2284

Airports POC:	Matt Freeman, 271-5455

ATO POC:	Tom Ondra, 271-2427

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts:

AVN Impacts:	TBD

Reimbursable Agreement Info:

# FAIRBANKS INTERNATIONAL AIRPORT	FAI

Project:  	Reconstruct 1L/19R (Primary Runway).  All operations, including design group 5 aircraft to be moved to Taxiway A.  Taxiway A will be used as a runway Summer 2009.

Design Start:

Construction Start:	Summer 2009

Proposed Completion Date:	Fall 2009

Sponsor/POC:	AKDOT/Cindie Little 451-2284

FAA Airports:	Matt Freeman, 271-5455

FAA Tech Ops Engineering POC:	Steve Cords, 271-2893

FAA Tech Ops Field Office POC:	Dale Greeley, 451-5724

FAA Real Estate POC:	Alice Salzman, 271-5876

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts: 	ILS and approach lights outage.

AVN Impacts:	Develop RNAV approaches to temporary runway.  Need data at least 10months before the approaches are required.  Will also update all approaches and DB’s for FAI when operations return to the large runway.  Need and data that changed no later than 10 months prior to the time the new runway will open.

AT Impacts:	TBD

Real Estate & Utility Impacts:	TBD

Notes:	Tech Ops needs Plans and Specifications and/or layout plan for this project.

# FORT YUKON AIRPORT	FYU

Project:  	Reconstruct runway, runway safety area, apron, and taxiways.

Design Start:

Construction Start:	Fall 2009

Proposed Completion Date:

Sponsor/POC:	AKDOT/Cindie Little 451-2284

FAA Airports:	Matt Freeman, 271-5455

FAA Tech Ops Engineering POC:	Jose Echevarria 271-2366

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts: 	None

AVN Impacts:	None.

AT Impacts:	None

Real Estate & Utility Impacts:	TBD

Notes:

GALENA	GAL

Project:  	Construct SREB.  Most likely an existing building will be converted to a SREB for this project.

Construction Start:	Fall 2010

Proposed Completion Date:	 Summer 2011

Sponsor/POC:	Ryan Anderson 451-5129

FAA Airports:	Matt Freeman, 271-5455

FAA Tech Ops Engineering POC:	Robert Yerkes, 271-5800

FAA Tech Ops Field Office POC:	Dale Greeley, 451-5724

FAA Real Estate POC:	Mary Boden, 271-5933

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts: 	TBD

AVN Impacts:	TBD

AT Impacts:	TBD

Real Estate & Utility Impacts:	TBD

Notes:

GRAYLING	KGX

Project:  	Rehab/Extend/Widen Runway

Design Start:	Complete.

Construction Start:	Fall 2008 at the earliest.

Proposed Completion Date:	Fall 2010

Sponsor/POC:	AKDOT/Ryan Anderson, 451-5129

FAA Airports:	Matt Freeman, 271-5455

FAA Tech Ops Engineering POC:	Jose Echevarria 271-2366

FAA Tech Ops Field Office POC:	Dale Greeley, 451-5724

FAA Real Estate POC:	Carmen Osmond, 271-5877

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts: 	PAPI pads to be constructed.

AVN Impacts:	TBD

AT Impacts:	TBD

Real Estate & Utility Impacts:	TBD

Notes:	Project on-hold until land is acquired.

MANLEY HOT SPRINGS	MLY

Project:  	Construct new airport, PAPI pads, and access road.

Design Start:

Construction Start: 	On hold until land is acquired.

Proposed Completion Date:

Sponsor/POC:	AKDOT/Ryan Anderson 451-5129

FAA Airports:	Matt Freeman, 271-5455

FAA Tech Ops Engineering POC:	Charlie Bader, 271-5395

FAA Tech Ops Field Office POC:	Dale Greeley, 451-5724

FAA Real Estate POC:	Linda Whitney, 271-5847

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts: 	TBD

AVN Impacts:	TBD

AT Impacts:	TBD

Real Estate & Utility Impacts:	TBD

Notes:	Tech Ops needs Plans and Specifications and/or layout plan for this project.

NOME	OME

Project:  	Reconstruct Runway 3/21 Crosswind Runway

Design Start:

Construction Start:	Under construction

Proposed Completion Date: Fall 2008

Sponsor/POC:	AKDOT/Ryan Anderson, 451-5129

FAA Airports:	Matt Freeman, 271-5455

FAA Tech Ops Engineering POC:	Robert Yerkes, 271-5800

FAA Tech Ops Field Office POC:	Dale Greeley, 451-5724

FAA Real Estate POC:	Nora Braman-Knox, 271-5849

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts: 	Possible LOC & VASI  shutdown

AVN Impacts:	TBD

AT Impacts:	TBD

Real Estate & Utility Impacts:	TBD

Notes:

MINTO	51Z

Project:  	Construct new runway, taxiway, PAPI pads, and apron

Design Start:

Construction Start:	Under construction

Proposed Completion Date:	Fall 2009

Sponsor/POC:	AKDOT/Ryan Anderson, 451-5129

FAA Airports:	Matt Freeman, 271-5455

FAA Tech Ops Engineering POC:	Robert Yerkes, 271-5800

FAA Tech Ops Field Office POC:	Dale Greeley, 451-5724

FAA Real Estate POC:	Nora Braman-Knox, 271-5849

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts: 	Possible PAPI equipment installation.

AVN Impacts:	TBD

AT Impacts:	TBD

Real Estate & Utility Impacts:	TBD

Notes:

NORTHWAY	ORT

Project:  	Reconstruct and pave runway, taxiway, and apron.  Relocate apron and access road near FSS.  NON-AIP funded project.

Design Start:

Construction Start:	Under construction

Proposed Completion Date:	Fall 2009,

Sponsor/POC:	AKDOT/Ryan Anderson, 451-5129

FAA Airports:	Matt Freeman, 271-5455

FAA Tech Ops Engineering POC:	Steve Cords, 271-2893

FAA Tech Ops Field Office POC:	Dale Greeley, 451-5724

FAA Real Estate POC:	Nora Braman-Knox, 271-5849

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts: 	Possible elevates VASI or new PAPI pads.

AVN Impacts:	Update all approaches due to new runway data.

AT Impacts:

Real Estate & Utility Impacts:	TBD

Notes:    FEMA funded and managed and no AIP Funds for this project.

POINT LAY	PIZ

Project:  	Widen and Extend RWY & RSA/Construct SREB, Etc.—Reconstruct and extend runway, construct runway safety area to meet standards, install runway lights, PAPI pads, expand apron.  Embankment fill to be placed starting Spring 2006.  Runway surfaced to be placed Summer 2007.

Construction Start:	Ongoing

Proposed Completion Date:	October 2009.  Construction is substantially complete as of 10/3/08.

Sponsor/POC:	North Slope Borough Dave Hodges, 561-6605

FAA Airports:	Krisjon Tabisola, 271-3785

FAA Tech Ops Engineering POC:	Charlie Bader, 271-5395

FAA Tech Ops Field Office POC:	Dale Greeley, 451-5724

FAA Real Estate POC:	Alice Salzman, 271-5876

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts:	Relocation of AWOS Facility, NDB Tower, NDB Shelter, RCO, and Maintenance Shelter complete.

PAPI’s and REIL’s for both ends possibly available, per 2/28/2006; pending final answer from ATO.

AVN Impacts:	Chart Date July 31, 2008

AT Impacts:	New approaches anticipated due to extension.

Real Estate & Utility Impacts:	TBD

# SAVOONGA	SVA

Project:  	Resurface runway, rehabilitate and expand apron.

Design Start:

Construction Start:	Fall 2008 - Fall 2008 at the earliest.

Proposed Completion Date: Fall 2010

Sponsor/POC:	AKDOT/Cindie Little, 451-2284

FAA Airports:	Matt Freeman, 271-5455

FAA Tech Ops Engineering POC:	Robert Yerkes, 271-5800

FAA Tech Ops Field Office POC:	Dale Greeley, 451-5724

FAA Real Estate POC:	Carmen Osmond, 271-5877

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts: 	TBD

AVN Impacts:	TBD

AT Impacts:	TBD

Real Estate & Utility Impacts:	TBD

Notes:    Possible runway safety area grade change will impact VASI.  Project delayed until 2009?

UNALAKLEET	UNK

Project:  	Pave runways, taxiways, and aprons.

Design Start:

Construction Start:	Under construction

Proposed Completion Date:	Fall 2009.

Sponsor/POC:	AKDOT/ Cindie Little, 451-2284

FAA Airports:	Matt Freeman, 271-5455

FAA Tech Ops Engineering POC:	Jose Echevarria 271-2366

FAA Tech Ops Field Office POC:	Dale Greeley, 451-5724

FAA Real Estate POC:	Carmen Osmond, 271-5877

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts: Paving Summer 2009.

AVN Impacts:	TBD

AT Impacts:	TBD

Real Estate & Utility Impacts:	TBD

Notes: Paving scheduled for Summer 2009.

STATE OF ALASKA SOUTHEAST REGION

GUSTAVUS										GST

Project:  	Construct RSA

Construction Start:	2010

Likely Completion:	2011

Sponsor POC:	Pat Carroll (907)465-4415

Airports POC:	John Lovett, 271-5446

ATO  POC: 	Suzanne Lee-Pang (425)917-6673

FAA Flight Procedures POC:  Kyle Christiansen, 271-5187

NAS Impacts:	TBD

AVN Impacts:	No threshold changes planned

Reimbursable Agreement Info:	TBD

HOONAH AIRPORT									HNH

Project:	Extend Runway/Apron Exp

Construction Start:	2009

Likely Completion:	2010

Sponsor/POC:	Pat Carroll 465-4415

Airports POC:	John Lovett, 271-5446

ATO POC: 	Suzanne Lee-Pang (425)917-6673

FAA Flight Procedures POC:  Kyle Christiansen, 271-5187

NAS Impacts:	TBD

AVN Impacts:  	TBD

Reimbursable Agreement Info:	TBD

JUNEAU INTERNATIONAL AIRPORT	JNU

Project:	Construct RSA/Apron/SREB

Construction Start:	Summer 2009

Likely Completion:	2012

Sponsor/POC:	CBJ/Terry Stone, 586-0889

Airports POC:	John Lovett, 271-5446

ATO POC:	Suzanne Lee-Pang (425)917-6673/Steve Cords 271-2893

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts:	Likely impacts to MALSR, VASI, RVR, Wind Sensor

AVN Impacts:	Threshold shifting requires new approach procedures.

Reimbursable Agreement Info: Signed Agreement in place

KETCHIKAN	KTN

Project:	Louis Reef Road (Non-AIP)

Construction Start: Summer 2007

Likely Completion: Winter 2009

Sponsor POC:	?

Airports POC:	Pat Oien, 271-5445

ATO POC:	?

FAA Flight Procedures POC:	Kyle Christiansen, 271-5187

NAS Impacts:	None known-airspace determination coordinated through AF

AVN Impacts:	None known

KETCHIKAN	KTN

Project:  	Rehabilitate Runway/Construct Runway Safety Area

Construction Start:  	Spring 2007

Likely Completion:   Fall 2008

Sponsor POC:  	Mark Figley, 225-8536

Airports POC:	Pat Oien, 271-5445

ATO POC:	Mike Edelmann, 271-3823

FAA Flight Procedures POC: Kyle Christiansen, 271-5187

NAS Impacts:	Localizer, MALSR/F, VASI/PAPI, RCO, NDB, ASOS, GS, DME

AVN Impacts:  	Runway shift requires new approach procedures

AT Impacts:  	coordination of vehicles in critical area during conduction of instrument approach procedures, CWO during ASOS relocation.  Localizer only approach for extended duration.

Reimbursable Agreement Info: Signed Agreement in place

PETERSBURG	PSG

Project:  	Rehabilitate Runway/Construct Runway Safety Area-Ph1

Construction Start:  Fall 2008 (PhaseI)

Likely Completion:	Fall 2009 (Phase I)

Sponsor/POC:  	Jim Heumann 465-4456

FAA Airports:	John Lovett, 271-5446

ATO POC:	Suzanne Lee-Pang (425)917-6673/Steve Cords

FAA Flight Procedures POC:  Kyle Christiansen, 271-5187

NAS Impacts:

AVN Impacts:

Reimbursable Agreement Info: Needed (draft in review)

PETERSBURG	PSG

Project:  	Rehabilitate Runway/Construct Runway Safety Area-Ph2

Construction Start:  Fall 2009 (PhaseII)

Likely Completion:   Fall 2010 (PhaseII)

Sponsor/POC:  	Jim Heumann 465-4456

FAA Airports:	John Lovett, 271-5446

ATO POC:	Suzanne Lee-Pang (425)917-6673/Steve Cords

FAA Flight Procedures POC:  Kyle Christiansen, 271-5187

NAS Impacts:	 ODALS, VASIs,

AVN Impacts:  	Threshold changes requires new flight procedures

Reimbursable Agreement Info: Needed (draft in review)

SITKA	SIT

Project:  	Construct Runway Safety Area

Construction Start:  	Summer 2010

Likely Completion:   Fall 2012

Sponsor POC:

Airports POC:  John Lovett, 271-5446

AT POC:   ?

NAS Impacts:	Threshold change, PAPI’s

AVN Impacts:	Threshold change

FAA Flight Procedures POC:  Kyle Christiansen, 271-5187

WRANGELL	WRG

Project:  	Rehabilitate Runway/Construct Runway Safety Area

Construction Start:  	Spring 2006

Likely Completion:   Fall/Winter 2008

Sponsor POC:  	Loren Gerhing, 465-4458

Airports POC:	Pat Oien, 271-5445

ATO POC:	Kyle Christiansen, 271-5187

NAS Impacts:	None

AVN Impacts:	None (no threshold shifts)

Reimbursable Agreement Info: N/A