| PRIORITY ONE: Maximize effective use of resources to achieve stable housing for all Nevadans. |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strategies | Actions |  | Manager¹ | Implementer² | Expected Outcomes |  | Benchmarks | Completion Date (Estimated) |
| Strategy 1.1 Integrate housing and mainstream services for the homeless, both chronic and episodic/situational. | Action 1.1.1 Inventory mainstream services |  | Shawna Parker Brody and new Regional Homeless Coordinator | Sabra Smith (SNCoC) Kelly Marschall (NNCoC) and Dale Capurro (RCoC) | Inventory complete and available for use |  | Contacts made, information available north, south and rural | By 5/31/04 as part of C of C |
|  | Action 1.1.2 Inventory all housing stock available to the homeless by population. |  | Jean Norton | Lynn Gondorcin, Roy Porter, C of C groups | Number of units available by target population understood |  | State survey revised; Distributed; Tallied; and Published | 1/31/04 2/15/04 4/1/04 7/31/04 |
|  | Action 1.1.3 Identify barriers to access housing and services |  | Tom Bolan | Kristen Cooper (LV) Stephani Kane (Reno) State person | Document produced that analyzes existing reports |  | Completion of: AI., CAPER, Fair Housing Plan | By 8/1/04 |
|  | Action 1.1.4 Identify gaps in services. |  | Anne Cory | PA Team | Document outlining gaps, to use in setting priorities |  | Completion of three steps above | 8/31/04 |
| Strategy 1.2 Increase quantity and quality of Data available. | Action 1.2.1 Develop cost offset analysis with technical assistance. |  | Darryl Martin | Duane Sonnenberg, Lynn Gondorcin, Brenda Dizon | Examples of cost savings |  | TA contract Examples R/N/rural Report | 3/04 |
|  | Action 1.2.2 Successfully implement HMIS statewide. |  | Anne | C of C groups north, south, rural | Statewide HMIS and statewide data |  | System selection and implementation north, south, rural | 12/31/04 |
| Progress to Date |  | Barriers and/or Situational Changes |  |  |  | Immediate Next Steps (including potential technical assistance needs) |  |  |

¹  The Manager is the individual responsible for coordinating each action.    ²   The Implementer is the individual (or entity) responsible for carrying out each action.

| PRIORITY TWO: Bring together key stakeholders in Nevada to address issues around homelessness. |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strategies | Actions |  | Manager | Implementer | Expected Outcomes |  | Benchmarks | Completion Date (Estimated) |
| Strategy 2.1 Create an Nevada Interagency Council on Homelessness | Action 2.1.1 Research experiences/resources from other states. |  | Tom Bolan |  | Executive Order establishing Interagency Council |  | Research on other states Framework and proposal for council completed. Meet with Governor | March 31, 2004 |
|  | Action 2.1.2 Contact national office for resources |  | Darryl Martin |  |  |  |  |  |
|  | Action 2.1.3 Identify appropriate representation And individuals for Council |  | Anne Cory | Policy Academy Team |  |  |  |  |
|  | Action 2.1.4 Create framework and infrastructure for Council |  | Decision by team based on resources |  |  |  |  |  |
|  | Action 2.1.5 Identify mission, goals, etc. for proposal for Governor (include costs) |  | Anne Cory | Policy Academy Team |  |  |  |  |
|  | Action 2.1.6 Meet with Governor |  | Team/Anne Cory/David Parks |  |  |  |  |  |
| Strategy 2.2 Provide public education on homelessness to increase awareness. | Action 2.2.1 Create media release on Policy Academy Team and Housing First |  | Darryl Martin |  | Actions will result in a growing public knowledge, awareness and support of ending chronic homelessness in 10 years. |  | Educate and inform full Policy Academy Team. Draft media release completed and delivered to team. Final media release to media outlets. | 1. November 15, 2003 2. November 9, 2003 3. November 15, 2003 |
|  | Action 2.2.2 Revisit and finalize work on the Policy Academy Public Relations Team |  | Jean Norton/Duane Sonnenberg |  | Public Education plan covering activities for general public and for media |  | Presentation to Policy Academy Team | February 2004 |
|  | Action 2.2.3 Presentation to Continuum of Care groups - North/South & Rural |  | Anne Cory – North/rural Brenda Dizon - South |  | Share Housing First focus |  |  | So Nev December No Nev January Rural January |
| Strategy 2.3 Advocate for a system that is client-centered. | Action 2.3.1 Actively work with agencies to advocate for policies that screen people in, not screen people out. |  | (no manager for this action yet) |  | More clearly understood and consistent eligibility policies leading to better services. |  | Sample policies/procedures available Discussions with groups of providers | 12/04 |
| ## Progress to Date |  | Barriers and/or Situational Changes |  |  |  | Immediate Next Steps (including potential technical assistance needs) |  |  |

¹  The Manager is the individual responsible for coordinating each action.    ²   The Implementer is the individual (or entity) responsible for carrying out each action.

| PRIORITY THREE: Incorporate the Housing First model into our continuum of services in Nevada to end chronic homelessness. |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strategies | Actions |  | Manager¹ | Implementer² | Expected Outcomes |  | Benchmarks | Completion Date (Estimated) |
| Strategy 3.1 Conduct a conference for state and local policy makers and providers. | Action 3.1.1 Decide on logistics – when/where/who/how/ how much (money) and program |  | Darryl and Brenda | Policy Academy Team | Educate policy makers about Housing First model in order to create a team committed to implementing pilot projects. |  | Date and location scheduled for conference. Costs and sponsors identified. Program completed. | Conference to be held in May or June, 2004 |
|  | Action 3.1.2 Identify sponsors – Omidyar, Schwab, Wells Fargo, Park Place Foundation, Nevada State Bank |  | Anne and Duane |  |  |  |  |  |
|  | Action 3.1.3 Identify participant list. |  | Anne Cory |  |  |  |  |  |
|  | Action 3.1.4 Get commitments from speakers |  | Darryl to call Phillip Mangano and Anne to call Governor’s office |  |  |  |  |  |
| Strategy 3.2 Conduct pilot projects of Housing First model. | Action 3.2.1 Conduct site visits to successful Housing First projects |  | Team – Anne Cory | Lynn Gondorcin, Darryl Martin | Site visits will help us develop a better program |  |  | June 30, 2004 |
|  | Action 3.2.2 Identify funding sources/lead agencies/collaborative partners for pilots. |  | Darryl Martin | Policy Academy Team | Support for the project |  | Continuum of Care application to obtain funding for pilot projects Create schematic of provider networks to support. | May/June 2005 |
|  | Action 3.2.3 Implement pilot projects in Las Vegas, rural area and Reno |  | Team |  | We will have pilot programs in North, South and Rural We will have new permanent supportive housing for chronic homeless |  |  | May/June 2005 for Las Vegas, dates TBD for Reno and rural |
| Strategy 3.3 Develop a Housing First Model that is client centered. | Action 3.3.1 Involve consumers in decision-making processes. |  | Anne Cory | Policy Academy Team | Agencies will offer more responsive programs. |  |  | Ongoing |
| Progress to Date |  | Barriers and/or Situational Changes |  |  |  | Immediate Next Steps (including potential technical assistance needs) |  |  |

¹  The Manager is the individual responsible for coordinating each action.         ² The Implementer is the individual (or entity) responsible for carrying out each action.