MODIFICATION OF PROJECTS FUNDED BY THE

HEALTH SERVICES RESEARCH AND DEVELOPMENT SERVICE (HSR&D)

1.  EXPECTATION.  Health Services Research and Development (HSR&D) Service expects all research projects it sponsors to be carried out according to the plan presented in the approved proposal.  Once funding has started, investigators must obtain formal approval from the Director, HSR&D, for any significant change in objectives, methods, budget, time, key personnel, or location.  Requests for changes must be submitted in writing by the medical center Director, through the Associate Chief of Staff (ACOS) for Research and Development (R&D) and the Principal Investigator of the HSR&D COE (if one) to the Director, HSR&D (124), in conformance with the following procedures.  A project that is changed without prior approval is at risk of termination.

## 2.  PROCEDURES FOR REQUESTING A MODIFICATION

a.  To permit careful review, all modification requests must be submitted as soon as the need becomes apparent and, in all cases, at least 3 months prior to the effective date of the proposed change.  Requests for modifications that are administrative in nature, and budget requests up to 20 percent of the approved budget, are generally reviewed by HSR&D staff.  Changes in the research objectives or methods, other changes that may alter the science, and requests for more than a 20 percent budget increase, may require review by one or more external expert(s).

b.  All requested modifications must be submitted in writing, through appropriate channels,.  The justification for every request must address in detail any implications for personnel, budget, timeline, and project feasibility (as applicable), and must include appropriate supporting documents, such as,  new budget pages, Gantt charts, curriculum vitae (CVs), etc.  Adequate information must be provided to permit reviewer(s) to determine why the change is necessary and to allow thorough evaluation of the request.

c.  Requestors must send the project modification request with the Modifications Cover Page (see Appendix B) electronically in a PDF file to: VHA CO HSR&D Project Modifications.

d. The following paragraphs address issues related to specific types of requested modifications.

### (1)  Change in Objectives.  Approval must be obtained to add, delete, or significantly alter the objectives of a funded project.  The written request must provide a detailed explanation of the proposed change, its rationale, and implications.

### (2)  Change in Methods

### (a)  Approval must be obtained to change any key component of the approved research plan.  This includes, but is not limited to:  sampling plan, source(s) of data, addition of another “arm” or comparison group, data collection instrument(s), data collection method(s), or analysis plan.  A fundamental change in study design (e.g., elimination of a control group, use of retrospective instead of prospective data, etc.) is not permitted unless prior approval has been obtained.

(b)  The request for approval of methodological changes must include a clear description of how the proposed change differs from the methodology described in the approved proposal, why a change is needed, and how the proposed change will resolve the problem.  The request must be supported with sufficient information to allow a comprehensive scientific review.  As an example, if a modification affects prior patient accrual expectations, the request needs to include a replication and comparison to the power analysis used in the original funded proposal, after appropriate adjustment for effect size, etc.

# (3)  Change in Budget

(a)  HSR&D approval must be requested in writing for any budget change.  HSR&D does not generally approve a budget increase of more than 20 percent of the originally approved project budget.

(b)  A request for an increase in budget must include a description of the steps taken locally to address the budgetary issues, including use of local HSR&D, R&D, or other resources.

# (4)  Increase in Time.  Investigators are expected to complete project work within the approved-funding period and to notify HSR&D early regarding any significant delay.  Formal approval is required to extend a project-completion date, whether or not additional budget is also requested.  All requests for additional time must be well justified, and the amount of time requested should be less than 6 months.

(a) Project Final Reports are due within 90 days of the official end date of the project period, and requests for additional time to prepare the Final Report should be made only in extremely unusual circumstances.  A delayed final report receipt date must be requested in writing and approved by the Director, HSR&D; however, a “Request for Modification” is not required for this purpose.

### (5)  Change in Key Personnel

(a)  The Principal Investigator (PI) and Co-PI (if one) are responsible for carrying the funded project through its completion.  A change in PI or co-PI may not be made without the approval of the Director, HSR&D.  Supporting information submitted with any request to change a PI must be accompanied by a letter from the current PI indicating the PI’s agreement to relinquish responsibility for the project to the proposed new PI.

(b)  Approval of Department of Veterans Affairs (VA) Central Office also is required to change any other project participants who are responsible, in whole or in part, for the design, execution, or management of the project, and for any change in their time commitment to the project.  Medical centers must provide a CV of the new participant(s) and other supporting documents to permit HSR&D to assess their qualifications, competing commitments, etc.

NOTE:  For a funded project involving a mentor (e.g., Career Development, Nursing Research Initiative), HSR&D expects that the time commitment and geographic proximity of the awardee and mentor remain as presented in the approved project.  If either the awardee or mentor seeks a decrease in time commitment or transfer to another facility, formal approval must be obtained.

# (6)  Change in PI (or Co-PI) Employment Status

# (a)  If the VA employment status of the PI or Co-PI drops below a 5/8 paid appointment, an eligible VA investigator must replace that PI.

# (b)  The ACOS for R&D is responsible for notifying HSR&D of a change affecting PI eligibility within 2 weeks of receipt of this information.  This notification must be accompanied by a request for approval of a new PI and supporting information (see preceding subpar. 2d(5)).

### (7)  Change in Location

(a)  HSR&D projects are awarded to the medical facility where the PI is stationed at the time of the award.  If the PI or co-PI transfers to another VA facility, the project remains at the original facility until approval is secured for transferring the project to the new facility.

- A request for transfer of a project between facilities must include written documentation from the medical center Director of each facility agreeing to the transfer.  However, final approval rests with the Director, HSR&D.

(c).  If the PI moves to another VA, and no longer wants to conduct research, the PI must provide written authorization agreeing to transfer the project to a new investigator.  Approval of the change in PI must be obtained from the Director, HSR&D before the new PI can assume responsibility for the project.

REQUEST FOR MODIFICATION OF HEALTH SERVICES RESEARCH AND DEVELOPMENT SERVICE-FUNDED PROJECT

SAMPLE FORMAT OF COVER PAGE

1.  Identifying Information

a.  Project Number__________________________________________________________

- b.  Project Title_____________________________________________________________

- c.  Name of Principal Investigator_______________________________________________

d.  Principal Investigator’s Department of Veterans Affairs (VA) Facility________________

- e.  Principal Investigator’s Telephone No._________________________________________

2.  Request for a change in:  NOTE:  Check all that apply.

a.  ________  Research Objectives

b.  ________  Research Methods

c.  ________  Budget

d.  ________  Time

e.  _________ Key Personnel

f.  _________ Location

3.  Preferred effective date of requested change ____________________________

__________________________________________________________	_________

(Signature of Principal Investigator)            			     (Date)

__________________________________________________________	_________

(Signature of Center of Excellence or Research Enhancement Award 	     (Date)

Principal Investigator (if applicable))

____________________________________________________________	_________

(Signature of Associate Chief of Staff for Research and Development)	     (Date)