XYZ Fire Planning Unit (FPU)

Fire Program Analysis (FPA) System

FPU Charter

Current Date

TABLE OF CONTENTS

1.	Fire Planning Unit Overview	3

1.1	Identification	3

1.2	Purpose / Business Need / Scope	3

1.3	FPU Objectives	3

1.4	Partnerships	4

1.5	Key References	4

1.6	Terminology	4

2.	Project Approach Section	4

2.1	FPU Deliverables and Quality Objectives	5

2.2	FPU Organization and Responsibilities	5

FPU Board of Directors (Managing Committee)	5

FPU Steering Committee	5

FPU Technical Team	6

Advisors	6

Support Services	6

2.3	Reporting, Oversight, & Review	7

Core Process Workflows	7

2.4	Communications	7

2.5	FPU Schedule	7

2.6	Project Effort/Cost Estimate	7

2.7	Mechanism for Transferring Funds (If Needed)	8

2.8	FPU Benefits	8

Appendices	10

Appendix A – Example - Shared Funding for FPU Planner/Team Administrator	10

Appendix B – Tables of Organizations	10

List of Tables

Table 1 – Management Committee	10

Table 2 – Steering Committee	11

Table 3 – FPU Team	11

Table 4 – FPU Advisors	11

Table 5 – Support Services	12

# 1.	Fire Planning Unit Overview

## 1.1	Identification

This project is to be known as the XYZ Fire Planning Unit (FPU), also referred as the “Back of the Beyond FPU”.  The FPU is an interagency project of the following wildland fire management agencies:

- Well Exposed National Forest

- Little Known National Park

- Where Is It District, BLM

- Shallow Water National Wildlife Refuge

- Local Indian Tribe (If Compacted) or Local Indian Agency (If Managed by BIA)

- Green Tree Area, State Department of Forestry

## Purpose / Business Need / Scope

The purpose of creating FPA Fire Planning Units is to support and contribute to the development of landscape scale interagency fire planning and budgeting to meet the intent of the National Fire Plan, Federal Wildland Fire Policy, 10 Year Implementation Plan, and other related documents, as well as direction provided by Congress and OMB in the FY2003 appropriations language. This is accomplished through:

- Providing subject matter expertise to be incorporated into FPU design and function

- Developing data sets that address all participating agency needs

- Conducting test analyses to ensure reasonable results

- Ensure consistent application of FPA business rules that affect analysis outcomes

- Provide defined roles and responsibilities for all levels of participating personnel from line officers to personnel in supporting disciplines

- Ensure timely completion of analysis to meet required planning and budget submission deadlines

- Ensure consistent implementation is coordinated by all participating agencies

## 1.3	FPU Objectives

The goal of the FPU is to provide an acceptable planning and budget analysis that will be used by the participating agencies to develop and implement associated budgets within the context of the Fire Program Analysis System, and to guide effective implementation of Fire Management Plans.

The overall objective of an FPU is to define the geographic scope of the landscape, or boundaries, for the local fire planning analysis.  Specific objectives are:

- Develop interagency planning partnerships.

- Develop or refine resource management objectives relative to fire, and the full suite of fire management objectives, constraints and restrictions.

- Develop and refine the required data inputs for the models in the FPA system.

- Evaluate both interim and final analysis results for reasonableness.

- Identify efficiencies through landscape integrated planning and budgeting.

- Provide comment on guidance and reference documents to improve quality of the information and operations

## 1.4	Partnerships

The following partnership team will provide executive level oversight.  The members of this team are fire staff or designee from the following agencies:

- USDA Forest Service

- DOI Bureau Of Land Management

- DOI National Park Service

- DOI Fish & Wildlife Service

- DOI Bureau of Indian Affairs

- State and Local government agencies, and Tribal governments

## Key References

References may be found at http://fpa.nifc.gov.  Following are significant documents guiding the FPA process:

- 1995 Federal Wildland Fire Policy

- 2001 Update to the Federal Wildland Fire Policy

- National Fire Plan

- A Collaborative Approach for Reducing Wildland Fire Risks to Communities and the Environment, 10-Year Comprehensive Strategy: Implementation Plan (a.k.a. 10-Year Comprehensive Strategy)

- Developing an Interagency, Landscape-scale Fire Planning Analysis and Budget Tool (a.k.a. “The Hubbard Report”)

## 1.6	Terminology

To improve communications the team will use terms consistent with those defined in the Glossary of Wildland Fire Terminology, published by the National Wildfire Coordinating Group (NWCG) or terms defined in the Appendix of the FPA Reference Guide.

# 2.	Project Approach Section

The Fire Planning Unit (see attached map) will include all the Well Exposed National Forest (National Unit Identifier), Little Known National Park (National Unit Identifier), Where Is It District, (National Unit Identifier), Shallow Water National Wildlife Refuge (National Unit Identifier), Local Indian Agency, BIA (National Unit Identifier), and the Green Tree Area Sate Department of Forestry (National Unit Identifier). These six agencies will be the partner agencies for fire program analysis.

The other agencies that will be viewed as “cooperators” for analysis purposes will be portions of the Left and Right National Forests, and Joyous and Pleasantville Counties’ Fire Departments.  Additional cooperators may become involved as the process matures.

## 2.1	FPU Deliverables and Quality Objectives

Primary deliverables from this undertaking will include:

- Annual analysis meeting tests of reasonableness;

- Provision of proposed budget to appropriate line officer(s) for approval and submission;

- Proposed interagency roles and responsibilities and operational procedures

## 2.2	FPU Organization and Responsibilities

### FPU Board of Directors (Managing Committee)

The FPU Board of Directors consists of line officers or in their absence their designees (deputies) from the respective administrative units.  They are responsible for overall management of the planning and budgeting process including conflict resolution, but not limited to the following: negotiation of differences in location and ownership of fire resources, distribution of FPU funding among the administrative units, decisions on implementation timeframes. If a vote is necessary, each agency regardless of the number of members only has one vote.

This group’s membership is identified in Table 1 in Appendix B.

XYZ FPU Organization Chart

XYZ Fire Planning Unit

Steering Committee

Fire Management Officers

Board of Directors

Agency Administrator (s)

FPU Technical Team

FPU Team Administrator

FPU Team Members

Support

Advisors

### FPU Steering Committee

Steering committee is made up of the Fire Management Officers (fire business specialists) or others with similar duties.  This group is responsible for the following:

- Draft the FPA Charter for the FPU, obtain approval, and review and update the document annually.

- Provide direction regarding fire management business strategy.

- Provide guidance on FPU business requirements

- Review project plans and deliverables especially business requirements.

- Help the FPU Team make decisions regarding scope, time, quality and cost tradeoffs.

- Ensure that the deliverables of the project will meet the business needs of the sponsoring agencies.

- Establish dispute or conflict protocols and provide the primary forum for resolving issues.

- Recommend alignment of fire resources (personnel, equipment, facilities)

- Draft the FPU Transition Plan

The FPU Steering Committee membership is listed in Appendix B, Table 2.

### FPU Technical Team

Members include representatives from participating agencies. This team has responsibility to:

- Establish fire management planning and budgeting business process and procedures for all participating wildland fire management agencies;

- Coordinate with technical support groups, and advisors;

- Obtain, enter and edit data, run the analysis and verify results from the analysis;

- Provide feedback on FPA system user interfaces, data structures and models to support preparedness planning;

- Present analysis information to peers, associates and managers.

NOTE:  The FPU Data Administrator often is the de facto FPU Team Lead.

FPU Technical Team Members are listed in Appendix B, Table 3

### Advisors

Advisors serve the FPU Team providing periodic input on specialty subjects. Members may include:

- Liaisons from other fire business areas, e.g. Fire Operations, Fire Planning, Fuels, Prevention, Education, providing input for consideration of interfaces, shared data/resources and to coordinate planning.

- Resource management specialists (botanist, wildlife biologist, range manager, forester, ecologist) advisors and participants in the identification of attributes in the FPA weighting process

- Liaison from States, Tribes and Federal Agencies.

Advisors are listed in Appendix B, Table 4.

### Support Services

Support service can include many disciplines depending on the needs of the individual FPU.  Examples include: GIS program support, Fire Ecology expertise, fire planning from a higher level, and other resource professionals.  A list of functions/personnel contributed by each participant is included in Appendix B, Table 5.

## 2.3	Reporting, Oversight, & Review

Reporting, oversight and review will ensure that the FPU stays within scope and on time.  Oversight is provided line officers/steering committee.

### Core Process Workflows

The FPU Team will be responsible for assembling data as needed for the FPA process. One individual (an FPU Team Administrator) will be assigned the role of gathering of data from all the agencies and input it into the FPA Modules.  That individual is responsible for tasking agency planners with data needs and due dates for timely implementation of the analysis.  The administrator will document processes used in developing the inputs for the Fire planning Analysis.

The team administrator has the responsibility of informing the Steering Committee of irresolvable issues such as discrepancies of data among agencies.

The Steering Committee has the responsibility of providing oversight and support to the team administrator in developing assumptions that best represents “real world” fire operations for their individual agencies and as a collective unit.

## 2.4	Communications

FPU Team

The following mailing list of XYZ FPU participants has been sent out to participants in the FPU.  Communication is encouraged within the FPU team to identify issues in a timely manner and to provide information when needed.

#### Name					Agency				Phone Number				Email Address

Joe Dinglefritz			USFS				123-555-1234				jdingle@fs.fed.us

Etc.

## 2.5	FPU Schedule

Timelines for FPU activities will be developed annually based on requests from the agencies’ national offices, that timeline will then be assembled and appended to this charter.

## 2.6	Project Effort/Cost Estimate

This section may be needed if shared positions are anticipated.  For example, one full time FPA team administrator (fire planner) position is required for the XYZ Fire Planning Unit to function as the coordinator/lead planner and primary contact.  The participating agencies will fund the planner’s salary according to the annual table in the Appendix to guarantee it is a dedicated position.  Travel and miscellaneous costs related to FPU activities will be incurred by the participating agencies for their employees.

## 2.7	Mechanism for Transferring Funds (If Needed)

This section, if needed, could include the mechanics for transfer of funds among agencies.  (To reduce the workload associated with changes in dollar amounts percentages should be established then the annual adjustments for step increases and base funding increases, etc. will be covered automatically.  This part of the document if needed could be very sensitive as far as interagency operations are concerned.)

## 2.8	FPU Benefits

The participating agencies in the FPU will benefit by interagency participation in fire management planning.  This agreement will support processes and standards for interagency collaborative wildland fire planning as required in recent and future policy documents.

3.	Approval Section

This charter is effective as of the last date of signature.  By signing, the signatories indicate their agreement and support of the project charter and their commitment to the project.

____________________________________	_______________

Forest Supervisor                                                              Data

USDA Forest Service

____________________________________	_______________

Field Office Manager                                                         Date

USDI Bureau of Land Management

____________________________________	_______________

Park Superintendent                                                            Date

USDI National Park Service

____________________________________	_______________

Indian Agency Superintendent or Tribal Chairman            Date

USDI Bureau of Indian Affairs

____________________________________	_______________

Refuge Manager                                                                  Date

USDI  U.S. Fish and Wildlife Service

____________________________________         ________________

Area Manager                                                                       Date

State Department of Forestry

Appendices

## Appendix A – Example - Shared Funding for FPU Planner/Team Administrator

| Shared Funding for FPU Team Administrator (FY 05) |  |
| --- | --- |
| USFS | 34,200 |
| BLM | 34,200 |
| NPS | 10,250 |
| BIA | 10,250 |
| FWS | 10,250 |
| Tribe | 3,420 |
| State | 3,420 |
| Total | $105,990 |

Note:  This table will be updated annually.  The FTE will be hosted by BLM with other agencies supporting the cost as listed in the table above.  Funding is developed as a percentage of the acreage of agency in the FPU.

## Appendix B – Tables of Organizations

The following tables will reviewed and updated as necessary.

Table 1 – Management Committee

| Agency | Title | Individual | Contact Information |
| --- | --- | --- | --- |
| Well Exposed National Forest | Forest Supervisor |  |  |
| Little Known National Park | Park Superintendent |  |  |
| Where Is It District, BLM | District Manager |  |  |
| Shallow Water National Wildlife Refuge | Refuge Manager |  |  |
| Local Indian Agency | BIA Agency Superintendent or Tribal Chairman |  |  |
| Green Tree Area | State Area Manager |  |  |

Table 2 – Steering Committee

| Agency | Title | Individual | Contact Information |
| --- | --- | --- | --- |
| Well Exposed National Forest | Fire Management Officer |  |  |
| Little Known National Park | Interpretive Specialist |  |  |
| Where Is It District, BLM | Fire Management Officer |  |  |
| Local Indian Tribe | Resource Specialist |  |  |
| Shallow Water National Wildlife Refuge | Biologist |  |  |
| Local Indian Agency | Fire Management Officer |  |  |
| Green Tree Area Department of Forestry | Fire Management Officer |  |  |

Table 3 – FPU Technical Team

| Agency | Individual | Contact Information |
| --- | --- | --- |
| Well Exposed National Forest |  |  |
| Little Known National Park |  |  |
| Where Is It District, BLM |  |  |
| Local Indian Agency |  |  |
| Shallow Water National Wildlife Refuge |  |  |
| Green Tree Area Department of Forestry |  |  |

* indicates FPU Data Administrator. The Data Administrator may also be the Team Lead.

# indicates backup FPU Data Administrator

Table 4 – FPU Advisors

| Agency | Specialty | Individual | Contact Information |
| --- | --- | --- | --- |
| College of Hard Knocks | Public Meeting assistance and facilitation |  |  |
| State of Confusion | Expertise in air quality and state regulations |  |  |
| Pleasantville County | WUI/ Rural FD support |  |  |

Table 5 – Support Services

| Agency | Support Type | Individual | Contact Information |
| --- | --- | --- | --- |
| Well Exposed National Forest | Office Space |  |  |
| Little Known National Park | GIS Expertise |  |  |
| Where Is It District, BLM | Fire Ecology |  |  |
| Local Indian Tribe | Archeology/Cultural Information |  |  |
| Shallow Water National Wildlife Refuge | Wildlife Information |  |  |
| Green Tree Area Department of Forestry | Communications |  |  |