1.  The total firm fixed price awarded on this contract is $___TBD____.

2.  DELIVERABLE REQUIREMENTS (GSFC 52.211-90) (OCT 1988)

A. The Contractor shall perform and/or deliver the following:

| Time After Award of Contract | Conditions to be Met |
| --- | --- |
| Base Contract Year |  |
| 3 Months | Progress report |
| 6 Months | Progress report, outline of historical project, research plans, and preliminary bibliography |
| 9 Months | Progress report, draft chapters of first third of manuscript, copies of oral history transcripts |
| 12 Months | Progress report, interview transcripts, revised chapters of first third of manuscript |
| Contract Year 1 |  |
| 15 Months | Progress report, interview transcripts, archival status, draft chapters of middle third of manuscript |
| 18 Months | Progress report, interview transcripts, revised chapters of middle third of manuscript |
| 21 Months | Progress report, all remaining oral history transcripts, back matter drafts, graphics plan |
| 24 Months | Progress report, archival status, draft of remaining manuscript, all oral history transcripts |
| Contract Year 2 |  |
| 27 Months | Progress report, revised chapters of first half of manuscript |
| 30 Months | Progress report, revised chapters of remainder of manuscript |
| 33 Months | Progress report, final manuscript acceptable for final critique |
| 36 Months | Final report, completed manuscript acceptable for publication, all oral history transcripts, all documents used in preparing work |

3. Equal milestone payments shall be made on a quarterly basis for the  deliverables for chart above in the amount of: $TBD.

(End of clause)

4.  OPTION TO EXTEND--SERVICE CONTRACT (GSFC 52.217-93) (DEC 1992)

This contract may be extended at the option of the Government in accordance with FAR clause 52.217-9, "Option to Extend the Term of the Contract".  The option periods and prices or costs and any fees are as follows:

# Option                        Period                  			Amount

Option 1	      12 months after basic 		                $ TBD

contract period

Option 2               12 months after option 1		                $ TBD

4.  SCOPE OF WORK (GSFC 52.211-91) (FEB 1991)

The Contractor shall provide the personnel, materials, and facilities necessary to and to furnish the items specified in Attachment A, Statement of Work NASA’s History of International Relations.

(End of clause)

5.  Reports of Work:

Submission:  The Contractor shall submit reports/deliverables as required in the Statement of Work and by this section as follows:

- This historical work shall begin with an introduction that explains the purpose and scope of the book as well as its contents, describes the method of research and the parameters of study, and introduces the major themes considered in the project.

- The work shall be organized chronologically, with significant allowance for topical treatment as necessary to explain fully the subject.

- All writing shall be in accordance with acceptable scholarly, literary, and methodological standards as established by the NASA History Division and reflected in earlier NASA history publications and the guide, Research in NASA History.  Reference to other written materials must be fully documented and reference notes in this narrative must appear in proper academic style as established in the above and in the most recent Chicago Manual of Style.  In general, the style shall conform to the NASA Historical Style Guide (available at http://history.nasa.gov/styleguide.html on the World Wide Web).

- There shall be no citations to documents in “private collections” or the like; documents obtained from private individuals shall be photocopied and the photocopies included in the Historical Reference Collection at Headquarters or a relevant Field Center.  If the original owner of a document does not want it  to be dispositioned in this manner, the historian should cite another relevant document or contact the NASA History Division for further guidance.

- A list of new or special terms and acronyms shall be included in a glossary and explained when first appearing in the text. Statistical material shall be organized in a readily understandable format. The contractor shall prepare an index after the manuscript reaches the page proof stage.

.

(M-Monthly, F-Final)

Copies	Report Type	Addressee		         Mail Code

1		M,F		Contracting Officer                210.H

2		M,F	    Contracting Officer’s

Technical Representative                  I

(End of Text)

6.  ACCEPTANCE--SINGLE LOCATION (GSFC 52.246-92) (SEPT 1989)

The Contracting Officer or authorized representative will accomplish acceptance at NASA Headquarters.  For the purpose of this clause, the Contracting Officer's Technical Representative named in this contract is the authorized representative.  The Contracting Officer reserves the right to unilaterally designate a different Government agent as the authorized representative.  The Contractor will be notified by a written notice or by a copy of the delegation of authority if different representative is designated.

If this is a fixed price type contract, acceptance shall be deemed to have occurred constructively--for the sole purpose of computing an interest penalty that might be due the Contractor under the Prompt Payment Act--on the 31st day after the Contractor has delivered the supplies or services in accordance with the terms and conditions of the contract.  In the event that actual acceptance occurs within the constructive acceptance period, the determination of an interest penalty shall be based on the date of the actual acceptance.

(End of clause)

7.  PLACE OF PERFORMANCE--SERVICES (GSFC 52.237-92) (OCT 1988)

The services specified by this contact shall be performed at the at the Contractor’s facility.

(End of clause)

8.  INVOICES - SUBMISSION OF (GSFC 52.232-95) (AUG 2000)

Invoices shall be prepared in accordance with the Prompt Payment clause of this contract and submitted to the Cost and Commercial Accounts Department, Code 155, NASA/Goddard Space Flight Center, Greenbelt, MD 20771.  For purposes of the Prompt Payment Act, the above office is considered to be the "Designated Billing Office" and the "Designated Payment Office".

If the terms are F.O.B. plant with "plus transportation charges allowed", the invoice must be supported by a receipted freight bill, express receipt, or parcel post receipt, evidencing the correctness of the amount paid and claimed.  If the amount is less than $100 per shipment and receipts are not available, the invoice will be accepted and payment made, provided it contains a certificate by the supplier, that transportation charges were in fact paid by the supplier, that receipts were not available, and lists the destination, weight, name of carrier, and the amount claimed.  The availability of this certification is not a waiver of the requirements for receipted transportation bills, and is to be used only when receipts are not available.  Bill of lading number and weight of shipment shall be shown for shipments made on Government bill of lading.

(End of clause)

9.  CONTRACTOR USE OF GSFC LIBRARY (GSFC 52.245-90) (AUG 1993)

The Contractor's professional employees performing work under this contract are granted borrowing privileges at the Goddard Space Flight Center (GSFC) Library.

(a) The Contractor shall establish procedures to account for borrowed materials and to ensure their timely return.  "Timely return" means prior to the expiration of the borrowing period, prior to the termination of employment of the particular employee, or prior to the expiration of this contract, whichever comes first.

(b) The Contractor shall initiate borrowing privileges for its employees by contacting the GSFC Librarian.  The Librarian will require the Contractor to provide the name and title of the company official responsible for ensuring compliance with (a) above.  The responsible official will be required to indicate the level of control for the issuance of Library charge plates and whether the countersignature of the responsible company official will be required on Goddard Library Card Applications.  The GSFC Librarian may impose additional information requirements if Library privileges are requested for employees that do not have permanent GSFC badges.

(c) The Contractor shall be responsible for all items lost, destroyed or not returned.  Such items shall be immediately replaced by the Contractor at no cost to the Government.  The GSFC Librarian may revoke library privileges at any time during the performance of the contract if the Contractor fails to comply with this clause or is experiencing an inordinate amount of loss or destruction of library materials.  Discontinuance of library privileges shall not entitle the Contractor to an increase in the cost or price for contract performance or to any other adjustment to the contract.

(End of clause)

10. ACCESS TO SENSITIVE INFORMATION  (1852.237-72)   (JUNE 2005)

(a) As used in this clause, ``sensitive information'' refers to information that a Contractor has developed at private expense, or that the Government has generated that qualifies for an exception to the Freedom of Information Act, which is not currently in the public domain, and which may embody trade secrets or commercial or financial information, and which may be sensitive or privileged.

(b) To assist NASA in accomplishing management activities and administrative functions, the Contractor shall provide the services specified elsewhere in this contract.

(c) If performing this contract entails access to sensitive information, as defined above, the Contractor agrees to--

(1) Utilize any sensitive information coming into its possession only for the purposes of performing the services specified in this contract, and not to improve its own competitive position in another procurement.

(2) Safeguard sensitive information coming into its possession from unauthorized use and disclosure.

(3) Allow access to sensitive information only to those employees that need it to perform services under this contract.

(4) Preclude access and disclosure of sensitive information to persons and entities outside of the Contractor's organization.

(5) Train employees who may require access to sensitive information about their obligations to utilize it only to perform the services specified in this contract and to safeguard it from unauthorized use and disclosure.

(6) Obtain a written affirmation from each employee that he/she has received and will comply with training on the authorized uses and mandatory protections of sensitive information needed in performing this contract.

(7) Administer a monitoring process to ensure that employees comply with all reasonable security procedures, report any breaches to the Contracting Officer, and implement any necessary corrective actions.

(d) The Contractor will comply with all procedures and obligations specified in its Organizational Conflicts of Interest Avoidance Plan, which this contract incorporates as a compliance document.

(e) The nature of the work on this contract may subject the Contractor and its employees to a variety of laws and regulations relating to ethics, conflicts of interest, corruption, and other criminal or civil matters relating to the award and administration

of government contracts. Recognizing that this contract establishes a high standard of accountability and trust, the Government will carefully review the Contractor's performance in relation to the mandates and restrictions found in these laws and regulations. Unauthorized uses or disclosures of sensitive information may result

in termination of this contract for default, or in debarment of the Contractor for serious misconduct affecting present responsibility as a government Contractor.

(f) The Contractor shall include the substance of this clause, including this paragraph (f), suitably modified to reflect the relationship of the parties, in all subcontracts that may involve access to sensitive information

(End of clause)

11.  RELEASE OF SENSITIVE INFORMATION (1852.237-73)(JUNE 2005)

(a) As used in this clause, “sensitive information” refers to information, not currently in the public domain, that the Contractor has developed at private expense, that may embody trade secrets or commercial or financial information, and that may be sensitive or privileged.

(b) In accomplishing management activities and administrative functions, NASA relies heavily on the support of various service providers.   To support NASA activities and functions, these service providers, as well as their subcontractors and their individual employees, may need access to sensitive information submitted by the Contractor under this contract.   By submitting this proposal or performing this contract, the Contractor agrees that NASA may release to its service providers, their subcontractors, and their individual employees, sensitive information submitted during the course of this procurement, subject to the enumerated protections mandated by the clause at 1852.237-72, Access to Sensitive Information.

(c)(1) The Contractor shall identify any sensitive information submitted in support of this proposal or in performing this contract.   For purposes of identifying sensitive information, the Contractor may, in addition to any other notice or legend otherwise required, use a notice similar to the following:

Mark the title page with the following legend:

This proposal or document includes sensitive information that NASA shall not disclose outside the Agency and its service providers that support management activities and administrative functions.   To gain access to this sensitive information, a service provider’s contract must contain the clause at NFS 1852.237-72, Access to Sensitive Information.   Consistent with this clause, the service provider shall not duplicate, use, or disclose the information in whole or in part for any purpose other than to perform the services specified in its contract.   This restriction does not limit the Government's right to use this information if it is obtained from another source without restriction.   The information subject to this restriction is contained in pages [insert page numbers or other identification of pages].

Mark each page of sensitive information the Contractor wishes to restrict with the following legend:

Use or disclosure of sensitive information contained on this page is subject to the restriction on the title page of this proposal or document.

(2) The Contracting Officer shall evaluate the facts supporting any claim that particular information is “sensitive.”   This evaluation shall consider the time and resources necessary to protect the information in accordance with the detailed safeguards mandated by the clause at 1852.237-72, Access to Sensitive Information.   However, unless the Contracting Officer decides, with the advice of Center counsel, that reasonable grounds exist to challenge the Contractor’s claim that particular information is sensitive, NASA and its service providers and their employees shall comply with all of the safeguards contained in paragraph (d) of this clause.

(d) To receive access to sensitive information needed to assist NASA in accomplishing management activities and administrative functions, the service provider must be operating under a contract that contains the clause at 1852.237-72, Access to Sensitive Information.   This clause obligates the service provider to do the following:

(1) Comply with all specified procedures and obligations, including the

Organizational Conflicts of Interest Avoidance Plan, which the contract has incorporated as a compliance document.

(2) Utilize any sensitive information coming into its possession only for the purpose of performing the services specified in its contract.

(3) Safeguard sensitive information coming into its possession from unauthorized use and disclosure.

(4) Allow access to sensitive information only to those employees that need it to perform services under its contract.

(5) Preclude access and disclosure of sensitive information to persons and entities outside of the service provider’s organization.

(6) Train employees who may require access to sensitive information about their obligations to utilize it only to perform the services specified in its contract and to safeguard it from unauthorized use and disclosure.

(7) Obtain a written affirmation from each employee that he/she has received and will comply with training on the authorized uses and mandatory protections of sensitive information needed in performing this contract.

(8) Administer a monitoring process to ensure that employees comply with all reasonable security procedures, report any breaches to the Contracting Officer, and implement any necessary corrective actions.

(e) When the service provider will have primary responsibility for operating an information technology system for NASA that contains sensitive information, the service provider’s contract shall include the clause at 1852.204-76, Security Requirements for Unclassified Information Technology Resources.   The Security Requirements clause requires the service provider to implement an Information Technology Security Plan to protect information processed, stored, or transmitted from unauthorized access, alteration, disclosure, or use.   Service provider personnel requiring privileged access or limited privileged access to these information technology systems are subject to screening using the standard National Agency Check (NAC) forms appropriate to the level of risk for adverse impact to NASA missions.   The Contracting Officer may allow the service provider to conduct its own screening, provided the service provider employs substantially equivalent screening procedures.

(f) This clause does not affect NASA's responsibilities under the Freedom of Information Act.

(g) The Contractor shall insert this clause, including this paragraph (g) , suitably modified to reflect the relationship of the parties, in all subcontracts that may require the furnishing of sensitive information.

(End of clause)

12.  CLAUSES INCORPORATED BY REFERENCE (52.252-2) (FEB 1998)

This contract incorporates one or more clauses by reference, with the same force and effect as if they were given in full text.  Upon request, the Contracting Officer will make their full text available.  Also, the full text of a clause may be accessed electronically at this/these address(es):

Federal Acquisition Regulation (FAR) clauses:

http://www.arnet.gov/far/

NASA FAR Supplement (NFS) clauses:

http://www.hq.nasa.gov/office/procurement/regs/nfstoc.htm

(End of clause)

13.  REPRESENTATIONS, CERTIFICATIONS AND OTHER STATEMENTS OF OFFEROR (GSFC 52.215-90) (NOV 1999)

In accordance with FAR 15.204-1(b), the completed and submitted   “Representations, Certifications, and Other Statements of Offeror”, are incorporated by reference in this resulting contract.

(End of clause)

14.  List of Clauses incorporated by reference:

TERMS AND CONDITIONS:

Contract Terms and Conditions Required to Implement Statutes or Executive Orders—Commercial Items (June 2006)

(a) The Contractor shall comply with the following Federal Acquisition Regulation (FAR) clauses, which are incorporated in this contract by reference, to implement provisions of law or Executive orders applicable to acquisitions of commercial items:

(1) 52.233-3, Protest After Award (Aug 1996) (31 U.S.C. 3553).

(2) 52.233-4, Applicable Law for Breach of Contract Claim (Oct 2004) (Pub. L. 108-77, 108-78)

(b) The Contractor shall comply with the FAR clauses in this paragraph (b) that the Contracting Officer has indicated as being incorporated in this contract by reference to implement provisions of law or Executive orders applicable to acquisitions of commercial items:

_X_ (1) 52.203-6, Restrictions on Subcontractor Sales to the Government (Jul 1995), with Alternate I (Oct 1995) (41 U.S.C. 253g and 10 U.S.C. 2402).

__ (2) 52.219-3, Notice of Total HUBZone Set-Aside (Jan 1999) (15 U.S.C. 657a).

__ (3) 52.219-4, Notice of Price Evaluation Preference for HUBZone Small Business Concerns (July 2005) (if the offeror elects to waive the preference, it shall so indicate in its offer) (15 U.S.C. 657a).

__ (4) [Reserved]

__ (5)(i)  52.219-6, Notice of Total Small Business Set-Aside (June 2003) (15 U.S.C. 644).

__ (ii) Alternate I (Oct 1995) of 52.219-6.

__ (iii) Alternate II (Mar 2004) of 52.219-6.

__ (6)(i)  52.219-7, Notice of Partial Small Business Set-Aside (June 2003) (15 U.S.C. 644).

__ (ii) Alternate I (Oct 1995) of 52.219-7.

__ (iii) Alternate II (Mar 2004) of 52.219-7.

__ (7) 52.219-8, Utilization of Small Business Concerns (May 2004) (15 U.S.C. 637(d)(2) and (3)).

__ (8)(i)  52.219-9, Small Business Subcontracting Plan (July 2005) (15 U.S.C. 637(d)(4).

__ (ii) Alternate I (Oct 2001) of 52.219-9.

__ (iii) Alternate II (Oct 2001) of 52.219-9.

__ (9) 52.219-14, Limitations on Subcontracting (Dec 1996) (15 U.S.C. 637(a)(14)).

__ (10)(i)  52.219-23, Notice of Price Evaluation Adjustment for Small Disadvantaged Business Concerns (Sept 2005) (10 U.S.C. 2323) (if the offeror elects to waive the adjustment, it shall so indicate in its offer).

__ (ii) Alternate I (June 2003) of 52.219-23.

__ (11) 52.219-25, Small Disadvantaged Business Participation Program—Disadvantaged Status and Reporting (Oct 1999) (Pub. L. 103-355, section 7102, and 10 U.S.C. 2323).

__ (12) 52.219-26, Small Disadvantaged Business Participation Program—Incentive Subcontracting (Oct 2000) (Pub. L. 103-355, section 7102, and 10 U.S.C. 2323).

__ (13) 52.219-27, Notice of Total Service-Disabled Veteran-Owned Small Business Set-Aside (May 2004).

_X_ (14) 52.222-3, Convict Labor (June 2003) (E.O. 11755).

_X_ (15) 52.222-19, Child Labor—Cooperation with Authorities and Remedies (Jan 2006) (E.O. 13126).

_X_ (16) 52.222-21, Prohibition of Segregated Facilities (Feb 1999).

_X_ (17) 52.222-26, Equal Opportunity (Apr 2002) (E.O. 11246).

_X_ (18) 52.222-35, Equal Opportunity for Special Disabled Veterans, Veterans of the Vietnam Era, and Other Eligible Veterans (Dec 2001) (38 U.S.C. 4212).

_X_ (19) 52.222-36, Affirmative Action for Workers with Disabilities (Jun 1998) (29 U.S.C. 793).

_X_ (20) 52.222-37, Employment Reports on Special Disabled Veterans, Veterans of the Vietnam Era, and Other Eligible Veterans (Dec 2001) (38 U.S.C. 4212).

_X_ (21) 52.222-39, Notification of Employee Rights Concerning Payment of Union Dues or Fees (Dec 2004) (E.O. 13201).

__ (22)(i)  52.223-9, Estimate of Percentage of Recovered Material Content for EPA-Designated Products (Aug 2000) (42 U.S.C. 6962(c)(3)(A)(ii)).

__ (ii) Alternate I (Aug 2000) of 52.223-9 (42 U.S.C. 6962(i)(2)(C)).

__ (23) 52.225-1, Buy American Act—Supplies (June 2003) (41 U.S.C. 10a-10d).

__ (24)(i) 52.225-3, Buy American Act—Free Trade Agreements—Israeli Trade Act (June 2006) (41 U.S.C. 10a-10d, 19 U.S.C. 3301 note, 19 U.S.C. 2112 note, Pub. L. 108-77, 108-78, 108-286), and 109-53.

__ (ii) Alternate I (Jan 2004) of 52.225-3.

__ (iii) Alternate II (Jan 2004) of 52.225-3.

__ (25) 52.225-5, Trade Agreements (June 2006) (19 U.S.C. 2501, et seq., 19 U.S.C. 3301 note).

__ (26) 52.225-13, Restrictions on Certain Foreign Purchases (Feb 2006) (E.o.s, proclamations, and statutes administered by the Office of Foreign Assets Control of the Department of the Treasury).

__ (27) [Reserved]

__ (28) [Reserved]

__ (29) 52.232-29, Terms for Financing of Purchases of Commercial Items (Feb 2002) (41 U.S.C. 255(f), 10 U.S.C. 2307(f)).

_X_ (30) 52.232-30, Installment Payments for Commercial Items (Oct 1995) (41 U.S.C. 255(f), 10 U.S.C. 2307(f)).

_X_ (31) 52.232-33, Payment by Electronic Funds Transfer—Central Contractor Registration (Oct 2003) (31 U.S.C. 3332).

_X_ (32) 52.232-34, Payment by Electronic Funds Transfer—Other than Central Contractor Registration (May 1999) (31 U.S.C. 3332).

_X_ (33) 52.232-36, Payment by Third Party (May 1999) (31 U.S.C. 3332).

__ (34) 52.239-1, Privacy or Security Safeguards (Aug 1996) (5 U.S.C. 552a).

__ (35)(i)  52.247-64, Preference for Privately Owned U.S.-Flag Commercial Vessels (Feb 2006) (46 U.S.C. Appx. 1241(b) and 10 U.S.C. 2631).

__ (ii) Alternate I (Apr 2003) of 52.247-64.

(c) The Contractor shall comply with the FAR clauses in this paragraph (c), applicable to commercial services, that the Contracting Officer has indicated as being incorporated in this contract by reference to implement provisions of law or Executive orders applicable to acquisitions of commercial items:

__ (1) 52.222-41, Service Contract Act of 1965, as Amended (July 2005) (41 U.S.C. 351, et seq.).

__ (2) 52.222-42, Statement of Equivalent Rates for Federal Hires (May 1989) (29 U.S.C. 206 and 41 U.S.C. 351, et seq.).

__ (3) 52.222-43, Fair Labor Standards Act and Service Contract Act—Price Adjustment (Multiple Year and Option Contracts) (May 1989) (29 U.S.C. 206 and 41 U.S.C. 351, et seq.).

__ (4) 52.222-44, Fair Labor Standards Act and Service Contract Act—Price Adjustment (Feb 2002) (29 U.S.C. 206 and 41 U.S.C. 351, et seq.).

(d) Comptroller General Examination of Record. The Contractor shall comply with the provisions of this paragraph (d) if this contract was awarded using other than sealed bid, is in excess of the simplified acquisition threshold, and does not contain the clause at 52.215-2, Audit and Records—Negotiation.

(1) The Comptroller General of the United States, or an authorized representative of the Comptroller General, shall have access to and right to examine any of the Contractor’s directly pertinent records involving transactions related to this contract.

(2) The Contractor shall make available at its offices at all reasonable times the records, materials, and other evidence for examination, audit, or reproduction, until 3 years after final payment under this contract or for any shorter period specified in FAR Subpart 4.7, Contractor Records Retention, of the other clauses of this contract. If this contract is completely or partially terminated, the records relating to the work terminated shall be made available for 3 years after any resulting final termination settlement. Records relating to appeals under the disputes clause or to litigation or the settlement of claims arising under or relating to this contract shall be made available until such appeals, litigation, or claims are finally resolved.

(3) As used in this clause, records include books, documents, accounting procedures and practices, and other data, regardless of type and regardless of form. This does not require the Contractor to create or maintain any record that the Contractor does not maintain in the ordinary course of business or pursuant to a provision of law.

(e)(1) Notwithstanding the requirements of the clauses in paragraphs (a), (b), (c), and (d) of this clause, the Contractor is not required to flow down any FAR clause, other than those in paragraphs (i) through (vii) of this paragraph in a subcontract for commercial items. Unless otherwise indicated below, the extent of the flow down shall be as required by the clause—

(i) 52.219-8, Utilization of Small Business Concerns (May 2004) (15 U.S.C. 637(d)(2) and (3)), in all subcontracts that offer further subcontracting opportunities. If the subcontract (except subcontracts to small business concerns) exceeds $500,000 ($1,000,000 for construction of any public facility), the subcontractor must include 52.219-8 in lower tier subcontracts that offer subcontracting opportunities.

(ii) 52.222-26, Equal Opportunity (Apr 2002) (E.O. 11246).

(iii) 52.222-35, Equal Opportunity for Special Disabled Veterans, Veterans of the Vietnam Era, and Other Eligible Veterans (Dec 2001) (38 U.S.C. 4212).

(iv) 52.222-36, Affirmative Action for Workers with Disabilities (June 1998) (29 U.S.C. 793).

(v) 52.222-39, Notification of Employee Rights Concerning Payment of Union Dues or Fees (Dec 2004) (E.O. 13201).

(vi) 52.222-41, Service Contract Act of 1965, as Amended (July 2005), flow down required for all subcontracts subject to the Service Contract Act of 1965 (41 U.S.C. 351, et seq.).

(vii) 52.247-64, Preference for Privately Owned U.S.-Flag Commercial Vessels (Feb 2006) (46 U.S.C. Appx. 1241(b) and 10 U.S.C. 2631). Flow down required in accordance with paragraph (d) of FAR clause 52.247-64.

(2) While not required, the contractor may include in its subcontracts for commercial items a minimal number of additional clauses necessary to satisfy its contractual obligations.

(End of clause)

### 15.  52.219-22  Small Disadvantaged Business Status

Small Disadvantaged Business Status (Oct 1999)

(a) General. This provision is used to assess an offeror’s small disadvantaged business status for the purpose of obtaining a benefit on this solicitation. Status as a small business and status as a small disadvantaged business for general statistical purposes is covered by the provision at FAR 52.219-1, Small Business Program Representation.

(b) Representations.

(1) General. The offeror represents, as part of its offer, that it is a small business under the size standard applicable to this acquisition; and either—

[  ] (i) It has received certification by the Small Business Administration as a small disadvantaged business concern consistent with 13 CFR 124, Subpart B; and

(A) No material change in disadvantaged ownership and control has occurred since its certification;

(B) Where the concern is owned by one or more disadvantaged individuals, the net worth of each individual upon whom the certification is based does not exceed $750,000 after taking into account the applicable exclusions set forth at 13 CFR 124.104(c)(2); and

(C) It is identified, on the date of its representation, as a certified small disadvantaged business concern in the database maintained by the Small Business Administration (PRO-Net); or

[  ] (ii) It has submitted a completed application to the Small Business Administration or a Private Certifier to be certified as a small disadvantaged business concern in accordance with 13 CFR 124, Subpart B, and a decision on that application is pending, and that no material change in disadvantaged ownership and control has occurred since its application was submitted.

(2) o  For Joint Ventures. The offeror represents, as part of its offer, that it is a joint venture that complies with the requirements at 13 CFR 124.1002(f) and that the representation in paragraph (b)(1) of this provision is accurate for the small disadvantaged business concern that is participating in the joint venture. [The offeror shall enter the name of the small disadvantaged business concern that is participating in the joint venture: _________________________.]

(c) Penalties and Remedies. Anyone who misrepresents any aspects of the disadvantaged status of a concern for the purposes of securing a contract or subcontract shall—

(1) Be punished by imposition of a fine, imprisonment, or both;

(2) Be subject to administrative remedies, including suspension and debarment; and

(3) Be ineligible for participation in programs conducted under the authority of the Small Business Act.

(End of provision)

### 16. 52.219-23  Notice of Price Evaluation Adjustment for Small Disadvantaged Business Concerns.

Notice of Price Evaluation Adjustment for Small Disadvantaged Business Concerns (Sept 2005)

(a) Definitions. As used in this clause—

“Small disadvantaged business concern” means an offeror that represents, as part of its offer, that it is a small business under the size standard applicable to this acquisition; and either—

(1) It has received certification by the Small Business Administration as a small disadvantaged business concern consistent with 13 CFR Part 124, subpart B; and

(i) No material change in disadvantaged ownership and control has occurred since its certification;

(ii) Where the concern is owned by one or more disadvantaged individuals, the net worth of each individual upon whom the certification is based does not exceed $750,000 after taking into account the applicable exclusions set forth at 13 CFR 124.104(c)(2); and

(iii) It is identified, on the date of its representation, as a certified small disadvantaged business concern in the database maintained by the Small Business Administration (PRO-Net).

(2) It has submitted a completed application to the Small Business Administration or a Private Certifier to be certified as a small disadvantaged business concern in accordance with 13 CFR Part 124, subpart B, and a decision on that application is pending, and that no material change in disadvantaged ownership and control has occurred since its application was submitted. In this case, in order to receive the benefit of a price evaluation adjustment, an offeror must receive certification as a small disadvantaged business concern by the Small Business Administration prior to contract award; or

(3) Is a joint venture as defined in 13 CFR 124.1002(f).

“Historically black college or university” means an institution determined by the Secretary of Education to meet the requirements of 34 CFR 608.2. For the Department of Defense (DoD), the National Aeronautics and Space Administration (NASA), and the Coast Guard, the term also includes any nonprofit research institution that was an integral part of such a college or university before November 14, 1986.

“Minority institution” means an institution of higher education meeting the requirements of Section 1046(3) of the Higher Education Act of 1965 (20 U.S.C. 1067k, including a Hispanic-serving institution of higher education, as defined in Section 316(b)(1) of the Act (20 U.S.C. 1101a)).

(b) Evaluation adjustment.

(1) The Contracting Officer will evaluate offers by adding a factor of 10 percent to the price of all offers, except—

(i) Offers from small disadvantaged business concerns that have not waived the adjustment; and

(ii) An otherwise successful offer from a historically black college or university or minority institution.

(2) The Contracting Officer will apply the factor to a line item or a group of line items on which award may be made. The Contracting Officer will apply other evaluation factors described in the solicitation before application of the factor. The factor may not be applied if using the adjustment would cause the contract award to be made at a price that exceeds the fair market price by more than the factor in paragraph (b)(1) of this clause.

(c) Waiver of evaluation adjustment. A small disadvantaged business concern may elect to waive the adjustment, in which case the factor will be added to its offer for evaluation purposes. The agreements in paragraph (d) of this clause do not apply to offers that waive the adjustment.

______ Offeror elects to waive the adjustment.

(d) Agreements.

(1) A small disadvantaged business concern, that did not waive the adjustment, agrees that in performance of the contract, in the case of a contract for—

(i) Services, except construction, at least 50 percent of the cost of personnel for contract performance will be spent for employees of the concern;

(ii) Supplies (other than procurement from a non manufacturer of such supplies), at least 50 percent of the cost of manufacturing, excluding the cost of materials, will be performed by the concern;

(iii) General construction, at least 15 percent of the cost of the contract, excluding the cost of materials, will be performed by employees of the concern; or

(iv) Construction by special trade contractors, at least 25 percent of the cost of the contract, excluding the cost of materials, will be performed by employees of the concern.

(2) A small disadvantaged business concern submitting an offer in its own name shall furnish in performing this contract only end items manufactured or produced by small disadvantaged business concerns in the United States or its outlying areas. This paragraph does not apply to construction or service contracts.

(End of clause)

17. FAR 52.212-4  (Sept 2005), Contract Terms and Conditions-Commercial Items is applicable. Addenda to FAR 52.212-4 are as follows:

## CLAUSES INCORPORATED BY REFERENCE

52.212-1 Instructions to Offerors-Commercial Items

52.212-3 Offeror Representations and Certifications-Commercial Items, Alternate I and         Alternate II (please see solicitation attachment).

52.217-9 Option to Extend the Term of the Contract

18. NASA FAR SUPPLEMENT CLAUSES:

1852.215-84, Ombudsman (OCT 2003)--ALTERNATE I (JUNE 2000) The installation Ombudsman is Brent Bennett, NASA HK, Washington DC, Business Phone, (202) 358-0837, Fax (202) 358-2826 E-mail address: Brent.J.Bennett@nasa.gov

1852.219-76, NASA 8 Percent Goal (JULY 1997)

1852.223-72, Safety and Health (Short Form) (APR 2002)

1852.223-75, Major Breach of Safety and Security (FEB 2002)

1852.225-70, Export Licenses (FEB 2000)

(END OF CLAUSE)

19. LIST OF ATTACHMENTS (GSFC 52.211-101) (OCT 1988)

The following attachments constitute part of this contract:

Attachment              Description                                              Date                      No. of Pages

A                      Statement of Work                                   08/06	         	10

(End of clause)