## General Comments
Draft RFP Document Comments
ID# | Date | Document Section | From: | To: | Comments | Questions | Recommended Action Items | Disposition
GenCom-01 | 2007-09-10 | Synopsis | See Comment | See Comment | The Synopsis indicates that the government intends to request proposals within 30 days of release of the final RFP. The scope of the proposal as outlined by the Draft RFP is large. For example, the requirements for Volume V are extensive, and the requirement to get detailed cost data and past performance information from the defined critical subcontractors is more complex than a standard proposal. | Would the government consider increasing the turn-around time from 30 days to 45 days to allow for the additional proposal complexity? |  | The Government will consider 45 days for submission.
GenCom-02 | 2007-09-12 | F&PS, UIIDs, GIRD, IRDs |  |  |  | Will the government be issuing DOORs databases for these documents? |  | No
GenCom-03 | 2007-09-12 | GFP 125771-SOL-001-009 |  |  | Recommend adding Instrument EGSE, bagging, simulator modules and stimulators to the GFP list |  |  | The Government consider the GFP list to be complete.
GenCom-04 | 2007-09-12 | GFP 125771-SOL-001-009 |  |  |  | Should a ground interface simulator/emulator be on the GFP list? |  | We do not have a ground contract in place to determine if that will be GFP
GenCom-05 | 2007-09-12 | GFP 125771-SOL-001-009 |  |  |  | Do emulators of the RF service uplinks need to be on the GFP list? |  | We do not have a ground contract in place to determine if that will be GFP
GenCom-06 | 2007-09-12 | Draft Award Fee Plan I.3.b,c,d,f and IV.B,C |  |  | Sections describes five major award fee pools but only three are listed in I.3.b. Please clarify. |  |  | The 5 pools included pools for two options. The final RFP will reflect the correct number of pools.
GenCom-07 | 2007-09-12 | Draft Award Fee Plan I.3.f | ...G.4, Award Fee for End Item Contracts, paragraph (c)(4) | ...G.3, Award Fee for End Item Contracts, paragraph (c)(4) | Administrative correction |  |  | Fixed
GenCom-08 | 2007-09-12 | Draft Award Fee Plan Att III-B.3 | The Contractor should normally be rewarded for meeting the estimated cost of the contract, but not to the maximum score allocated for cost control, to the degree that the Contractor has prudently managed costs while meeting contract requirements. | The Contractor should normally be rewarded for meeting the estimated cost of the contract to the maximum score allocated for cost control, to the degree that the Contractor has prudently managed costs while meeting contract requirements. | Recommend the contractor be able to earn 100% of available fee for performance consistent with contractual requirements. |  |  | The plan is consistent with current NASA policy
GenCom-09 | 2007-09-12 | Draft Award Fee Plan Att III-C | In order to earn a total overall rating of Excellent, the contractor must be under contract cost, on or ahead of schedule, and be rated excellent under Technical Performance. | In order to earn a total overall rating of Excellent, the contractor must be at or under contract cost, on or ahead of schedule, and be rated excellent under Technical Performance. | Recommend the contractor be able to earn 100% of available fee for performance consistent with contractual requirements. |  |  | The plan is consistent with current NASA policy
GenCom-10 | 2007-09-12 | 417-R-RPT-0027 Para 1. | On-orbit locations are 75 and 135 degrees W longitude. | On-orbit locations are 75 and 137 degrees W longitude. | Suggest change to be consistent with F&PS |  |  | Concur, will revise
GenCom-11 | 2007-09-18 | Entire Document |  |  | The interchangeable use of "system" and "segment" throughout the document creates some confusion. |  | Ensure "system" is used to refer to the overall GOES-R System which includes the Space and Ground Segments. | Concur, will revise
GenCom-12 | 2007-09-18 | B.3 | Contract Funding |  | Target Cost and Fiscal Year Funding profile not provided. With a single draft RFP and a proposed 30-day response to the final RFP, any adjustments to fit program within the Government's funding profile (provided with Final RFP) will be rushed. |  |  | We do not currently plan on providing a target cost and fiscal year funding profiles.
GenCom-13 | 2007-09-08 | F.1 | Delivery Schedule | Item 6. Simulators | Delivery Date is TBP. Dates will need to be coordinated with Ground Segment for integration into Mission Mangement element. |  |  | Delivery dates will be specified in RFP
GenCom-14 | 2007-09-18 | H.18 |  |  | Text states "Liaison and coordination activity between the Contractor and the instrument contractors may be necessary." There is no provision for similar coordination with the Ground Segment contractor. |  | Add provision for"Liaison and coordination activity between the Spacecraft Contractor and the Ground Segment Contractor". | Scope added to SOW.
GenCom-15 | 2007-09-12 | DRFP B.1 |  |  | Recommend adding a CLIN for contractor support of the Government's Systems Engineering and Integration activities |  |  | The Government does not consider a separate CLIN to be necessary
GenCom-16 | 2007-09-12 | DRFP B.1 |  |  | Recommend adding CLINs for optional spacecraft. This provides the potential for program cost savings and increased efficiency as funding permits. |  |  | The inclusion of options is at the discretion of NOAA
GenCom-17 | 2007-09-12 | DRFP B.1 |  |  | Recommend adding a CLIN for parts and materials for optional spacecraft. This provides risk mitigation against parts obsolescence and the potential for program cost savings and increased efficiency as funding permits. |  |  | The inclusion of options is at the discretion of NOAA
GenCom-18 | 2007-09-12 | DRFP B.1, F.1, L.15.3.f.2 Cost Format 2 and SOW 1.3 pages 4, 14, 101 and SOW page 2 | ` |  | RFP Sections B.1, F.1 and section 1.3 of the SOW list the deliverables and scope and appear to be inconsistent with the columns of data requested for Cost Format 2. Cost format 2 lists column headers that include parts for GOES-T, parts for GOES-U, and spares as part of the baseline cost. Please clarify. |  |  | IF we delete parts for T and U from the basic contract we will revise cost format 2. Spares will remain as part of basic contract
GenCom-19 | 2007-09-12 | DRFP C.2 | The Contractor shall submit CDRL PS-18 for the purposes of compliance with this clause |  | There is no item PS-18 in the CDRL. Please clarify |  |  | Revised to PS 08
GenCom-20 | 2007-09-12 | DRFP F.1 (p. 14) and F.4 (p. 15) | ESTE (Qty = 2) to be delivered March 2014 (same as GOES R Spacecraft) to KSFC |  | Recommend the delivery of 1 set of ESTE with the delivery of the GOES-R spacecraft. Recommend 2nd set or ESTE remain at contractors facility to enable integration and test of GOES-S. |  |  | The SOW addresses the return of ESTE to the contractor's facility
GenCom-21 | 2007-09-12 | DRFP H.19, page 37 and L14.1 page 84 |  |  |  | Is it the Government's intent to consider enhancements as options to be considered above and beyond a proposal for a fully compliant spacecraft solution? In addition, how will the proposed enhancements be evaluated and scored with respect to section M? |  | Enhancements are not considered to be options and shall not be proposed as options. Enhancements will be evaluated within the applicable evaluation subfactors.
GenCom-22 | 2007-09-12 | DRFP I.1 | 52.215-21 - Requirement for Cost or Pricing or Information Other than Cost and Pricing Data - Modifications (OCT 1997) | 52.215-21 - Requirement for Cost or Pricing or Information Other than Cost and Pricing Data - Modifications (OCT 1997) Alternate I (OCT 1997) | Request addition of Alternate IV, which will result in reduced proposal preparation time and cost to the Government. If Alternate IV is not included, recommend Alternate I, which requires submittal of essentially the same information as the primary clause, while providing added flexibility to accommodate Government preference regarding proposal format. |  |  | The Government does not consider the suggested alternates to be appropriate.
GenCom-23 | 2007-09-12 | DRFP I.1 | 52.219-14 Limitations on Subcontracting (Dec 1996) | - | Recommend deletion of this clause as not applicable to this contract. |  |  | Agreed. Will delete if internal GSFC policy approves.
GenCom-24 | 2007-09-12 | DRFP I.1 | NFS 1852.227-14 Rights in Data--General | - | Recommend deletion as not applicable to the primary contract deliverables and copyright development is not the objective of this contract. The Government's ability to use and distribute the software for Government purposes will not be adversely affected. |  |  | The Government does not agree.
GenCom-25 | 2007-09-12 | DRFP I.5 | 52.227-14 Rights in Data - General (JUN 1987) - Alternate II (JUN 1987) | 52.227-14 Rights in Data - General (JUN 1987) - Alternate I (JUN 1987), Alternate II (JUN 1987) | Recommend addition of Alternate I as it provides a more appropriate definition of Limited Rights Data. |  |  | The Government does not consider the suggested alternate to be appropriate.
GenCom-26 | 2007-09-12 | DRFP L.12 |  |  | The proposal format does not include Executive Summary information which we believe would be useful. Recommend addition of an Executive Summary proposal volume. |  |  | The Government does not want an Executive Summary with the proposal.
GenCom-27 | 2007-09-17 | Past Performance Volume |  |  | Please provide the level of security classification that will be accommodated for past performance data, whether electronic submittal will be allowed and a point of contact for submittal of information. |  |  | No classified information is to be included in any proposal volume, including Past Performance.
GenCom-28 | 2007-09-17 | Past Performance Questionnaire, IV. SOW Survey: Experience Level and Performance Rating |  |  | The SOW Elements listed on the questionnaire do not correspond to the GOES R Series Flight Project Spacecraft Statement of Work dated August 21, 2007 provided in the DRFP. Please provide clarification regarding the listed SOW elements. |  |  | The questionnaire has been revised to be consistent with the SOW.
GenCom-29 | 2007-09-17 | n/a |  |  | Recommend adding an 'Order of Precedence' list for technical documents |  |  | Unless specifically addressed within a technical document, the Contracting Officer will adjudicate conflicts regarding order of precedence.
GenCom-30 | 2007-11-12 | Past Performance | Section L16 (b) pg 107 |  | Recommend that past performance be limited to "most relevant" efforts vs. "all" efforts. Recommend that no classified programs be required for past performance if they are not relevant. |  |  | The Government requires that "all" efforts be listed so that it can determine what is most relevant. No classified information is to be included in Past Performance or any other proposal volume.
GenCom-31 | 2007-11-26 | Solicitation, Sections L14.3 and M.3, Subfactor D |  |  | Sections refer to NPR 8715.3A. Document has been superseded by NPR 8715.3B and is not available. |  | Recommend updating reference document or providing NPR 8715.3A. | RFP will be updated
GenCom-32 | 2007-11-26 | Solicitation L.16 - Past Performance | If the contract was fixed price, and you suffered a loss under the contract, state the value of the loss, and the reason it occurred. |  | We do not release financial data on an individual program basis. Program profitability of a given program under a firm fixed price contract is company proprietary competition sensitive data. |  | Recommend deletion of this requirement | The Government treats all proposal and financial data as proprietary competition sensitive data. The requirement will not be changed
GenCom33 | 2007-11-14 | IT Security |  |  | The referenced NPRs related to IT Security are restricted from public access. Please provide referenced documents so bidders can prepare proposals. |  |  | L.2 of the RFP will be revised to include directions for obtaining these documents. They will only be provided to those who are bidding as primes
GenCom34 | 2007-09-10 | B.1 Deliverable Requirements | See comment | See comment | Item 6: Simulators quantity of six is unclear with regards to what type of Simulator. | Is a subset of these 6 simulators intended to perform the function of the spacecraft/instrument interface simulator (SIIS) as defined in CDRL GS-02? | Recommend providing lower level detail on the specific type and number of simulators to be delivered. | This information is under review with the Ops Project. The government will consider revising.
GenCom35 | 2007-09-10 | B.1 Deliverable Requirements | See comment | See comment | SOW 2.5.2 indicates that one spacecraft simulator is delivered to each Instrument contractor, yet Spacecraft Simulator is not listed in the Deliverable Requirements table. If the SOW reference is to Satellite Simulators, they are more capable and complex than would be required to validate spacecraft/Instrument interfaces and would unnecessarily drive program cost. |  | Please clarify deliverable requirements for the Spacecraft Simulators vs. Satellite Simulators. | This requirement has been removed.
GenCom36 | 2007-09-10 | B.1 Deliverable Requirements | See comment | See comment | The Spacecraft F&PS includes requirements for the Spacecraft Command and Telemetry Simulator (SCTS), but the SCTS is not included as a deliverable. |  | Suggest adding deliverable requirements for the Spacecraft Command and Telemetry Simulator (SCTS). | Not all hardware developed under this contract is intended to be formal deliverables.
GenCom37 | 2007-09-10 | B.1 Deliverable Requirements | Information Technology Security Plan, Contingency Plan, Assessment Plan | See comment | These plans are identified as deliverables, but are not included in the CDRL listing. | Should these be CDRL items? | Add these plans to the CDRL listing. | It is PM-18
GenCom38 | 2007-09-10 | DRFP Section F.1 Delivery Schedule & H.13 Launch Date Changes | See comment | See comment | In F.1 the GOES R Spacecraft delivery date is specified as March 2014 to the SPF at KSC. In H.13 Launch is specified as December 2014. An approximate 3 month site processing flow would leave 6 months unaccounted for. | What is the assumed state of the Satellite during a presumed 6 month hold at the SPF? | Specify that the Satellite will be ready for delivery on March 2104 and held at the Contractor's facility until called-up for Launch Site processing to support a December 2014 launch. | The 6 months is the schedule margin held by the government.
GenCom39 | 2007-09-10 | DRFP Section F.1 Delivery Schedule & H.13 Launch Date Changes | See comment | See comment | In F.1 the GOES S Spacecraft delivery date is specified as July 2015 to the SPF at KSC. In H.13 Launch is specified as April 2016. An approximate 3 month site processing flow would leave 5 months unaccounted for. | What is the assumed state of the Satellite during a presumed 5 month hold at the SPF? | Specify that the Satellite will be ready for delivery on July 2015 and held at the Contractor's facility until called-up for Launch Site processing to support a April 2016 launch. | The 5 months is the schedule margin held by the government.
GenCom40 | 2007-09-10 | DRFP Section F.4 Shipping Instructions | See comment | See comment | DRFP requires the delivery of 1 set of GSE software and source code. Our GSE approach leverages almost entirely from COTS code. Source code will not be available. | Will source code be expected for GSE COTS software? | H.26 specifies source code of software first developed on this contract | Source Code only applies to software developed by the contractor.
GenCom41 | 2007-09-10 | Section G.3 (2), Page 18 | …amount of interim award fee payment is limited to the lesser of the interim evaluation score or 80 percent of the fee allocated to that period…" | …amount of interim award fee payment will equal the interim evaluation score as a percentage of the fee allocated to that period… | The current language limits the maximum award fee payment for an interim evaluation to 80 percent of the fee allocated to the period. This is inconsistent with the approach defined in the Performance Evaluation Plan |  | Update Section G.3 (2) language to be consistent with the PEP. | See SecG-1
GenCom42 | 2007-09-10 | Section G.2 (3) | Provisional award fee payments will not be made under this contract pending interim evaluation. | See comment | Will the government consider allowing for provisional monthly billing of interim award fees? |  |  | See SecG-2
GenCom43 | 2007-09-10 | Sections 4, 5, and 6.2.1.3 | See Comment | See Comment | The PRAD includes resource allocation requirements for an Advanced Instrument, but none of the other RFP documents address requirements for incorporation or accommodation of an Advanced Instrument. In addition, the SCFPS provided with the RFP increased the X-and downlink rate, which implies addition of an advanced instrument to the satellite. | Does the government intend to require the contractor to address alternatives designs and/or perform trade studies in the A&O phase for accommodation of the advanced instrument? | Please clarify reason for providing the advanced instrument resource requirements. | Yes. The intention is to possibly accommodate an advance instrument for GOES-T&U
GenCom44 | 2007-12-12 | F.1, F.4, M.4 |  |  | Some of the deliverable items that are deliverable under the contract may be available at no cost to the Government as re-use from other programs | Does the Government intend to make adjustments for no-cost items in the same manner as government-furnished property as part of the probable cost adjustment? | Provide additional information in M.4 | Such property is considered to be non-furnished Government property and will be handled in accordance with FAR 45.2, i.e., the cost of the property will be included in the probable cost adjustment
GenCom45 | 2007-12-12 | F.1, F.4, SOW 1.3, 2.5 |  |  | The RFP specifies delivery of 2 sets of ESTE, but does not provide the scope or requirements for the ESTE in the technical documents. EGSE is addressed but EGSE is not a deliverable | Are ESTE and EGSE to be considered the same thing? If not, please clarify the anticipated scope for ESTE and clarify deliverable requirements in Section F for EGSE. | Clarify definitions and delivery requirements for ESTE and EGSE | ESTE is the system required to provide commanding to and receive telemetry from the spacecraft during integration and test. EGSE is electrical support equipment required by the spacecraft during development, assembly, and I&T.
Note on H2: Identify what action you recommend be taken to address/resolve the issues.

## Cover Letter
Draft RFP Document Comments
ID# | Date | Document Section | From: | To: | Comments | Questions | Recommended Action Items | Disposition
Cover-1 |  | Cover Letter |  |  |  | Please identify the proposed ATP date. |  | The cover letter will include the appropriate information
Cover-2 | 2007-09-10 | Synopsis | See Comment | See Comment | The Synopsis indicates that the government intends to request proposals within 30 days of release of the final RFP. The scope of the proposal as outlined by the Draft RFP is large. For example, the requirements for Volume V are extensive, and the requirement to get detailed cost data and past performance information from the defined critical subcontractors is more complex than a standard proposal. | Would the government consider increasing the turn-around time from 30 days to 45 days to allow for the additional proposal complexity? |  | The Government will consider 45 days for submission of proposals.
Note on H2: Identify what action you recommend be taken to address/resolve the issues.

## PEP
Draft RFP Document Comments
ID# | Date | Document Section | From: | To: | Comments | Questions | Recommended Action Items | Disposition
PEP-1 |  | Performance Evaluation Plan, Section 1c. Page 4 |  |  |  | Section 1c of the PEP states award fee will be divided among five major pools but only lists 3: 1.) Non-Recurring Effort (NRE) and FM1, 2.) FM 2 and 3.) Post-Delivery Support. Please clarify the number and type of award fee pools available. If fee is allocated to on-orbit incentives, during what timeframe can it be provisionally billed, as part of pre-on-orbit performance or after launch? |  | 5 pools are required if there are options. The PEP will reflect the appropriate number of pools. Currently there is no plan for provisional payment of on-orbit fee.
PEP-2 |  | Attachment III-B.4 |  |  |  | Would NASA like the Contractor to provide recommendations for the definitions associated with "Fully Operational", "Slight Degraded", etc. as part of its proposal submission? If yes, in what section of the proposal would you like it to be included? |  | The contractor may propose recommendations at any time. Recommendations should be provided separate from the proposal
PEP-3 | 2007-09-10 | Paragraph I (h), page 5 | On-orbit evaluation are made based on on-orbit performance, which begins after launch. On-orbit evaluation is evaluated against the evaluation criteria in Attachment III-B.4. | See question |  | Would the government consider making previously unearned award fees available to be earned for Flight vehicle life past the 15 year (storage and operational) requirement? |  | NASA policy does not permit roll over of fee that has been "lost"..
PEP-4 | 2007-09-10 | Paragraph I (l), Page 6 | "… will be no formal structured hardware performance incentives as set forth in the NFS. This exception was granted by the GSFC director, in accordance with the NFS. The reasons for the exception are stated in the request for the exception." | See question |  | Would the government make the request for the exception available to the contractors? |  | No.
PEP-5 | 2007-09-10 | Paragraph IV.C | The fee available for on-orbit performance is 50% of the fee as determined by the final evaluation of each of Pools 1-4. | The fee available for on-orbit performance is 50% of the total fee. | The current language implies the on-orbit fee is 50% of the amount of fee earned for pre-on-orbit performance. |  | Update language. | The language is correct.
PEP-6 | 2007-09-10 | Performance Evaluation Plan (PEP) Section 1 b. and Section 1 c. | Award Fee will be divided among five major pools: 1. Non-Recurring Effort (NRE) and FM 1 2. FM 2 3. Post-Delivery Support | Award Fee will be divided among four major pools: 1. Non-Recurring Effort (NRE) and Recurring Effort for Spacecraft #1 2. Recurring Effort for Spacecraft #2 3. Post-Delivery Support for Spacecraft #1 4. Post-Delivery Support for Spacecraft #2 | The structure of the Award Fee determination requires separate pools for spacecraft #1 and spacecraft #2. It would seem that a similar approach for the Post-Delivery Support would be appropriate. For example, it does not appear to be the Government's intent to award the entire Post-Delivery fee for spacecraft #2 in the event of a launch vehicle failure for spacecraft #1, but the current pool structure allows this to occur. |  | Suggest modifying text in b. and c to identify four pools. Update text in the rest of the PEP to be consistent with 4 award fee pools. | See PEP-1
Note on H2: Identify what action you recommend be taken to address/resolve the issues.

## Section G
Draft RFP Document Comments
ID# | Date | Document Section | From: | To: | Comments | Questions | Recommended Action Items | Disposition
SecG-1 |  | Section G.3 (2), Page 17 | "The amount of the interim award fee payment is limited to the lesser of the interim evaluation score or 80 percent of the fee allocated to that period less any provisional payments made during the period." | Delete | At the time of each period's evaluation, any difference between the period's provisional payment and the interim evaluation is balanced. NASA retains sole authority to suspend or reduce provisional payments in the event of poor performance. This maximizes contractor's motivation to achieve highest possible award fee scores to the benefit of NASA. |  |  | This is a standard NASA FAR Supplement clause. No change required
SECG-2 |  | Section G.3 (3), Page 17 | "(3) Provisional award fee payments will not be made under this contract pending each interim evaluation. If applicable, provisional award fee payments will be made to the Contractor on a (not applicable) basis. The amount of award fee which will be provisionally paid in each evaluation period is limited to (not applicable) of the prior interim evaluation score." | "(3) Provisional award fee payments will be made under this contract pending each interim evaluation. Provisional award fee payments will be made to the Contractor on a monthly basis. The amount of award fee which will be provisionally paid in each evaluation period is limited to the prior interim evaluation score ." | This section does not allow for provisional award fee payments to be made under the contract pending each interim evaluation. Consequently, a contractor may only invoice for interim award fee payments every 6 months at the lesser of 80% or the interim evaluation score. This maximizes contractor's motivation to achieve highest possible award fee scores to the benefit of NASA. |  |  | We do not believe that the interm provisional fee payments provide significant motivation to justify the administrative burden. No change required
Note on H2: Identify what action you recommend be taken to address/resolve the issues.

## Section H
Draft RFP Document Comments
ID# | Date | Document Section | From: | To: | Comments | Questions | Recommended Action Items | Disposition
SecH-1 | 2007-09-10 | Section H.19 | See comment | See comment | It is unclear how Attachment J (Contractor Proposed Enhancements) relates to the contractor's proposed concept, specifically with respect to cost. | Are the enhancements proposed in Attachment J assumed to be included in the proposed costs contained in Volume III? If not, is the contractor allowed to provide cost information in Attachment J? |  | The cost of the enhancements is to be included in the cost proposal and segregated so the Government can assess the value of the enhancement given the cost. RFP language revised to clarify
SecH-2 | 2007-09-10 | Section H.25 | See comment | See comment | The intent of Attachment K (Implementation Approaches) is not clear from the description. | Can the government provide a template or example for Attachment K to further describe the expectations for this attachment? |  | The intent is to have a document that captures an offeror's proposed approach. Whether it is word for word from the proposal or paraphrased will depend upon how the proposal is written. Will review RFP to improve instructions.
Note on H2: Identify what action you recommend be taken to address/resolve the issues.

## Section L
Draft RFP Document Comments
ID# | Date | Document Section | From: | To: | Comments | Questions | Recommended Action Items | Disposition
SecL-09 | 2007-09-10 | Section L.6 | See comment | See comment | Will there be a preproposal conference? If yes, where and when? |  |  | The Government may hold a pre-proposal conference. If one is planned it will be synopsized
SecL-18 | 2007-09-10 | Section L.14.1 (Page 85) | "However, these instructions include Government identified risks that the offeror must also address…." | See comment | The RFP does not appear to include a listing of Government identified risks that must be addressed. |  | Provide the Government risk list. | The Government will not provide its risk list. The government has revised the RFP.
SecL-23 | 2007-09-10 | Section L.15 (4), Page 103 | BOEs are to be submitted only to CWBS Level 4. The volume shall comply with the page limitation in L.12. | See comment | Section L.12 limits the BOEs to 3 pages per WBS element. In some cases it will be difficult to provide the requested information at level 4 of the CWBS within 3 pages. In other cases, 3 pages will not be required. | Would it be possible to change the Section L.12 requirement to limit the page count to an average of 3 pages per WBS element? | Consider modifying page limit requirement to an average of 3 pages per BOE. | The RFP will retain the 3 page limitation on BOEs. The offeror can define a WBS beyond Level 4 and provide associated BOEs as long as they add up to the level 4 subtotals.
SecL-28 | 2007-09-12 | DRFP L.14.3 B.3 Spacecraft Ground Support Equipment (GSE) | Describe the spacecraft simulator design and its use for verification testing, operator training and launch simulations, on-orbit simulations, on-orbit anomaly investigation/resolution, ground system changes, and operational procedure development and validation. Provide a detailed listing of spacecraft subsystem and environmental modes included in the simulator and describe the fidelity of each model |  |  | For the bold text, did you mean Modes or Models? Please clarify. |  | Yes. Typo. Should be models vs. modes.
SecL-29 | 2007-09-12 | DRFP L.14.3 B.2.7 pg 93 | Describe the comment heritage --- |  | Please clarify. |  |  | Typo. Component vs. comment.
SecL-33 | 2007-09-13 | DRFP L B.1.5, page 91 | Provide a post-launch test approach describing the tests to be performed by NASA to initialize and/or characterize INR in orbit performance and the interval required between calibrations | Provide your approach to verify INR related performance requirements at spacecraft, satellite, space segment and system level as appropriate. Provide your approach to supporting post-launch INR testing to be performed by NASA. | Recommend the Government request the contractor's approach to verifying the specified spacecraft requirements as well as the contractor's approach to supporting end-to-end INR verification. |  |  | Concur
SecL-01 |  | Section L.12, Page 80 Section L.14.3 Subsection B.2.5, Page 93 Section M.3 Subsection B.2.5, Page 118 CDRL Attachment (417-R-SCCDRL-0015) |  |  |  | B.2.5 asks for SCCDRL-0015 Communications Links spreadsheet. Please clarify where to package this item and whether or not this is included in page count limits. |  | Should be included in CDRL volume, which is not page limited.
SecL-02 |  | Section L.12, Page 80 Section L14.3 Subfactor D, Page 97 Section L.17, Page 108 |  |  |  | Section L.12 requests the Safety & Health Plan to be delivered as Volume II, Subfactor D and also as CDRL PM-13 in Volume V. Please clarify where the complete plan should be packaged. |  | Safety and Health Plan should be included in CDRL volume. RFP will be clarified.
SecL-03 |  | Section L.12, Page 80 Section L.17, Page 108 |  |  |  | Section L.12 requests the Small Business Development Plan to be delivered in Volume II and also as CDRL PM-04 in Volume V. Please clarify where the plan should be packaged. |  | Subcontracting Plan should be included in CDRL volume. RFP will be clarified
SecL-04 |  | Section L.12, Page 79, Paragraph 2 Section L.15, Page 99, Paragraph 2 Section L.15, Page 100, Paragraph (f) |  |  |  | Please clarify whether electronic copies are to be provided on CD-ROM (CD-R) format or DVD-R media. |  | CD-ROM (CD-R) format is required. RFP will be clarified
SecL-05 |  | Section L.15 3.g and l Pages 101 and 102 |  |  |  | Section L.15 3.g requires contractors to provide cumulative funding requirements,etc. by GFY quarter. Section L.15 3.l requires contractors to provide any other relevant cost assumptions and information including termination costs, etc. Should the contractor include termination costs in the Funding Summary by GFY Quarter (Cost Format 2b)? |  | Offerors should include termination cost in the funding summary, preferably on a separate line.
SecL-06 |  | Deleted | Deleted | Deleted | Deleted |  |  | Deleted
SecL-07 |  | Section L B.1.7 page 91 | "Provide details against the Atlas 531 vehicle." | "Provide details against the Atlas 531, 541 and 551 vehicles." | To provide the government with the best value system, we recommend this change so GSFC obtains margins for launch vehicles consistent with SCFPSS35, which states: "The Satellite shall be compatible with an Evolved Expendable Launch Vehicle - Medium (EELV-M) class vehicle." |  |  | If alternate LV configurations are permitted, the RFP will be revised so that a cost will be assessed to the s/c vendor for the difference in LV price.
SecL-08 |  | Section L.15 1. page 98 | "The cost proposal will be in three separate volumes:" | "The cost proposal will be in five separate volumes: Cost Information (Volume IIIA), Basis of Estimate (BOE) (Volume IIIB), Summary of Deviations/Exceptions (Cost Proposal)(Volume IIIC), GOES-T (Option), GOES-U (Option)" | Would like NASA to consider allowing the contractors to bid separately priced options for a third and fourth spacecraft. Obtaining a third and forth spacecraft from the same contractor could offer NASA considerable cost savings. Since they are to be priced as options, contractor understands there is no commitment for NASA to procure more than 2 spacecraft. |  |  | The inclusion of options is at the discretion of NOAA. The RFP will reflect NOAA's requirements
SecL-10 | 2007-09-10 | L.12 (a) (4), page 79 | Two electronic copies of each volume of the offeror's proposal, designating one as "back-up", shall be submitted (in addition to the hardcopies specified above) in Microsoft Word, Excel Windows 2003 and Portable Document Format… | Two electronic copies of each volume of the offeror's proposal, designating one as "back-up", shall be submitted (in addition to the hardcopies specified above) in Microsoft Word, Excel Windows 2003, Microsoft Project and Portable Document Format… |  |  | Consider allowing MS-01 to be delivered in Microsoft Project format. | RFP will be clarified to instruct that the schedule be delivered in MS Project
SecL-11 | 2007-09-10 | L.12 (b) (1) table (Page 80) | IT-01, Spacecraft I&T Plan | Delete | The CDRL list specifies initial submission of IT-01 at PDR. |  | Recommend removing IT-01 from Section L.12, Volume 5 | Changed. IT-01 (Now IT-02) not requested with proposal.
SecL-12 | 2007-09-10 | L.12 (b) (1) table (Page 80) | PM-01, Program Management Plan | No Change | The CDRL list specifies submittal of PM-01 at 30 DACA, but Section L.12 specifies inclusion in Volume V. |  | Recommend modifying CDRL to show initial PM-01 due with proposal | CDRLs submitted w/proposal do not satisfy contract requirement for initial submission. RFP will be clarified
SecL-13 | 2007-09-10 | L.12 (b) (1) table (Page 80) | MS-01, Spacecraft Master Schedule | No Change | The CDRL Section 2.0 specifies initial submittal of MS-01 at 60 DACA, but Section L.12 specifies inclusion in Volume V. |  | Recommend modifying CDRL to show initial MS-01 due with proposal | CDRLs submitted w/proposal do not satisfy contract requirement for initial submission. RFP will be clarified
SecL-14 | 2007-09-10 | L.12 (b) (1) table (Page 80) | PM-57, Risk Management Plan | RM-01, Risk Management Plan | PM-57 Risk Management Plan is specified as part of CDRL Volume, but the CDRL Section 2.0 has no PM-57. It does have RM-01 Risk Management Plan with initial submittal as Proposal. |  | Recommend changing PM-57 to RM-01. | RFP will reflect correction
SecL-15 | 2007-09-10 | L.12 (b) (1) table (Page 80) | MA-01, Mission Assurance Plan | No Change | The CDRL Section 2.0 specifies initial submittal of MA-01 at PDR-30 days, but Section L.12 specifies inclusion in Volume V. |  | Recommend modifying CDRL to show initial MA-01 due with proposal | CDRLs submitted w/proposal do not satisfy contract requirement for initial submission. No action required
SecL-16 | 2007-09-10 | L.12 (b) (1) table (Page 80) | SE-05, Validation and Verification Plan | SE-04, System Performance Verification Plan | SE-05 is listed as Validation and Verification Plan and specified as part of CDRL Volume, but CDRL Section 2.0 defines SE-05 as the Spacecraft to Instrument ICD, with initial submittal as PDR -14 days. |  | Replace SE-05 with SE-04. | This has been corrected
SecL-17 | 2007-09-10 | Section L.14.1 (Page 84) | "The offeror shall include Contract Attachment J as part of the model contract included in the mission suitability volume of the proposal" | See comment | This statement implies the model contract is included as part of the mission suitability volume rather than a separate volume as specified in L.12. | Is Attachment J to be provided with the mission suitability volume? |  | Attachment J is to be included in Model Contract. The RFP will be clarified
SecL-19 |  | Section L.15 (1) Page 98 | If the Offeror’s estimating and/or accounting practice differs from the required price proposal format, the costs should be computed in accordance with the Offeror’s normal accounting and estimating procedures and provide your rationale for the format adjustments. | See comment | This implies that the Offferor’s format can be provided in lieu of the format defined in the Enclosure 1 exhibits and schedules. | If the Offeror’s computer generated forms provides the information requested, but in a slightly different format, can Offeror computer generated forms be submitted in place of the Enclosure 1 forms? |  | The RFP instructions in the cost proposal will be revised to indicate when Offeror formats can be used in lieu of RFP formats. Formats are to be in MS Excel with formulas coded to allow the proper application of rates.
SecL-20 | 2007-09-10 | Section L.15 (3) (k) (3) Page 102 | See comment | See comment | Paragraph (3) is missing. |  | Provide missing paragraph or renumber. | RFP paragraphs will be renumbered.
SecL-21 | 2007-09-10 | Section L.15 (1) (f) Page 100 | The requirements for each set are summarized below. Within each set, each chart shall have the same format (number of columns, number of rows, headers, titles, etc.) | See comment | Can Offeror’s provide charts as generated by computer in lieu of the same format requirement, if their cost data is provided as “self-calculating in MS-Excel” where the Government has the ability to adjust cost (rates or hours) through the tools provided? |  |  | The RFP instructions in the cost proposal will be revised to indicate when Offeror formats can be used in lieu of RFP formats. Formats are to be in MS Excel with formulas coded to allow the proper application of rates.
SecL-22 | 2007-09-10 | Section L.15 (3) (d), Page 100 | Management Reserve: Provide rationale and approach to management reserve. Indicate the percentage of proposed management reserve and where it is in the cost proposal…. | See comment | The inclusion of management reserve in a cost plus proposal is inconsistent with the FAR. |  | Consider deleting this paragraph. | Management reserve is not inconsistent with FAR. Failure to propose and clearly identify MR may be considered a cost realism weakness .
SecL-24 | 2007-09-10 | Section L.16 (4), Page 103 | Offerors shall package the BOE volume so that the BOEs (Level 2, 3, and 4) at each WBS Level 2, as set forth in cost format #2, are included together. For example: WBS 1.1 Program Management WBS 1.2 Systems Engineering | Offerors shall package the BOE volume so that the BOEs (Level 2, 3, and 4) at each WBS Level 2, as set forth in cost format #2, are included together. For example: WBS 1.1 Program Management WBS 1.1.1 Resource Management WBS 1.1.2 Configuration/Data Management WBS 1.1.3 Information Technology Management WBS 1.2 Systems Engineering... |  |  | Please clarify the example provided. | For each WBS level provided by the offeror in format 2 we want the BOEs for the NRE, FM1, FM2 and each option packaged together. This will allow evaluators to see the entire BOE for a particular WBS in place. The RFP instructions and example will be clarified
SecL-25 | 2007-09-10 | Section L.16 pg 103 | However, Offerors may submit additional information at their discretion if they consider such information necessary to establish a record of relevant past performance. | See comment | This comment is interpreted to mean that additional narrative information can be provided for programs listed in the two matrices that are considered to be most relevant to GOES-R, as long as the 75 page limitation is not exceeded. | Is this interpretation correct? |  | Yes.
SecL-26 | 2007-09-10 | Section L.16 (b) pg 107 | Offerors and any proposed critical and major subcontractor(s), shall provide the questionnaires provided as Enclosure 2 to each of the above references to establish a record of relevant past performance. | Offerors and any proposed critical and major subcontractor(s), shall provide the questionnaires provided as Enclosure 2 to each of the above references indicated as most relevant to GOES-R to establish a record of relevant past performance. | The number of programs included in the two past performance matrices will be very large, and many of these programs will not be relevant to GOES-R because the are not of similar size, complexity or value. We recommend limiting the programs for which the questionnaires are provided to those that are most relevant to GOES-R. |  |  | Offerors shall provide the questionnaires to each of the programs addressed in the Past Performance volume. It is necessary to have the program customer provide its assessment of past performance.
SecL-27 | 2007-09-12 | DRFP L.12.b.1 page 80 and footnotes page 81 | Page Limitation for Basis of Estimates (BOE) - The BOE shall be addressed in narrative not to exceed three (3) pages per WBS element |  | The 3 page limitation on BOEs by WBS is very aggressive if it includes the contractor's and subcontractor's support rationale at 12 point type. Recommend unlimited page count at 12 point type and diagrams, pictures, tables, artwork and charts no smaller than 8 point type; but if that is not approved, recommend 5 page count each for NRE & RE (total 10 pages) for each WBS element. |  |  | The RFP page limitation for BOEs will not be changed. Offerors are reminded that they can define WBS levels below those in the RFP WBS and provide a separate BOE to that lowest level.
SecL-30 | 2007-09-12 | DRFP L.15.1 -Cost, page 98 | For critical and major subcontracts, the proposed subcontractor shall provide the same cost exhibits, formats and supporting information that is requested from the prime Offeror. |  | For critical subcontractors that are proposed as fixed price, the cost exhibits and formats would not necessarily be appropriate. Are the detailed cost exhibits and formats required for fixed price subcontracts? |  |  | The Government needs information to determine the cost reasonableness. However, in the case of critical subcontracts (e.g, star trackers), if the product is a standard product with standard market pricing, the offeror can provide the FFP data along with an explanation.
SecL-31 | 2007-09-12 | DRFP L.15.3.e Schedule of Rates, and L.15.3.f Cost Summary, page 100 | Submit a schedule showing proposed direct and indirect rates by contractor fiscal year (CFY)…(see Cost Exhibit #1) The offeror shall submit the data in the designated exhibit and format schedule layouts. |  | There were no cost exhibit layouts provided electronically with the RFP, only cost formats. Are cost exhibit layouts to be provided? |  |  | All cost formats will be provided with final RFP.
SecL-32 | 2007-09-12 | DRFP L.15.3.f Cost Summary, page 100 | Two sets of exhibits and formats are required. |  | It says two sets of exhibits and formats are required. We interpret this to mean two identical sets of the same data. Is this correct? |  |  | Yes.
SecL-33 | 2007-11-05 | Section L14.3 B.2.4 (Command & Data Handling) Page 92 | Identify the type of on-board computer(s) (OBC) proposed. Provide the processing requirements for the OBC and discuss the margins available. Discuss OBC subsystem reliability. | Identify the type of on-board computer(s) (OBC) proposed. Provide the processing requirements for the OBC and discuss the margins available. Discuss C&DH subsystem reliability. |  |  |  | Concur. Update will be incorporated.
Note on H2: Identify what action you recommend be taken to address/resolve the issues.

## Section M
Draft RFP Document Comments
ID# | Date | Document Section | From: | To: | Comments | Questions | Recommended Action Items | Disposition
SecM-3 | 2007-09-12 | DRFP M B.1.7, pg 115 | efficiency of your implantations --- |  | Please clarify. |  |  | Typo. RFP will reflect correction.
SecM-4 | 2007-09-10 | Attachment M List of GFP | See comment | See comment | GFP list only includes instrument related items. Our assumptions also include the LV, separation system, LV services, Launch Support Services, Payload Fairing, Satellite Fuel and Oxidizer, pressurant etc. |  | Please clarify other non-instrument items that are common to all bidders on the GFP list. | The Spacecraft Contractor will only be required to provide personnel to fuel the sat3llite. All other resources will be provided by the Launch Services Contract. This is now reflected in the SOW.
SecM-1 |  | Section M B 1.7, page 115 | "The Government will evaluate the reasonableness and adequacy of the margins against the Atlas 531 vehicle." | "The Government will evaluate the reasonableness and adequacy of the margins against the Atlas 531, 541 and 551 vehicles." | To provide the government with the best value system, we recommend this change so GSFC obtains margins for launch vehicles consistent with SCFPSS35, which states: "The Satellite shall be compatible with an Evolved Expendable Launch Vehicle - Medium (EELV-M) class vehicle." |  |  | The government is requiesting margins against the Atlas 531 vehicle to standardize the evaluation process. This does not imply that the government is specifying only the Atlas 531 vehicle is to be used.
SecM-2 | 2007-09-12 | DRFP M B.1.5, page 115 | The Government will evaluate the completeness, soundness, effectiveness and efficiency of the post-launch INR test approach describing the tests to be performed by NASA to initialize and/or characterize INR in orbit performance, using either test plans or test groups, and the interval required between calibrations. | The Government will evaluate the completeness, soundness, effectiveness and efficiency of the spacecraft contractor's approach to verifying INR performance related requirements. The Government will evaluate the completeness, soundness, effectiveness and efficiency of the spacecraft contractor's approach to supporting post-launch INR testing. | Recommend the Government evaluate the contractor's approach to verifying the specified spacecraft requirements as well as the contractor's approach to supporting end-to-end INR verification. |  |  | See Section L-33 Comment.
Note on H2: Identify what action you recommend be taken to address/resolve the issues.

## SOW
Draft RFP Document Comments
ID# | Date | Document Section | From: | To: | Comments | Questions | Recommended Action Items | Disposition
SOW-01 |  | SOW 2.2.7, Pg 17 | “The Contractor shall conduct INR analyses and tests using flight-like environments and scenarios." "The [Spacecraft] Contractor shall perform performance verification of Space Segment INR for each instrument (TBR). Space Segment INR performance verification is defined as photons in through Level 1-B products out.” | Deleted | Per the PRAD Section 6.1.1, "Spacecraft does not get explicit allocation of INR error, instead, it has to meet interface requirements." Please clarify your expectations for INR testing responsibility assuming a lack of detailed information from the instrument providers. |  |  | Concur, will be clarified
SOW-02 | 2007-09-12 | 2.5 pg 24 | The contractor shall provide all the resources to provide radioactive sources, in accordance with SEISS, for use with SEISS both on and off the spacecraft. |  |  | Does this requirement apply only to spacecraft and launch processing facilities? |  | Yes, this will be clarified
SOW-03 | 2007-09-12 | 2.5.2 and SCFPS606 PSPEC 3.9 | The Contractor shall furnish all resources to develop, deliver, integrate, test, and maintain all satellite, spacecraft, and instrument interface simulators. |  | 417-R-PSPEC-0014 sec. 3.8 calls out a satellite simulator and Sec. 3.9 calls out a spacecraft command and telemetry simulator. Please clarify simulator deliverable requirements. |  |  | This will be clarified.
SOW-04 | 2007-09-12 | 2.6 | The contractor shall furnish all resources to perform all integration and testing of the spacecraft bus, spacecraft and satellite. |  | These two statements appear to be in conflict with one another, i.e. Sec 2.6.2 seems to indicate the Government intends to perform instrument testing. Please clarify resources required by the contractor during instrument testing. |  |  | Concur. Clarified the exception of GFE Instrument CPTs and FPTs.
SOW-05 | 2007-09-12 | 2.6.2 | The Contractor shall allocate and support 30 days (TBR) dedicated to GFP instrument functional testing prior to the start of environmental testing. |  | See comment above. |  |  | Concur. Clarified the exception of GFE Instrument CPTs and FPTs.
SOW-06 | 2007-09-12 | 2.7 | The Contractor shall provide flight operations support at the NOAA SOCC from L-5 months (TBR) until delivery of the satellite to the Government (TBR). |  | Contract Sec F.1 indicates spacecraft delivery is March 2014 (L-9 months). Please clarify. |  |  | L-9 months represents 6 months of schedule margin to be held by the flight project. L-5 month is when support will most likely be required at the SOCC.
SOW-07 | 2007-09-18 | 2.1.5.3 |  |  | PDR date (and other significant system-level events/milestones) are not specified. |  | To facilitated synchronization of separate plans and proposals from the spacecraft and ground bidders, provide specific target dates for the major system-level events and milestones. | Do Not Concur. This info will not be available until Ground Contract IBR.
SOW-08 | 2007-09-18 | 2.2.6.2 |  |  | The spacecraft contractor develops and maintains the space-to-ground interface control document (ICD). | Will System Integration establish a Government/ Spacecraft/ Ground Interface Working Group? | Consider placing responsibility for inter-segment requirements with system integration. | No, there is no Systems Integrator.
SOW-09 | 2007-09-18 | 2.5.2 |  |  | While the spacecraft contractor has responsibility to develop and deliver a spacecraft simulator to each instrument contractor, and the responsibility to integrate the spacecraft and instrument simulators into a satellite simulator, there is no requirement for the spacecraft contractor to deliver satellite simulators to the ground segment contractor for integration into the ground segment mission management element. |  | Establish requirement for spacecraft contractor to deliver three (3) high fidelity satellite simulators to the ground segment contractor for integration into the Mission Management element at the primary and backup operational sites and the factory sustainment site. | This will be clarified.
SOW-10 | 2007-09-18 | 2.6 |  |  | The spacecraft contractor manages all integration and testing of the spacecraft bus, spacecraft, satellite, launch vehicle, and ground segment. |  | Consider placing responsibility for inter-segment requirements with system integration. | No, there is no Systems Integrator.
SOW-11 | 2007-09-18 | 2.6.5 |  |  | The spacecraft contractor supports five (5) spacecraft-to-ground ETE tests. However, prior to these tests there is no support for spacecraft-ground I&T specified as there is for spacecraft-LV I&T in Sec 2.6.4. |  | Add spacecraft contractor support of spacecraft-to-ground I&T prior to the spacecraft-ground ETE tests. | ETE Testing is spacecraft-to-ground I&T.
SOW-12 |  | SOW 1.3, Pg 2 and throughout proposal (such as, B1, F1, F4) |  |  |  | Please clarify the breakdown of the quantity, type, and purpose of each of the “Six Satellite Simulators” and the definition of the two sets of “Electrical System Test Equipment." |  | This will be clarified.
SOW-13 | 2007-09-18 | 2.7 |  |  | The spacecraft contractor provides flight operations support at the ground segment contractor's facility from L-5 months (TBR) to launch. | Please clarify intent of this flight operations support at the ground contractor's facility during this time period. | At L-5 months, the ground segment will be fully installed and tested at the NOAA SOCC. Flight operations support should be available to the ground segment contractor at the NOAA SOCC. | Duplicate of SOW-06
SOW-14 | 2007-09-10 | 1.2 Mission Overview | A general overview of the GOES-R system is given in figure 1. | <Deleted> | Figure 1 is not included in the document. |  | Delete reference to figure | Concur. Document will be clarified
SOW-15 | 2007-09-10 | 1.3 Scope | d) Two Flight Software Development Environments (FSDEs) (One for delivery and one for use by contractor) |  | DRFP SOW 1.3 calls for delivery of one FSDE and one to be kept by contractor. This does not align with DRFP B.1 Deliverables and F.1 Delivery schedule which indicates delivery of both FSDE to the customer. |  | Please clarify whether both delivered or one is for use by contractor. | F.4 revised to indicate that one remains with vendor
SOW-16 | 2007-09-10 | 1.5 Reference Documents | See comment | See Comment | The GOES-R TEMP and IIRP are listed as reference documents, but were not provided as part of the Draft RFP. |  | Provide TEMP and IIRP if available. | Will provide with other RFP reference documents
SOW-17 | 2007-09-10 | 1.6 Definitions and Terminology | The contractor shall coordinate all TBR requirement proposals with the government and other contractors. | See Comment | The SOW defines TBR as requirements where the contractors are expected to provide a recommendation to the government for the appropriate value. | Is the government looking for feedback for the TBR values prior to release of the Final RFP? If yes, what forum does the government envision for coordination of the proposed values? | Clarify treatment of TBR values. | No, the government is not looking for resolution of TBRs prior to contract award.
SOW-18 | 2007-09-10 | 2.1 Program Management & 2.1.1 Program Management Office | The contractor shall perform the necessary direct management functions…" | See Comment | The full text in Section 2.1 is repeated in 2.1.1, with the exception that Section 2.1.1 deletes the term "necessary" from the requirement, "The Contractor shall perform the necessary direct management functions and provide a management structure responsible for overall project control to assure that all requirements of this contract and all attachments are accomplished within cost and on schedule." |  | Suggest deleting one of the repeated requirements | Concur, text will be clarified.
SOW-19 | 2007-09-10 | 2.1.2 Resource Management | The Contractor shall track non-recurring and recurring costs separately. | See comment | There are several ways to delineate between non-recurring and recurring costs, does the government have a standard definition of non-recurring and recurring engineering? |  | Suggest clarifying the desired transition point from non-recurring to recurring. | The contractor will be directed to transition charges from SC#1 to SC#2 at a specific time when the majority of tasks are associated with SC#2.
SOW-20 | 2007-09-10 | 2.1.2.2 Information Technology Management | The contractor shall provide, utilize, and maintain video conferencing, …. | See comment | Is the contractor to provide the link between contractor and Government facilities for Video Teleconferencing or will this be provided as GFE? |  | Please clarify | The government will not provide the contractor with Video Teleconferencing GFE.
SOW-21 | 2007-09-10 | 2.1.5.3 PMR | Two requirements: "The Contractor shall prepare monthly PMR data packages for the purpose of reviewing the technical, risk, schedule, and cost status of the contract." and, The PMRs will be held every other month (bi-monthly) at the Government’s facility (TBR) through successful completion of the CDR, and then alternate between a Government designated facility and the Contractor’s facility. | See comment | The requirement seems to state that while a PMR data package is required monthly, the meeting is only held every-other month and then only at the government's facility until CDR, after which the PMRs will occur monthly at alternating locations. | Is it correct to assume that, after CDR, PMRs are held monthly, with the location alternating between the contractors facility and at the government's facility while before CDR the meeting is held only every-other month at the government's facility? | Please clarify. | The assumption is correct.
SOW-22 | 2007-09-10 | 2.1.5.10.1 Systems Definition Review (SDR) | The contractor shall prepare and conduct an SDR approximately…. | See comment | This section describes requirements to conduct an SDR. The Spacecraft CDRL defines submittal requirements in relation to System Requirements Review (SRR). | Does the Government desire an SDR or an SRR? | Please clarify review requirements. | Clarified in SOW/CDRL. SRR/SDR combined into one requirement.
SOW-23 |  | SOW 2.8, Pg 31 | The Contractor shall provide all management functions to perform all integration and testing of the spacecraft bus, spacecraft, satellite, launch vehicle, and ground segment. | The Contractor shall provide all management functions to perform all integration and testing of the spacecraft bus, spacecraft and satellite and support of special testing, launch vehicle to satellite I&T, and End to End (ETE) Testing. | We propose the suggested reconciliation of terminology. |  |  | Concur, RFP will be clarified.
SOW-24 | 2007-09-10 | 2.1.5.10.6 Program System Integration Review | The contractor shall support the government in the preparation and execution of the SIR… | See comment | What is the definition of the SIR? Is this a systems design review at the Program level (space, ground, instruments, operations, etc.)? |  | Please clarify intent and timing of the SIR. | RFP will provide SIR information.
SOW-25 | 2007-09-10 | 2.2.7 Image Navigation and Registration (INR) | The contractor shall perform performance verification of Space Segment INR for each instrument (TBR). Space Segment INR performance is defined as photons in through level 1b products out. | See Comment | It is not clear if the required performance verification is limited to INR or includes radiometric performance verification also. | Does this include the radiometric performance verification of Level 1b products or only the registration and geolocation? | Please clarify whether performance verification of Space Segment INR includes the radiometric performance verification of Level 1b products or only the registration and geolocation. | SOW clarified
SOW-26 | 2007-09-10 | 2.2.8 Contamination | The contractor shall establish and document contamination allowances and budgets for performance degradation of spacecraft optical and thermal contamination sensitive hardware are within the specification over the mission lifetime. | See Comment | This task requires the spacecraft contractor to establish contamination budgets for spacecraft optical and thermal hardware. | Is the intent of this task to develop a contamination budget at the satellite level (including instruments) or only at the spacecraft level? | Please clarify whether this includes any of the instrument contamination effects. | SoW clarified. The spacecraft contractor shall incorporate instrument conamination into satellite contamination efforts.
SOW-27 | 2007-09-10 | 2.3.6.2 | Missing paragraph. | See comment | Section numbering goes from 2.3.6.1 to 2.3.6.3. Section 2.3.6.2 is skipped or missing. |  | Suggest renumbering paragraphs or inserting missing text. | Numbering has been fixed
SOW-28 | 2007-09-10 | 2.4.9 Flight Software | The Contractor shall provide and maintain one FSDE, including hardware, software, procedures and associated documentation, to be used for the life cycle management, development and verification of the flight software at the Contractor's facility. | See comment | This paragraph also cites delivery of 1 FSDE to the government. This does not align with the Section RFP F.4 Delivery schedule which indicates both FSDEs remain at the contractor's facility. |  | Please clarify whether both FSDEs are delivered to the government or one is for use by contractor. | F.4 revised to indicate that one remains with vendor
SOW-29 | 2007-09-10 | 2.5 GSE | The contractor shall provide all the resources to provide radioactive sources, in accordance with SEISS radioactive Source Specification (TBS)… | See comment | This paragraph requires the contractor to provide the radioactive sources used by the SEISS per the to be supplied SEISS Radioactive Source Specification. | In order to scope this effort correctly in the proposal, additional detail is required on the requirements for the radioactive source, including handling and disposal of the material. Is the Radioactive Source Specification available? | An alternative and possibly lower cost option would be for the SEISS instrument provider to supply radioactive sources used during Instrument testing for use at the Satellite contractor's I&T facility. Sources would be well known and consistent with what was used at the instrument level during I&T. | Do Not Concur with suggested alternative. Radioactive Source Specification will be provided.
SOW-30 | 2007-09-10 | 2.5.1 GSE Software | The Contractor shall classify all Spacecraft Simulator software as Class B software. (TBR) | See comment | GSE Software calls for all Spacecraft Simulator software to be Class B, which is the same as flight software. This will have a very large cost impacts to simulator development. |  | Recommended changing GSE and simulator software to Class C consistent with NASA standard policies. | Concur, Simulator Software will be Class C. CDRL will be modified to ask for delieverable for Class B & C software.
SOW-31 | 2007-09-10 | 2.6.5 End-to-End (ETE) Testing | The contractor shall provide all resources for and execute five (5) ETE tests (TBR). | See Comment | The DRFP does not provide details as to the scope, duration, and complexity of the 5 ETE tests. Assessment of whether 5 are the appropriate number of tests, and development of the costs associated with executing these tests is impacted by not having the details of these tests. |  | Please provide additional detail on the scope, duration, timing and complexity of the ETE system tests. | Will be provided with RFP.
SOW-32 | 2007-09-10 | 2.7 Launch and Operations | The contractor shall provide all resources to perform a CPT at the launch processing facility. | The contractor shall perform a CPT at the launch processing facility. | The current wording could imply the contractor needs to supply facilities, power, etc. required to perform the CPT, and does not actually require a CPT to be performed at the launch processing facility. |  | Expand RFP Attachment M to include GFP items covered under the launch services contract. | Agree that SOW needs clarification. Do not Concur on addition to GFP for launch services.
SOW-33 | 2007-09-10 | 2.7 Launch and Operations | The contractor shall provide all resources to perform a LPT after mating to the launch vehicle. | The contractor shall provide perform a LPT after mating to the launch vehicle. | The current wording could imply the contractor needs to supply facilities, power, etc. required to perform the LPT, and does not actually require a LPT to be performed. |  | Expand RFP Attachment M to include GFP items covered under the launch services contract. | Concur on SOW language change. Do not Concur on addition to GFP for launch services.
SOW-34 |  | SOW 2.1.5.10.4, Page 13 | "…hardware…" | "…flight hardware…" | We suggest clarifying that only flight hardware cannot be manufactured prior to CDR. |  |  | Concur. Will clarify
SOW-35 | 2007-09-10 | 2.7 Launch and Operations | The contractor shall provide all resources to support satellite fueling. | The contractor shall support satellite fueling at the launch processing facility. | The SOW specifies that the contractor will provide all resources to support satellite fueling. Typically under NASA launch service contracts, the fuel, pressurants, launch support services, site training, scape suits, etc. are government furnished. |  | Please clarify launch site items that are common to all bidders on the GFP list. | Concur on SOW language change. Do not Concur on addition to GFP for launch services.
SOW-36 | 2007-09-10 | 2.7.2 Flight Training Simulator Support | The Contractor shall operate and maintain a simulator at the NOAA SOCC until the completion of orbital checkout of the satellite. | The Contractor shall operate and maintain a Satellite Simulator at the NOAA SOCC until the completion of orbital checkout of the satellite. |  |  | Suggest adding text to clarify simulator as the Satellite Simulator. | Concur. Will clarify
SOW-37 | 2007-09-10 | 3.0 Spacecraft #2 | This WBS element includes all sub-elements to level 3 as described in WBS element 1.0…. | This paragraph describes the tasks to be performed by the contractor for the design, analysis, fabrication, assembly, integration, testing, delivery, launch and operation of the GOES-S satellite. | The text references WBS elements rather than SOW tasks. It is not clear how the GOES-S effort is scoped given current language. |  | Suggest expanding SOW to reflect the subset of section 2.0 tasks required for GOES-S. | Concur. SOW has been updated
SOW-38 |  | SOW 2.3.4, Page 19, SCMAR 139 4.1.0-3 |  |  |  | There appears to be an inconsistency between the SOW and the SCMAR in the area of PRA. The SCMAR requires the contractor to perform a "full scope" PRA, integrating the instruments and ground system into the analysis. The SOW says that the contractor will provide data to assist the government in the development of the PRA. This implies that the government is doing the PRA with data inputs from the various contractors. Please clarify. |  | Concur. Deleted from SOW.
SOW-39 | 2007-09-10 | 2.7 Launch and Operations | The contractor shall provide all resources to support satellite fueling. | The contractor shall support satellite fueling at the launch processing facility. | The SOW specifies that the contractor will provide all resources to support satellite fueling. Typically under NASA launch service contracts, the fuel, pressurants, launch support services, site training, scape suits, etc. are government furnished. |  | Please clarify launch site items that are common to all bidders on the GFP list. | Clarified in SOW.
SOW-40 | 2007-09-10 | 2.7.2 Flight Training Simulator Support | The Contractor shall operate and maintain a simulator at the NOAA SOCC until the completion of orbital checkout of the satellite. | The Contractor shall operate and maintain a Satellite Simulator at the NOAA SOCC until the completion of orbital checkout of the satellite. |  |  | Suggest adding text to clarify simulator as the Satellite Simulator. | Concur. Will clarify
SOW-41 | 2007-09-10 | 3.0 Spacecraft #2 | This WBS element includes all sub-elements to level 3 as described in WBS element 1.0…. | This paragraph describes the tasks to be performed by the contractor for the design, analysis, fabrication, assembly, integration, testing, delivery, launch and operation of the GOES-S satellite. | The text references WBS elements rather than SOW tasks. It is not clear how the GOES-S effort is scoped given current language. |  | Suggest expanding SOW to reflect the subset of section 2.0 tasks required for GOES-S. | Concur. SOW has been updated
SOW-42 | 2007-09-12 | 2.4.7.3 Battery Life Testing | If cell voltage balancing is planned for flight, the qualification/life test battery shall incorporate the flight voltage balancing electronics and its planned flight use into the battery life testing. | If cell voltage balancing is planned for flight, the life test battery shall incorporate the flight voltage balancing electronics and its planned flight use into the battery life testing. |  |  |  | Concur. Will clarify
SOW-43 | 2007-09-12 | 1.3 & 2.4.7.1 and DRFP B.1, F.1, F.4 |  |  | Battery deliverable lists are inconsistent between SOW & contract. Please clarify. |  |  | Concur. Will clarify
SOW-44 | 2007-09-12 | 2.1.3 | The contractor shall manage and coordinate the resolution of problems and anomalies within the risk management system | The contractor shall manage and coordinate the resolution of problems within the issue and action management system. The contractor shall manage and coordinate the resolution of anomalies within the quality management system. | Suggest moving the first sentence to the program management section and the second sentence to the Quality assurance section. |  |  | Concur. Will clarify
SOW-45 | 2007-11-19 | 2.2.6.2 | "The Contractor shall develop and maintain a space-to-ground interface control document (ICD) between the space and ground systems …" |  | There are two space-ground ICDs in the CDRL table, SE-06 (Spacecraft to STDN / DSN ICD) and SE-07 (Spacecraft Communications Services ICD), both cover the communications interfaces. | Does the ICD called out in the SOW encompass both SE-06 or SE-07 or is another CDRL being referred to that would cover more than communications interfaces (e.g. magnetometer algorithm interfaces)? |  | Yes, this SOW statement covers SE-06 and SE-07.
Note on H2: Identify what action you recommend be taken to address/resolve the issues.

## WBS
Draft RFP Document Comments
ID# | Date | Document Section | From: | To: | Comments | Questions | Recommended Action Items | Disposition
WBS-1 | 2007-09-10 | 1.4.1 Spacecraft Management | The Spacecraft Management element includes all resources related to systems engineering, project management, and integration and test of the bus hardware and software…. | The Spacecraft Management element includes all resources related to the systems engineering and project management of the spacecraft… | Integration and test of the spacecraft bus is covered under WBS 1.6.1 and SOW paragraph 2.6.1. |  | Update 1.4.1 text | Change Completed in 417-R-SCWBS-0060_091207.doc
WBS-2 | 2007-09-10 | 1.4.4 Guidance Navigation and Control | It includes all related GN&C flight hardware, flight software and propulsion interfaces. | It includes all related GN&C flight hardware. It also includes interfaces for the flight software and propulsion subsystem. | Current wording implies the GN&C flight software is included in this WBS instead of 1.4.9. |  | Update 1.4.4 text | Change Completed in 417-R-SCWBS-0060_091207.doc
WBS-3 | 2007-09-10 | 1.4.6.2 Auxiliary Communication Services | Title: Auxiliary Communication Services | Title: Unique Payload Services | Inconsistency between the title of the WBS element (Auxiliary Communication Services) and the text (Unique Payload services). |  | Update title. | Change Completed in 417-R-SCWBS-0060_091207.doc
WBS-4 | 2007-09-10 | 1.7 Launch and Operations | This element includes the resources required to perform launch operations of the satellite. | This element includes the resources required to perform launch site processing, pre-launch flight operations support, and operations support through completion of satellite deployment and checkout. | Scope could be interpreted as limited to launch site processing of the satellite. |  | Expand definition of WBS element. | Change Completed in 417-R-SCWBS-0060_091207.doc
WBS-5 | 2007-09-12 | WBS, Sec. 1.4 | ` |  | Section 1.4 defines the spacecraft to include all design, analysis, fabrication, assembly, test efforts to deliver the spacecraft bus for integration with the instruments. SC BUS I&T is identified as 1.6.1 in the WBS. | 1.6.1 scope seems to be included in 1.4. Please clarify. |  | Clarification Completed in 417-R-SCWBS-0060_091207.doc
WBS-6 | 2007-09-18 | 1.6.6 |  |  | This section includes ETE testing. Per the SOW (2.6.5), this is a series of spacecraft-ground ETE tests in a mission operations context; however, there is no WBS element for spacecraft/ground I&T analogous to 1.6.5 Spacecraft/Launch vehicle I&T. |  |  | Clarification Completed in 417-R-SCWBS-0060_Baseline.doc
Note on H2: Identify what action you recommend be taken to address/resolve the issues.

## CDRL
Draft RFP Document Comments
ID# | Date | Document Section | From: | To: | Comments | Questions | Recommended Action Items | Disposition
CDRL-01 |  | CDRL Attachment (417-R-SCCDRL-0015), Page 9, Page 91 | System Requirements Specification | Spacecraft Requirements Specification | We suggest changing the name of CDRL SE-02 since this is a Spacecraft level document. |  |  | Concur. Will revise
CDRL-02 |  | CDRL Attachment (417-R-SCCDRL-0015), Page 9, Page 92 | Spacecraft Detailed Design Specification | Delete | We suggest deletion of SE-03 as a CDRL since requirements specifications below SE-02 (Level 3) are not government approved. |  |  | Disagree
CDRL-03 |  | CDRL Attachment (417-R-SCCDRL-0015), Page 93 | System Performance Verification Plan | Spacecraft Performance Verification Plan | We suggest changing the name of CDRL SE-04, Spacecraft Detailed Design Specification, since this is a Spacecraft level document. |  |  | Concur. Will revise
CDRL-04 |  | CDRL Attachment (417-R-SCCDRL-0015), Page 113 | "Provide the total mission flux over 6 years." | "Provide the total mission flux over 15 years." | We assume that the calculation of total mission flux should cover the entire mission duration. |  |  | Concur. Will clarify
CDRL-05 | 2007-09-10 | 2.0 Spacecraft CDRLs DIDs | GS-01, GS-02, GS-03, GS-04, and GS-05. | See comment | The Spacecraft F&PS identifies the Spacecraft Command and Telemetry Simulator (SCTS) as a deliverable. The DIDs for CDRLs GS-01, GS-02, GS-03, GS-04 and GS-05 address the Spacecraft Sim, SIIS and FSDE but not the SCTS. | Is a CDRL required for the SCTS? | Add a CDRL for the SCTS to the DIDs | Under consideration
CDRL-06 | 2007-09-10 | 2.0 Spacecraft CDRLs DIDs | GS-02, GS-03 | See comment | CDRLs GS-02 and GS-03 detail the Spacecraft/Instrument Interface Simulator (SIIS). But the Spacecraft F&PS has deleted all requirements for the SIIS. And there are no deliverable quantities for the SIIS called out in the DRFP | Is the SIIS a deliverable and should the requirements be detailed in the F&PS? | Align the DRFP, CDRLs and F&PS with respect to the Spacecraft/Instrument Interface Simulator (SIIS). | Concur. Will clarify
CDRL-07 | 2007-09-10 | 2.0 Spacecraft CDRLs DIDs | DR-10, Senior Management Readiness Review (SMRR) Data Package | See comment | DID for DR-10 refers to the SOW, but the SOW does not define an SMRR | Is there a contractual requirement for an SMRR? | If no contractual requirement for SMRR, recommend removing DR-10 from CDRL | Concur. Will clarify
CDRL-08 | 2007-09-10 | 2.0 Spacecraft CDRLs DIDs | PR-07, Independent Review Package | See comment | DID for PR-07 Independent Review Package references a GOES-N document and defines an independent review for launch readiness | Is the GOES-N document reference intended, or is there an update for GOES-R? Are the independent reviews related to MRR/FRR/LRR, etc.? |  | Deleted PR-07
CDRL-09 | 2007-09-12 | CDRL Section 2.0, page 17 |  |  | CDRL Section list CDRL SC-COMM-05 Communications Link Budgets to be delivered at proposal. | Section L & CDRL List inconsistent. Please clarify. |  | See comment 5 above
CDRL-10 | 2007-09-12 | CDRL Section 2.0, page 18 | Subsequent column for CDRL SC-ELEC-06 |  | Subsequent column has +F257 as a delivery date. | Is this an excel error or is there a missing delivery date? |  | Concur. Will fix error.
CDRL-11 | 2007-09-12 | CDRL Section 2.0, page 24 |  |  | CDRL Section list CDRL IT-20 Spacecraft/Launch Vehicle Interface Requirement Document (IRD), to be delivered with the proposal. | Section L & CDRL List inconsistent. Please clarify. |  | Will change to Preliminary at PDR, final at CDR.Prelim @L-40; Final @L-36
CDRL-12 | 2007-09-12 | CDRL Section 2.0, page 24 |  |  | CDRL Section list CDRL PS-02, Flight Operations Training Plan, to be delivered at proposal. | Section L & CDRL List inconsistent. Please clarify. |  | See comment 5 above
CDRL-13 | 2007-09-12 | CDRL Section 3.0, page 93 |  |  | Can the Government provide guidance on whether INR verification should be addressed as a whole and, if so, where in the proposal? For example should this topic be addressed as a whole in CDRL SE-04? Reference SOW 2.2.7 section L B1.5 & B4. | Please clarify. |  | CDRL and RFP will be clarified
CDRL-14 | 2007-09-12 | CDRL Section 3.0, page 286 | Provides initial verification requirements and compliance from the SCMAR, ICDs, SOW, F&PS, GFSC-STD-1000, etc. |  |  | Can the government provide guidance on what documents are include in "etc.?". |  | "etc." deleted.
CDRL-15 | 2007-09-12 | CDRL Section 3.0, page 286 | Provides initial verification requirements and compliance from the SCMAR, ICDs, SOW, F&PS, GFSC-STD-1000, etc. |  |  | When requirements are located in both the F&PS and GFSC-STD-1000 (e.g. mass margins), can guidance be provided on which requirements shall be in the verification matrix? |  | Reference to STD 1000 removed from DID.
CDRL-16 | 2007-09-12 | CDRL Section 3.0, page 286 | Provides initial verification requirements and compliance from the SCMAR, ICDs, SOW, F&PS, GFSC-STD-1000, etc. |  | Section 2.2.5 of the SOW does not call out GSFC-STD-1000 for requirements verification, but it is listed in CDRL DID IT-01. Please clarify. |  |  | Reference to STD 1000 removed from DID.
CDRL-17 | 2007-09-12 | CDRL Section 3.0, page 286 | Provides initial verification requirements and compliance from the SCMAR, ICDs, SOW, F&PS, GFSC-STD-1000, etc. |  |  | Is it appropriate to require verification compliance to a statement of work? |  | Yes, we would like tracibility or compliance of the SOW documented in DOORs.
CDRL-18 | 2007-09-18 | CDRL DID SE-07 | Spacecraft Communications Services ICD |  | The Space Segment appears to be responsible for defining the space-ground interfaces in the form of the Spacecraft Communications Services ICDs. |  | Consider placing responsibility for inter-segment requirements with system integration. | There is no plan to have a separate systems integrator.
CDRL-19 | 2007-09-18 | CDRL DID SE-09 | Data Format Control Book |  | Data Format Control Book is under space segment control. Impacts Ground Segment Mission Management element. The initial (and only) delivery is PER-30 days -- relatively late in spacecraft development and required by the ground segment sooner. |  | Consider placing responsibility for inter-segment requirements with system integration. | There is no plan to have a separate systems integrator.
CDRL-20 | 2007-09-18 | CDRL DID SE-10 | Command Encryptor M&O Manual |  | Command Encryptor M&O Manual also under space segment control. |  | Consider placing responsibility for inter-segment requirements with system integration. | There is no plan to have a separate systems integrator.
CDRL-21 | 2007-09-18 | CDRL DID SE-13 and SE-14 | INR Test Plan |  | INR Test Plan also under space segment control. |  | Consider placing responsibility for inter-segment requirements with system integration. | There is no plan to have a separate systems integrator.
CDRL-22 | 2007-09-18 | CDRL DID SC-CD&H-03 | Satellite Telemetry and Command Database |  | No Ground Segment input or coordination specified. |  | Consider adding that the format of this database is jointly developed with the Ground Segment Contractor. | Scope added to SOW.
CDRL-23 |  | CDRL Attachment (417-R-SCCDRL-0015), Page 4, PM-01 Initial Submission | 30 DACA | Proposal | We assume that the CDRL delivery schedule should align with the DRFP requirement for PM-01 initial submission with the proposal. |  |  | CDRLs submitted with proposal are for evaluation purposes only. They do not constitute the initial submission required after award. Delivery dates in CDRL apply to after contract award.
CDRL-24 |  | CDRL Attachment (417-R-SCCDRL-0015), Page 8, MS-01 Initial Submission Section L.12, Page 80 Section L14.3 Subsection A.5, Page 86 Section L.17, Page 108 | 60 DACA | Proposal | We assume that the CDRL delivery schedule should align with the DRFP requirement for MS-01 initial submission with the proposal. |  |  | See comment 5 above
CDRL-25 |  | CDRL Attachment (417-R-SCCDRL-0015), Page 11, MA-01 Initial Submission | PDR-30 days | Proposal | We assume that the CDRL delivery schedule should align with the DRFP requirement for MA-01 initial submission with the proposal. |  |  | See comment 5 above
CDRL-26 |  | CDRL Attachment (417-R-SCCDRL-0015), Page 22, IT-01 Initial Submission | PDR | Proposal | We assume that the CDRL delivery schedule should align with the DRFP requirement for IT-01 initial submission with the proposal. |  |  | See comment 5 above
CDRL-27 |  | Section L.12, Page 80 Section L14.3 Subsection B.4, Page 95 Section L.17, Page 108 CDRL Attachment (417-R-SCCDRL-0015), Page 9 | SE-05, Validation and Verification Plan | SE-04, System Performance Verification Plan | We assume that the DRFP should align with the CDRL list. |  |  | See comment 5 above
CDRL-28 |  | Section L.12, Page 80 Section L14.3 Subsection A7, Page 87 Section L.17, Page 108 CDRL Attachment (417-R-SCCDRL-0015), Page 9 | PM-57 | RM-01 | We assume that the DRFP should align with the CDRL reference numbers. |  |  | See comment 5 above
CDRL-29 |  | CDRL Attachment (417-R-SCCDRL-0015), Page 10, SE-16 Initial Submission | Proposal | PDR-14 days |  | Please clarify when SE-16 should be submitted. |  | See comment 5 above
CDRL-30 |  | CDRL Attachment (417-R-SCCDRL-0015), Page 24, IT-20 Initial Submission | Proposal | PDR-3 months |  | Please clarify when IT-20 should be submitted. |  | See comment 5 above
CDRL-31 |  | CDRL Attachment (417-R-SCCDRL-0015), Page 24, PS-02 Initial Submission | Proposal | SDR |  | Please clarify when PS-02 should be submitted. |  | PS-02 deleted.
CDRL-32 |  | CDRL Attachment (417-R-SCCDRL-0015), Throughout |  |  |  | The SOW does not require an SRR. However, the CDRL attachment has 18 references to an SRR. Please clarify whether or not an SRR is required and update the DRFP documents to reflect this direction. |  | SRR is combined with SDR.
CDRL-33 |  | Section L.12, Page 80 Section L14.3 Subsection A.8, Page 87 Section L.17, Page 108 CDRL Attachment (417-R-SCCDRL-0015), Page 11, Page 118 |  |  |  | The DRFP refers to MA-01 as a "Mission Assurance Implementation Plan" whereas the CDRL attachment refers to it as a "Mission Assurance Plan." Which title is preferred? |  | Changed to Mission Implentation Plan.
CDRL-34 | 2007-09-12 | CDRL Section 2.0, page 7 |  |  | For CDRL FM-01, the requirement is to submit data package minimum 6 week prior to review. In order to submit most responsive package possible, we recommend submit delivery 2 weeks prior to IBR review. |  |  | Due to the large amount of data needed to be reviewed prior to the IBR, the government will consider 4 weeks.
CDRL-35 | 2007-09-10 | 2.0 Spacecraft CDRLs DIDs (page 26) | PM-01, Program Management Plan, Initial 30 DACA | PM-01, Program Management Plan, Initial Submission: Proposal | Section L.12 and L.17 requires PM-01 as part of proposal Volume 5 | When is initial PM-01 due? | Recommend modifying CDRL to show initial PM-01 due with proposal | PM-01 will be due 30 DACA. CDRL due dates refer to post award requirements. Proposal submissions do not count as initial submissions
CDRL-36 | 2007-09-10 | 2.0 Spacecraft CDRLs | PM-04, Small Business Subcontracting Plan | See comment | This plan is required by the RFP to be included in Volume V and as Attachment G to the Offer Volume. |  | Please clarify if the document is to be provided in both volumes. | See SecL-03. CDRL should be included in Volume V.
CDRL-37 | 2007-09-10 | 2.0 Spacecraft CDRLs | PM-13, Safety and Health Plan | See comment | This plan is required by the RFP to be included in Volume V and as Attachment G to the Offer Volume. |  | Please clarify if the document is to be provided in both volumes. | See SecL-02. CDRL should be included in Volume V.
CDRL-38 | 2007-09-10 | 2.0 Spacecraft CDRLs | SE-04 System Performance Verification Plan Initial Submission: Proposal | See comment | CDRL Section 2.0 states SE-04 System Performance Verification Plan as due at Proposal, but it is not listed in the table in RFP Section L.12 (b) (1) and Section L.17 as required with the CDRL Volume submittal. |  | Please clarify initial submittal requirement of SE-04. | SE-04 is due 30 DACA. CDRL due dates refer to post award requirements. Proposal submissions do not count as initial submissions
CDRL-39 | 2007-09-10 | 2.0 Spacecraft CDRLs | SE-16, Contamination Control Plan, Initial Submission: Proposal | SE-16, Contamination Control Plan, Initial Submission: PDR - 30 days | CDRL Section 2.0 states SE-16 Contamination Control Plan as due at Proposal, but it is not listed in the table in Section L.12 (b) (1) or Section L.17 as required with the CDRL Volume submittal. |  | Recommend modifying CDRL to show initial SE-16 due at PDR-30 days | See CDRL-29 (hence CDRL-23). CDRL due dates refer to post award requirements. Proposal submissions do not count as initial submissions
CDRL-40 | 2007-09-10 | 2.0 Spacecraft CDRLs | SC-COMM-05, Communications Link Budgets, Initial Submittal: Proposal | See comment | CDRL Section 2.0 states SC-COMM-05 Communications Link Budgets as due at Proposal, but it is not listed in the table in Section L.12 (b) (1) or Section L.17 as required with the CDRL Volume submittal. |  | Please clarify initial submittal requirement of SC-COMM-05. | See CDRL-09 (hence CDRL-23). RFP has been updated to require this CDRL as part of proposal
CDRL-41 | 2007-09-10 | 2.0 Spacecraft CDRLs DID for CDRL IT-02 (p288/289) | IT-02, Spacecraft Launch Site Integration Plan. | See comment | The Astrotech processing facility is referenced twice as part of the content for IT-02 but not specified in the DRFP or SOW. | Will Astrotech be the baseline processing facilities for the GOES-R series Satellite? | Add Astrotech to the RFP and SOW to clarify prescribed launch processing facilities. | The payload processing facility currently under contract is Astrotech, however the RFP and all technical document will refer to the payload processing facilithy.
CDRL-42 | 2007-09-10 | 2.0 Spacecraft CDRLs | IT-20, Spacecraft/Launch Vehicle Interface Requirements Document, Initial Submission: Proposal | IT-20, Spacecraft/Launch Vehicle Interface Requirements Document, Initial Submission: SDR | CDRL Section 2.0 states IT-20 Spacecraft/Launch Vehicle Interface Requirements Document as due at Proposal, but it is not listed in the table in Section L.12 (b) (1) or Section L.17 as required with the CDRL Volume submittal. |  | Recommend modifying CDRL to show initial IT-20 due at SDR | See CDRL-30 (hence CDRL-23). CDRL updated to reflect due 40 months prior to LRD
CDRL-43 | 2007-09-10 | 2.0 Spacecraft CDRLs | MS-01, Spacecraft Master Schedule, Initial Submission: 60 DACA | MS-01, Spacecraft Master Schedule, Initial Submission: Proposal | RFP Section L.12 and L.17 requires MS-01 as part of proposal Volume 5 |  | Recommend modifying CDRL to show initial MS-01 due with proposal | See CDRL-24 (hence CDRL-23). CDRL due dates refer to post award requirements. Proposal submissions do not count as initial submissions
CDRL-44 | 2007-09-10 | 2.0 Spacecraft CDRLs | MA-01, Mission Assurance Implementation Plan Initial Submission: PDR-30 days | MA-01, Mission Assurance Implementation Plan, Initial submission: Proposal | Section L.12 directs MA-01 as part of proposal Volume 5 |  | Recommend modifying CDRL to show initial MA-01 due with proposal | See CDRL-25 (hence CDRL-23). CDRL due dates refer to post award requirements. Proposal submissions do not count as initial submissions
CDRL-45 | 2007-09-10 | 2.0 Spacecraft CDRLs | SC-COMM-05, Communications Link Budgets, Initial Submission: Proposal | SC-COMM-05, Communications Link Budgets, Initial Submission: PDR - 30 days | Section L.12 does not include SC-COMM-05 as part of Volume 5 |  | Recommend modifying CDRL to show initial SC-COMM-05 due PDR-30 days | See CDRL-09 (hence CDRL-23). CDRL due dates refer to post award requirements. Proposal submissions do not count as initial submissions
CDRL-46 | 2007-09-10 | 2.0 Spacecraft CDRLs | DR-01, System Requirements Review (SRR) Data Package | See comment | This section defines submittal requirements in relation to System Requirements Review (SRR) and DR-01 SRR Data Package is identified. SOW Section 2.1.5.10.1 Systems Definition Review (SDR) describes requirements to conduct an SDR. | Based on the Statement of Work, we assume that an SDR is the required review. | Please clarify review requirements and CDRL submittal relationships. | See CDRL-32
Note on H2: Identify what action you recommend be taken to address/resolve the issues.

## PSPEC
Draft RFP Document Comments
ID# | Date | Document Section | From: | To: | Comments | Questions | Recommended Action Items | Disposition
PSPEC-01 |  | SCFPS46, Section 3.2.5, Pg 10 | "Each autonomous Fault Management System detection test and corrective action shall be individually enabled and disabled by ground commands without affecting the health and safety of the satellite." | "Each autonomous Fault Management System detection test and corrective action shall be individually enabled and disabled by ground commands, as identified in the FMS description documentation (i.e., specific detection tests and constraints), without affecting the health and safety of the satellite." | We recommend documenting specific constraints on disabling detection tests to ensure health and safety of the satellite is maintained. |  |  | Government does not consider this necessary. FMS design process requires vendor to document specific constraints on disabling detection tests.
PSPEC-02 |  | SCFPS636, Section 3.2.3, Pg 10 |  |  |  | Can you clarify the sources and type of emissions referred to in SCFPS 636? The hardening needed for space nuclear radiation protection in the military JCS-1 standards (CJCSI6811.01A) requires significant changes in flight hardware. Heritage with military programs exists to bring these capabilities to GOES-R, but these requirements adversely affect mass, cost, and schedule risk, and thus, are not desirable for use on GOES-R unless essential to meet mission requirements. |  | Government is considering deletion of the requirement
PSPEC-03 |  | SCFPS31, Section 3.2.2.0-1, Page 10 |  | Add following sentence : Reliability at the end of 10 years of operations is computed as the reliability after 15 years (five years of storage and ten years of operation) divided by the reliability after 5 years of storage. | We recommend adding the identified wording to be consistent with the Magnetometer reliability requirement SCFPS432. |  |  | Government does not consider this necessary. Reliability defiition for Magnetometer is different because it is off during storage.
PSPEC-04 |  | SCFPS32, Section 3.2.2.0-2, Page 10 |  | Add following sentence : Reliability at the end of 10 years of operations is computed as the reliability after 15 years (five years of storage and ten years of operation) divided by the reliability after 5 years of storage. | We recommend adding the identified wording to be consistent with the Magnetometer reliability requirement SCFPS432. |  |  | Government does not consider this necessary. Reliability defiition for Magnetometer is different because it is off during storage.
PSPEC-05 |  | SCFPS614, Section 1.3.0-2, Page 1 |  |  |  | What backup CDAS location would you like us to use for our analyses until a final decision is made? |  | Use Fairmont, WV as a baseline until NOAA decides upon the location.
PSPEC-06 | 2007-09-10 | 3.8 Satellite Simulator | See comment | See comment | The Spacecraft to Instrument Interface Simulator (SIIS) has been deleted from the F&PS, and the RFP specifies delivery of 6 Satellite Simulators. | Does the Satellite Simulator replace the SIIS? The Satellite Simulators are significantly more capable and expensive than the SIIS and using them in their full configuration as a replacement for the SIIS is cost driver. |  | Satellite simulators are required. These simulators do not replace the SIIS.
PSPEC-07 | 2007-09-12 | 3.2.5.0-4 | ` |  |  | Was the intention to include failures in the magnetometer instrument? |  | Yes
PSPEC-08 | 2007-09-12 | 3.4.1.6.1 | Ground storage temperature of the cell/battery shall be 5±5°C. Transportation temperature of the cell/battery shall be 5±5°C |  |  | Is it correct to assume that these requirements apply to the cell and battery level, but not while the battery is mounted on the spacecraft? |  | Yes
PSPEC-09 | 2007-09-12 | 3.4.1.6.2 | The battery insulation resistance between mutually isolated electrical circuits shall be at least 100MΩ at a test voltage > 500 Vdc for at least 60 seconds. | The battery insulation resistance between mutually isolated electrical circuits shall be at least 100MΩ at a test voltage two times the battery voltage for at least 60 seconds. |  | Recommend test voltage be factored from the battery voltage rather than an absolute value. Recommend 2X. |  | The government does not intend to change the requirement
PSPEC-10 | 2007-09-12 | SCFPS518 | The Satellite Simulator shall incorporate Engineering Test Units (ETUs), i.e., non-flight qualified versions, of the on-board processors. |  |  | Is it correct to assume the "on-board processors" means the OBC? |  | Yes
PSPEC-11 |  | SCFPS706, Section 3.4.3.2, Pg 20 |  |  |  | What is the definition of ancillary data? What are the associated downlink rate and any latency requirements? |  | The ancillary data is defined in GRID 946 for GN&C attitude knowledge (quaternion), attidude rate, and orbit position(position & knowledge). The GIRD specifies representation, accuracy, and rates for each of these parameters. The ancillary packet rate is defined in GIRD 461.
PSPEC-12 |  | SCFPS705, Section 3.4.2.7, Pg 19 |  |  |  | Does this requirement imply full routing capability from any instrument to any other instrument (ABI, GLM, SEISS, SUVI, EXIS, Advanced Instrument, Magnetometer)? Is data to be routed to another instrument included in the science or telemetry data volumes specified in the UIIDs? What are the data rate that must be routed to/from instruments? What are the latency requirements on these instrument-to-instrument data transfers? On which protocol layer will the routing occur: GRDDP, SpaceWire, or CCSDS (by APID)? |  | The Government does not intennd to provide that detail at this time.
PSPEC-13 | 2007-11-05 | 1.5.d Mission Phases - Operations SCFPS 31, 32, 431, 432 |  |  | SCFPS states "The requirements for mission lifetime (5 years on-orbit storage and 10 years on-orbit operation), begins with the initiation of this phase." Oprerations Phase starts after satellite is declared operational (L+180 [TBR]). | Is the design life for the satellite supposed to be 15 years plus the length of the Post Launch Test phase (currently L+180 days [TBR])? Are the spacecraft, auxillary comm services, and magnetometer reliabilities to be calculated over this same period? |  | The design life requirement does not include the Post Launch Test Phase.
PSPEC-14 | 2007-11-05 | SCFPS 31 & 32 |  |  | Not clear if RD link is a part of Spacecraft bus (like TT&C) or is a part of Comm Payload (like GRB etc.) | For the purpose of calculating Spacecraft Bus reliability, should the RD link be considered as a part of the Spacecraft Bus or the Auxillary Comm Services? |  | see scfps20, RD is NOT under Auxiliary Comm
PSPEC-15 | 2007-11-05 | SCFPS 461 & 467 |  |  | The SCFPS Section says "3.5.3.1 Spacecraft Magnetic Requirements" but they appear to be Satellite level requirements. | Do the magnetic requirements specified in SCFPS 461 & 467 apply to the "spacecraft" or "satellite" as defined by the SCFPS? |  | 461 and 467 will be corrected
PSPEC-16 | 2007-10-17 | SCFPS26 | The spacecraft shall provide stationkeeping to maintain a North/South position of ±0.1º about the equator and East/West position of ±0.1º of the on-station longitude. |  | Does the ±0.1º apply to storage mode? |  |  | No.
PSPEC-17 | 2007-10-17 | SCFPS89 | The spacecraft power regulator and power supplies shall have gain and phase margins greater than or equal to the values given in the table below at the indicated project milestone. |  | Please confirm that PSR margins may be employed for power supplies which are unmodified relative to flight heritage. |  |  | We will evaluate this requirement with respect to heratiage hardware on a case by case basis.
PSPEC-18 | 2007-10-17 | SCFPS459 | The spacecraft shall provide for normal operations all telemetry necessary to calculate the magnetic field in spacecraft Body Reference Frame (BRF) coordinates, Geographic/Satellite Coordinates, and Earth Centric Inertial (ECI) coordinates with a latency of less than 5.0 seconds. |  | Please described how latency is evaluated. Please describe whether there is a latency allocation to ground algorithm processing separate from the spacecraft provided telemetry. |  |  | The total latency is the sum of any delay in the spacecraft between the time the data is sampled in the magnetometers and the time it is transmitted, the propagation delay (practicaly negligible), and the processing delay on the ground before the data appears on a "real time" CRT monitor or, if applicable, an alarm. The Magnetometer data will buffered in the instrument while a data packet is being assembled and transferred to the spacecraft. SCFPS72 provides in 3.2.15 Data Latency that the additional delay before tranmission to earth must be less than one second . The processing time on the ground to perform the matrix transformations on the resulting small packet is added to produce the total latency. The net effect of the spec of 5 seconds maximum data latency is a limit on packet size. There is an additional requirement that all of the ancillary data such as spacecraft state and attitude quaternions must be known a priori at the magnetometer data sample time.
PSPEC-19 | 2007-10-17 | SCFPS460 | The spacecraft shall provide algorithms to correct, with a latency of less than 5.0 seconds, for spacecraft generated magnetic fields that exceed ambient magnetic field accuracy requirements. |  | Please described how latency is evaluated. Please describe whether there is a latency allocation to spacecraft provided telemetry separate from the ground algorithm processing. |  |  | See SCFPS459. The total data latency is the sum of the on-board latency and the ground processing latency.
PSPEC-20 | 2007-10-17 | SCFPS459 | The spacecraft shall provide for normal operations all telemetry necessary to calculate the magnetic field in spacecraft Body Reference Frame (BRF) coordinates, Geographic/Satellite Coordinates, and Earth Centric Inertial (ECI) coordinates with a latency |  | What is the accuracy requirement for the telemetry used to express the magnetic field in the three indicated reference frames? Or alternatively, what is the required accuracy of the resulting magnetic field components expressed in the three indicated reference frames? Is the required accuracy the same during Storage and Normal Operations? |  |  | The accuracy requirement is 1 nanoTesla per axis in the orthogonal system embedded in the Magnetometer sensor. The vector in that system is then transformed to the BRF coordinates by a static transformation matrix and further transformed to ECI coordinates through the quaternions provided in spacecraft telemetry. There is not a "shall" statement for operation or non operation of the Magnetometer in storage mode although operation is sometimes desired. There is no stated requirement for attitude data to be available when in storage mode.
Note on H2: Identify what action you recommend be taken to address/resolve the issues.

## SCMAR
Draft RFP Document Comments
ID# | Date | Document Section | From: | To: | Comments | Questions | Recommended Action Items | Disposition
SCMAR-1 |  | MAR 2.1.1.0-1, Page 2 | "…hardware…" | "…flight hardware…" | We suggest clarifying that nonconformance reporting is only required for flight hardware. |  |  | The government does not intend to change the requirement
SCMAR-2 | 2007-09-10 | SCMAR191 | New draft version states "The contractor's QMS shall address software assurance functions for all software developed under this contract." | See Comment | This paragraph previously included "software and firmware". The definition of software provided in SCMAR836 still includes firmware. | Does "software" in this context include firmware, or is the change meant to relieve firmware from the QMS? | Provide clarification. | It does not relieve firmawre from the QMS
SCMAR-3 | 2007-09-10 | 8.2.0-7 | The following materials shall be considered as prohibited: a) Cadmium b) Zinc c) Pure Tin (>97% content) d) Silicone Greases and adhesive tapes e) Plasticized Polymers especially Polyvinyl Chlorides (PVCs) f) Particle/debris generating materials | Change requirement to read: The following materials shall be considered as prohibited: a) Cadmium plating b) Zinc plating c) Pure Tin (>97% content) d) Silicone Greases and adhesive tapes e) Plasticized Polymers especially Polyvinyl Chlorides (PVCs) f) Particle/debris generating materials | Several common alloys (e.g., brass, magnesium alloys ZK60A and AZ31B, aluminum 7075 alloy) contain zinc. Other alloys may contain small amounts of cadmium or zinc. Recommend changing the requirement to prohibit Cadmium and Zinc plating. |  |  | Agree / Will revise the SCMAR
SCMAR-4 | 2007-09-12 | 3.2.8.0-3 | All Ground Operations procedures to be used at the launch site shall be submitted to the GOES-R Project Office at GSFC in accordance with the CDRL |  |  | What is the applicable CDRL item for this requirement? |  | The reference to the CDRL will be deleted
SCMAR-5 | 2007-09-12 | 4.1.0-1 | The contractor shall prepare and deliver a Reliability Program Plan (RPP) in accordance with the CDRL, …. |  |  | Is it correct to assume this requirement is addressed in CDRL MA-26, Reliability and Probabilistic Risk Assessment (PRA) Program Plan? If not, please advise of the correct CDRL item. |  | Yes
SCMAR-6 | 2007-09-12 | 7.1.0-8 | The PMCP shall be delivered in accordance with the CDRL. |  | The applicable CDRL item for this requirement appears to be MA-04, Parts and Materials Control Plan. Is it correct to assume this requirement is addressed solely in MA-04? If so, there is no reference in the SCMAR for CDRL MA-05, Parts Control Program Plan. Are these CDRL items duplicative? |  |  | The released SCMAR will have this clarified, CDRLs MA-04 and MA-05 will remain.
SCMAR-7 | 2007-09-12 | 8.2.4.3.0-5 | When a limited-life piece part is installed in a subassembly, its usage shall be approved by the PMCB and included in the CDRL |  |  | What is the applicable CDRL item for this requirement? |  | MA-22
SCMAR-8 | 2007-09-12 | 11.1.0-4 | The contractor shall review, document and submit results of GIDEP reports and NASA advisories in accordance with the CDRL. |  | Please advise the appropriate CDRL item. MA-19, Responses to Alerts and MA-20, GIDEP Alert/NASA Advisory Disposition appear to be duplicative |  |  | MA-20 is correct / MA-19 has been merged into MA-20
Note on H2: Identify what action you recommend be taken to address/resolve the issues.

## GIRD & UIIDs
Draft RFP Document Comments
ID# | Date | Document Section | From: | To: | Comments | Questions | Recommended Action Items | Disposition
UIID-01 | 2007-09-11 | SUVI and EXIS UIIDs | See Comment | See Comment | Based on discussions held in the last SIS TIM, we were expecting the EXIS and SUVI UIIDs to be changed such that the EXIS unit and the SUVI sensor unit would have the same lengths and each require a single, non-adjacent, aft-side area on each instrument for thermal radiator purposes. These changes are not reflected in the current UIIDs. | Are UIID updates planned prior to the final RFP to reflect this change, or is this no longer a planned change to the SUVI/EXIS configuration? |  | The current plan is to change the envelope requirement, however not the physical length of the intstruments. This will be reflected in the RFP version if the UIIDs.
GIRD-01 | 2007-11-05 | GIRD832 and GIRD834 Page 45 |  |  | Specify maximum spacecraft and instrument particulate and molecular contamination contributions, respectively, to sensitive surfaces at end of life | Do these requirements refer only to contamination originating from the spacecraft and instruments? (i.e. do they exclude any particulate or molecular contamination contributions from any other source, including the launch vehicle fairing from spacecraft encapsulation through fairing jettison?) |  | The launch vechicle is also a contamination source.
GIRD-02 | 2007-09-12 | GIRD44 | The satellite will operate in a geosynchronous orbit (Semi-major axis of approximately 42,164 Km) located at either 75° or 135° west longitude. Normal on-orbit operations entail periodic… | The satellite will operate in a geosynchronous orbit (Semi-major axis of approximately 42,164 Km) located at either 75° or 137° west longitude. Normal on-orbit operations entail periodic… | Suggest make consistent with F&PS requirements. |  |  | Concur. Change will be made.
GIRD-03 | 2007-09-12 | GIRD44 | ...station keeping maneuvers that keep the satellite within a 0.5° inclination about the equator and within ±0.5° of the on-station longitude. | ...station keeping maneuvers that keep the satellite within a 0.1° inclination about the equator and within ±0.1° of the on-station longitude. | Suggest make consistent with F&PS requirements. |  |  | GIRD and F&PS reflect margin and are therfore consistent.. The instruments shall operate within +/-0.5 degrees and the S/C shall stationkeep within +/-0.1 degree.
Note on H2: Identify what action you recommend be taken to address/resolve the issues.

## IRD Comments
Draft RFP Document Comments
ID# | Date | Document Section | From: | To: | Comments | Questions | Recommended Action Items | Disposition
GenIRDCom-01 | 2007-09-10 | General |  |  | The IRDs provided with the Draft RFP include significant changes from the versions used during the PDRR phase. In some cases, these changes may drive cost into the spacecraft design. In other cases the changes require clarification. | Would the government entertain a communications TIM with the bidders prior to release of the Final RFP? | Hold a communications TIM with the contractors prior to Final RFP release. | Will consider if the government's schedule permits
GenIRDCom-02 | 2007-09-10 | 417-R-IRD-0001 to 0006 |  |  | All of the IRDs have Long Term frequency stability of 1e-7. Vendors typically spec +/-1ppm/year plus +/-4ppm temperature for TCXOs. Adopting this requirement could be a cost driver. |  | Suggest specifying Raw data link and telemetry downlinks to +/-20 ppm of downlink frequency and the other transponder links to have a "translation frequency" accuracy of +/-20 ppm. | Under Review. Will Consider.
GenIRDCom-03 | 2007-09-06 | 417-R-IRD-0001 to 0006 |  |  | Specification value of <1deg phase noise down to 100 Hz is tighter than TDRSS high data rate user req's and can be a cost driver. |  | Consider phase noise specification value of <2 deg to 10kHz (or 1k minimum). | Tight phase stability required for direct modulated low data rate links, particularly the 8-PSK 300 bps DCPR links. DCPR link requirement will not be relaxed. Other links under review.
SS-0DCS-01 |  | SDCSIRD120, 417-R-IRD-0005, Section 5.1.4, Page 13 |  |  |  | The indicated data rate for DCPC is 300 bps uncoded and 343 bps coded. There is no other mention of anything at 1800 bps. What does the requirement for the test to be run at 1800 bps relate to? Will this transponder carry other traffic that is not identified in the IRD? |  | 1800 bps reference incorrect. The bit rate will be 306.1 bps before coding and 350 bps after coding. The bit rate to use for error free testing is 350 bps.
SS-0DCS-02 |  | 417-R-IRD-0005, ALL |  |  |  | References to DGRS are made throughout IRD-0005 but there is no such acronym in the acronym list at the end of the document. It is assumed this is intended to be DRGS rather than DGRS. Please advise. |  | Will be corrected
SS-0DCS-03 |  | 417-R-IRD-0005, Throughout |  |  |  | All references to the DCPC downlink indicate that it is intended for reception by DGRS (assumed to be DRGS). Should this be to DCP (Data Collection Platform) instead? |  | See SS-DCS-2
SS-0DCS-04 |  | 417-R-IRD-0005, SDCSIRD54 Section 4.2.2 Page 7, and SDCSIRD70 Section 4.2.10 Page 8 |  |  |  | The two indicated sections appear to be in conflict with each other regarding the specifics of what modulation type is used. Should 8-PSK or BPSK modulation be used? |  | 300 and 1200 bps are 8-PSK, CDMA overlay is BPSK. Will clarify IRD.
SS-0DCS-05 |  | 417-R-IRD-4.1.4, Pages 6 and 7 |  |  |  | Please specify how many DCPR carriers are required for this test? |  | As specified in section 4.2.2. This method of specification accounts for the spatial isolations between GOES East and GOES West. No change required.
SS-0DCS-06 | 2007-09-10 | 5.1.1 DCPC Requirements Summary | See comment | See comment | The four channel CDMA approach, drives amplifier size and spacecraft power ( the required 20 dB space transmitter NPR with need for significant output power backoff coupled 6 dB power sharing, coupled with a 9 dB reduction in ground receive G/T specification). |  | Consider a single signal with the added code spreading to reduce power requirements. | Will eliminate NPR requirement and update the receive G/T. Will make some modifications of requirements of IRD.
SS-0DCS-07 | 2007-09-10 | 5.3.9.1 Automatic Gain Control | See comment | See comment | Specification value of 1 dB p-p AGC output power control over life (implies thermal aging and temp, dynamic range) could be a cost driver |  | Consider CONOPs that allows adjustment via spacecraft command at infrequent interval to maintain desired level vs over life. | Adjustment by command not precluded by IRD. No change required.
SS-0DCS-08 | 2007-09-10 | 5.1.1 DCPC Requirements Summary | See comment | See comment |  | Is the convolutional encoding gone for the DCPC? The required Eb/No does not seem to reflect it. |  | NOAA has not determined the specifications for the DCPC link. Contractor should assume only R-S 255,223 coding is used. No change required.
SS-0EMWIN-01 | 2007-09-10 | 3.1 Requirements Summary | See comment | See comment | Req'd Eb/No for ground receive in IRD listed as 7 dB while link budget entries add to 6.6 dB (2.6 Theory and 4.0 dB Gnd Implementation loss). Which should be used? |  | Update IRD and link budget to be consistent. | IRD requirement will be changed to 6.6 dB.
SS-0EMWIN-02 | 2007-09-10 | 5.3 Shared Spacecraft HPA | See comment | See comment |  | Reference the requirement stated in paragraph 5.3 " Shared S/C HPA": What kind of interference with LRIT is implied? Power robbing? The limiter mentioned inconsistent with 20 dB down sidebands as specified in paragraph 3.12. | Please clarify | See LRIT-2. No change required.
SS-0EMWIN-03 | 2007-09-10 | 5.10.1 Automatic Gain Control Mode | See comment | See comment | Specification value of 1 dB p-p AGC output power control over life (implies thermal aging and temp, dynamic range) could be a cost driver |  | Consider CONOPs that allows adjustment via spacecraft command at infrequent interval to maintain desired level vs over life. | Adjustment by command not precluded by IRD. No change required.
SS-0GLC3S-01 |  | SC3SIRD64, 417-R-IRD-0001, Section 3.2.6, Page 7 |  |  |  | What backup CDAS location would you like us to use for our analyses until a final decision is made? |  | Fairmont, WV
SS-0GLC3S-02 | 2007-09-10 | 3.3.3 Receive Ground Interference Loss | See comment | See comment | The Ground Interference loss of 3dB is high and could be a cost driver. | What drives the need cited in paragraph 3.3.3 Ground receive interference loss of 3 dB? |  | Coordination with Navy transmission drives this requirement.
SS-0GLC3S-03 | 2007-09-12 | SC3SIRD para 3.1.4 | The spacecraft shall meet all of its performance requirements with a pointing loss of 1.0 dB for the CDAS receive antenna. The satellite transmit pointing loss will be determined by the contractor and incorporated into the spacecraft contractor's ICD. |  | We suggest that using the terms "spacecraft contractor" and "ground contractor" and not just "contractor" in an IRD will help avoid confusion. |  |  | Concur. Will revise
SS-0GLC3S-04 | 2007-09-12 | SC3SIRD para 6.6.2.0-1 | The ranging signal path to the transmitter's phase modulator shall be commandable ON and | The ranging signal path to the transmitter's phase modulator shall be commandable ON and OFF. | The word "OFF" appears to have been omitted. |  |  | agreed, will change IRD
SS-0GLC3S-05 | 2007-09-12 | SC3SIRD |  |  |  | When will the backup CDAS be defined? |  | NOAA has not fixed a time table. It may be assumed that the link losses will be less than the losses from GOES West to CDAS.
SS-0GRB-01 |  | SGRBIRD20, 417-R-IRD-0002, Section 3.2, Page 4 |  |  |  | How is link margin defined for the uplink from CDAS or back up CDAS? What backup CDAS location would you like us to use for our analyses until a final decision is made? |  | The link must close with the specified performance with the combined uplink margin and atmospheric losses and the downlink atmospheric losses and margin, as per the link budget CDRL. It may be assumed that the link losses will be less than the losses from GOES West to CDAS.
SS-0GRB-02 |  | SGRBIRD18, 417-R-IRD-0002, Section 3.1.0-1, Page 4 |  |  | Waveform is "contractor specified". We assume this is a ground segment trade. We recommend specifying a waveform assumption for Spacecraft contractors to ensure consistency in link budget parameters. For Example: Modulation from "OQPSK or 8PSK", To: OQPSK (TBR). FEC, from "Contractor specified", To: TPC rate 7/8 (TBR) |  |  | This is a space segment trade-off. Will change IRD to allow trade-off between QPSK or OQPSK. FEC will remain contractor specified as "such as LDPC."
SS-0GRB-03 |  | SGRBIRD38, 417-R-IRD-0002, Section 3.11, Page 5 | 0.5 dB axial ratio | 1.6 dB axial ratio | We recommend this change to provide a satisfactory implementation. |  |  | Relaxation of requirement is likely but awaiting depolarization L band measurement results at Wallops
SS-0GRB-04 | 2007-09-10 | 3.1 Requirements Summary | See comment | See comment | The GRB link is specified to 31 Mbps including dual polarization antennas but nowhere is a data rate split defined. This data rate split is needed for link budget design. |  | update the specification to explicitly state if two simultaneous 15.5 Mbps links are required. See also question on link budgets | Clarified in Link Budget CDRL
SS-0GRB-05 | 2007-09-10 | 3.1 Requirements Summary | See comment | See comment | No required receive Eb/No specified. This information is necessary to size amplifiers. |  | Specify both the Theoretical Eb/No and Implementation loss for the envisioned modulation/code as a baseline for all to bid. | The coding can be selected by the spacecraft contractor so he has to determine the required Eb/No.
SS-0GRB-06 | 2007-09-10 | 5.10.1 Automatic Gain Control Mode | See comment | See comment | Specification value of 1 dB p-p AGC output power control over life (implies thermal aging and temp, dynamic range) could be a cost driver |  | Consider CONOPs that allows adjustment via spacecraft command at infrequent interval to maintain desired level vs over life. | Adjustment by command not precluded by IRD. No change required.
SS-0GRB-07 | 2007-09-11 | GRB 4.3 | See comment | See comment | The GRB uplink EIRP is specified to be 100 dBmi minimum. There is a 2 dB margin imposed on the uplink in addition to the propagation losses. For a spacecraft receive antenna configured to receive from Wallops and TBS backup site this results in a composite link C/No that is degraded by the uplink C/No. This results in a higher downlink power amplifier size on what is already a high power link. |  | Increase the GRB minimum uplink EIRP to 110 dBmi. This will make the uplink degradation of the composite C/No fairly insignificant and remove the need for increased downlink power to compensate, thus reducing risk. Increase uplink EIRP in the link budget template as well. | Will consider change in uplink power if final link budget shows significant impairment of total link due to uplink power.
SS-0GRB-08 | 2007-09-12 | 417-R-IRD-0002 SS to GRB IRD para. 4.3 Uplink G/T | The spacecraft shall meet all of its performance requirements for the GRB uplink with a platform uplink EIRP of 100 to 110 dBmi. |  |  | The GRB EIRP is 100 to 110 dBmi in the IRD. In the Link Budget Template, it says it is 99.25 dBmi. We are currently assuming the lower figure (99.25) and that it is per polarization. Is this correct? |  | Yes, the lower figure is per polariztion and includes all antenna losses. The link budget subtracts out polarization and pointing losses which are seperately itmeized in the IRD. No change required.
SS-0LRIT-01 | 2007-09-10 | 3.1 Requirements Summary | See comment | See comment | IRD required Eb/No of 3.6 dB inconsistent with EMWIN value of 7 dB. Also, this value is inconsistent with LRIT link budget entries totaling 4.9 dB (2.6+2.3). |  | Update this for intended value, which should be similar to EMWIN value, which is presently 7.0 dB. | Requirement correct due to different ground equipment.
SS-0LRIT-02 | 2007-09-10 | 5.3 Shared Spacecraft HPA | See comment | See comment |  | Reference the requirement stated in paragraph 5.3 " Shared S/C HPA": What kind of interference with EMWIN is implied? Power robbing? The limiter mentioned is inconsistent with 20 dB down sidebands as specified in paragraph 3.12. | Please clarify | Power robbing can occur if EMWIN and LRIT share a common output SSPA.
SS-0SAR-01 |  | SSARIRD41, 417-R-IRD-0006, Section 3.12, Page 5 | AR = 1.0 dB | AR = 2.0 db | Relaxing the requirement as recommended can significantly reduce the net cost and weight of the comm. payload design while maintaining other link parameters. |  |  | Requirement will not be relaxed.
SS-0SAR-02 | 2007-09-10 | 3.1 Requirements Summary | See comment | See comment | 1 dB RCP transmit axial ratio could be a cost driver |  | Consider change to 2 dB to reduce risk. | Requirement will not be changed.
SS-0SAR-03 | 2007-09-10 | 3.1 Requirements Summary | See comment | See comment | Downlink freq listed as 1544.5 vs previous IRD specified 1544.55 |  | Correct IRD to 1544.55 if this is still correct | the correct value is 1544.50 MHz.
SS-0SAR-04 | 2007-09-10 | 5.9 Downlink Polarization Loss | See comment | See comment | Downlink polarization loss paragraph 5.9 seems inconsistent at 4.1 dB for this RHCP to RHCP link. Link equations worksheet has 0.6 dB. |  | Recommend change to a link loss value consistent with 2 dB transmit axial ratio (recommended above) and 3 dB axial ratio LUT receiver terminal value. This calculates to recommended link value is 0.4 dB. | The downlink SAR axial ratio corrected
SS-0SAR-05 | 2007-09-10 | 5.10.1 Automatic Gain Control Mode | See comment | See comment | Specification value of 1 dB p-p AGC output power control over life (implies thermal aging and temp, dynamic range) could be a cost driver |  | Consider CONOPs that allows adjustment via spacecraft command at infrequent interval to maintain desired level vs over life. | Adjustment by command not precluded by IRD.
SS-0SAR-06 | 2007-09-10 | 3.12 Axial Ratio | See comment | See comment | 1 dB RCP receive axial ratio at UHFcost be a cost driver |  | Consider change to 2 dB to reduce risk. | Uplink UHF AR requirement driven by DCPR requirement.
Note on H3: Identify what action you recommend be taken to address/resolve the issues.

## Link Budget Equations
Draft RFP Document Comments
ID# | Date | Document Section | From: | To: | Comments | Questions | Recommended Action Items | Disposition
LBE-01 | 2007-09-10 | DCPR at 1.2k | See comment | See comment | Cell G30 downlink polarization loss at 2.5 dB appears high by 2 dB for linear to linear polarization link.. Conflicts with same cell in "DCPR at 0.3k" worksheet value of 1 dB |  | Correct both worksheets to assume a linear to linear polarization link. consider using 0.5 dB value to reflect 20 deg misalignment. If contractor chooses circular transmit polarization then contractor can make the required adjustment based on their axial ratio to linear | Polarization loss changed to 1 dB
LBE-02 | 2007-09-10 | DCPR at 1.2k | See comment | See comment | IRD Uplink transmitter polarization loss and pointing loss specified as 1 dB and 0.5 dB not found in link budget. |  | Update/confirm spreadsheet | The average uplink power of 250 carriers is 41 dBmi which includes one carrier at 37 and 43 dBmi for 300/1200 bps links respectively. This includes pointing and polarization loss.
LBE-03 | 2007-09-10 | DCPR at 1.2k | See comment | See comment | Link budget for 1.2k case Uplink Atm loss of 0.2 dB does not agree with IRD 0.7 dB. |  | Correct/confirm spreadsheet value | Link budget corrected
LBE-04 | 2007-09-10 | SAR | See comment | See comment | Cell C9 on EIRP missing the 0.5 dB pointing loss of IRD paragraph 4.7 |  | Correct/confirm spreadsheet for pointing loss | Cells C8 and C9 corrected. Polarization loss of 3 dB due to RHC/Linear loss clarified in link budget.
LBE-05 | 2007-09-10 | SAR | See comment | See comment | IRD Req'd Eb/No is 4.6 dB vs link worksheet has 4.9 dB (2.6+ 2.3) |  | Correct/confirm spreadsheet | Cell C39 corrected
LBE-06 | 2007-09-10 | DCPC | See comment | See comment | IRD ground receive has pointing loss of 0.5 dB, link template has 0 |  | Correct/confirm spreadsheet | IRD will be corrected to agree with link budget.
LEB-07 | 2007-09-12 | Comm Link Budgets 125771-AMEND-001-001 file, CDA command sheet |  |  | C/No calculation for CDA CMD appears to double count the antenna gain. (Antenna gain already included in G/T calculation earlier) |  |  | Will correct link budget
LEB-08 | 2007-09-10 | GRB Link | See comment | See comment | Downlink EIRP cell G17 subtracts losses twice |  | Correct/confirm formula | Link budget corrected
LEB-09 | 2007-09-10 | GRB Link | See comment | See comment | Cell G36 calculating Eb/No uses the full 31 Mbps vs assumption of half that rate on two simultaneous channels |  | Specify per polarization requirement which is what the link budget quantifies. | Link budget clarified
LEB-10 | 2007-09-10 | GRB Link | See comment | See comment |  | Cell G40, which calculates link margin does not use Eb/No degraded for uplink or downlink increased cross polarization interference due to atmospheric effects. Is the intent to allow the increased link margin requirement to cover this degradation while allowing for the uncertainties of the L-band atmospheric effects? | Please clarify | Method of calculation now includes cross polarization degradation
LEB-11 | 2007-09-10 | GRB Link | See comment | See comment | Cell G38 "Theoretical Eb/No" entry is color coded to indicate contractor entry while implementation loss is supplied in cell G39. IRD suggests a LDPC code for this link. |  | Specify both the Theoretical Eb/No and Implementation loss for the LDPC modulation/code. | The FEC and modulation are contractor specified. Cell C7 is also tan for this reason. No change required.
LEB-12 | 2007-09-10 | GRB Link | See comment | See comment | The link budget has separate entries for transmit polarization loss and receive polarization loss (G13 , G27). polarization loss is usually determined once at the link level based on the interaction of the transmit and receive antenna |  | Change budget to a link polarization loss or provide direction on how to apportion it separately to transmit and receive. Note this comment applies to almost all the links which seem to follow this same format. | Method of calculation changed.
LEB-13 | 2007-09-10 | GRB Link | See comment | See comment | Cell C5 contains 31 Mbps value for link that is inferred to be simultaneous on 2 channels |  | Change entry to reflect the intended data rate per channel. | Changed cells C5 and C6 to clarify. Downlink changed as per previous comment
LEB-14 | 2007-09-10 | DCPR at 0.3k | See comment | See comment | Cell G6 specifies a Transmitter power of 6.78W where calculation result usually goes. |  | Correct/confirm spreadsheet | link budget corrected
LEB-15 | 2007-09-10 | DCPR at 0.3k | See comment | See comment | IRD Uplink transmitter polarization loss and pointing loss specified as 1 dB and 0.5 dB not found in link budget. |  | Correct/confirm spreadsheet | The average uplink power of 250 carriers is 41 dBmi with one carrier at 37 and one at 43 dBmi for 300/1200 bps links respectively. This includes pointing and polarization loss. IRD and link budget will be clarified.
Note on H2: Identify what action you recommend be taken to address/resolve the issues.