PERFORMANCE EVALUATION PLAN

FOR

R SERIES

GEOSTATIONARY OPERATIONAL ENVIRONMENTAL SATELLITES (GOES)

SPACECRAFT

SIGNATURE PAGE FOR

PERFORMANCE EVALUATION PLAN

FOR GOES R SERIES SPACECRAFT

_________________________________   			______________________________

Fee Determination Official					Date

_________________________________   			______________________________

Procurement Officer						Date

CONTENTS

PART                                                   						Page

I.		Introduction								4

II.		Organization Structure						6

III.		Evaluation Requirements						9

IV.		Method for Determining Award Fee					10

V.		Changes in Plan Coverage						12

ATTACHMENTS

III-A	Evaluation Periods and Available Fee

III-B	Performance Evaluation Factors and Performance Evaluation Criteria

III-B.1	Performance Criteria for Technical Performance Evaluation Factor

III-B.2	Performance Criteria for Management Performance Evaluation Factor

III-B.3 Performance Criteria for Cost Performance Evaluation Factor

III-B.4 Performance Criteria for On Orbit Performance Evaluation

III-C	Grading Table

IV-A	General Instructions for Performance Monitors

IV-B    Actions and Schedules for Award Fee Determinations

I.	Introduction

1.	This plan covers the administration of the award fee provisions of Contract No. NNG07XXXX, dated TBD, with TBD.  The contract was awarded in accordance with the provisions of RFP NNG07193033R.

2.	Contract Summary

a.	The basic contract is for the development of two flight model (FM) spacecraft (GOES R and GOES S).  The contractor is also required to provide pre-launch, launch and post-launch support.

b.	The term of the contract is from the effective date of the contract through the tenth year of performance of the spacecraft that is launched last.

- The estimated cost and fees, set forth in Contract Clause B.4, Estimated Cost and Award Fee, of the contract, are subject to equitable adjustments arising from changes or other contract modifications.

- Award fee is earned based on final overall performance for each FM and on-orbit performance of each FM.

- This contract contains NFS Clause 1852.216-77, “Award Fee for End Item Contracts,” and the award fee determination is considered interim pending the final award fee determination as described below.

- Provisional award fee payments will not be made pending the determination of the amount of fee earned for the evaluation period.

3.	Award Fee Plan Summary

a.  The award fee payable will be determined periodically by the Fee Determination Official (FDO) in accordance with this plan.

b.  Award fee will be divided among five major pools:

1.   Non-Recurring Effort (NRE) and FM 1

- FM 2

- Post-Delivery Support

c.  The award fee in the each of pools 1-5 will be divided among technical performance (40%), management performance (35%) and cost control (25%).  Fee will not be straight-lined throughout the periods.  Rather, fee will be spread to be concomitant with the magnitude and priority of activities throughout the program life.

d.  There are three types of award fee evaluations:  Interim, Final and On-Orbit.  Interim evaluations are performed through completion of activities under each FM pool and the NRE pool.  Final evaluations are conducted for Pools 1- 4 after the interim evaluations are complete.  Final evaluations are also conducted for Pool 5 and for on-orbit performance.  Final evaluations for Pools 1- 4 are performed after the completion of post launch checkout for each FM and provide for a "look back" feature.  Final evaluations for Pools 1- 4 result in final award fee determinations for pre-on-orbit performance and establish the amount of award fee available for on-orbit performance.  The respective allocation of fee for pre-on-orbit performance and on-orbit performance under this final evaluation is 50% and 50%.  On-orbit performance evaluations are performed during the on-orbit performance (which may include on-orbit storage) of each FM.  Each evaluation of on-orbit performance is considered to be a final evaluation.  Each evaluation of post-delivery support is considered to be a final evaluation.

e.  Interim award fee evaluations for NRE and FMs are based on technical, management and cost performance.  Evaluations will include milestone performance, technical performance, Project management, business management and cost control.  The score for each interim evaluation will determine the amount of fee that may be paid provisionally for pre-on-orbit performance   Fee not provisionally paid can be 1) reserved and made available to be earned at the final evaluation; or 2) reserved and made available to be earned for special events.  Disposition of fee not provisionally paid during a period is at the discretion of the FDO.  If the score for an interim evaluation is 60 or less, no provisional fee is paid and the all fee for the period is reserved for the final evaluation.  Fee that is paid provisionally is not considered to be earned by the contractor.   The amount of fee earned for pre-on-orbit performance is determined at the final evaluation.  The amount of fee earned for on-orbit performance is determined periodically during on-orbit performance.

f.  The final evaluation for Pools 1- 4 is the last evaluation of technical, management and cost performance for NRE and each FM.  The final evaluation for each pool takes place upon the completion of the post launch checkout of the respective FM.  In the final evaluation, there is a "look back" feature.  This means that total performance under the pool is evaluated to determine the final total award fee score for the pre-on-orbit performance and the total fee available for on-orbit performance.  The total award fee pool, less any fee that was previously reserved for special events, is available to be earned for pre-on-orbit performance and provisionally earned for on-orbit performance.  If there are any differences between the cumulative previous provisional payments and the final evaluation, those differences shall be reconciled in accordance with Contract Clause G.4, Award Fee for End Item Contracts, paragraph (c)(4).

The provisions in this item f do not apply to the last evaluation for post-delivery support or the last evaluation for on-orbit performance.  Each evaluation for post-delivery support and on-orbit performance is considered to be a final evaluation.

g.  Award fee evaluations for post-delivery support begin after delivery of the first FM.  There is no look-back feature for post-delivery support; award fee evaluations for each period of post-delivery support are stand-alone evaluations and are final.  Award fee evaluations are based on technical, management and cost performance.  Evaluations will include milestone performance, technical performance, Project management, business management and cost control.   Unearned fee cannot be reserved for other purposes.

h.  On-orbit evaluations are made based on on-orbit performance, which begins after launch.  On-orbit performance is evaluated against the evaluation criteria in Attachment III-B.4. Provisionally paid on-orbit fee will be finalized with each on-orbit evaluation period.  In the event of a launch failure or other catastrophic failure during the first period of on-orbit performance for which the Contractor is not responsible, in whole or in part, the associated on-orbit fee for that mission will be finalized in full.  In the event of a catastrophic failure for which the Contractor is not responsible, in whole or in part, after the first award fee period, the FDO shall determine what portion, if any, of the on-orbit fee shall be finalized based upon previous on-orbit performance evaluations and any other data that indicates what the future performance would have been.  In the event of catastrophic failures for which the Contractor is in part responsible, but not wholly responsible, the FDO shall determine what portion, if any, of the on-orbit fee shall be finalized.  Each on-orbit evaluation is considered to be a final evaluation.  The Contractor shall pay back to the Government any provisional payments of award fee for on-orbit performance that were not earned for that period, in accordance with paragraph (c)(4) of Contract Clause G.4, Award Fee for End Item Contracts.

i. The determination and methodology for determining award fee are unilateral decisions made solely at the discretion of the Government.

j.  The Government will maintain a matrix that will reflect the amount of award fee (available and earned) for each interim and on-orbit period.  Updates to the matrix will be provided to the Contractor.  Updates to the matrix do not require a change to this PEP in accordance with Section V.

k.  The FDO may unilaterally change the matters in this plan, provided the contractor receives notice of the changes 30 days prior to the beginning of the evaluation period to which the changes apply.

l.  There will be no formal structured hardware performance incentive as set forth in the NFS.  This exception was granted by the GSFC Director, in accordance with the NFS.  The reasons for the exception are stated in the request for the exception.

II – Organization Structures for Award Fee Administration

The following organizational structure is established for administering the award provisions of the contract.

A.  	Performance Evaluation Board (PEB)

The PEB primary responsibilities of the Board are to:

(1)	Conduct ongoing evaluations of contractor performance based upon Performance Monitor Reports and such additional performance information as may be obtained from the contractor and other sources.  The PEB will evaluate the contractor's performance according to the standards and criteria stated in this performance evaluation plan;

- Submit an award fee letter to the FDO covering the PEB's findings and recommendations for each evaluation period; and

- Recommend for approval by the FDO proposed changes in the performance evaluation plan.

B.	Fee Determination Official (FDO)

The FDO is the Director, Flight Programs and Flight Projects at the NASA/Goddard Space Flight Center (GSFC) in Greenbelt, Maryland.  The FDO may designate an Alternate FDO when appropriate.

The primary responsibilities of the FDO are to:

- Consider the PEB findings for each evaluation period and discuss it with the PEB chair and, if appropriate, with others such as the contractor;

- Determine the Award Fee earned and payable for each evaluation period as addressed in Section IV and ensure that the amount and percentage of award fee earned is commensurate with the contractor's performance.  Any variance between the PEB recommendation and FDO determination must be justified and documented in the official contract file;

- Issue and sign the award fee determination letter for the evaluation period, specifying the amount of award fee determined and the basis for that determination;

- Change this plan as addressed in Section V as appropriate; and

(5)	Appoint the voting members of the PEB by memorandum.

C.	Performance Evaluation Board (PEB) Chairperson

The PEB Chairperson is the System Program Director (or Acting System Program Director) in the GOES R Program Office at NASA/GSFC in Greenbelt, Maryland.  The primary responsibilities of the PEB Chairperson are to:

- Appoint non-voting members, if appropriate, to assist the PEB in performing its functions, e.g., a recording secretary;

- Appoint performance monitors for the contract effort and assure that they are providing appropriate instructions and guidance;

- Request and obtain performance information from other units or personnel involved in observing contractor performance, as appropriate;

- Call on personnel from various organizational units to consult, as needed, with the PEB;

- Assume responsibility for the actual preparation and approval of the award fee letter and other documentation such as PEB minutes;

- Ensure the timeliness of award fee evaluations; and

- Recommend appropriate changes in this plan for consideration, as addressed in Section V.

D.	Contracting Officer’s Technical Representative (COTR)

The COTR will be located at the NASA/GSFC facility in Greenbelt, Maryland.

The primary responsibilities of the COTR are to:

- Receive and analyze the Monitor Evaluation Reports submitted by the

Performance Monitors;

- Monitor, evaluate, and assess Contractor performance;

- Prepare the Contract Performance Summary Report for the CO;

- Prepare the award fee determination letter for the FDO’s review and signature in coordination with the CO;

- Complete the technical portion of the annual NF 1680, Evaluation of Performance; and

- Recommend appropriate changes in this plan for consideration, as addressed in Section V.

# E.        Performance Monitors

Performance monitors will be designated by the PEB Chairperson to each performance area to be evaluated.

The primary responsibilities of the Performance Monitor are to:

- Monitor, evaluate, and assess contractor performance in assigned areas and in accordance with this award fee plan;

(2)	Periodically prepare a Performance Monitor Report for the PEB that will be submitted to the Contracting Officer Technical Representative, as described in section "II. D. Contracting Officer Technical Representative (COTR), " or others as appropriate; and

(3)	Recommend appropriate changes in this plan for consideration, as addressed in Section V.

- Functional Monitor/Performance Evaluation Coordinator

The Functional Monitor (FM) will be the contract specialist or contracting officer who is responsible for contract at NASA/GSFC in Greenbelt, MD.

The primary responsibilities of the FM are to:

- Advise the PEB on Cost-Plus-Award-Fee rating standards, policies, and procedures and ensure the consistent application of Agency policy in these matters;

- Receive and analyze the Performance Monitor Evaluation Reports submitted by the Performance Monitors via the assigned COTR;

- Monitor, evaluate, and assess Contractor performance;

- Consider changes to this plan and recommend those he/she determines appropriate for presentation to the FDO; and

- Attend all PEB meetings and record the findings of the PEB and assist the COTR in preparing all PEB correspondence for the FDO.

III.  Evaluation Requirements

The applicable evaluation requirements are attached as indicated below:

Requirement				Attachment

Evaluation Periods and Available

Award Fee for Each Period		           		 III-A

Performance Evaluation Factors and

Performance Evaluation Criteria        			III-B

Performance Criteria for Technical

Performance Evaluation Factor 			III-B.1

Performance Criteria for Management

Performance Evaluation Factor                      		III-B.2

Performance Criteria for Cost

Performance Evaluation Factor                     	 	III-B.3

Performance Criteria for On-Orbit

Performance Evaluation Factor                   	   	III-B.4

Grading Table                                 			III-C

General Instructions for Performance			IV-A

Monitors

Actions and Schedules for Award Fee		IV-B

Determinations

The percentage weights indicated in Attachment III-B and Attachment III-C grading table are quantifying devices.  Their sole purpose is to provide guidance in arriving at a general assessment of the amount of interim or final award fee earned.  In no way do they imply an arithmetical precision to any judgmental determination of the contractor's overall performance and amount of interim or final award fee earned.

IV. 	Method For Determining Award Fee

A determination of the award fee earned for each evaluation period will be made by the FDO within 45 days after the end of the period.  The method to be followed in monitoring, evaluating, and assessing contractor performance during the period, as well as for determining the award fee earned or paid, is described below.

A.  Interim Award Fee Evaluations

1.	Monitors will evaluate and assess contractor performance and discuss the results with evaluation coordinators and contractor personnel as appropriate, in accordance with the General Instructions for Performance Monitors, Attachment IV-A, and the specific instructions and guidance furnished by the PEB Chair.

2.	Monitors shall prepare Individual Event Reports on a Goddard Form 18-15 or similar format, as necessary to document performance, but as a minimum on a semi-annual basis.  These reports shall be submitted to the appropriate Evaluation Coordinator following each evaluation period.

3.	The Evaluation Coordinators will request and obtain performance information from other units or personnel normally involved in observing contractor performance, as appropriate.  The Evaluation Coordinators will number, validate, and assess the significance of the event reports and other information for submission to the PEB.  The Evaluation Coordinators will be responsible for resolving any differences between a Goddard report and a contractor report.  Documentation of the contractor's overall performance shall be prepared by the Evaluation Coordinators in accordance with Attachment IV-A.  All members of the PEB shall receive a copy of this package, no later than 24 hours prior to the PEB meeting.

4.	Within 15 days after the end of the evaluation period, the contractor may submit a "Self-Evaluation" to be considered by the PEB.  The contractor is also afforded an opportunity to present a brief overview of their performance to PEB members at the scheduled meeting.

5.	Semi-annually, the PEB will meet and perform an in-depth review of the Contractor's Self Assessment (if one is provided), the Evaluation Coordinator's report and other performance information as appropriate.

6.	The PEB shall discuss all the performance information it has obtained and determine a score for each factor.

9.	Following the PEB meeting, the COTR will summarize the PEB's findings in a letter to the contractor that will be signed by the FDO.

10.	The FDO may meet with the PEB Chairperson, Contracting Officer, COTR and other personnel as appropriate to discuss the PEB findings and recommendation.   The FDO may also consider additional information from the contractor in determining the amount of award fee to be provisionally earned and/or paid for the period.

- Once all revisions are made to the letter, the FDO shall send it to the contractor.

- If the contractor requests a debriefing, the PEB Chairperson shall provide one.

B.  Final Evaluations of Pools 1- 4

At the final evaluation of each of pools 1- 4, the total award fee pool, less any unearned fee that was reserved for a special event, is available, and the total performance is evaluated against the award fee plan to determine the total award fee score.  This evaluation supersedes the previous interim evaluations.

If the final award fee score is lower than that of the interim periods, the provisionally earned award shall be adjusted downward accordingly and any provisional fee payments that exceed the final amount shall be returned.  If the two scores are the same no adjustment is required.  If the final amount exceeds that earned during interim periods, the provisionally earned fee is increased accordingly.

The final award fee score for the pool determines the amount of fee to be finalized for pre-on-orbit performance and to be provisionally paid for on-orbit performance.

The criteria for final evaluations of pools 1- 4 shall be the same as for interim evaluations, except that the scope of the evaluation shall include total performance.

## C.  On-Orbit Performance Evaluation

The fee available for on-orbit performance is 50% of the fee as determined by the final evaluation of each of Pools 1- 4.

Fee earned for on-orbit performance for each FM is determined by a qualitative assessment and assigned a percentage score in accordance with the matrix in Attachment III-B.4.  A score less than 100% will be assigned in the event of any performance or functional degradation.

V. 	CHANGING THE PERFORMANCE EVALUATION PLAN (PEP)

A.	Right to Make Unilateral Changes

Anything in this plan not specifically identified as requiring mutual agreement under the contract, may be changed unilaterally by the FDO prior to the beginning of an evaluation period by timely notice to the contractor in writing at least 30 calendar days prior to the start of the relevant evaluation period.  Significant changes to this Plan will require the approval of the Procurement Officer.   The changes will be made without formal modification of the contract.

B.	Steps to Change the PEP

The following is a summary of the principal actions involved in changing the PEP for an evaluation period (actions may be modified to reflect different approval or notification levels).

Action							Schedule

PEB members draft proposed revisions to PEP	Ongoing

PEP revisions submitted to CO for drafting		Ongoing

###### FDO reviews and approves revisions to PEP		45 days prior to the start of period

Procurement Officer reviews and approves		45 days prior to the start of period

significant revisions to the PEP

FM notifies the Contractor regarding			30 days prior to the start of period

revisions to PEP

The PEB will establish lists of subsidiary actions and schedules necessary to meet the above schedules.

C.	Method for Changing Plan Coverage

The method to be followed for changing the PEP is described below:

1.	Personnel involved in the administration of the award fee provisions of the contract are encouraged to recommend plan changes with a view toward changing management emphasis, motivating higher performance levels, or improving the award fee determination process.  Recommended changes should be sent to the CO for PEB consideration and drafting.

- Prior to the end of each evaluation period, the PEB will submit its recommended changes, if any, applicable to the next evaluation period for approval by the FDO with appropriate comments and justification.  If the changes are considered to be significant by the CO, then the revised plan must be sent to the Procurement Officer for approval after the FDO review.

3.	No later than thirty (30) calendar days before the beginning of each evaluation period, the CO will notify the contractor in writing of any changes to be applied during the next period.  If the contractor is not provided with timely notification, or if the notification is not provided within a mutually agreed upon number of calendar days before the beginning of the next period, then the existing plan will continue in effect for the next evaluation period, unless the Contractor agrees in writing to accept the changes.

| ATTACHMENT III-A |
| --- |
| Performance Evaluation Periods and Available Award Fee for Each Period |
| Pool No. 1 - Non-Recurring and FM 1 |
| Period # | Start Date | End Date |  | Technical | Management | Cost | Total |
| 1 |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |  |
| 11 |  |  |  |  |  |  |  |
| 12 |  |  |  |  |  |  |  |
| 13 |  |  |  |  |  |  |  |
| 14 |  |  |  |  |  |  |  |
| 15 |  |  |  |  |  |  |  |
| 16 |  |  |  |  |  |  |  |
| 17 |  |  |  |  |  |  |  |
| 18 |  |  |  |  |  |  |  |
| 19 |  |  |  |  |  |  |  |
| 20 |  |  |  |  |  |  |  |
| 21 |  |  |  |  |  |  |  |
| 22 |  |  |  |  |  |  |  |
| 23 |  |  |  |  |  |  |  |
| 24 |  |  |  |  |  |  |  |
| 25 |  |  |  |  |  |  |  |
| 26 |  |  |  |  |  |  |  |
| 27 |  |  |  |  |  |  |  |
| 28 |  |  |  |  |  |  |  |
| 29 |  |  |  |  |  |  |  |
| 30 |  |  |  |  |  |  |  |
| 31 |  |  |  |  |  |  |  |
| 32 |  |  |  |  |  |  |  |
| 33 |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |

| ATTACHMENT III-A |
| --- |
| Performance Evaluation Periods and Available Award Fee for Each Period |
| Pool No. 2 - FM 2 |
| Period # | Start Date | End Date |  | Technical | Management | Cost | Total |
| 1 |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |  |
| 11 |  |  |  |  |  |  |  |
| 12 |  |  |  |  |  |  |  |
| 13 |  |  |  |  |  |  |  |
| 14 |  |  |  |  |  |  |  |
| 15 |  |  |  |  |  |  |  |
| 16 |  |  |  |  |  |  |  |
| 17 |  |  |  |  |  |  |  |
| 18 |  |  |  |  |  |  |  |
| 19 |  |  |  |  |  |  |  |
| 20 |  |  |  |  |  |  |  |
| 21 |  |  |  |  |  |  |  |
| 22 |  |  |  |  |  |  |  |
| 23 |  |  |  |  |  |  |  |
| 24 |  |  |  |  |  |  |  |
| 25 |  |  |  |  |  |  |  |
| 26 |  |  |  |  |  |  |  |
| 27 |  |  |  |  |  |  |  |
| 28 |  |  |  |  |  |  |  |
| 29 |  |  |  |  |  |  |  |
| 30 |  |  |  |  |  |  |  |
| 31 |  |  |  |  |  |  |  |
| 32 |  |  |  |  |  |  |  |
| 33 |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |

ATTACHMENT III-A

ATTACHMENT III-A

| ATTACHMENT III-A |
| --- |
| Performance Evaluation Periods and Available Award Fee for Each Period |
| Pool No. 3 - Post Delivery Support |
| Period # | Start Date | End Date |  | Technical | Management | Cost | Total |
| 1 |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |  |
| 11 |  |  |  |  |  |  |  |
| 12 |  |  |  |  |  |  |  |
| 13 |  |  |  |  |  |  |  |
| 14 |  |  |  |  |  |  |  |
| 15 |  |  |  |  |  |  |  |
| 16 |  |  |  |  |  |  |  |
| 17 |  |  |  |  |  |  |  |
| 18 |  |  |  |  |  |  |  |
| 19 |  |  |  |  |  |  |  |
| 20 |  |  |  |  |  |  |  |
| 21 |  |  |  |  |  |  |  |
| 22 |  |  |  |  |  |  |  |
| 23 |  |  |  |  |  |  |  |
| 24 |  |  |  |  |  |  |  |
| 25 |  |  |  |  |  |  |  |
| 26 |  |  |  |  |  |  |  |
| 27 |  |  |  |  |  |  |  |
| 28 |  |  |  |  |  |  |  |
| 29 |  |  |  |  |  |  |  |
| 30 |  |  |  |  |  |  |  |
| 31 |  |  |  |  |  |  |  |
| 32 |  |  |  |  |  |  |  |
| 33 |  |  |  |  |  |  |  |
| 34 |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |

ATTACHMENT III-A

PERFORMANCE EVALUATION

PERIODS AND AVAILABLE AWARD FEE

FOR EACH PERIOD OF ON-ORBIT PERFORMANCE

Period                                  				Maximum Available Award Fee

Number	Start Date	End Date	   Technical	Management	Cost Control  Total

This matrix will be developed during performance of the contract and evaluation of performance. Fee associated with NRE will be included in the on-orbit fee for FM 1.  Fee associated with FM 2 will be allocated to the respective FM on-orbit performance.

ATTACHMENT III-B

PERFORMANCE EVALUATION FACTORS AND CRITERIA

The performance factors to be evaluated for award fee pools 1-5 are identified below.  The performance criteria for each factor are attached.

Area		Brief  Factor	   		Factor	      	See

No.		Identification			Weight	    	Attachment

1        		Technical                 		40%          	III-B.1

2         		Management		         	35%          	III-B.2

3         		Cost Control		         	25%          	III-B.3

The performance factors/criteria to be evaluated for on-orbit performance are identified in Attachment III-B.4.

#### ATTACHMENT III-B.1

PERFORMANCE CRITERIA

FOR TECHNICAL PERFORMANCE EVALUATION FACTOR

Factor Weight  40

This category will consist of "Scheduled" and "Unscheduled" milestones or tasks and overall technical/schedule performance for effort during the period, including management of risk, safety and security.  Scheduled milestones are those that are identified by Chairperson, Contracting Officer’s Technical Representative, or other PEB members, and issued by the Contracting Officer before or close to the beginning of each performance evaluation period.  Unscheduled milestones are those that arise during the period and are not anticipated.   Overall technical/schedule performance covers performance not specifically identified in a milestone.  This Factor also encompasses:

Safety & Security - The Contractor will be evaluated based on their ability to provide a safe work environment, including inspections and processes for accident and incident files, mishap reporting, and training.  A major breach of safety consists of an accident, incident, or exposure resulting in a fatality or mission failure; or in damage to equipment or property equal to or greater than $1 million; or in any "willful" or "repeat" violation cited by the Occupational Health and Safety Administration (OSHA) or by a state agency operating under an OSHA approved plan.  Security is the condition of safeguarding against espionage, sabotage, crime (including computer crime), or attack.  A major breach of security may arise from any of the following: compromise of classified information; illegal technology transfer; workplace violence resulting in criminal conviction; sabotage; compromise or denial of information technology services; damage, vandalism, theft or loss greater than $250,000 to the Government.  In no case will any Award Fee be earned by the Contractor in any interim evaluation period in which, there is a major breach of safety or security.  In addition, the overall maximum available award fee shall be reduced by the amount of the fee available for the evaluation period in which the major breach occurred.

Risk Management – The Contractor will be evaluated on its ability to identify risks; analyze their impact and prioritize them; develop and carry out plans for risk mitigation, acceptance, or other action; track risks and the implementation of mitigation plans; support informed, timely, and effective decisions to control risks and mitigation plans; and assure that risk information is communicated among all levels of a program/project.

In evaluating the Contractor's performance, the monitor may consider, but is not limited to, any of the following subfactors:

Performance Subfactors

1.  Success - The degree to which the Contractor was successful in accomplishing the task or achieving the milestone.

2.  Timeliness - Meeting milestone schedules and accomplishing tasks in a timely manner.

3.  Efficiency - Using the appropriate resources or work-arounds to minimize impacts to cost and schedule.  Working independently compared to relying on the Government to a high degree.

ATTACHMENT III-B.2

PERFORMANCE CRITERIA

FOR MANAGEMENT PERFORMANCE FACTOR

Factor Weight   35

Performance Criteria

Program Planning/Organization/Management

Subcontract Management

External Interfaces

Contract Administration and Compliance

Cost and Schedule Performance Measurement System(s)

1.	Program Planning/Organization/Management

This includes, but is not limited to, the following:  Program Management, including management; direction, control, reporting, export control, and damage to the environment; assignment and utilization of personnel; resource and business management; corporate visibility; and thoroughness of this interface with GSFC management.

2.	Subcontract Management

This includes, but is not limited to, subcontractor management, direction, control and reporting, and integration of these into the overall program, purchase order and subcontract administration and timely and complete requests for consent to subcontract.

3.	External Interfaces

The efforts required by the contractor in response to and in support of all external interfaces and Government-furnished property/equipment (GFP/E), including, but not limited to, the following:  launch vehicle and processing facilities, spacecraft, ground system and interfaces, GFP/E.

4.	Contract Administration and Compliance

This includes, but is not limited to, the following:  compliance with contract clauses, performance against the Small Business Subcontracting plan goals; SDB Participation targets; Mentor-Protégé participation; effectiveness of property and material control; timeliness and thorough preparation, implementation and closeout of all required documentation and reports including property and subcontracting reports; efforts to definitize adjustments to the contract, which include accurate, complete and timely proposal submissions; responsiveness to requests for change proposals, including submission of timely, complete proposals and cooperation in negotiating the changes; and timely subcontract adjustments.

5.	Cost and Schedule Performance Measurement System(s)

The implementation and operation of a system(s) which integrates all cost and schedule components in order to carry out sound and thorough planning, control and authorization of all work.  This shall include the demonstrated ability to use an Earned Value Measurement System (EVMS) and an automated schedule management system as management tools to effectively avoid cost and schedule impacts.  The system shall provide accurate and effective variance analysis reports, including problem analysis, project/task impact, corrective action plans and resources impact on a timely basis.  The system shall be capable of maintaining accurate and complete vertical and horizontal schedule/cost traceability and identify schedule interrelationships between activities.  This element includes the Contractor's ability to control, adjust, and accurately project contract planned milestones (consistent with the Work Breakdown Structure) versus actual performance.  This does not include cost performance vs. plan or schedule performance vs. plan, which is covered elsewhere in this plan.

ATTACHMENT III-B.3

PERFORMANCE CRITERIA

FOR COST PERFORMANCE FACTOR

Factor Weight   25

Overall cost performance will be evaluated on how well the total cumulative actual costs were controlled as compared to the negotiated baseline estimated costs.  For each period the Government will complete a comparative analysis of NF533 and Earned Value Management System reports to actual accrued costs versus total negotiated baseline estimated costs.  This analysis will be utilized to evaluate and score cumulative cost management progress.

An analysis of cost performance will give consideration to anticipated but unreported overruns/underruns, changed requirements, undefinitized contract actions, changed statutory requirements, and/or other changes that are within or beyond the Contractor's control that impact contract costs.  Each cost element will be analyzed to determine its effect on total costs.

The evaluation of cost control will also consider the following guidelines:

- Normally, the Contractor should be given a score of 0 for cost control when there is a significant cost overrun within its control.  However, the Contractor may receive higher scores for cost control if the overrun is insignificant.  Scores should decrease sharply as the size of the overrun increases.  In any evaluation of Contractor overrun performance, the Government will consider the reasons for the overrun and assess the extent and effectiveness of the Contractor’s efforts to control or mitigate the overrun.

- The Contractor should normally be rewarded for an underrun within its control, up to the maximum score allocated for cost control, provided the average numerical rating for all other award fee evaluation factors is 81 or higher.  An underrun will be rewarded as if the Contractor has met the estimated cost of the contract when the average numerical rating for all other factors is less than 81 but greater than 60.

- The Contractor should normally be rewarded for meeting the estimated cost of the contract, but not to the maximum score allocated for cost control, to the degree that the Contractor has prudently managed costs while meeting contract requirements.  No award will be given in this circumstance unless the average numerical rating for all other award fee evaluation factors is 61 or greater.

ATTACHMENT III-B.4

ON-ORBIT EVALUATION CRITERIA

All of the percentages below apply after ground storage and launch.

Fully Operational – No reduction in fee

No mission function failures.

All performance parameters within specification

Slight Degraded – 20% reduction in fee

Loss of some non-critical health and safety telemetry not impacting operations

TBD

Degraded – 40% reduction in fee

TBD

Significantly Degraded – 60% reduction in fee

TBD

Severely Degraded – 80% reduction in fee

TBD

Failed – 100% reduction in fee

TBD

Reductions in on-orbit fee for a degraded performance classification shall be prorated for the amount of time during the period in which the instrument was in that classification(s).

Example:

FM-001 was in fully operational status 95% of the period.  It was in slightly degraded condition 5% of the time.  The reduction is 15% x 5% = 0.75% of the available fee for the period.

The on-orbit award fee matrix reflects the schedule for liquidating (finalizing) previously paid award fee for on-orbit performance:

On-Orbit Storage

|  | <1yr | 1 yr | 2 yr | 3 yr | 4 yr | 5 yr | 6 yr | 7 yr |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Operation |  |  |  |  |  |  |  |  |  |
| <1yr | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 60% |  |
| 1 yr | 90% | 80% | 70% | 60% | 50% | 40% | 30% | 20% |  |
| 2 yr | 80% | 70% | 60% | 50% | 40% | 30% | 20% | 10% |  |
| 3 yr | 70% | 60% | 50% | 40% | 30% | 20% | 10% | 0% |  |
| 4 yr | 60% | 50% | 40% | 30% | 20% | 10% | 0% | 0% |  |
| 5 yr | 50% | 40% | 30% | 20% | 10% | 0% | 0% | 0% |  |
| 6 yr | 40% | 30% | 20% | 10% | 0% | 0% | 0% | 0% |  |
| 7 yr | 20% | 20% | 10% | 0% | 0% | 0% | 0% | 0% |  |
| 8 yr | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0% |  |
| 9 yr | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |
| 10 yr | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |

ATTACHMENT III-C

GRADING TABLE

Adjectival		 			 Range of Performance

Rating          		   Points   			Description

Excellent          		(100-91)		Of exceptional merit; exemplary performance in a timely, efficient and economical manner; very minor (if any) deficiencies with no adverse effect on overall performance.

Very Good        		(90-81)		Very effective performance, fully responsive to contract; contract requirements accomplished in a timely, efficient and economical manner for the most part; only minor deficiencies.

Good               		(80-71)		Effective performance; fully responsive to contract requirements; reportable deficiencies, but with little identifiable effect on overall performance.

Satisfactory       	(70-61)		Meets or slightly exceeds minimum acceptable standards; adequate results; reportable deficiencies with identifiable, but not substantial, effects on overall performance.

Poor/Unsatisfactory	(less than 61)  		Does not meet minimum acceptable standards in one or more 	areas; remedial action required in one or more areas; deficiencies in one or more areas which adversely affect overall performance.

Any factor receiving a grade of poor/unsatisfactory (less than 61) will be assigned zero performance points for purposes of calculating the award fee amount.  The contractor will not be paid any award fee when the total award fee score is "Poor/Unsatisfactory" (less than 61).

In order to earn a total overall rating of Excellent, the contractor must be under contract cost, on or ahead of schedule, and be rated excellent under Technical Performance.

ATTACHMENT IV-A

GENERAL INSTRUCTIONS

FOR EVALUATION AND MONITORING OF PERFORMANCE

- Performance Monitors will conduct all assessments in an open, objective, and cooperative manner so that a fair and accurate evaluation is obtained.  This will ensure that both the Performance Monitor and the contractor receive accurate and complete information from which to prepare assessments and to plan improvements in performance.  Positive performance accomplishments will be emphasized just as readily as negative ones and extraordinary circumstances will be noted in reports.

- Performance Monitors will discuss their assessments with the appropriate contractor

personnel, noting observed accomplishments, deficiencies, or unusual circumstances.  This affords the contractor an opportunity to clarify possible misunderstandings regarding areas of poor performance and to correct or resolve deficiencies in a timely manner.

- Performance Monitors will conduct their contacts and visits with contractor personnel

within the context of official contractual relationships.  They will avoid activities or associations that might cause, or give the appearance of, a conflict of interest on either part.

- Performance Monitor contacts with contractor personnel will not be used to instruct,

direct, or supervise or control these personnel in the performance of the contract.  The role of the monitor is to monitor, assess, and evaluate, not to manage the contractor's effort.

- Performance Monitors will document their assessments of contractor performance in their reports that they will submit to the PEB at the end of each evaluation period.

6.	Monitors will be prepared to make verbal reports of their evaluations and assessments as required by the PEB Chairperson.

ATTACHMENT IV-B

ACTIONS AND SCHEDULES FOR AWARD FEE DETERMINATIONS

The following is a summary of the principal actions involved in determining the award fee for the evaluation periods.  The PEB will establish lists of subsidiary actions and schedules as necessary to meet the schedule for principal actions.

## Action						Schedule

PEB Chairperson and members appointed		Prior to first period and ongoing

PEB Chairperson appoints Performance Monitors	Prior to first period and ongoing

and informs contractor

Monitors receive orientation and guidance		Prior to first period

Performance Monitors assess performance		Ongoing

and discuss results with contractor

Performance Monitors submit performance 		Not later than (NLT) 10

reports to PEB 					days after end of period

PEB meets to discuss performance reports		NLT 30 days after end of

and prepare preliminary findings and            		period

recommendations

PEB forwards findings and summary 		NLT 40 days after end of

recommendations to FDO in award fee letter.           	period

The FDO reviews and signs the FDO letter.		NLT 45 days after end of

CO forwards FDO letter and executed		period

contract modification to contractor

Award fee payment made to contractor		NLT 60 days after end of

via contract modification				period