| List of Contract Deliverables Contract Specific From SOW |
| --- |
| Deliverable | Periodic Date or Specific Due Date | Comments | Contract Ref. | Delivery Method |
| Integrated Management Plan | Draft version due with proposal. Final version due 180 days after contract inception. Updated as required. | Revisions require NASA approval | SOW Section 1.0 & 1.2.4 | Hardcopy with proposal. Maintained on WOCR. |
| Contract Work Breakdown Structure | Due with proposal. Updated as required. | Updates require NASA approval. | SOW Section 1.0 & 1.2.4 | Hardcopy with proposal. Maintained on WOCR. |
| List of Long Lead Items for Phase Out | 18 months prior to completion of contract | List is to be coordinated with and approved by COTR | SOW Section 1.1.1.2 | Electronic to COTR and on WOCR |
| Overall Integrated Schedule | Initial due 30 days after contract inception and updated monthly thereafter | Schedule to be reviewed with NASA at Monthly Scheduling Meeting | SOW Section 1.1.2 | Electronically maintained on WOCR |
| Safety and Health Program Plan | Draft version due with proposal. Final version due 30 days after contract inception. Updated as required. | Final and revisions require NASA approval | SOW Section 1.1.4 | Hardcopy with proposal. Final electronically to Safety Office and maintained on WOCR |
| Quality Manual | 90 days after contract inception | Requires NASA approval | SOW Section 1.1.5 | Electronically to COTR and maintained on the WOCR |
| Configuration Management Control Plan | 90 days after contract inception | Requires NASA approval | SOW Section 1.1.6 | Electronically to COTR and maintained on the WOCR |
| Training Plan | 90 days after contract inception and updated as necessary |  | SOW Section 1.1.9 | Electronically to COTR and maintained on the WOCR |
| Monthly Progress Reports | 15th day after the close of the monthly reporting period |  | SOW Section 1.2.1 | Electronically to COTR and maintained on the WOCR |
| Contract Management Review | Semi-Annually | Conducted in conjunction with the self-evaluation portion of the Performance Evaluation Board review | SOW Section 1.2.1 | Electronically to COTR and maintained on the WOCR |
| 533 Monthly Report | Due 10 working days after the close of the monthly accounting period | Also provided in Excel version acceptable to COTR which includes marketing tasks and includes variance report. | SOW Section 1.2.2 | Electronically to COTR and maintained on the WOCR |
| Costing Summary Database (CSDB) | Within 2 days of 533 Monthly Delivery | Database maintains and allocates 533M task costs into NASA "funding baskets" | SOW Section 1.2.2 | Electronically to COTR and maintained on the WOCR |
| NASA Form 1018 (Monthly & Annually) | Monthly-The 21st of every month Annually- Every October | Subject - NASA Property in the Custody of Contractors | SOW Section 1.2.5 | Hard Copy to COTR and maintained in the WOCR |
| Inventory Usage Report | Monthly |  | SOW Section 1.2.5 | Electronically to COTR and maintained in the WOCR |
| List of Contract Deliverables Mission Specific From SOW |
| Deliverable | Periodic Date or Specific Due Date | Comments | Contract Ref. | Delivery Method |
| Requirements Definition Meeting Memorandum for each mission | Within 5 days of the Requirements Definition Meeting (RDM) | RDM to be held within 45 calendar days of the Mission Initiation Conference | SOW Sections 1.1.3 & 3.0 and Section H | Hardcopy to COTR |
| Preliminary Hazard Assessment for each mission | Provided at Requirements Definition Meeting | Provided directly to Wallops Safety Office | SOW Section 1.1.4.1 | Electronically and maintained in the WOCR |
| Risk Documentation for each mission and significant PTO | 90 days after contract inception and updated monthly | Reviewed at monthly scheduling meetings and mission specific Design and Mission Readiness Reviews | SOW Section 1.1.7 and 1.1.2 | Electronically in the WOCR |
| Design Review Package for each mission | Provided at Design Review | Comprehensive package of information presented at review | SOW Section 2.1.1 & Design and Mission Readiness Review Clause in Section H | Hard Copy at review and maintained in the WOCR |
| Design Review Memorandum for each mission | 5 working days after Design Review |  | SOW Section 2.1.1 & Design and Mission Readiness Review Clause in Section H | Hard Copy to COTR and maintained in the WOCR |
| Design Review Action Item Closeout Memo for each mission (w/ supporting technical documentation) | Review Panel approval 5 days prior to Mission Readiness Review |  | SOW Section 2.1.1 & Design and Mission Readiness Review Clause in Section H | Hard Copy to COTR and maintained in the WOCR |
| Flight Requirements Plan for each mission | Preliminary at Design Review & final at Mission Readiness Review | Included in Design and Mission Readiness Review Packages | SOW Section 2.1.1 & 2.3.1 | Hard Copy to COTR and maintained in the WOCR |
| Flight Worthiness Assessment for each mission | Preliminary at Design Review and updated 10 days prior to Mission Readiness Review | Provided directly to Wallops Safety Office | SOW Section 1.1.4.1 | Electronically and maintained in the WOCR |
| Range Safety Data Package for each mission | Due 90 days prior to scheduled launch date and updated as necessary | Provided directly to Wallops Safety Office | SOW Section 1.1.4.1 | Electronically and maintained on WOCR |
| Mission Readiness Review Package for each mission | Provided at Mission Readiness Review | Comprehensive package of information presented at review | SOW Section 2.1.1 & Design and Mission Readiness Review Clause in Section H | Hard Copy at review and maintained in the WOCR |
| Mission Readiness Review Memorandum for each mission | 5 working days after Mission Readiness Review |  | SOW Section 2.1.1 & Design and Mission Readiness Review Clause in Section H | Hard Copy to COTR and maintained in the WOCR |
| Mission Readiness Review Action Item Closeout Memo for each mission (w/ supporting technical documentation) | Review Panel approval 2 days prior to scheduled launch |  | SOW Section 2.1.1 & Design and Mission Readiness Review Clause in Section H | Hard Copy to COTR and maintained in the WOCR |
| Mission Closeout Report for each mission | Within 180 days after launch |  | SOW Section 4.4 | Hardcopy to COTR and maintained in the WOCR |
| List of Contract Deliverables Non-Mission Specific From SOW |
| Empirical Dispersion Flight History Database | Updated monthly |  | SOW Section 1.2.4 | Maintained in WOCR |
| Class C and D Mishap Investigation Reports for each Class C and D mishap | Within 30 days after mishap |  | SOW Section 4.3 | Electronic copy to COTR and maintained in the WOCR |
| Copy of safety reports submitted to any cognizant agency or local base authorities | Concurrent with original submittal |  | SOW Section 1.1.4.2 | Electronically to Contracting Officer and COTR and maintained on WOCR |
| NASA Form 1627 | Within 1 working day of Mishap | Subject - Mishap Report | SOW Section 1.1.4.2 & 4.3 | Hard Copy to Wallops safety Office |