SOUTH COAST AIR QUALITY MANAGEMENT DISTRICT

REQUEST FOR PROPOSALS

RFP# 2009-10

RFP for High-Emitter Repair or Scrap Program, Phase II

The South Coast Air Quality Management District (SCAQMD or AQMD) requests proposals for the following purpose according to terms and conditions attached.  In the preparation of this Request for Proposals (RFP) the words "Proposer," "Contractor," and "Consultant" are used interchangeably.

PURPOSE

The purpose of this Request for Proposals (RFP) is to solicit proposals for development and implementation of the second phase of AQMD's High Emitter Repair or Scrap (HEROS) program.  The first phase of the HEROS program utilized remote sensing at freeway on-ramps to screen for high-emitting in-use vehicles.  Owners of vehicles identified through remote sensing who also met specific eligibility requirements were invited to participate in the voluntary incentive program for vehicle repair or scrap.

The goal of this second phase is to achieve a higher program participation rate by drawing interested, pre-qualified participants into advertised weekend events for vehicle pre-screening.  Owners of vehicles identified as potential high emitters would then be eligible to schedule appointments for confirmatory emissions testing at select smog check stations.  Effective program implementation would result in a large number of participants with confirmed high-emitting vehicles who proceed to have their vehicles either repaired or scrapped through the program.

The proposal shall include, but not be limited to, conducting publicity/marketing/outreach, establishment and management of a call center, holding weekend events, screening potential high emitting vehicles at events, establishing a network of smog check stations for smog check testing and repairs, oversight of smog check testing and repair authorization/ invoicing, and database/data processing and reporting.  The AQMD may select one or several potential contractors to conduct the HEROS program.

Total funding for this RFP will be up to $1,600,000 with an expected time frame of eighteen (18) months from contract initiation to completion.

INDEX - The following are contained in this RFP:

Section I	Background/Information

Section II	Contact Person

Section III	Schedule of Events

Section IV	Participation in the Procurement Process

Section V	Statement of Work/Schedule of Deliverables

Section VI	Required Qualifications

Section VII	Proposal Submittal Requirements

Section VIII	Proposal Submission

Section IX	Proposal Evaluation/Contractor Selection Criteria

Section X		Funding

Section XI	Draft Contract

Attachment A - Certifications and Representations

SECTION I:	BACKGROUND / INFORMATION

The South Coast Air Quality Management District (SCAQMD or AQMD) is the regional air pollution control agency for the four-county South Coast Air Basin (Basin) (Orange County and the non-desert portions of Los Angeles, Riverside and San Bernardino counties), and the Riverside County portions of the Salton Sea Air Basin (SSAB) and Mojave Desert Air Basin (MDAB), covering an area of approximately 10,743 square miles.  The AQMD has primary regulatory authority over the region’s stationary sources and has limited jurisdiction over mobile sources.  Due to stringent controls imposed on stationary sources over the last two decades, the AQMD has recently focused attention to controlling mobile source emissions.  Past remote sensing studies conducted in the South Coast Air Basin and in other urbanized areas of the country have determined that approximately 10% of the light- and medium-duty vehicles are responsible for close to 50% of the total precursor inventory for on-road light-duty category (National Resource Council, 2001).  With this in mind, the Governing Board of the AQMD authorized the expenditure of funds to develop and implement a program for the purpose of identifying high-emitting vehicles and the subsequent repair or scrappage of such vehicles.

The proposed light- and medium-duty high-emitting vehicle program was developed from recently adopted legislation AB 923 (Firebaugh) which broadens the definition and the eligibility of Carl Moyer projects to include light- and medium-duty vehicles.  This program is expected to advance emission reductions and achieve greater reductions than the ARB’s adopted Voluntary Accelerated Vehicle Retirement (VAVR) program (set forth in sections 2601 through 2610 of Title 13 of the California Code of Regulations).

The HEROS Program was initiated in March 2007, at which time the remote sensing component of the program began.  Screening of potential high emitting vehicles was performed at freeway on-ramps through remote sensing.  Once identified as potential high emitters, DMV data was obtained for the vehicles, and with this information, VAVR eligibility was determined.  Owners of eligible vehicles were mailed letters inviting them to participate in the program, with potential incentives being offered of up to $500 in vehicle repairs or $1,000 for vehicle scrapping.  Low-income eligible participants qualified for another $1,000 incentive for replacement of the scrapped vehicle with a CARB-certified Low Emission Vehicle.  While the technical aspects of the program have been proven, the voluntary nature of the program has not provided sufficient participation.

The goal of this second phase of the program is to achieve a higher program participation rate by drawing interested, pre-qualified participants into advertised weekend events for vehicle pre-screening.  Owners of vehicles identified as potential high emitters would then be eligible to schedule appointments for confirmatory emissions testing at select smog check station.  The objective of the second phase is to scrap or repair about 3,000 high-emitting vehicles.

The AQMD proposes to retain contractor services to implement the second phase of the program to identify high-emitting light- and medium-duty vehicles operating within its jurisdiction and reduce these vehicles’ emissions through a voluntary repair or retirement program.  The proposed program has multiple components, all of which are covered under this RFP.

SECTION II:	CONTACT PERSON

Questions regarding the content or intent of this RFP, or on procedural matters should be addressed to:

Lori Berard

Mobile Source Division, On-Road Section

South Coast Air Quality Management District

21865 East Copley Drive

Diamond Bar, CA  91765

Tel. No.: (909) 396-2436

E-mail: lberard@aqmd.gov

SECTION III:	SCHEDULE OF EVENTS

December 5, 2008	Board Approval of RFP

December 5, 2008	RFP Released

December 10, 2008	MANDATORY Bidder’s Conference at
	10:00 a.m. in Room CC-6

February 6, 2009	Proposals Due by 1 p.m.

March 6, 2009	Recommendation to Board

April 2009	Anticipated Contract Start

June 2009	Anticipated Start of Events

January 2011	Final Report Due

A MANDATORY Bidders Conference will be held at the AQMD Headquarters in Diamond Bar, California at 10:00 a.m. on Wednesday, December 10, 2008 in Room CC-6.  Please contact Lori Berard at (909) 396-2436 by close of business on Tuesday, December 9, 2008 if you plan to attend in person or via teleconference.

SECTION IV:	PARTICIPATION IN THE PROCUREMENT PROCESS

- It is the policy of the South Coast Air Quality Management District to ensure that all businesses including minority business enterprises, women business enterprises, disabled veteran business enterprises and small businesses have a fair and equitable opportunity to compete for and participate in AQMD contracts.

- Definitions:

The definition of minority or women business enterprise set forth below is included for purposes of determining compliance with the affirmative steps requirement described in Paragraph F below on procurements funded in whole or in part with EPA grant funds which involve the use of subcontractors.  The definition provided for disabled veteran business enterprise, local business, small business enterprise, low-emission vehicle business and off-peak hours delivery business are provided for purposes of determining eligibility for point or cost considerations in the evaluation process.

- "Minority-or-women business enterprise" as used in this policy means a business enterprise that meets all the following criteria:

- a business that is at least 51 percent owned by one or more minority persons or women, or in the case of any business whose stock is publicly held, at least 51 percent of the stock is owned by one or more minority persons or women.

- a business whose management and daily business operations are controlled by one or more minority persons or women.

- a business which is a sole proprietorship, corporation, or partnership with its primary headquarters office located in the United States, which is not a branch or subsidiary of a foreign corporation, foreign firm, or other foreign-based business.

- "Minority person" for purposes of this policy, means a Black American, Hispanic American, Native American (including American Indian, Eskimo, Aleut, and Native Hawaiian), Asian-Indian American (including a person whose origins are from India, Pakistan, and Bangladesh), Asian-Pacific American (including a person whose origins are from Japan, China, the Philippines, Vietnam, Korea, Samoa, Guam, the United States Trust Territories of the Pacific, Northern Marianas, Laos, Cambodia, and Taiwan).

- "Disabled veteran" as used in this policy is a United States military, naval, or air service veteran with at least 10 percent service-connected disability who is a resident of California.

- "Disabled veteran business enterprise" as used in this policy means a business enterprise that meets all of the following criteria:

- is a sole proprietorship or partnership of which is at least 51 percent owned by one or more disabled veterans or, in the case of a publicly owned business, at least 51 percent of its stock is owned by one or more disabled veterans; a subsidiary which is wholly owned by a parent corporation but only if at least 51 percent of the voting stock of the parent corporation is owned by one or more disabled veterans; or a joint venture in which at least 51 percent of the joint venture's management and control and earnings are held by one or more disabled veterans.

- the management and control of the daily business operations are by one or more disabled veterans.  The disabled veterans who exercise management and control are not required to be the same disabled veterans as the owners of the business.

- is a sole proprietorship, corporation, or partnership with its primary headquarters office located in the United States, which is not a branch or subsidiary of a foreign corporation, firm, or other foreign-based business.

- "Local business" as used in the Procurement Policy and Procedure means a company that has an ongoing business within the boundaries of the South Coast AQMD at the time of bid application and performs 90% of the work related to the contract within the boundaries of the AQMD and satisfies the requirements of Paragraph H below.

- “Small business” as used in this policy means a business that meets the following criteria:

- 1) an independently owned and operated business; 2) not dominant in its field of operation; 3) together with affiliates is either:

- A service, construction, or non-manufacturer with 100 or fewer employees, and average annual gross receipts of ten million dollars ($10,000,000) or less over the previous three years, or

- A manufacturer with 100 or fewer employees.

- Manufacturer means a business that is both of the following:

- Primarily engaged in the chemical or mechanical transformation of raw materials or processed substances into new products.

- Classified between Codes 2000 to 3999, inclusive, of the Standard Industrial Classification (SIC) Manual published by the United States Office of Management and Budget, 1987 edition.

- "Joint ventures" as defined in this policy pertaining to certification means that one party to the joint venture is a DVBE and owns at least 51 percent of the joint venture.

- "Low-Emission Vehicle Business" as used in this policy means a company or contractor that uses low-emission vehicles in conducting deliveries to the AQMD. Low-emission vehicles include vehicles powered by electric, compressed natural gas (CNG), liquefied natural gas (LNG), liquefied petroleum gas (LPG), ethanol, methanol, hydrogen and diesel retrofitted with particulate matter (PM) traps.

- “Off-Peak Hours Delivery Business” as used in this policy means a company or contractor that commits to conducting deliveries to the AQMD during off-peak traffic hours defined as between 10:00 a.m. and 3:00 p.m.

- Under Request for Quotations (RFQ), DVBEs, DVBE business joint ventures, small businesses, and small business joint ventures shall be granted a preference in an amount equal to 5% of the lowest cost responsive bid.  Low-Emission Vehicle Businesses shall be granted a preference in an amount equal to 5 percent of the lowest cost responsive bid.  Off-Peak Hours Delivery Businesses shall be granted a preference in an amount equal to 2 percent of the lowest cost responsive bid.  Local businesses (if the procurement is not funded in whole or in part by EPA grant funds) shall be granted a preference in an amount equal to 2% of the lowest cost responsive bid.

- Under Request for Proposals, DVBEs, DVBE joint ventures, small businesses, and small business joint ventures shall be awarded ten (10) points in the evaluation process.  A non-DVBE or large business shall receive seven (7) points for subcontracting at least twenty-five (25%) of the total contract value to a DVBE and/or small business.  Low-Emission Vehicle Businesses shall be awarded five (5) points in the evaluation process. On procurements which are not funded in whole or in part by EPA grant funds local businesses shall receive five (5) points.  Off-Peak Hours Delivery Businesses shall be awarded two (2) points in the evaluation process.

- AQMD will ensure that discrimination in the award and performance of contracts does not occur on the basis of race, color, sex, national origin, marital status, sexual preference, creed, ancestry, medical condition, or retaliation for having filed a discrimination complaint in the performance of AQMD contractual obligations.

- AQMD requires Contractor to be incompliance with all state and federal laws and regulations with respect to its employees throughout the term of any awarded contract, including state minimum wage laws and OSHA requirements.

- When contracts are funded in whole or in part by EPA grant funds and if subcontracts are to be let, the Contractor must comply with the steps listed below, which demonstrate a good faith effort to solicit minority and women owned enterprises.  Contractor shall submit a certification signed by an authorized official affirming compliance with the steps below at the time of proposal submission.  The AQMD reserves the right to request documentation demonstrating compliance with these steps prior to contract execution.

- Place qualified small-and-minority businesses and women’s business enterprises on solicitation lists;

- Ensure that small-and-minority businesses, and women’s business enterprises are solicited whenever they are potential sources including advertising at least ten days in advance of the bid in a variety of media directed to minority-and women-owned business audiences;

- Divide total requirements, when economically feasible, into smaller tasks or quantities to permit maximum participation by small-and-minority business, and women’s business enterprises;

- Establish delivery schedules, where requirements permit, which encourage participation by small-and-minority business, and women’s business enterprises; and

- Use the services and assistance of the Small Business Administration and the Minority Business Development Agency of the Department of Commerce.

- To the extent that any conflict exists between this policy and any requirements imposed by federal and state law relating to participation in a contract by a certified MBE/WBE/DVBE as a condition of receipt of federal or state funds, the federal or state requirements shall prevail.

- When contracts are not funded in whole or in part by EPA grant funds, a local business preference will be awarded.  For such contracts that involve the purchase of commercial off-the-shelf products, local business preference will be given to suppliers or distributors of commercial off-the-shelf products who maintain an ongoing business within the geographical boundaries of the AQMD.  However, if the subject matter of the RFP or RFQ calls for the fabrication or manufacture of custom products, only companies performing 90% of the manufacturing or fabrication effort within the geographical boundaries of the AQMD shall be entitled to the local business preference.

- In compliance with federal fair share requirements set forth in 40 CFR 35.6580, the AQMD shall establish a fair share goal annually for expenditures covered by its procurement policy.

SECTION V:	STATEMENT OF WORK/SCHEDULE OF DELIVERABLES

A.	Statement of Work

The overall objective of the program is to maximize the generation of qualified emission reductions under the Carl Moyer Program by implementing a program that provides participants from the general public the opportunity, through incentives, to voluntarily scrap or repair high-emitting vehicles.  Potential bidders may submit proposals for one or all of the tasks listed below.  In addition, Contractor(s) would develop and may implement the entire program.  Six tasks have been identified for this project as follows:

1	Marketing/Outreach Activities

2	Establishment and Management of a Call Center

3	Conduct Events

4	Collection, Tracking, and Analysis of Data

5	Testing/Repair/Scrapping of High-Emitting Vehicles

6	Project Reporting

For purposes of clarity and brevity, the following term is defined:

Gold Shield Station - in this Section shall include, a licensed smog check station that is currently certified by the California Bureau of Automotive Repair as a Gold Shield Station.  The Gold Shield Program is designed to make the Smog Check Program more convenient for motorists. It allows a licensed smog check station, which meets higher performance standards, to provide a variety of inspection and repair services to California motorists. In addition to the regular Smog Check inspection and repair services, Gold Shield stations can inspect and certify "Directed Vehicles," issue certificates to "Gross Polluters," and perform state subsidized repairs.

To be eligible for Gold Shield certification, a Gold Shield station must:

- Have no disciplinary actions against its Automotive Repair Dealer Registration
(ARD), Smog Check station license or the licenses of its technicians or managers.

- Meet strict testing and repair performance standards each calendar quarter.

- Submit to periodic performance inspections and monitoring.

Bidders may address all tasks or specific tasks based on their background and expertise in their proposal and shall apply the format criteria specified in Section VII – Proposal Submittal Requirements in response to addressing each task.  The six tasks listed below are integral to the goal of repairing and scrapping a combined total of at least3,000 VAVR-qualified high-emitting vehicles.  Each task is, however, separate and inclusive on its own.  Bidders should describe the Technical Approach and Work Statement for each task.  The District reserves the right to select individual tasks for award to fit its needs and resources.

Task 1 – Marketing/Outreach Activities

The purpose of this task is to generate public awareness and interest to draw in a large number of pre-qualified participants with high-emitting vehicles into weekend events for vehicle pre-screening.  Effective outreach would result in participants who are willing to participate in the program, with eligible participants proceeding to subsequent steps which include confirmatory smog check testing, and subsequent repair or scrapping of vehicles.  The objectives are to provide sufficient outreach to support vehicle scrapping/repair goals as indicated in Task 5.

Pre-qualified participants would meet all applicable specifications identified for the Voluntary Repair of Vehicles (VRV) and Voluntary Accelerated Vehicle Retirement (VAVR), per Chapter 11 of the Carl Moyer Guidelines, approved revision 2008.

Task 2 – Establishment and Management of Call Center

A bilingual call center would be responsible for responding to inquiries generated by marketing/outreach, pre-screening potential participants for Moyer Program eligibility by accessing a database maintained by the California Department of Motor Vehicles (DMV), scheduling event appointments for pre-screened participants, and making reminder calls before events.  The objectives are to provide sufficient call center response to support vehicle scrapping/repair goals as indicated in Task 5.

The scope of this task will include, but not necessarily be limited to the following:

2.1	Responding to Inquiries

2.1.1	Hire and manage bilingual or multi-lingual staff to answer questions
		related to upcoming events, testing, repair, and scrapping.

2.2	Vehicle Prequalification

2.2.1	Perform evaluation of vehicle eligibility for the VRV and VAVR
		per Chapter 11 of the Carl Moyer Program Guidelines, approved
		revision 2008
	2.2.2	When evaluating vehicle eligibility, allow sufficient time so that
		vehicles are repaired or scrapped within an appropriate number of
		days prior to the vehicle's next biennial smog check test to maintain
		eligibility through the Carl Moyer Program.

2.3	Scheduling Appointments

2.3.1	Schedule appointments for events with those participants who have
		been prequalified.

2.4	Reminder Calls

2.4.1	Make reminder calls to eligible participants prior to events, and to
		participants prior to confirmatory smog check testing or repairs.

Task 3 - Conduct Weekend Events

Weekend events would be held at locations throughout the four counties that are served by the AQMD, with the goal of screening as many vehicles as possible in an organized, effective manner, and optimizing the next step, the scheduling of confirmatory testing of emissions-screened vehicles.  The objectives are to provide sufficient resources to support twenty events and reach vehicle scrapping/repair goals as indicated in Task 5.

The scope of this task will include, but not necessarily be limited to, the following:

3.1	Obtaining/providing permits, security, event staffing, traffic management, and event signage for venue locations

3.2	Emissions screening of vehicles should include the following techniques in at least one event:

- Remote sensing measurements for purpose of screening high emitting vehicles;

- Two speed idle testing of vehicles for purpose of screening high emitting vehicles;

- Use of MAHA’s  MPM4 and 4 gas analyzers/smoke opacity meters for purpose of screening high emitting vehicles (equipment will be made available by SCAQMD)

Analysis of the most effective screening tool shall be made by selected contractor for purposes of remaining events.

3.3	Distribution of vouchers and instructions for vehicles deemed to be eligible for confirmatory smog check testing at select Gold Shield Stations.

3.4	Representatives of selected Gold Shield Stations at the events to schedule appointments for confirmatory smog check testing.

3.5	Creating a welcoming, comfortable environment.

Task 4 - Data Collection/Tracking/Analysis

The goal of this task is to develop and implement database and web application software to document and report all aspects of program activities related to program marketing and call center activities, event activities, repair station vehicle emission testing and repair, and vehicle scrapping.

The scope of this task will include, but not necessarily be limited to the following:

4.1	Web interface shall provide SCAQMD staff access to all aspects of database
		in terms of data input, data output with export capabilities, and report 
		generation features.

4.2		Database and web application software shall provide real time status of all
	significant program related activities for tracking purposes.

4.3	Database and web application software shall use to the greatest 
		extent feasible, HEROS I database and web application software for cost 
		minimization purposes.

Task 5 - Vehicle Testing/Repairs/Scrapping

The objective of this task is to conduct confirmatory emission tests of pre-screened potential high emitting vehicles, and to repair or scrap vehicles that meet Carl Moyer Program eligibility requirements for the VRV and the VAVR, accordingly.  The scope of this task will include, but not necessarily be limited to the following:

5.1	Procurement of testing and repair services at Gold Shield Stations that are located throughout the four counties that are served by the AQMD.

5.2	Authorization, oversight, and tracking of appropriate smog check tests, repairs, and invoicing for eligible vehicles.

5.3	Compliance with the Project Criteria specified in Chapter 11 of Carl Moyer Program Guidelines, Approved Revision 2008.

5.4  The objectives are to have 4,500 to 5,600 eligible vehicles receive confirmatory
		smog check tests and to have at least 3,000 eligible vehicles repaired or
		scrapped through the program.

Task 6 – Project Reporting

In this task, reports are to be completed to monitor the progress and effectiveness of the HEROS Program.

6.1	Contractor shall make monthly reports that shall include, but not be limited to, the number of vehicle owners inquiring about the program, the number of vehicle owners eligible to participate in vehicle pre-screening and their status in the process, the costs associated with program including repairs, the staff hours and costs, and other information deemed necessary by AQMD staff to track the progress of the program and its costs

6.2	At or near the midpoint of Task 5, Contractor shall, in consultation with AQMD staff, analyze the results of the program and determine if any changes to methods or processes are necessary

6.3	Contractor shall provide monthly reports, final report, and a two-page summary report

6.4	At the conclusion of Task 5, Contractor shall prepare a final report that shall include but not be limited to:

a) Complete documentation of database and web application tools,

b) Documentation of the development of the program with lessons learned and 
	suggested improvements, and

c) Discussion of issues and challenges to implement program into the future

6.5	Contractor shall provide AQMD all hardware and software purchased as part of the contract

6.6	Contractor shall provide AQMD all data and information collected during the duration of the contract

B:	Schedule of Deliverables / Tasks

Execution of Task 6 shall be contingent upon approval by District staff of the final program plan report specified in the Deliverables portion of this Section as well as the monthly data analysis and transmittal of data.  It should be noted that District costs for contract(s) resulting from this RFP shall not exceed $1,600,000 in total.  In the event that additional funding either direct or in-kind (e.g., use of facilities or equipment), for this project is secured, the contract for this project will be amended and the scope of the work expanded.

SECTION VI:	REQUIRED QUALIFICATIONS

Include detailed specifications on experience, education, and training.  Also indicate proof of qualification requirements such as licenses, memberships and/or endorsements.

Teams of qualified corporations and/or individuals are encouraged to submit bids.

SECTION VII:	PROPOSAL SUBMITTAL REQUIREMENTS

Submitted proposals must follow the format outlined below and all requested information must be supplied.  Failure to submit proposals in the required format will result in elimination from proposal evaluation.

Each proposal must be submitted in three separate volumes:

- Volume I - Technical Proposal

- Volume II - Cost Proposal

- Volume III - Certifications and Representations included in Attachment A to this RFP, should be executed by an authorized official of the Contractor.

A separate cover letter including the name, address, and telephone number of the contractor, and signed by the person or persons authorized to represent the firm should accompany the proposal submission. Firm contact information as follows should also be included in the cover letter:

1.	Address and telephone number of office in, or nearest to, Diamond Bar, California.

- Name and title of firm's representative designated as contact.

A separate Table of Contents should be provided for Volumes I and II.

VOLUME  I - TECHNICAL PROPOSAL

DO NOT INCLUDE ANY COST INFORMATION IN THE TECHNICAL VOLUME

Summary (Section A) - State overall approach to meeting the objectives and satisfying the scope of work to be performed, the sequence of activities, and a description of methodology or techniques to be used.

Program Schedule (Section B) - Provide projected milestones or benchmarks for submitting reports within the total time allowed.

Project Organization (Section C) - Describe the proposed management structure, program monitoring procedures, and organization of the proposed team.

Qualifications (Section D) - Describe the technical capabilities of the firm.  Provide references of other similar studies performed during the last five years demonstrating ability to successfully complete the project.  Include contact name, title, and telephone number for any references listed.  Provide a statement of your firm's background and experience in performing similar projects for other governmental organizations.

Assigned Personnel (Section E) - Provide the following information on the staff to be assigned to this project:

- List all key personnel assigned to the project by level and name.  Provide a resume or similar statement of the qualifications of the lead person and all persons assigned to the project.  Substitution of project manager or lead personnel will not be permitted without prior written approval of AQMD.

- Provide a spreadsheet of the labor hours proposed for each labor category at the task level.

- Provide a statement indicating whether or not 100% of the work will be performed within the geographical boundaries of the AQMD.

- Provide a statement of the education and training program provided by, or required of, the staff identified for participation in the project, particularly with reference to management consulting, governmental practices and procedures, and technical matters.

- Provide a summary of your firm’s general qualifications to meet required qualifications and fulfill statement of work, including additional firm personnel and resources beyond those who may be assigned to the project.

Subcontractors (Section F) - This project may require expertise in multiple technical areas.  List any subcontractors that may be used and the work to be performed by them.

Conflict of Interest (Section G) - Address possible conflicts of interest with other clients affected by actions performed by the firm on behalf of AQMD.  Although the Proposer will not be automatically disqualified by reason of work performed for such firms, AQMD reserves the right to consider the nature and extent of such work in evaluating the proposal.

Additional Data (Section H) - Provide other essential data that may assist in the evaluation of this proposal.

VOLUME  II - COST PROPOSAL

Name and Address - The Cost Proposal must list the name and complete address of the Proposer in the upper left-hand corner.

Cost Proposal – Contractor shall propose a Time and Materials (T&M) effort to accomplish all tasks incorporated herein.  Cost information must be provided as listed below:

1.	Detail must be provided by the following categories:

- Labor - List the total number of hours and the hourly billing rate for each level of professional staff.  A breakdown of the proposed billing rates must identify the direct labor rate, overhead rate and amount, fringe benefit rate and amount, General and Administrative rate and amount, and proposed profit or fee.  Provide a basis of estimate justifying the proposed labor hours and proposed labor mix.

- Subcontractor Costs - List subcontractor costs and identify subcontractors by name.  Itemize subcontractor charges per hour or per day.

- Travel Costs - Indicate amount of travel cost and basis of estimate to include trip destination, purpose of trip, length of trip, airline fare or mileage expense, per diem costs, lodging and car rental.

- Other Direct Costs -This category may include such items as postage and mailing expense, printing and reproduction costs, etc.  Provide a basis of estimate for these costs.

VOLUME  III - CERTIFICATIONS AND REPRESENTATIONS

(see Attachment A to this RFP)

SECTION VIII:	PROPOSAL SUBMISSION

All proposals must be submitted according to specifications set forth in the section above.  Failure to adhere to these specifications may be cause for rejection of proposal.

Signature - All proposals should be signed by an authorized representative of the Proposer.

Due Date - The Proposer shall submit eight (8) complete copies of the proposal in a sealed envelope, plainly marked in the upper left-hand corner with the name and address of the Proposer and the words "Request for Proposals #2009-10."  All proposals are due no later than 1:00 p.m., February 6, 2009, and should be directed to:

Lori Berard, Air Quality Specialist

Mobile Source Division

South Coast Air Quality Management District

21865 Copley Drive

Diamond Bar, CA  91765-4178

(909) 396-2436

Late bids/proposals will not be accepted.  Any correction or resubmission done by the Proposer will not extend the submittal due date.

Grounds for Rejection - A proposal may be immediately rejected if:

- It is not prepared in the format described, or

- It is signed by an individual not authorized to represent the firm.

Disposition of Proposals - AQMD reserves the right to reject any or all proposals.  All responses become the property of AQMD.  One copy of the proposal shall be retained for AQMD files.  Additional copies and materials will be returned only if requested and at the proposer's expense.

Modification or Withdrawal -  Once submitted, proposals cannot be altered without the prior written consent of AQMD.  All proposals shall constitute firm offers and may not be withdrawn for a period of ninety (90) days following the last day to accept proposals.

SECTION IX:	PROPOSAL EVALUATION/CONTRACTOR SELECTION CRITERIA

- Proposals will be evaluated by a panel of three to five members familiar with the subject matter of the project.  The panel shall be appointed by the Executive Officer or his designee.  The panel will make a recommendation to the Executive Officer and/or the Governing Board of the AQMD for final selection of a contractor and negotiation of a contract.

- Each member of the evaluation panel shall be accorded equal weight in his or her rating of proposals.  The evaluation panel members shall evaluate the proposals according to the specified criteria and numerical weightings set forth below.

1.	Technical Proposal	(maximum 70 Points )

- Understanding the Problem/Requirements 	10 points

- Technical/Management Approach	25 points

- Contractor Qualifications	10 points

- Previous Experience on Similar Projects	25 Points

Sub Total	70 points

In step 1, all proposers would be required to score a minimum of 56 points to be considered technically qualified.  Those considered technically qualified would proceed to Step 2.

Cost Proposal	(maximum 30 Points )

- Cost, including Cost Sharing	30 points

- Proposal proposing the greatest amount of cost share
will receive maximum points – others will be prorated
 accordingly

Sub Total	30 points

____________

Total 	100 points

In step 1, all proposers would be required to score a minimum of 56 points to be considered technically qualified.  Those considered technically qualified would proceed to Step 2.

Additional Points

- Small Business or Small Business Joint Venture	10 points

- DVBE or DVBE Joint Venture	10 points

- Use of DVBE or Small Business Subcontractors	7 points

- Local Business (Non-EPA Funded Projects Only)	5 points

- Low Emission Vehicle Business	5 points

- Off Peak Hours Delivery Business	2 points

The cumulative points awarded for small business, DVBE, use of small business or DVBE subcontractors, low-emission vehicle business, local business, and off-peak hours delivery business shall not exceed 15 points.

- To receive additional points in the evaluation process for the categories of Small Business or Small Business Joint Venture, DVBE or DVBE Joint Venture or Local Business (for non-EPA funded projects), the proposer must submit a self-certification or certification from the State of California Office of Small Business Certification and Resources at the time of proposal submission certifying that the proposer meets the requirements set forth in Section III.  To receive points for the use of DVBE and/or Small Business subcontractors, at least 25 percent of the total contract value must be subcontracted to DVBEs and/or Small Businesses.  To receive points as a Low-Emission Vehicle Business, the proposer must demonstrate to the Executive Officer, or designee, that supplies and materials delivered to the AQMD are delivered in vehicles that operate on either clean-fuels or if powered by diesel fuel, that the vehicles have particulate traps installed.  To receive points as an Off-Peak Hours Delivery Business, the proposer must submit, at proposal submission, certification of its commitment to delivering supplies and materials to AQMD between the hours of 10:00 a.m. and 3:00 p.m.  The cumulative points awarded for small business, DVBE, use of Small Business or DVBE Subcontractors, Local Business, Low-Emission Vehicle Business and Off-Peak Hour Delivery Business shall not exceed 15 points.

The Procurement Section will be responsible for monitoring compliance of suppliers awarded purchase orders based upon use of low-emission vehicles or off-peak traffic hour delivery commitments through the use of vendor logs which will identify the contractor awarded the incentive.  The purchase order shall incorporate terms which obligate the supplier to deliver materials in low-emission vehicles or deliver during off-peak traffic hours.  The Receiving department will monitor those qualified supplier deliveries to ensure compliance to the purchase order requirements.  Suppliers in non-compliance will be subject to a two percent of total purchase order value penalty.  The Procurement Manager will adjudicate any disputes regarding either low-emission vehicle or off-peak hour deliveries.

- For procurement of Research and Development (R & D) projects or projects requiring technical or scientific expertise or special projects requiring unique knowledge and abilities, technical factors including past experience shall be weighted at 70 points and cost shall be weighted at 30 points.  A proposal must receive at least 56 out of 70 points on R & D projects and projects requiring technical or scientific expertise or special projects requiring unique knowledge and abilities, in order to be deemed qualified for award.

- The lowest cost proposal will be awarded the maximum cost points available and all other cost proposals will receive points on a prorated basis.  For example if the lowest cost proposal is $1,000 and the maximum points available are 30 points, this proposal would receive the full 30 points.  If the next lowest cost proposal is $1,100 it would receive 27 points reflecting the fact that it is 10% higher than the lowest cost (90% of 30 points = 27 points).

- During the selection process the evaluation panel may wish to interview some proposers for clarification purposes only.  No new material will be permitted at this time.

- The Executive Officer or Governing Board may award the contract to a proposer other than the proposer receiving the highest rating in the event the Governing Board determines that another proposer from among those technically qualified would provide the best value to AQMD considering cost and technical factors.  The determination shall be based solely on the Evaluation Criteria contained in the Request for Proposal (RFP), on evidence provided in the proposal and on any other evidence provided during the bid review process.  Evidence provided during the bid review process is limited to clarification by the Proposer of information presented in his/her proposal.

- Selection will be made based on the above-described criteria and rating factors.  The selection will be made by and is subject to Executive Officer or Governing Board approval.  All proposers will be notified of the results by letter.

- The Executive Officer or Governing Board may award contracts to more than one proposer if in (his or their) sole judgment the purposes of the (contract or award) would best be served by selecting multiple proposers.

- If additional funds become available, the Executive Officer or Governing Board may increase the amount awarded.  The Executive Officer or Governing Board may also select additional proposers for a grant or contract if additional funds become available.

- Upon mutual agreement of the parties of any resultant contract from this RFP, the original contract term may be extended.

SECTION X:	FUNDING

The total funding for the work contemplated by this RFP will be a maximum $1,600,000 for the full term of the contract.

SECTION XI:	 DRAFT CONTRACT (Provided as a sample only)

South Coast

Air Quality Management District

This Contract consists of *** pages.

- PARTIES - The parties to this Contract are the South Coast Air Quality Management District (referred to here as "AQMD") whose address is 21865 Copley Drive, Diamond Bar, California 91765-4178, and *** (referred to here as "CONTRACTOR") whose address is ***.

- RECITALS

- AQMD is the local agency with primary responsibility for regulating stationary source air pollution in the South Coast Air Basin in the State of California.  AQMD is authorized to enter into this Contract under California Health and Safety Code Section 40489.  AQMD desires to contract with CONTRACTOR for services described in Attachment 1 - Statement of Work, attached here and made a part here by this reference.  CONTRACTOR warrants that it is well-qualified and has the experience to provide such services on the terms set forth here.

- CONTRACTOR is authorized to do business in the State of California and attests that it is in good tax standing with the California Franchise Tax Board.

- All parties to this Contract have had the opportunity to have this Contract reviewed by their attorney.

- CONTRACTOR agrees to obtain the required licenses, permits, and all other appropriate legal authorizations from all applicable federal, state and local jurisdictions and pay all applicable fees.

- PERFORMANCE REQUIREMENTS

- CONTRACTOR warrants that it holds all necessary and required licenses and permits to provide these services.  CONTRACTOR further agrees to immediately notify AQMD in writing of any change in its licensing status.

- CONTRACTOR shall submit reports to AQMD as outlined in Attachment 1 - Statement of Work.  All reports shall be submitted in an environmentally friendly format:  recycled paper; stapled, not bound; black and white, double-sided print; and no three-ring, spiral, or plastic binders or cardstock covers.  AQMD reserves the right to review, comment, and request changes to any report produced as a result of this Contract.

- CONTRACTOR shall perform all tasks set forth in Attachment 1 - Statement of Work, and shall not engage, during the term of this Contract, in any performance of work that is in direct or indirect conflict with duties and responsibilities set forth in Attachment 1 - Statement of Work.

- CONTRACTOR shall be responsible for exercising the degree of skill and care customarily required by accepted professional practices and procedures subject to AQMD's final approval which AQMD will not unreasonably withhold.  Any costs incurred due to the failure to meet the foregoing standards, or otherwise defective services which require re-performance, as directed by AQMD, shall be the responsibility of CONTRACTOR.  CONTRACTOR's failure to achieve the performance goals and objectives stated in Attachment 1- Statement of Work, is not a basis for requesting re-performance unless work conducted by CONTRACTOR is deemed by AQMD to have failed the foregoing standards of performance.

- Remove if not needed:CONTRACTOR shall post a performance bond in the amount of *** Dollars ($***) from a surety authorized to issue such bonds within the State. [USE IF REQUIRED]

- Remove if not needed:AQMD has the right to review the terms and conditions of the performance bond and to request modifications thereto which will ensure that AQMD will be compensated in the event CONTRACTOR fails to perform and also provides AQMD with the opportunity to review the qualifications of the entity designated by the issuer of the performance bond to perform in CONTRACTOR's absence and, if necessary, the right to reject such entity. [USE IF REQUIRED]

- CONTRACTOR shall ensure, through its contracts with any subcontractor(s), that employees and agents performing under this Contract shall abide by the requirements set forth in this clause.

- TERM - The term of this Contract is from the date of execution by both parties (or insert date) to ***, unless further extended by amendment of this Contract in writing.  No work shall commence until this Contract is fully executed by all parties.

- TERMINATION - In the event any party fails to comply with any term or condition of this Contract, or fails to provide the services in the manner agreed upon by the parties, including, but not limited to, the requirements of Attachment 1 - Statement of Work, this failure shall constitute a breach of the Contract.  The nonbreaching party shall either notify the breaching party that it must cure this breach or provide written notification of its intention to terminate this Contract.  Notification shall be provided in the manner set forth in Clause 10.  The nonbreaching party reserves all rights under law and equity to enforce this Contract and recover any damages.  AQMD reserves the right to terminate this Contract at any time for nonbreach, and for the convenience of AQMD for any reason judged sufficient by AQMD. AQMD will reimburse CONTRACTOR for actual costs incurred (not to exceed the total Contract value), including all noncancellable commitments incurred in performance of this Contract through the effective date of termination for any reason other than breach.

- INSURANCE

- CONTRACTOR shall furnish evidence to AQMD of workers' compensation insurance for each of its employees, and the employees of all subcontractors, in accordance with either California or other applicable statutory requirements prior to commencement of any work on this Contract.

- CONTRACTOR shall furnish evidence to AQMD of liability insurance with a combined single limit (general and automotive) of *** Dollars ($***) prior to commencement of any work on this Contract.  AQMD shall be named as an additional insured on any such liability policy, and thirty (30)-days written notice prior to any modification of any such insurance shall be given by CONTRACTOR to AQMD and such modifications are subject to pre-approval by AQMD.

- If CONTRACTOR fails to maintain the required insurance coverage set forth above, AQMD reserves the right either to purchase such additional insurance and to deduct the cost thereof from any payments owed to CONTRACTOR or terminate this Contract for breach.

- All insurance certificates should be mailed to: AQMD Risk Management, 21865 Copley Drive, Diamond Bar, CA 91765-4178.  Include the AQMD Contract Number on the face of the certificate.

- CONTRACTOR must provide updates on the insurance coverage throughout the term of the Contract to ensure that there is no break in coverage during the period of contract performance.  Failure to provide evidence of current coverage shall be grounds for termination for breach of Contract.

- INDEMNIFICATION - CONTRACTOR agrees to hold harmless, indemnify, and defend AQMD, its officers, employees, agents, representatives, and successors-in-interest against any and all loss, damage, cost, or expenses which AQMD, its officers, employees, agents, representatives, and successors-in-interest may incur or be required to pay by reason of any injury or property damage caused or incurred by CONTRACTOR, its employees, subcontractors, or agents as a result of the performance of this Contract.

- CO-FUNDING [USE IF REQUIRED]

- CONTRACTOR shall obtain co-funding as follows:  ***, *** Dollars ($***); ***, *** Dollars ($***); ***, *** Dollars ($***); ***, *** Dollars ($***); ***, *** Dollars ($***); and ***, *** Dollars ($***).

- If CONTRACTOR fails to obtain co-funding in the amount(s) referenced above, then AQMD reserves the right to renegotiate or terminate this Contract.

- CONTRACTOR shall provide co-funding in the amount of *** Dollars ($***) for this project.  If CONTRACTOR fails to provide this co-funding, then AQMD reserves the right to renegotiate or terminate this Contract.

- PAYMENT

[FIXED PRICE](Choose one of the following)

- AQMD shall pay CONTRACTOR a fixed price of *** Dollars ($***) for work performed under this Contract in accordance with Attachment 2 - Payment Schedule, attached here and included here by reference.  Payment shall be made by AQMD to CONTRACTOR within thirty (30) days after approval by AQMD of an invoice prepared and furnished by CONTRACTOR showing services performed and referencing tasks and deliverables as shown in Attachment 1 - Statement of Work, and the amount of charge claimed.  Each invoice must be prepared in duplicate, on company letterhead, and list AQMD's Contract number, period covered by invoice, and CONTRACTOR's social security number or Employer Identification Number and submitted to: South Coast Air Quality Management District, Attn: ***.

- An amount equal to ten percent (10%) shall be withheld from all charges paid until satisfactory completion and final acceptance of work by AQMD. [OPTIONAL]

- AQMD reserves the right to disallow charges when the invoiced services are not performed satisfactorily in AQMD sole judgment.

[T & M].

- AQMD shall pay CONTRACTOR a total not to exceed amount of *** Dollars ($***), including any authorized travel-related expenses, for time and materials at rates in accordance with Attachment 2 - Payment Schedule, attached here and included here by this reference. Payment of charges shall be made by AQMD to CONTRACTOR within thirty (30) days after approval by AQMD of an itemized invoice prepared and furnished by CONTRACTOR referencing line item expenditures as listed in Attachment 2 and the amount of charge claimed.  Each invoice must be prepared in duplicate, on company letterhead, and list AQMD's Contract number, period covered by invoice, and CONTRACTOR's social security number or Employer Identification Number and submitted to:  South Coast Air Quality Management District, Attn: ***.

- CONTRACTOR shall adhere to total tasks and/or cost elements (cost category) expenditures as listed in Attachment 2.  Reallocation of costs between tasks and/or cost category expenditures is permitted up to One Thousand Dollars ($1,000) upon prior written approval from AQMD.  Reallocation of costs in excess of One Thousand Dollars ($1,000) between tasks and/or cost category expenditures requires an amendment to this Contract.

- AQMD's payment of invoices shall be subject to the following limitations and requirements:

i) Charges for equipment, material, and supply costs, travel expenses, subcontractors, and other charges, as applicable, must be itemized by CONTRACTOR.  Reimbursement for equipment, material, supplies, subcontractors, and other charges shall be made at actual cost.  Supporting documentation must be provided for all individual charges (with the exception of direct labor charges provided by CONTRACTOR) in excess of Two Hundred and Fifty Dollars ($250).  AQMD's reimbursement of travel expenses and requirements for supporting documentation are listed below.

ii)CONTRACTOR's failure to provide receipts shall be grounds for AQMD's non-reimbursement of such charges.  AQMD may reduce payments on invoices by those charges for which receipts were not provided.

iii)AQMD shall not pay interest, fees, handling charges, or cost of money on Contract.

- AQMD shall reimburse CONTRACTOR for travel-related expenses only if such travel is expressly set forth in Attachment 2 - Payment Schedule of this Contract or pre-authorized by AQMD in writing.

i)AQMD's reimbursement of travel-related expenses shall cover lodging, meals, other incidental expenses, and costs of transportation subject to the following  limitations:

Air Transportation - Coach class rate for all flights.  If coach is not available, business class rate is permissible.

Car Rental - A compact car rental.  A mid-size car rental is permissible if car rental is shared by three or more individuals.

Lodging - Up to Ninety Dollars ($90) per night.  A higher amount of reimbursement is permissible if pre-approved by AQMD.

Meals - Daily allowance is Thirty-Five Dollars Fifty Cents ($35.50).

ii)Supporting documentation shall be provided for travel-related expenses in accordance with the following requirements:

Lodging, Airfare, Car Rentals - Bill(s) for actual expenses incurred.

Meals - Meals billed in excess of $35.50 each day require receipts or other supporting documentation for the total amount of the bill and must be approved by AQMD.

Mileage - Beginning each January 1, the rate shall be adjusted effective February 1 by the Chief Financial Officer based on the Internal Revenue Service Standard Mileage Rate

Other travel-related expenses - Receipts are required for all individual items in excess of Fifty Dollars ($50).

- AQMD reserves the right to disallow charges when the invoiced services are not performed satisfactorily in AQMD sole judgment.

- INTELLECTUAL PROPERTY RIGHTS - Title and full ownership rights to any software, documents, or reports developed under this Contract shall at all times remain with AQMD.  Such material is agreed to be AQMD proprietary information.

- Rights of Technical Data - AQMD shall have the unlimited right to use technical data, including material designated as a trade secret, resulting from the performance of services by CONTRACTOR under this Contract.  CONTRACTOR shall have the right to use technical data for its own benefit.

- Copyright - CONTRACTOR agrees to grant AQMD a royalty-free, nonexclusive, irrevocable license to produce, translate, publish, use, and dispose of all copyrightable material first produced or composed in the performance of this Contract.

- NOTICES - Any notices from either party to the other shall be given in writing to the attention of the persons listed below, or to other such addresses or addressees as may hereafter be designated in writing for notices by either party to the other.  Notice shall be given by certified, express, or registered mail, return receipt requested, and shall be effective as of the date of receipt indicated on the return receipt card.

AQMD:		South Coast Air Quality Management District

21865 Copley Drive

Diamond Bar, CA  91765-4178

Attn: ***

CONTRACTOR:	***

***

***

Attn: ***

- EMPLOYEES OF CONTRACTOR

- AQMD reserves the right to review the resumes of any of CONTRACTOR employees, and/or any subcontractors selected to perform the work specified here and to disapprove CONTRACTOR choices.  CONTRACTOR warrants that it will employ no subcontractor without written approval from AQMD.  CONTRACTOR shall be responsible for the cost of regular pay to its employees, as well as cost of vacation, vacation replacements, sick leave, severance pay and pay for legal holidays.

- CONTRACTOR, its officers, employees, agents, representatives or subcontractors shall in no sense be considered employees or agents of AQMD, nor shall CONTRACTOR, its officers, employees, agents, representatives or subcontractors be entitled to or eligible to participate in any benefits, privileges, or plans, given or extended by AQMD to its employees.

- CONFIDENTIALITY - It is expressly understood and agreed that AQMD may designate in a conspicuous manner the information which CONTRACTOR obtains from AQMD as confidential. CONTRACTOR agrees to:

- Observe complete confidentiality with respect to such information, including without limitation, agreeing not to disclose or otherwise permit access to such information by any other person or entity in any manner whatsoever, except that such disclosure or access shall be permitted to employees or subcontractors of CONTRACTOR requiring access in fulfillment of the services provided under this Contract.

- Ensure that CONTRACTOR's officers, employees, agents, representatives, and independent contractors are informed of the confidential nature of such information and to assure by agreement or otherwise that they are prohibited from copying or revealing, for any purpose whatsoever, the contents of such information or any part thereof, or from taking any action otherwise prohibited under this clause.

- Not use such information or any part thereof in the performance of services to others or for the benefit of others in any form whatsoever whether gratuitously or for valuable consideration, except as permitted under this Contract.

- Notify AQMD promptly and in writing of the circumstances surrounding any possession, use, or knowledge of such information or any part thereof by any person or entity other than those authorized by this clause.

- Take at CONTRACTOR expense, but at AQMD's option and in any event under AQMD's control, any legal action necessary to prevent unauthorized use of such information by any third party or entity which has gained access to such information at least in part due to the fault of CONTRACTOR.

- Take any and all other actions necessary or desirable to assure such continued confidentiality and protection of such information.

- Prevent access to such information by any person or entity not authorized under this Contract.

- Establish specific procedures in order to fulfill the obligations of this clause.

- Notwithstanding the above, nothing herein is intended to abrogate or modify the provisions of Government Code Section 6250 et.seq. (Public Records Act).

- PUBLICATION

- AQMD shall have the right of prior written approval of any document which shall be disseminated to the public by CONTRACTOR in which CONTRACTOR utilized information obtained from AQMD in connection with performance under this Contract.

- Information, data, documents, or reports developed by CONTRACTOR for AQMD, pursuant to this Contract, shall be part of AQMD public record unless otherwise indicated.  CONTRACTOR may use or publish, at its own expense, such information provided to AQMD.  The following acknowledgment of support and disclaimer must appear in each publication of materials, whether copyrighted or not, based upon or developed under this Contract.

"This report was prepared as a result of work sponsored, paid for, in whole or in part, by the South Coast Air Quality Management District (AQMD).  The opinions, findings, conclusions, and recommendations are those of the author and do not necessarily represent the views of AQMD.  AQMD, its officers, employees, contractors, and subcontractors make no warranty, expressed or implied, and assume no legal liability for the information in this report.  AQMD has not approved or disapproved this report, nor has AQMD passed upon the accuracy or adequacy of the information contained herein."

- CONTRACTOR shall inform its officers, employees, and subcontractors involved in the performance of this Contract of the restrictions contained herein and require compliance with the above.

- NON-DISCRIMINATION - In the performance of this Contract, CONTRACTOR shall not discriminate in recruiting, hiring, promotion, demotion, or termination practices on the basis of race, religious creed, color, national origin, ancestry, sex, age, or physical or mental disability and shall comply with the provisions of the California Fair Employment & Housing Act (Government Code Section 12900 et seq.), the Federal Civil Rights Act of 1964 (P.L. 88-352) and all amendments thereto, Executive Order No. 11246 (30 Federal Register 12319), and all administrative rules and regulations issued pursuant to said Acts and Order.  CONTRACTOR shall likewise require each subcontractor to comply with this clause and shall include in each such subcontract language similar to this clause.

- SOLICITATION OF EMPLOYEES - CONTRACTOR expressly agrees that CONTRACTOR shall not, during the term of this Contract, nor for a period of six months after termination, solicit for employment, whether as an employee or independent contractor, any person who is or has been employed by AQMD during the term of this Contract without the consent of AQMD.

- PROPERTY AND SECURITY - Without limiting CONTRACTOR obligations with regard to security, CONTRACTOR shall comply with all the rules and regulations established by AQMD for access to and activity in and around AQMD premises.

- ASSIGNMENT - The rights granted hereby may not be assigned, sold, licensed, or otherwise transferred by either party without the prior written consent of the other, and any attempt by either party to do so shall be void upon inception.

- NON-EFFECT OF WAIVER - The failure of CONTRACTOR or AQMD to insist upon the performance of any or all of the terms, covenants, or conditions of this Contract, or failure to exercise any rights or remedies hereunder, shall not be construed as a waiver or relinquishment of the future performance of any such terms, covenants, or conditions, or of the future exercise of such rights or remedies, unless otherwise provided for herein.

- ATTORNEYS' FEES - In the event any action is filed in connection with the enforcement or interpretation of this Contract, each party shall bear its own attorneys' fees and costs.

- FORCE MAJEURE - Neither AQMD nor CONTRACTOR shall be liable or deemed to be in default for any delay or failure in performance under this Contract or interruption of services resulting, directly or indirectly, from acts of God, civil or military authority, acts of public enemy, war, strikes, labor disputes, shortages of suitable parts, materials, labor or transportation, or any similar cause beyond the reasonable control of AQMD or CONTRACTOR.

- SEVERABILITY - In the event that any one or more of the provisions contained in this Contract shall for any reason be held to be unenforceable in any respect by a court of competent jurisdiction, such holding shall not affect any other provisions of this Contract, and the Contract shall then be construed as if such unenforceable provisions are not a part hereof.

- HEADINGS - Headings on the clauses of this Contract are for convenience and reference only, and the words contained therein shall in no way be held to explain, modify, amplify, or aid in the interpretation, construction, or meaning of the provisions of this Contract.

- DUPLICATE EXECUTION - This Contract is executed in duplicate.  Each signed copy shall have the force and effect of an original.

- GOVERNING LAW - This Contract shall be construed and interpreted and the legal relations created thereby shall be determined in accordance with the laws of the State of California.  Venue for resolution of any disputes under this Contract shall be Los Angeles County, California.

- CITIZENSHIP AND ALIEN STATUS

- CONTRACTOR warrants that it fully complies with all laws regarding the employment of aliens and others, and that its employees performing services hereunder meet the citizenship or alien status requirements contained in federal and state statutes and regulations including, but not limited to, the Immigration Reform and Control Act of 1986 (P.L. 99-603).  CONTRACTOR shall obtain from all covered employees performing services hereunder all verification and other documentation of employees' eligibility status required by federal statutes and regulations as they currently exist and as they may be hereafter amended.  CONTRACTOR shall have a continuing obligation to verify and document the continuing employment authorization and authorized alien status of employees performing services under this Contract to insure continued compliance with all federal statutes and regulations.

- Notwithstanding paragraph A above, CONTRACTOR, in the performance of this Contract, shall not discriminate against any person in violation of 8 USC Section 1324b.

- CONTRACTOR shall retain such documentation for all covered employees for the period described by law.  CONTRACTOR shall indemnify, defend, and hold harmless AQMD, its officers and employees from employer sanctions and other liability which may be assessed against CONTRACTOR or AQMD, or both in connection with any alleged violation of federal statutes or regulations pertaining to the eligibility for employment of persons performing services under this Contract.

- FEDERAL FAIR SHARE POLICY - As a recipient of Environmental Protection Agency (EPA) grant funds, AQMD is required to flow down to all of its contractors the provisions of 40 CFR Section 31.36(e) which addresses affirmative steps for contracting with small-and-minority firms, women’s business enterprises, and labor surplus area firms.  CONTRACTOR agrees to comply with these provisions.

- REQUIREMENT FOR FILING STATEMENT OF ECONOMIC INTERESTS - In accordance with the Political Reform Act of 1974 (Government Code Sec. 81000 et seq.) and regulations issued by the Fair Political Practices Commission (FPPC), AQMD has determined that the nature of the work to be performed under this Contract requires CONTRACTOR to submit a Form 700, Statement of Economic Interests for Designated Officials and Employees, for each of its employees assigned to work on this Contract.  These forms may be obtained from AQMD's District Counsels’ office. [USE IF REQUIRED]

- COMPLIANCE WITH SINGLE AUDIT ACT REQUIREMENTS [OPTIONAL - TO BE INCLUDED IN CONTRACTS WITH FOR-PROFIT CONTRACTORS WHICH HAVE FEDERAL PASS-THROUGH FUNDING] - During the term of the Contract, and f]or a period of three (3) years from the date of Contract expiration, and if requested in writing by the AQMD, CONTRACTOR shall allow the AQMD, its designated representatives and/or the cognizant Federal Audit Agency, access during normal business hours to all records and reports related to the work performed under this Contract.  [OPTIONAL - TO BE INCLUDED IN CONTRACTS WITH FEDERAL PASS-THROUGH FUNDING]CONTRACTOR assumes sole responsibility for reimbursement to the Federal Agency funding the prime grant or contract, a sum of money equivalent to the amount of any expenditures disallowed should the AQMD, its designated representatives and/or the cognizant Federal Audit Agency rule through audit exception or some other appropriate means that expenditures from funds allocated to the CONTRACTOR were not made in compliance with the applicable cost principles, regulations of the funding agency, or the provisions of this Contract. [OPTIONAL - TO BE INCLUDED IN CONTRACTS WITH FEDERAL PASS-THROUGH FUNDING]

[OPTIONAL - TO BE INCLUDED IN CONTRACTS WITH NON-PROFIT CONTRACTORS WHICH HAVE FEDERAL PASS-THROUGH FUNDING] - Beginning with CONTRACTOR's current fiscal year and continuing through the term of this Contract, Contractor shall have a single or program-specific audit conducted in accordance with the requirements of the Office of Management and Budget (OMB) Circular A-133 (Audits of States, Local Governments and Non-Profit Organizations), if CONTRACTOR expended Three Hundred Thousand Dollars ($300,000) or more in a year in Federal Awards.  Such audit shall be conducted by a firm of independent accountants in accordance with Generally Accepted Government Audit Standards (GAGAS). Within thirty (30) days of Contract execution,  CONTRACTOR shall forward to AQMD the most recent A-133 Audit Report issued by its independent auditors.  Subsequent A-133 Audit Reports shall be submitted to the AQMD within thirty (30) days of issuance.

CONTRACTOR shall allow the AQMD, its designated representatives and/or the cognizant Federal Audit Agency, access during normal business hours to all records and reports related to the work performed under this Contract. CONTRACTOR assumes sole responsibility for reimbursement to the Federal Agency funding the prime grant or contract, a sum of money equivalent to the amount of any expenditures disallowed should the AQMD, its designated representatives and/or the cognizant Federal Audit Agency rule through audit exception or some other appropriate means that expenditures from funds allocated to the CONTRACTOR were not made in compliance with the applicable cost principles, regulations of the funding agency, or the provisions of this Contract.

- OPTION TO EXTEND THE TERM OF THE CONTRACT - AQMD reserves the right to extend the contract for a one-year period commencing *****(enter date) at the (option price or Not-to-Exceed Amount) set forth in Attachment 2.  In the event that AQMD elects to extend the contract, a written notice of its intent to extend the contract shall be provided to CONTRACTOR no later than thirty (30) days prior to Contract expiration. [USE IF REQUIRED]

- KEY PERSONNEL - [OPTIONAL]insert person's name is deemed critical to the successful performance of this Contract.  Any changes in key personnel by CONTRACTOR must be approved by AQMD.  All substitute personnel must possess qualifications/experience equal to the original named key personnel and must be approved by AQMD.  AQMD reserves the right to interview proposed substitute key personnel. [USE IF REQUIRED]

- PREVAILING WAGES – [USE FOR INFRASTRUCTURE PROJECTS] CONTRACTOR is alerted to the prevailing wage requirements of California Labor Code section 1770 et seq.  Copies of the prevailing rate of per diem wages are on file at the AQMD’s headquarters, of which shall be made available to any interested party on request.  Notwithstanding the preceding sentence, CONTRACTOR shall be responsible for determining the applicability of the provisions of California Labor Code and complying with the same, including, without limitation, obtaining from the Director of the Department of Industrial Relations the general prevailing rate of per diem wages and the general prevailing rate for holiday and overtime work, making the same available to any interested party upon request, paying any applicable prevailing rates, posting copies thereof at the job site and flowing all applicable prevailing wage rate requirements to its subcontractors. CONTRACTOR shall indemnify, defend and hold harmless the South Coast Air Quality Management District against any and all claims, demands, damages, defense costs or liabilities based on failure to adhere to the above referenced statutes.

- APPROVAL OF SUBCONTRACT

- If CONTRACTOR intends to subcontract a portion of the work under this Contract, written approval of the terms of the proposed subcontract(s) shall be obtained from AQMD’s Executive Officer or designee prior to execution of the subcontract.  No subcontract charges will be reimbursed unless such approval has been obtained.

- Any material changes to the subcontract(s) that affect the scope of work, deliverable schedule, and/or cost schedule shall also require the written approval of the Executive Officer or designee prior to execution.

- The sole purpose of AQMD’s review is to insure that AQMD’s contract rights have not been diminished in the subcontractor agreement.  AQMD shall not supervise, direct, or have control over, or be responsible for, subcontractor’s means, methods, techniques, work sequences or procedures or for the safety precautions and programs incident thereto, or for any failure of subcontractor to comply with any local, state, or federal laws, or rules or regulations.

- ENTIRE CONTRACT - This Contract represents the entire agreement between the parties hereto related to CONTRACTOR providing services to AQMD and there are no understandings, representations, or warranties of any kind except as expressly set forth herein.  No waiver, alteration, or modification of any of the provisions herein shall be binding on any party unless in writing and signed by the party against whom enforcement of such waiver, alteration, or modification is sought.

IN WITNESS WHEREOF, the parties to this Contract have caused this Contract to be duly executed on their behalf by their authorized representatives.

SOUTH COAST AIR QUALITY MANAGEMENT DISTRICT		***

By:_________________________________________    By:____________________________________

Barry R. Wallerstein, D.Env., Executive Officer	            Dr. William A. Burke, Chairman, Governing Board

Date: _________________________________________

ATTEST:

Saundra McDaniel, Clerk of the Board

By: _____________________________________________

APPROVED AS TO FORM:

Kurt R. Wiese, District Counsel

By: _____________________________________________

ATTACHMENT A

CERTIFICATIONS AND REPRESENTATIONS

South Coast

Air Quality Management District

21865 Copley Drive, Diamond Bar, CA 91765-4178

(909) 396-2000 • www.aqmd.gov

Business Information Request

Dear SCAQMD Contractor/Supplier:

The South Coast Air Quality Management District (SCAQMD) is committed to ensuring that our contractor/supplier records are current and accurate.  If your firm is selected for award of a purchase order or contract, it is imperative that the information requested herein be supplied in a timely manner to facilitate payment of invoices.  In order to process your payments, we need the enclosed information regarding your account.  Please review and complete the information identified on the following pages, complete the enclosed W-9 form, remember to sign both documents for our files, and return them as soon as possible to the address below:

Attention:  Accounts Payable, Accounting Department

South Coast Air Quality Management District

21865 Copley Drive

Diamond Bar, CA 91765-4178

If you do not return this information, we will not be able to establish you as a vendor.  This will delay any payments and would still necessitate your submittal of the enclosed information to our Accounting department before payment could be initiated.  Completion of this document and enclosed forms would ensure that your payments are processed timely and accurately.

If you have any questions or need assistance in completing this information, please contact Accounting at (909) 396-3777.  We appreciate your cooperation in completing this necessary information.

Sincerely,

Patrick H. Pearce

Chief Financial Officer

DH:LV:CW:tm

Enclosures:	Business Information Request

Disadvantaged Business Certification

W-9

Federal Contract Debarment Certification

REV 8/06

South Coast

Air Quality Management District

21865 Copley Drive, Diamond Bar, CA 91765-4178

(909) 396-2000 • www.aqmd.gov

| ## BUSINESS INFORMATION REQUEST |  |  |  |
| --- | --- | --- | --- |
| Business Name |  |  |  |
| Division of: |  |  |  |
| Subsidiary of: |  |  |  |
| Website Address |  |  |  |
| Type of Business |  |  |  |
| ## REMITTING ADDRESS INFORMATION |  |  |  |
| Address |  |  |  |
| City/Town |  |  |  |
| State/Province |  | Zip |  |
| Phone | ( ) - Ext | Fax | ( ) - |
| Contact |  | Title |  |
| E-mail Address |  |  |  |
| Payment Name if Different |  |  |  |

All invoices must reference the corresponding Purchase Order Number(s)/Contract Number(s) if applicable and mailed to:

Attention:  Accounts Payable, Accounting Department

South Coast Air Quality Management District

21865 Copley Drive

Diamond Bar, CA  91765-4178

DISADVANTAGED BUSINESS CERTIFICATION

Federal guidance for utilization of disadvantaged business enterprises allows a vendor to be deemed a small business enterprise (SBE), minority business enterprise (MBE) or women business enterprise (WBE) if it meets the criteria below.

- is certified by the Small Business Administration or

- is certified by a state or federal agency or

- is an independent MBE(s) or WBE(s) business concern which is at least 51 percent owned and controlled by minority group member(s) who are citizens of the United States.

Following state guidance, a vendor may be deemed a disabled veteran business enterprise (DVBE) if it meets the following:

- is an independent business concern which is at least 51 percent owned and controlled by disabled veteran(s), and the home office is located in the U.S.

Statements of certification:

As a prime contractor to the SCAQMD,	     	 (name of business) will engage in good faith efforts to achieve the fair share in accordance with 40 CFR Section 31.36(e), and will follow the six affirmative steps listed below for contracts or purchase orders funded in whole or in part by federal grants and contracts.

- Place qualified SBEs, MBEs, and WBEs on solicitation lists.

- Assure that SBEs, MBEs, and WBEs are solicited whenever possible.

- When economically feasible, divide total requirements into small tasks or quantities to permit greater participation by SBEs, MBEs, and WBEs.

- Establish delivery schedules, if possible, to encourage participation by SBEs, MBEs, and WBEs.

- Use services of Small Business Administration, Minority Business Development Agency of the Department of Commerce, and/or any agency authorized as a clearinghouse for SBEs, MBEs, and WBEs.

- If subcontracts are to be let, take the above affirmative steps.

###### Self-Certification Verification:

Check all that apply:

Small business enterprise		Women-owned business enterprise

Local business		Disabled veteran-owned business enterprise

Minority-owned business enterprise

Percent of ownership:  	     	 	%

Name of Qualifying Owner(s):

I, the undersigned, hereby declare that to the best of my knowledge the above information is accurate.  Upon penalty of perjury, I certify information submitted is factual.

## NAME	TITLE

## TELEPHONE NUMBER	DATE

Definitions

Disabled Veteran-Owned Business Enterprise means a business that meets all of the following criteria:

- is a sole proprietorship or partnership of which is at least 51 percent owned by one or more disabled veterans, or in the case of any business whose stock is publicly held, at least 51 percent of the stock is owned by one or more disabled veterans; a subsidiary which is wholly owned by a parent corporation but only if at least 51 percent of the voting stock of the parent corporation is owned by one or more disabled veterans; or a joint venture in which at least 51 percent of the joint venture’s management and control and earnings are held by one or more disabled veterans.

- the management and control of the daily business operations are by one or more disabled veterans.  The disabled veterans who exercise management and control are not required to be the same disabled veterans as the owners of the business.

- is a sole proprietorship, corporation, partnership, or joint venture with its primary headquarters office located in the United States and which is not a branch or subsidiary of a foreign corporation, firm, or other foreign-based business.

Joint Venture means that one party to the joint venture is a MBE/WBE/DVBE and owns at least 51 percent of the joint venture.  In the case of a joint venture formed for a single project this means that MBE/WBE/DVBE will receive at least 51 percent of the project dollars.

Local Business means a business that meets all of the following criteria:

- has an ongoing business within the boundary of the SCAQMD at the time of bid application.

- performs 90 percent of the work within SCAQMD’s jurisdiction.

Minority-Owned Business Enterprise means a business that meets all of the following criteria:

- is at least 51 percent owned by one or more minority persons or in the case of any business whose stock is publicly held, at least 51 percent of the stock is owned by one or more minority persons.

- is a business whose management and daily business operations are controlled or owned by one or more minority person.

- is a business which is a sole proprietorship, corporation, partnership, joint venture, an association, or a cooperative with its primary headquarters office located in the United States, which is not a branch or subsidiary of a foreign corporation, foreign firm, or other foreign business.

“Minority” person means a Black American, Hispanic American, Native American (including American Indian, Eskimo, Aleut, and Native Hawaiian), Asian-Indian American (including a person whose origins are from India, Pakistan, or Bangladesh), Asian-Pacific American (including a person whose origins are from Japan, China, the Philippines, Vietnam, Korea, Samoa, Guam, the United States Trust Territories of the Pacific, Northern Marianas, Laos, Cambodia, or Taiwan).

Small Business Enterprise means a business that meets the following criteria:

- 1) an independently owned and operated business; 2) not dominant in its field of operation; 3) together with affiliates is either:

- A service, construction, or non-manufacturer with 100 or fewer employees, and average annual gross receipts of ten million dollars ($10,000,000) or less over the previous three years, or

- A manufacturer with 100 or fewer employees.

- Manufacturer means a business that is both of the following:

- Primarily engaged in the chemical or mechanical transformation of raw materials or processed substances into new products.

- Classified between Codes 2000 to 3999, inclusive, of the Standard Industrial Classification (SIC) Manual published by the United States Office of Management and Budget, 1987 edition.

Women-Owned Business Enterprise means a business that meets all of the following criteria:

- is at least 51 percent owned by one or more women or in the case of any business whose stock is publicly held, at least 51 percent of the stock is owned by one or more women.

- is a business whose management and daily business operations are controlled or owned by one or more women.

- is a business which is a sole proprietorship, corporation, partnership, or a joint venture, with its primary headquarters office located in the United States, which is not a branch or subsidiary of a foreign corporation, foreign firm, or other foreign business.

United State Environmental Protection Agency

Washington, DC 20460

Certification Regarding

Debarment, Suspension, and Other Responsibility Matters

The prospective participant certifies to the best of its knowledge and belief that it and the principals:

- Are not presently debarred, suspended, proposed for debarment, declared ineligible, or voluntarily excluded from covered transactions by any Federal department or agency;

- Have not within a three year period preceding this proposal been convicted of or had a civil judgement rendered against them or commission of fraud or a criminal offense in connection with obtaining, attempting to obtain, or performing a public (Federal, State, or local) transaction or contract under a public transaction: violation of Federal or State antitrust statute or commission of embezzlement, theft, forgery, bribery, falsification or destruction of records, making false statements, or receiving stolen property:

- Are not presently indicted for or otherwise criminally or civilly charged by a government entity (Federal, State, or local) with commission of any of the offenses enumerated in paragraph (1)(b) of this certification; and

- Have not within a three-year period preceding this application/proposal had one or more public transactions (Federal, State, or local) terminated for cause or default.

I understand that a false statement on this certification may be grounds for rejection of this proposal or termination of the award. In addition, under 18 USC Sec. 1001, a false statement may result in a fine of up to $10,000 or imprisonment for up to 5 years, or both.

________________________________________________________________________

Typed Name & Title of Authorized Representative

________________________________________________________________________

Signature of Authorized Representative                                Date

  I am unable to certify to the above statements.  My explanation is attached.

EPA Form 5700-49 (11-88)

CAMPAIGN CONTRIBUTIONS DISCLOSURE

California law prohibits a party, or an agent, from making campaign contributions to AQMD Governing Board Members or members/alternates of the Mobile Source Pollution Reduction Committee (MSRC) of $250 or more while their contract or permit is pending before the AQMD; and further prohibits a campaign contribution from being made for three (3) months following the date of the final decision by the Governing Board or the MSRC on a donor’s contract or permit.  Gov’t Code §84308(d).  For purposes of reaching the $250 limit, the campaign contributions of the bidder or contractor plus contributions by its parents, affiliates, and related companies of the contractor or bidder are added together.  2 C.C.R. §18438.5.

In addition, Board Members or members/alternates of the MSRC must abstain from voting on a contract or permit if they have received a campaign contribution from a party or participant to the proceeding, or agent, totaling $250 or more in the 12-month period prior to the consideration of the item by the Governing Board or the MSRC.  Gov’t Code §84308(c).  When abstaining, the Board Member or members/alternates of the MSRC must announce the source of the campaign contribution on the record.  Id.  The requirement to abstain is triggered by campaign contributions of $250 or more in total contributions of the bidder or contractor, plus any of its parent, subsidiary, or affiliated companies.  2 C.C.R. §18438.5.

In accordance with California law, bidders and contracting parties are required to disclose, at the time the application is filed, information relating to any campaign contributions made to Board Members or members/alternates of the MSRC, including: the name of the party making the contribution (which includes any parent, subsidiary or otherwise related business entity, as defined below), the amount of the contribution, and the date the contribution was made.  2 C.C.R. §18438.8(b).

The list of current AQMD Governing Board Members can be found at the AQMD website (www.aqmd.gov).  The list of current MSRC members/alternates can be found at the MSRC website (http://www.cleantransportationfunding.org).

SECTION I.  Please complete Section I.

Contractor:	RFP #:

List any parent, subsidiaries, or otherwise affiliated business entities of Contractor:  (See definition below).

SECTION II

Has contractor and/or parent, subsidiary, or affiliated company, or agent thereof, made a campaign contribution(s) totaling $250 or more in the aggregate to a current member of the South Coast Air Quality Management Governing Board or members/alternates of the MSRC in the 12 months preceding the date of execution of this disclosure?

Yes	  No	If YES, complete Section II below and then sign and date the form.
		If NO, sign and date below.  Include this form with your submittal.

Campaign Contributions Disclosure, continued:

Name of Contributor

Governing Board Member or MSRC Member/Alternate	Amount of Contribution		Date of Contribution

Name of Contributor

Governing Board Member or MSRC Member/Alternate	Amount of Contribution		Date of Contribution

Name of Contributor

Governing Board Member or MSRC Member/Alternate	Amount of Contribution		Date of Contribution

Name of Contributor

Governing Board Member or MSRC Member/Alternate	Amount of Contribution		Date of Contribution

Name of Contributor

Governing Board Member or MSRC Member/alternate	Amount of Contribution		Date of Contribution

I declare the foregoing disclosures to be true and correct.

By:

Title:

Date:

DEFINITIONS

Parent, Subsidiary, or Otherwise Related Business Entity.

(1)	Parent subsidiary. A parent subsidiary relationship exists when one corporation directly or indirectly owns shares possessing more than 50 percent of the voting power of another corporation.

(2)	Otherwise related business entity. Business entities, including corporations, partnerships, joint ventures and any other organizations and enterprises operated for profit, which do not have a parent subsidiary relationship are otherwise related if any one of the following three tests is met:

(A)	One business entity has a controlling ownership interest in the other business entity.

(B)	There is shared management and control between the entities. In determining whether there is shared management and control, consideration should be given to the following factors:

- The same person or substantially the same person owns and manages the two entities;

- There are common or commingled funds or assets;

- The business entities share the use of the same offices or employees, or otherwise share activities, resources or personnel on a regular basis;

- There is otherwise a regular and close working relationship between the entities; or

(C)	A controlling owner (50% or greater interest as a shareholder or as a general partner) in one entity also is a controlling owner in the other entity.

2 Cal. Code of Regs., §18703.1(d).