[Editor's Note:  This chapter is an example of a cost/benefit measurement report.  It is written as though reporting in the second year of the project described in Chapters 2 and 3.  This clarifies the relationship between the planning stage studies and the post-implementation measurement and reporting phase.]

Annual APD Update:  Section VII

Cost / Benefit Measurement Report:  Year 2

| Overview: | Costs and benefits are conforming closely with those projected during the planning phase of this systems development project. |
| --- | --- |
| Costs: | Costs incurred this fiscal year were about ten percent more than projected for this fiscal year, primarily due to support services and training costs. In response, the State has initiated cost control procedures to closely regulate contractor task assignments and performance and to provide in-house training. Further, reduced expenditures will be sought in the site and facility categories, given the local recession in the commercial real estate market and the corresponding drop in market prices. Part of this year's costs were offset by last year's lower than anticipated prices, which resulted from keen competition for the system hardware contract. |

|  | The graph at the top of the next page depicts the relationship of actual costs to projected costs. Details are on page 5 |
| --- | --- |
| Benefits Measurement: | Benefits were lower than anticipated in only two of the six benefit categories: overtime (benefit 2) and service bureau processing costs (benefit 4). Overtime was reduced $111,291 — $38,709 short of the $150,000 target. The overtime was required early in the year, when caseworkers were adapting to the new system and had not yet achieved operational efficiency. Given the performance of the last eight months, we expect that the full reduction of $150,000 will be met next year. Moderate service bureau processing costs ($21,655) were incurred this year, due to a slight slippage in full cut-over to the new system. Fully $589,340 of the projected $610,995 in benefits was realized. We expect that the full benefit will be realized next year. |

|  | The graph at the bottom of the preceding page depicts the relationship of actual benefits to projected benefits. Details are provided on page 5. |
| --- | --- |
|  | The State's plan to reduce caseworkers' administrative duties to 10% of their time has been realized (benefit 1), proven by repeating the study originally conducted in support of the cost/benefit analysis. In addition, the objective to control staff expenditures in meeting caseload growth was realized this year (benefit 3) and is on track for future years. With the new system and reductions in administrative duties, caseworker caseload increased from the old system's average of 460 per year, to 500 (annualized) in the first six months and 550 (annualized) in the last six months. Increasing operational efficiency and minor procedural improvements (already effected) should enable the caseworkers to attain the projected 560 case workload next year. Finally, the projected cost savings resulting from eliminating the use of courier services was realized (benefit 5). |
| Projected Breakeven: | The State still anticipates that the systems project will breakeven, at approximately the same time as originally projected. See below. |

| Performance Baseline: |  | The State has also made considerable progress toward the performance objectives set forth in the cost/benefit analysis. The chart below shows the baseline, current average, and target average. The current average was based on the last six months of operations, considered a more accurate representation due to increasing operational efficiency. While the goal has not been achieved in all cases, the State is implementing procedural changes to support full realization of the benefits by next year. |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | PERFORMANCE BASELINE AND TARGET |  |  |  |  |  |  |  |  |
|  | Category |  | Baseline | Current Average | Target Average |  |
|  | Input processing |  | 7 days | 3 days | Same day |  |
|  | Internal control checks |  | 3 days | 1 day | 1 day |  |
|  | Report transmission |  | 4 days | Same day | Same day |  |
|  | Acceptance of client data |  | 3 weeks | 8 days | 1 week |  |
|  | Delay to benefits |  | 3 months | 6 weeks | 1 month |  |

| Summary: | There were no unanticipated costs. There are preliminary indications that some unanticipated benefits may accrue. Based on information provided by the personnel office, absenteeism and employee turnover rates among caseworkers have decreased significantly. If this trend continues, the staffing plan may be further reduced for increased cost-avoidance benefits. |
| --- | --- |

Cost / Benefit Measurement Profile

Year Two

| SYSTEM LIFE COST PROFILE |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total |
| Non-Recurring Costs* | 3,580,472 | 0 | 0 | 0 | 0 | 3,580,472 |
| Recurring Costs* | 1,621,868 | 1,782,320 | 0 | 0 | 0 | 3,404,188 |
| Total Costs* | 5,202,340 | 1,782,320 | 0 | 0 | 0 | 6,984,660 |
| Total Projected Costs | 5,321,868 | 1,621,868 | 796,145 | 796,145 | 796,145 | 9,332,171 |
| Difference | -119,528 | 160,452 | 0 | 0 | 0 | 40,924 |
| SYSTEM LIFE BENEFITS PROFILE |  |  |  |  |  |  |  |  |  |  |  |  |
| Description | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total |
| Total Benefits* | 65,000 | 1,722,058 | 0 | 0 | 0 | 1,787,058 |
| Total Projected Benefits | 65,000 | 1,782,422 | 3,081,271 | 2,755,058 | 3,039,414 | 10,723,165 |
| Difference | 0 | -60,364 | 0 | 0 | 0 | -60,364 |
| CUMULATIVE BENEFIT / COST PROFILE (ACTUAL AND PROJECTED) |  |  |  |  |  |  |  |  |  |  |  |  |
| Description | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total |
| Cumulative Total Actual and Projected Benefits* | 65,000 | 1,787,058 | 4,868,329 | 7,623,387 | 10,662,801 | N/A |
| Cumulative Total Actual and Projected Costs* | 5,202,340 | 6,984,660 | 7,780,805 | 8,576,950 | 9,373,095 | N/A |
| COMPARISONS |  |  |  |  |  |  |  |  |  |  |  |  |
| Description | Actual to Date |  |  | Current Projected |  |  | Baseline |  |  |
| Total Benefits | 1,787,058 |  |  | 10,662,801 |  |  | 10,723,165 |  |  |
| Less Total Costs | 6,984,660 |  |  | 9,373,095 |  |  | 9,332,171 |  |  |
| Net Benefit (Cost) | -5,197,602 |  |  | 1,289,706 |  |  | 1,390,994 |  |  |
| Benefit/Cost Ratio | .26 |  |  | 1.14 |  |  | 1.15 |  |  |
| Breakeven | N/A |  |  | 58 |  |  | 58 |  |  |

*  Actuals, years 1 and 2.