PROCUREMENT SENSITIVE

MOST EFFICIENT ORGANIZATION

Food Services

7/28/2026

National Institutes of Health

Food Services

MEO

Chapter 1. Introduction	1-1

1.1 Background	1-1

1.2 Purpose	1-2

1.3 Scope of the Study	1-2

1.4 Methodology	1-3

1.5 Assumptions	1-3

1.6 MEO Format	1-3

Chapter 2. Most Efficient Organization	2-1

2.1 Current Operations	2-2

2.2 Management Analysis	2-12

2.3 Proposed MEO	2-18

Chapter 3. Quality Control Plan	3-1

3.1 Overview	3-2

3.2 Purpose	3-2

3.3 Responsibility	3-2

3.4 Record Keeping	3-2

3.5 Annual Evaluation Instructions	3-2

3.6 Completing the Annual Evaluation Report	3-2

3.7 Completing the Letter of Certification	3-3

3.8 Evaluation Score	3-3

Chapter 4. Continuing Government Activity (CGA)	4-1

4.1 General	4-2

4.2 CGA Staffing Calculations	4-2

Chapter 5. Phase-In Plan	5-1

5.1 General	5-2

5.2 Assumptions, References and Affected Organizations	5-2

5.3 Pre-Performance Decision Activities	5-2

5.4 Post-Performance Decision Activities	5-3

5.5 Utilities and Any Other Services And Costs To Be Transferred	5-6

5.6 Indicators Of Successful Transition	5-6

Chapter 6. Agency Cost Estimate	6-12

ATTACHMENTS

| Attachment Number | Description | Page |
| --- | --- | --- |
| Attachment 1 | Current Nutrition Department Organizational Chart | 1 |
| Technical Exhibit 2-001 | MEO Staffing Crosswalk | TE-2-001-1 |
| Technical Exhibit 2-002 | MEO Workload Analysis | TE-2-002-1 |
| Technical Exhibit 2-003 | MEO Position Descriptions | TE-2-003-1 |

National Institutes of Health

Food Services

MEO

# Introduction

## Background

As an agency of the Department of Health and Human Services (DHHS), The National Institutes of Health (NIH) is the primary Federal agency for administering and supporting medical and behavioral research.

Composed of 27 Institutes and Centers (IC), the NIH is the steward of medical and behavioral research for the Nation.  Its mission is science in pursuit of fundamental knowledge about the nature and behavior of living systems and the application of that knowledge to extend healthy life and reduce the burdens of illness and disability.

The NIH Clinical Center (CC) is one of the 27 ICs that establish NIH.  The CC is comprised of two facilities, the Mark O. Hatfield Clinical Research Center and the Warren 
Grant Magnuson Clinical Center. The NIH CC serves as the nation’s premier research hospital for conducting clinical research to improve the health of human kind.  Numerous NIH guest scientists from around the world collaborate in NIH CC activities. The NIH CC also offers training in research medicine for physicians, medical students, and nursing students.  The CC does not customarily provide standard diagnostic and treatment services.  Patients volunteer, are recruited or are referred by their Physicians and consent to participate in research studies (protocols) and are treated without charge.

Through the Food Services function the NIH CC Nutrition Department provides meals, nourishments, formulas, tube feedings and supplements to patients who are in an inpatient unit, day hospital, outpatient clinic or other location including, but not limited to, the Blood Bank and Radiation Clinic.  A state-of-the-art integrated food management computer system, CBORD, allows for the integration of varied clinical and research protocol needs through over 150 diet types and nutritional analysis of patient food intake.  The Food Service function of this department also provides room service, meal assembly and preparation, maintenance and the stocking of kitchen and food supplies.

The mission of the NIH Clinical Center Nutrition Department is to provide cost efficient, comprehensive, and properly coordinated nutritional care, food services and research support of the highest quality to patients of the Clinical Center in support of biomedical research.  The vision is to serve as a national model of excellence in provision of nutritional care, food services and research support.  The Clinical Center is a research hospital that caters to an international clinical patient population that is unique.  Patients that come to the Clinical Center are subject to research protocols and restrictions and may endure constant surveillance and medical testing by CC staff.  Many of the patients are recruited and are sought after for the research studies, thus the CC strives to create a comfortable environment to encourage patients to continue to return.  Therefore, it is extremely imperative that patients are given extraordinary service by the hospital.  Many of the research patients may be the link to discovering new information on medical treatments and prevention and are ministered to with the utmost care.  For these reasons the CC Nutrition Department Food Services operations strives to provide the CC patients quality service and respond to individual patient needs and requests affording the patients a comfortable visit in the CC.  The Food Services operations provide needed consistency to patients so that they can feel at ease.  With the addition of the room service operations patients are allowed much more flexibility to order an assortment of foods at times that are suitable for their needs.

Room service allows patient’s to telephone the call center and use a restaurant style menu that consists of a variety of foods.  The menu choices include breakfast, lunch and dinner meals available throughout the day.   Patients may place a meal order at their convenience between 6:30am-6:30pm and receive their food in a timely fashion.

The CC Nutrition Department Food Services operations make every effort to attain all patient choices rather than sending a non-select tray while accommodating up to 150 different diet types.  Paper Menu services are also provided for selected patient populations such as Spanish, kosher and behavioral health.

The Food Services operations also include the metabolic kitchen, which is responsible for the preparation of meals for research protocols and special diets.  The preparation and attention that is involved in producing a meal in the metabolic kitchen is very stringent and precise from the portion sizes to the delivery of trays to protocol patients.

## Purpose

The purpose of this report is to present a Most Efficient Organization (MEO) that is designed to provide the most efficient and cost-effective Government organization proposed to perform the critical operations that the CC Nutrition Department, Food Services function within NIH and responsive to the Requirements Document dated November 21, 2005.  This report will also demonstrate the MEO’s ability to achieve the levels of quality of service outlined within the Requirements Document (RD).

The MEO is utilized as the foundation for developing the Governments Agency Cost Estimate (ACE).  Consequently, implementation of the proposed MEO guarantees that the in-house workforce is as competitive as possible against the Estimated Private Sector Cost Estimate (PSCE) during the streamlined competition.  The proposed MEO will have the ability to perform all the work that has been identified in the RD, at the quality levels defined therein.  Since the MEO is being developed as part of an A-76 study, all recommendations made are in accordance with OMB Circular No. A-76 (Revised May 29, 2003).

Recommendations used to structure and authenticate the MEO are based on qualified information obtained by the MEO team and verified with the NIH CC Nutrition Department, which consists of mission and organizational analysis, interviews, historical data, task analyses, and technical estimates.

The result is an MEO that is practical, feasible, and will perform the work required by the RD in accordance with applicable directives utilizing sound management practices.

## Scope of the Study

The functional area under study is the Nutrition Department Food Services operations situated in the Nutrition Department of the CC.  The number of Federal Government Full-time Equivalents (FTE) announced for this study is 55.243 FTEs.

Of the 55.243 FTE there are currently 3.600 vacancies.

The breakout of FTE for the current organization is reflected in Technical Exhibit 2-001.  All positions under study are located at the Clinical Center hospital in Bethesda, MD.

## Methodology

To develop the MEO, the MEO Team examined the current organization to identify potential changes that will improve the organizational structure, work processes and environment; and reduce costs while maintaining organizational effectiveness and flexibility.  In doing so, a series of data collection techniques were implemented.  All of the techniques below were used in the preparation of this study, with modifications based upon the circumstances specific to each functional area.

- Physical inspection of facilities.

- Multiple interviews with affected staff and management.

- Review of operational reports, and directives.

- Examination of work flow, databases and other sources of historical workload data.

- Review of Position Descriptions for each FTE within the organization.

- The bargaining unit contract with the Local 2419 American Federation of Government Employees.

The data collection techniques used were focused on providing sufficient information with which to evaluate potential process improvements and varied enough to provide a multi-dimensional and accurate picture of the processes at issue.  The information collected was then subjected to analysis and discussion by the MEO Team.  From this analysis, a list of preliminary findings and considerations resulted.

NIH CC indicated that the management analysis should be based upon considerations, which were deemed logistically possible and easily facilitated as key to the development of a successful product.  The MEO Team embraced the following key study considerations:

- Provide recommendations that are realistic and feasible in the existing operating environment.

- Involve the functional Directors to the maximum allowable extent.

- Eliminate redundant and unnecessary movements of staff, materials, and equipment.

- Eliminate excess cost and inefficient processes.

- Carry out the A-76 work in a manner which will not interfere with ongoing activities.

- Provide clearly documented evidence of findings and cost savings.

## Assumptions

The following assumptions are relevant to the development of the MEO.

- The RD accurately describes the current Food Services performance requirements to satisfy the organizational mission.

- The Government will provide all facilities, equipment, technology and materials, in kind or on a reimbursable basis.

## MEO Format

The MEO report follows the format below:

Chapter 1:	Introduction.  Describes the basis for the study, its purpose and approach.

Section 1: Background. Section 1 describes the National Institutes of Health (NIH) Clinical Center (CC) and Nutrition Department and the mission of the Center as well as the Department.

Section 2: Purpose.  Section 2 presents a discussion of findings on key data and information that may be utilized to create recommendations.

Section 3: Scope of the Study.  Section 3 outlines the current organization and staffing structure.

Section 4: Methodology.  Section 4 describes the methodology the MEO Team used to develop the new organization.

Section 5: Assumptions.  Section 5 presents a discussion of assumptions the MEO Team made in order to develop the organization.

Section 6: MEO Format.  Section 6 outlines the format of this document.

Chapter 2:	Most Efficient Organization.

Section 1: Current Operations.  Section 1 describes the current organization and operations of the functional services of the Department.  The current organization provides the baseline for the analysis, recommendations, and MEO detailed in the following Chapters.

Section 2: Management Analysis.  Section 2 presents a discussion of findings on key data and information that may be utilized to create recommendations.

Section 3: Proposed MEO.  Section 3 outlines the MEO’s organizational and staffing structure.

Chapter 3:	Quality Control Plan.  Describes and defines how the MEO will provide quality services and prevent problems from occurring.

Section 1: Overview:  Section 1 gives an overview of how the MEO will maintain a Quality Control Plan (QCP).

Section 2: Purpose.  Section 2 provides an overview of the importance and use of the Quality Control Plan.

Section 3: Responsibility.  Section 3 presents a discussion of the personnel responsible and tasks performed to verify that Quality Control (QC) is correctly performed in the MEO.

Section 4: Record Keeping.  Section 4 describes the importance of documentation for Quality Assurance Surveillance.

Section 5: Annual Evaluation Instructions.  Section 5 outlines the inspection criteria used to evaluate the MEO’s performance of RD tasks.

Section 6: Completing the Annual Evaluation Report.  Section 6 identifies specific instructions on how to complete the report.

Section 7: Completing the Letter of Certification. Section 7 presents the instructions needed to complete the Letter of Certification.

Section 8: Evaluation Score.  Section 8 presents the steps that follow the completion of the report.

Chapter 4:	Continuing Government Activity (CGA).  Outlines the staffing characteristics of the Government Organization required for either an MEO or an outside Service Provider decision.

Section 1: General. Section 1 covers the definition and importance of staffing the CGA for the MEO or private sector Service Provider.

Section 2: CGA Staffing Calculations.  Section 2 presents a discussion of findings on key data and information that may be utilized to create recommendations.

Chapter 5:	Phase In Plan.  Describes how The NIH CC Nutrition Department will transition from the current organization to a new Service Provider.

Section 1: General. Section 1 describes the logistics of a Phase-In Plan to replace the incumbent Service Provider.

Section 2: Assumptions, References and Affected Organizations.  Section 2 lists key impacts of an A-76 study.

Section 3: Pre-Performance Decision Activities.  Section 3 outlines the planning steps and personnel actions required to initiate and complete a successful phase-in to the new organization.

Section 4: Post-Performance Decision Activities.  Section 4 describes the personnel actions necessary and CGA actions included in organizing and implementing the MEO.

Section 5: Utilities and Any Other Services And Costs To Be Transferred.  Section 5 presents critical utilities and services to transfer to the MEO or new Service Provider.

Section 6: Indicators of a Successful Transition.  Section 6 itemizes key factors to a successful transition to a new Service Provider.

Chapter 6:	Agency Cost Estimate.  This document will itemize the cost of the Government’s MEO to be bid in the Streamlined Competition.

Food Services Trends Analysis

# Most Efficient Organization

Chapter 2. Most Efficient Organization	2-1

2.1 Current Operations	2-2

2.2 Management Analysis	2-12

2.3 Proposed MEO	2-18

| Technical Exhibit Number | Title |
| --- | --- |
| Technical Exhibit 2-001 | MEO Staffing Crosswalk |
| Technical Exhibit 2-002 | MEO Workload Analysis |
| Technical Exhibit 2-003 | MEO Position Descriptions |

## Current Operations

Chapter 2 describes the current organization, mission and function statements, operational environment and position responsibilities.

### Organizational Structure and Functions

The Nutrition Department is organized into two different sections, the Food Services operations and the Clinical Nutrition Services section.  Refer to Attachment 1 for more details.

The Food Services section is responsible for processing menus and room service orders to the main kitchen via the call center.  The food services staff are responsible for main kitchen operations, delivery and the retrieval of food trays in the different units in the hospital, production of menu items, procurement of food items and non-food items as well as monitoring kitchen inventory and supplies.

The Clinical Nutrition Services section retains the metabolic kitchen, which is responsible for the preparation of meals for research studies and special diets.  The metabolic kitchen cooks are specially trained in careful measurement, weighing, and preparation of specific meals for patients in the different research studies that the Clinical Center supports.

### Current Staffing and Responsibilities

The RD describes all the work and functions required within the food services organization except those identified as inherently governmental (IG).  Personnel assigned to the current organization are performing the RD functions.

The public announcement for this study identified 69 federal government employees.  The total amount of FTE identified under the Federal Activities Inventory Reform (FAIR) Act Inventory is 55.243.

Table 1 below is the current staffing matrix for the NIH food services.  This matrix breaks down the current positions by series and grade and also identifies those FTE that are vacant.  3.6 FTE of the positions identified are now vacant.

The paragraphs that follow Table 1 provide brief descriptions of each position’s major functions and responsibilities.

Table 1- CURRENT STAFFING MATRIX

| CURRENT POSITIONS |  |  |  |  |
| --- | --- | --- | --- | --- |
| TITLE | SERIES & GRADE | AUTH POS. | EXCL FROM STUDY | Total FTE |
| Manager |  |  |  |  |
| Manager | Title 42 CRS | 0.096 | 0.904 | 1.000 |
| Manager | Commissioned Corps | 0.083 | 0.917 | 1.000 |
| Manager | Title 42 CRS | 0.156 | 0.844 | 1.000 |
| Manager | Title 42 CRS | 0.108 | 0.892 | 1.000 |
| Supervisor |  |  |  |  |
| Supervisor | WS-7404-07 | 1.000 |  | 1.000 |
| Supervisor | WS-7404-07 | 1.000 |  | 1.000 |
| Supervisor | WS-7404-07 | 1.000 |  | 1.000 |
| Supervisor | WS-7404-07 | 0.400 |  | 0.400 |
| Health Technician/Purchasing |  |  |  |  |
| Health Technician (Dietetics) | GS-640-08 | 1.000 |  | 1.000 |
| Food Service Worker-Leader |  |  |  |  |
| Food Service Worker-Leader | WL-7408-04 | 1.000 |  | 1.000 |
| Food Service Worker-Leader | WL-7408-04 | 1.000 |  | 1.000 |
| Food Service Worker-Leader | WL-7408-04 | 1.000 |  | 1.000 |
| Call Center |  |  |  |  |
| Program Assistant (Previously Nutrition Database Technician- GS-640-08 Position Title change effective 12/11/2005) | GS-303-8 | 1.000 |  | 1.000 |
| Food Service Assistant | GS-1603-05 | 0.200 |  | 0.200 |
| Food Service Assistant (VACANT) | GS-1603-05 | 0.400 |  | 0.400 |
| Food Service Assistant | GS-1603-07 | 1.000 |  | 1.000 |
| Food Service Assistant | GS-1603-05 | 0.200 |  | 0.200 |
| Food Service Assistant | GS-1603-05 | 0.200 |  | 0.200 |
| Food Service Assistant | GS-1603-05 | 0.300 |  | 0.300 |
| Food Service Assistant | GS-1603-06 | 1.000 |  | 1.000 |
| Food Service Assistant | GS-1603-06 | 1.000 |  | 1.000 |
| Food Service Assistant | GS-1603-06 | 1.000 |  | 1.000 |
| Food Service Assistant | GS-1603-06 | 1.000 |  | 1.000 |
| Point of Service (POS) |  |  |  |  |
| Nutrition Service Asst (OA) (VACANT) | GS-303-05 | 1.000 |  | 1.000 |
| Nutrition Service Asst (OA) | GS-303-05 | 1.000 |  | 1.000 |
| Nutrition Service Asst (OA) | GS-303-06 | 1.000 |  | 1.000 |
| Nutrition Service Asst (OA) | GS-303-06 | 1.000 |  | 1.000 |
| Nutrition Service Asst (OA) | GS-303-06 | 1.000 |  | 1.000 |
| Nutrition Service Asst (OA) | GS-303-06 | 1.000 |  | 1.000 |
| Metabolic Cooks |  |  |  |  |
| Cook-Metabolic | WG-7404-08 | 1.000 |  | 1.000 |
| Cook-Metabolic | WG-7404-08 | 1.000 |  | 1.000 |
| Cook-Metabolic | WG-7404-08 | 1.000 |  | 1.000 |
| Cooks |  |  |  |  |
| Cook | WG-7404-08 | 1.000 |  | 1.000 |
| Cook | WG-7404-08 | 1.000 |  | 1.000 |
| Cook | WG-7404-08 | 1.000 |  | 1.000 |
| Cook | WG-7404-08 | 1.000 |  | 1.000 |
| Cook | WG-7404-08 | 1.000 |  | 1.000 |
| Cook | WG-7404-08 | 1.000 |  | 1.000 |
| Cooks/Cooks Assistants/Control Center |  |  |  |  |
| Cook Assistant (VACANT) | WG-7404-04 | 0.400 |  | 0.400 |
| Cook Assistant (VACANT) | WG-7404-04 | 0.400 |  | 0.400 |
| Cook Assistant | WG-7404-04 | 0.400 |  | 0.400 |
| Cook Assistant | WG-7404-04 | 0.400 |  | 0.400 |
| Cook Assistant | WG-7404-04 | 0.400 |  | 0.400 |
| Cook Assistant | WG-7404-04 | 1.000 |  | 1.000 |
| Cook Assistant | WG-7404-04 | 1.000 |  | 1.000 |
| Cook Assistant | WG-7404-04 | 1.000 |  | 1.000 |
| Cook Assistant | WG-7404-04 | 1.000 |  | 1.000 |
| Cook Assistant | WG-7404-04 | 1.000 |  | 1.000 |
| Cook Assistant | WG-7404-04 | 1.000 |  | 1.000 |
| Food Service Workers |  |  |  |  |
| Food Service Worker | WG-7408-03 | 1.000 |  | 1.000 |
| Food Service Worker | WG-7408-03 | 1.000 |  | 1.000 |
| Food Service Worker | WG-7408-03 | 0.500 |  | 0.500 |
| Food Service Worker | WG-7408-03 | 0.400 |  | 0.400 |
| Food Service Worker | WG-7408-03 | 0.400 |  | 0.400 |
| Food Service Worker | WG-7408-03 | 0.400 |  | 0.400 |
| Food Service Worker (VACANT) | WG-7408-03 | 0.400 |  | 0.400 |
| Food Service Worker (VACANT) | WG-7408-04 | 1.000 |  | 1.000 |
| Food Service Worker | WG-7408-04 | 1.000 |  | 1.000 |
| Food Service Worker | WG-7408-04 | 1.000 |  | 1.000 |
| Food Service Worker | WG-7408-04 | 1.000 |  | 1.000 |
| Food Service Worker | WG-7408-04 | 1.000 |  | 1.000 |
| Food Service Worker | WG-7408-04 | 1.000 |  | 1.000 |
| Food Service Worker | WG-7408-04 | 1.000 |  | 1.000 |
| Food Service Worker | WG-7408-04 | 1.000 |  | 1.000 |
| Food Service Worker | WG-7408-04 | 1.000 |  | 1.000 |
| Food Service Worker | WG-7408-04 | 1.000 |  | 1.000 |
| Food Service Worker | WG-7408-04 | 1.000 |  | 1.000 |
| Food Service Worker | WG-7408-04 | 1.000 |  | 1.000 |
| Food Service Worker | WG-7408-04 | 1.000 |  | 1.000 |
|  | Total | 55.243 | 3.557 | 58.800 |

#### Current Positions – Brief Descriptions

Manager (Title 42 CRS and Commissioned Corps) .443 FTE

The Manager positions are responsible for management and the overall operations within their sections.  All managers are responsible for the administration and direction of the staff within their sections.  The Managers are also responsible for CGA tasks which include approval and interpretation of new and/or policy clarification while directing any decisions on policies for the Food Services operation.

Supervisor (WS-7404-7) 3.400 FTE

This position is responsible for supervising food service workers, cooks, and cook assistants, point of service staff, food service worker-leaders and call center staff, metabolic kitchen staff on weekends and holidays.  The incumbent supervises tray line set-up of equipment, utensils, dishes, silverware, trays, condiments and food to ensure maintenance of correct food temperatures and efficiency of tray assembly.  Position is responsible for assuring the timeliness and completeness of tray pick-up on the units.  Incumbent also manages the production of meals at various stages from pre-preparation through service and cleanup. Utilizes skills and technical knowledge about foods to resolve unexpected problems, including the assistance of subordinates with production duties.   Assigns and monitors the work of subordinates to ensure it is progressing on schedule, in accordance with standards for safe and sanitary food handling practices, and that the quality and quantity of products meet pre-determined standards. Responsibilities also include preparing schedules, approving requests for leave, assigning work and adjusting assignments based on current priorities and staffing. Develops job routines and revises staffing plan to meet changing requirements for service.  Interviews and recommends appointment of staff; provides on-the-job training or outside training needed; determines standards of performance and evaluates performance of staff.  Counsel; recognizes exceptional performance; recommends disciplinary action and effect discipline per current delegation of authority and department policy.  Plans quality of work related issues.  Assures equal treatment of all employees.  Communicates effectively with subordinates and supervisors to promote a team approach in the accomplishment for common goals.   Writes performance standards and makes formal appraisals of subordinate work performance.  Incumbent also opens and closes the department 7 days a week 365 days a year, attends to cellular phone calls and issues, implements new procedures, provides breaks and lunches for employees. Collects quality control data and uses results to improve quality.  Completes a variety of official forms that may require decision such as those for work related accidents and worker’s compensation.  Other responsibilities include inventory of food and supplies, placing orders from vendors and or requisitions from stock.

Health Technician (Dietetics) (GS-640-08) 1.000 FTE

Incumbent purchases food, supplies and equipment needed to support program needs of a department that is divided into three requesting sections, Office of Chief, Food Service and Clinical Nutrition Service.  Has delegated procurement authority under small purchase procedures, and is responsible for a variety of acquisition methods to procure food, dietary supplies, administrative and computer supplies and equipment, services and subscriptions.  Orders include perishables such as meat, fresh fruits, vegetables, dairy or formulas with expiration dates.  Is involved in substantive matters such as what, where, under what terms and conditions to purchase and the processing if a variety of procurement documents.  As a Health Technician is responsible for maintaining the food supply needed to provide meal service to Clinical Center patients.  Provides information about the availability of food in the market.  Establishes and maintains food specifications and standards to meet nutritional requirements.  Conducts market searches of new products; keeps Production manager informed about availability of items (i.e. Shortages, seasonal products) and possible replacements or substitutions.  Locates sources of specific items required for protocols and studies.   Maintains database for inventory control, vendors, costs and purchasing.  Reviews historical information and makes recommendations to change databases based on trends in usage and levels, menu changes, market availability or cost, patient senses, and related factors.  Forecasts and places orders for food and dietetic supplies in absence of production supervisor.  Participates in conducting physical inventories and/ or identifying discrepancies between physical and perpetual counts.  Enters receiving information in the Delpro system for the DFM technical service contract and resolves any payment problems.  Calculates and adjusts discrepancies on vendor bills to correct billing.  Prepares monthly budget summary through spreadsheet application for prime vendor purchase orders and cost.    Manages the internal organization of the requests and receipt or orders and the documentation of procurement files.  Incumbent must ensure compliance with all procurement regulations and is subject to audits by the NIH auditors and the Inspector Generals Office.  Reviews, coordinates, and places orders for supplies, equipment and services primarily through the use of purchase card and prime vendors contact.  When necessary, confers with requests to obtain technical specifications to get better understanding of needs.  Forwards receiving information to Office of Financial Management (OFM) and resolves payment problems.  Resolves delivery problems such as incomplete delivery, damage in transit, or items, which fail to meet specifications with the vendor to obtain corrective actions.  Coordinates exchange of materials, equipment trade-in for a newer model or return for credit.  Verifies the accuracy of invoices and completeness of all receiving documents.  Collects data and compiles statistical reports using various tools and spreadsheets, and updates computer files.  Maintains bidder’s mailing lists for specific RFQ acquisitions.  Establishes files and filing systems to organize and maintain a comprehensive record of all procurement activities carried out by the department.

Program Assistant (GS-303-08) 1.000 FTE (Previously Nutrition Database Technician (GS-640-08))

This position is located in the Call Center.  The responsibilities of this position encompass a broad range of program activities.  The incumbent is a principle program support team member and is dedicated to the provision of program support for a wide variety of activities within the Food Service section of the Nutrition Department, CC.  The incumbent coordinates the receipt and computer processing of the admission/transfer/discharge information, diet changes, and menu selections for service of patient meals and nourishments.  Enters daily data into the computer system.  Using written scripts receives phone calls from patients and uses a computer to perform entry of patient data, and menu selections.  Confirms selections are consistent with diet order and makes modifications with patient if needed.  Verifies active diet orders and other patient data using the hospital computer system.  Receives phone calls from nursing units with requests and problems with food service.  Identifies and takes the appropriate steps to meet the request and/or resolve the problem(s).  Generates reports for distribution using the department’s computerized menu software.  Reports and printouts are distributed to various sections or the department to direct food ordering, production, and assembly functions.    Conducts entry of menus into department’s computerized menu software.  Identifies computer software and hardware malfunctions and takes steps to resolve routine problems.  Provides assistance with tray assembly as needed.  Responds and cooperates with changes in workload.  Actively supports and participates in performance improvement activities, including but not limited to tray assessments, meal rounds, and department committees.  Trains new employees and retrains existing employees to expand skills to meet a changing work environment.  Incumbent works persistently to find causes of problems, is able to determine when a problem requires the work of a higher skilled person.  Assists with investigating occurrence reports.  Methodically reviews occurrence and provides statement of resolution to permanently correct issue.  Actively supports and participates in performance improvement activities, including but not limited to tray assessments, meal rounds, and department committees.  Generates nutrition call center work schedules, reassigns workloads as needed, and coordinates approval of call center work schedules through direct manager.  Incumbent is responsible for collection and organization of monthly quality assurance projects for the nutrition call center.  Quality assurance projects may include tracking menu entry and accuracy, tracking number of received calls with completed problem resolutions, and/or tracking patient room issues for CRIS/nursing teams.

Food Service Assistant (GS-1603-05 to GS-1603-07) 6.300 FTE

This position is located in the Call Center.  The Managers of the Food service section directly supervise the individuals in this position.  The duties include coordinating the diet related orders from admission to discharge on every inpatient and outpatient who receives meals.  The incumbent coordinates the receipt and computer processing of admission/transfer/discharge information, diet changes, and menu selections for service of patient meals and nourishments.  Enters daily data into computer system.  Using written scripts receives phone calls from patients and used computer to perform entry of patient data, and menu selections.  Confirms selections are consistent with diet order and makes modifications with patient if needed.  This involves planning with the patient, collecting data and calculating data.  The precision required by the process requires the use of the department’s computerized nutrition database.  Verifies active diet orders and other patient data using hospital computer system.  Generates reports for distribution using the department’s computerized menu software.  Reports and printouts are distributed to various sections or the department to direct food ordering, production, and assembly functions.    Conducts entry of menus into department’s computerized menu software.  Identifies computer software and hardware malfunctions and takes steps to resolve routine problems.  Provides assistance with tray assembly as needed.  Responds and cooperates with changes in workload.  Actively supports and participates in performance improvement activities, including but not limited to tray assessments, meal rounds, and department committees.

Nutrition Service Assistant (GS-303-05 to GS-303-06) 6.000 FTE

This position is responsible for tray delivery and collections to and from patient’s rooms, patient care units, or outpatient clinics.  The incumbent promptly removes soiled trays from patient’s rooms and returns them to the kitchen for dishwashing.  Assignments include completing inventory of bulk food and fluids for assigned unit pantries, documenting supply needs and recording unit refrigerator temperatures.  The incumbent additionally uses the Nutrition Department computers to perform entry of daily fluid orders and weekly bulk food orders to generate a requisition.  The incumbent completes inventory of bulk food and fluids for assigned unit pantries.  Uses worksheet with par levels to determine bulk food/fluid needs.  Takes temperature of unit pantry refrigerators and records temperature on log.  Fills pantry and unit refrigerators with supplies.  Ensures all fluids have expiration dates and all outdated items are discarded.  Rotates stock so first in, first out procedure is followed.  Discards food not part of nutrition floor stock.  Reports maintenance and sanitation issues to supervisor.  Other duties include any other food services related duties such as meal assembly and service.  Reading tray assembly tickets and placing correct food on trays as they proceed along the tray line. Load trays on delivery cart and may collect patient menus.  May collect satisfaction surveys for Quality Assurance Data Collection.  Additional duties may include working in the call center answering the telephone to receive menu selection from room service patients and entering selections into computer system and printing a meal ticket.

Cook-Metabolic (WG-7404-08) 3.000 FTE

This position provides food service for patients who are on diets that must be precisely controlled for research studies.  The position entails precise weighing and measuring of ingredients and foods, and standardized preparation methods.  Menus, diets, recipes, specific foods, portion sizes, and quantities required for menus, meals and diets are predetermined for the incumbent.  Incumbent uses menus and standardized recipes to independently schedule and prepare foods for meals in accordance with quality and timeliness for service.  This position prepares the full range of foods required for constant diets/test meals with strict compliance to precise standardization.  Prepares special liquid formulas.  Incumbent precisely weighs and measures ingredients for recipes, and portions foods to ensure standard servings and nutrient content for research studies.  Position precisely follows standardized recipes of varying complexities to schedule cooking assignments.  Incumbent uses many cooking methods and procedures and effectively applied knowledge of various cooking procedures to produce standard food products.    Incumbent interacts with patients and nurses regarding diet orders, diet changes and food requests and teaches metabolic techniques for food consumption.  Responsibilities include assisting supervisor to train new cooks in metabolic procedures and techniques.  Coordinates the work of lower grade cooks to ensure that a variety of foods are prepared simultaneously so that meals are completed and served at times needed.  Incumbent assembles food for patients and verifies accuracy or completeness of trays.  Delivers meals directly to the patients and returns to pick up trays after the meal to perform, analysis of any foods not consumed.  Weighs and records refused foods and prepares replacements based on protocol requirements.  Incumbent may be assigned to take inventories and orders foods and prepares supply requisitions in accordance with established guidelines.  Incumbent maintains a clean, orderly and sanitary work area.  The incumbent may be assigned to assist Health Technicians with duties such as menu collection and checking, or may work in the main kitchen performing duties such as cooking, weighing, and measuring in the ingredient room, checking/serving trays on the patient tray line.

Cooks (WG-7404-08) 6.000 FTE

This position performs as a top-level senior cook using menus, standardized recipes, and production tallies to independently schedule and prepare foods for meals in accordance with quality and timeliness standards for the service.  Incumbent coordinates the food preparation assignments of lower graded less skilled cooks and food service workers who assist with preparation, ensuring that lower graded employees perform cooking assignments correctly.  Responsibilities include planning and coordinating the preparation of either the entire line of meats and entrees, or vegetables, or soups/gravies or bakery products for one or more meals per day.  Incumbent prepares and cooks a full range of foods for bulk and for single orders including but not limited to room service.  Prepares and cooks a full line of breakfast, lunch and dinner items; and a limited number of bakery type foods.  Incumbent prepares products that adhere to standardized recipes involving different levels of difficulty to meet established standards.  Incumbent makes judgments about products being prepared at different steps during the preparation process to ensure that quality meets standards.  Responsibilities include assisting supervisor with recipe development, standardization, and yield testing.  Incumbent performs quality control checks on food as required.  Assists cook assistants in performing food preparation tasks, and coordinates the work of lower graded cooks to ensure that a variety of foods are prepared simultaneously so that meals are completed and served at times needed.  Takes daily inventory of items stored in production unit and communicates needs to Supervisor. Incumbent maintains a clean, orderly and sanitary work area.  Incumbent also sets up hot food station with pasta, soups, gravies and other large quantity production food items.  The position also checks tray assembly line during peak meal service time and replenishes as needed.  Incumbent also works at any assembly station on the tray line.  Reads the tray assembly tickets and places correct foods on trays as they proceed along the tray line, as well as loading trays on delivery carts.

Food Service Worker-Leader (WL-7408-04) 3.000 FTE

This position serves as a working leader in the food service operations in the main kitchen.  The incumbent is responsible for directing WG-04 and lower food service workers on tray line and dish room set up, service and sanitation.  Responsibilities include informing employees where they are stationed to work and also work as a checker to assure that trays are complete and accurate, monitoring and enforcing tray delivery standard. Also, obtains information and/or direction from supervisor concerning tray line problems and reports action to be taken to appropriate employees.  Incumbent performs quality checks on tray line items prior to service as deemed necessary by supervisor or manager.  Takes and records temperature of all tray line food.  Incumbent communicates with cooking staff of food items that are needed, and instructs food service workers to serve the correct portion size using the correct serving utensils.  Assigns tasks to employees as necessary and insures employee breaks are given adequately and coverage is provided.  Other duties include assisting with on-the-job training of food service workers at the same or lower grade.

Cooks Assistants (WG-7404-04) 8.000 FTE

This position performs as an assistant to the cooks by preparing foods to fulfill requirements for the regular and special diets of inpatients and outpatients.  A production schedule of foods requiring preparation for a particular meal is provided to the incumbent for use in the duties assigned.  Incumbent seeks guidance from a cook or supervisor only when non-routine assignments are performed.  The position performs a full range of simple cooking duties for items that require little or no processing such as pancakes, eggs, hamburgers, etc.  Incumbent also prepares hot cereals, soups and gravies.  Under the general guidance of a cook the incumbent also performs food preparation tasks such as slicing meat and cheese using the slicer, rolling out pie dough, mixing fresh fruit, meat and vegetables salads and cooking ingredients for salads, such as potatoes.  Prepares salads and sandwiches to order. Uses standardized recipes and exacting sanitation techniques.  Measures and mixes formulas, tube feeding, and special foods (milkshakes, and nutritionally fortified foods).  Incumbent also weighs measures, labels and packages ingredients for recipes, using scales and measuring devices.  The position also sets up food for tray line with dishes, flatware, napkins, condiments, and cold food items such as salads, desserts and breads, as well as beverages.  Incumbent also sets up hot food on the steam table.  Works at any assembly station on the tray line.  Incumbent reads the tray assembly tickets and places correct foods on tray as they proceed along the tray line.  Loads trays on delivery carts and delivers trays to patient units.  Position also delivers meals, nourishments, picnics, menus and supplies to Patient Care Units, patient rooms and outpatient units.  Incumbent removes soiled trays from patient’s rooms and returns them to the kitchen for dishwashing.  The position also delivers selective menus to patients; collects completed menus and delivers to health technicians.  Incumbent breaks down tray line by removing unused foods to the appropriate storage area or discarding.  Other duties include operating and cleaning kitchen equipment and washing dishes.  Incumbent receives non-food items as well as food items for inventories.  Responsibilities include inspecting and counting deliveries, storing stock in designated areas, and filling requisitions from food service sections.  Incumbent uses department computer to enter requisitions.  Position transports food and other nutrient related items to/from the loading dock to/from Nutrition Services and within the Clinical Center.  This includes food to patient units utilizing motorized transportation equipment.  Also, conducts daily inspection of motorized transportation equipment.  Using hitches on food carts, connects and disconnects carts onto tugger and / or another food cart.  Conducts daily maintenance check of the motorized equipment including the battery monitoring and charging.  Communicates any issues to supervisor or manager regarding equipment operation and maintenance.  Will use walkie-talkie to communicate to co-workers including supervisors, tray passers, and kitchen personnel.  Other duties as assigned.

Food Service Worker (WG-7408-03 to WG-7408-04) 17.100 FTE

This position performs a variety of food service tasks in the areas of meal assembly, service, ware washing, sanitation and safety, food preparation and distribution.  The work encompasses a variety of tasks from meal delivery, inventory/ordering of patient care unit supplies in day hospitals, outpatient clinic areas and inpatient units as well as menu distribution and collection. The incumbent at the higher-grade level is also responsible for final check of diet trays assembled by lower graded food service workers.   The position also sets up food for tray line with dishes, flatware, napkins, condiments, and cold food items such as salads, desserts and breads, as well as beverages.  Incumbent also sets up hot food on the steam table.  This position works at any assembly station on the tray line during peak service times.  Reads the tray ticket and places the correct food items on trays as they proceed along the tray line.  Loads meal trays onto delivery carts and assembles complete room service trays during non-peak room service times.  Incumbent assembles fluids and bulk food supplies for distribution to unit pantries.  This position evaluates the accuracy, completeness and appearance of each tray at the end of the tray line to ensure that meals meet quality standards.  Responsibilities include breaking down the tray line and delivering soiled pans and utensils to pot washing area.  Incumbent also prepares and delivers bagged meals for outpatient clinics.  Takes inventory of bulk foods and fluids on Patient Care Units, replaces expired products, records temperatures of unit refrigerators.  Position also delivers meals, nourishments, picnics, menus and supplies to Patient Care Units, patient rooms and outpatient units.  The incumbent promptly removes soiled trays from patient’s rooms and returns them to the kitchen for dishwashing.  Coordinates process of tray delivery in kitchen by implementing established standards.  Incumbent is also responsible for performing simple cooking duties such as preparing convenience foods utilizing microwave, toaster, griddle, deep fat fryer and ovens.  Under the general guidance of a cook, performs food preparation tasks such as slicing meat and cheese using an institutional slicer, mixing meat and vegetable salads, cooking ingredients for salads, opens, pours and heats soup. Incumbent also, portions salads, desserts, juices, and measures items for serving.  Uses standardized recipes and exacting sanitation techniques.  Measures and mixes formulas, tube feeding, and special foods (milkshakes, and nutritionally fortified foods.  Incumbent also weighs measures, labels and packages ingredients for recipes, using scales and measuring devices.  Other duties include operating and cleaning kitchen equipment and washing dishes.  Position also assists with on-the-job-training with food service workers at the same or lower grade levels.

### Internal and External Interfaces

There are working relationships currently in place within the CC Nutrition Department Food Services operations; however, there are also other critical interfaces between the CC Nutrition Department Food Services operations and other Clinical Center departments.  Constant interactions with hospital unit staff are a daily affair.

The external interfaces are very important in that the Food Services operations is a customer service based function.  The CC Nutrition Department Food Services operations strives to provide the best possible service so that patients of the CC are comfortable and their nutritional needs are accommodated in every manner.

### Current Operations and Procedures

The Food Services function of the NIH CC Nutrition Department provides meals, nourishments, formulas, tube feedings and supplements to patients who are in an inpatient unit, day hospital, outpatient clinic or other location including, but not limited to, the Blood Bank and Radiation Clinic.  The Food Services operations of the Nutrition Department also provide room service, meal assembly and preparation, maintenance and the stocking of kitchen and food supplies.

The work performed by the Food Services operations is critical to the patients of the NIH, CC.  The food services organization provides precise preparation of foods for research protocols through its metabolic kitchen as well as its ability accommodate 150 different diet types.  In order to maintain a comfortable environment for patients the Food Services operations also provides room service with a varied menu of breakfast, lunch, and dinner foods which can be served at any time between 6:30am to 6:30pm seven days a week 365 days a year.

#### Operational Structure

As indicated in 2.1.1 the Nutrition Department is organized into two different sections, the Food Services operations and the clinical nutrition services section.

The Food Services section is responsible for processing menus and room service orders to the main kitchen via the call center.  The food services staff are responsible for main kitchen operations, delivery and the retrieval of food trays in the different units in the hospital, production of menu items, procurement of food items and non-food items as well as monitoring kitchen inventory and supplies.

The Clinical Nutrition Services section retains the metabolic kitchen, which is responsible for the preparation of meals for research studies and special diets.  The metabolic kitchen cooks are specially trained in careful measurement, weighing, and preparation of specific meals for patients in the different research studies that the Clinical Center supports.

Operations within the Food Services operations will remain the same with some anticipated changes in staffing.

#### Work Schedule and Overtime

Currently the NIH CC Nutrition Department, Food Services operations operates from 5:30am to 8pm seven days a week 365 days a year. Schedules are posted two weeks in advance.

Currently, the staff have overlapping shifts that they work.  In order to perform more efficiently with less staff the MEO will be realigning the schedules to make better use of staff time.    With the changes in positions the MEO will be able to utilize all their staff to their full array of duties and cover all functions in the main kitchen as well as eliminate redundancies.  Breaks and lunches are scheduled in accordance with the current Union contract.  In addition, the amount of productive non-overtime hours allowed per position per day had to be in accordance with the current Union contract (which is currently less than 8 hours/ position/ day).

When there is a shortage of staff due to unanticipated leave or a problem occurs, the staff are given the option to sign up for overtime.  There were approximately 2,434 hours of overtime used by the Food Services operations last year.  The MEO, due to the proposed staffing, will not account for overtime, as efficiencies identified will allow the Nutrition department, Food Services operations to meet its mission goals without the use of any overtime.

#### Cross-Training

Currently, there is little or no cross training.  Staff in each section performs the duties and functions based on their position. The MEO proposes on-the-job (OTJ) cross-training to be widely used.

Due to the proposed changes in staffing cross-training will be utilized to support a more efficient and flexible operation.

Currently, some of the positions frequently serve as back up for one another.  There are also functions where an employee previously performed a particular function and can assist in backfilling as required for extended and other absences.  This trend will continue for the MEO.

#### Training

Currently, all staff are trained and certified in the different operations they need in order to perform their work.  With some of the proposed position changes additional staff will be trained in other process, such as the motorized operating vehicles.

Staff will continue to attend informal and formal training sessions.  Technical Exhibit 5-001 provides the specific training that will continue to be provided by the MEO.  On the job training will also be continuously provided for new and seasoned staff members.

#### Travel

Due to the nature of the functions performed by the NIH CC Nutrition Department, Food Services operations travel is not an inherent requirement and therefore does not impact the operations within the organization.

## Management Analysis

### Analysis of Current Mission and Functions

The current overall mission, core functions and organization of the NIH CC Nutrition Department Food Services operations are expected to remain the same during the performance periods under consideration.  This includes the tasks and duties of the current sections within the Food Services organization.  However, there are several anticipated changes to staffing, which will increase staffing efficiency while reducing the grade structure and some decrease to the current staffing.  However, it is noted that the CC, Nutrition Department Food Services operations has decreased its staff in the past few years although there has been an increase of workload due to the implementation of room service and the expansion of the Clinical Center.

### Analysis of Current Organizational Structure

One of the most important aspects of creating an MEO is structuring the new organization for the most efficient and cost effective performance of work required by the RD.  As a starting point of this development, the MEO Team examined the current strengths and weaknesses of the organization and its structure while identifying any weaknesses that could be eliminated or readily identifiable efficiencies for the Nutrition Department, Food Services operations to utilize.

In the course of its organizational analysis, the MEO Team identified 3.60 FTE within the Food Services operations that are currently vacant.  These vacant positions are identified as one GS-1603-05 Food Service Assistant, one GS-303-05 Nutrition Service Assistant, two WG-7404-04 Cook Assistants, and a Food Service Worker WG-7408-03 and WG-7408-04.  It should be noted that the Food Services operations has decreased its staff over the last 10 years by 30 percent.  Based upon the current mission and operations of the Food Services operations, the MEO workforce will be able to efficiently and effectively meet the RD requirements without 2.04 of the current 3.60 FTE worth of vacancies.

#### Strengths of Current Organizational Structure

A positive element that the MEO Team noted was the organizations ability to adapt to the different changes that has occurred with the expansion of duties and the increase in customers.  In the past, there have been many process improvements in the Nutrition Department Food Services operations that have allowed the organization to perform extra work with fewer staff.  The department is in a constant state of reorganization based on business processes and changing budgetary and staffing environments.  This restructuring has allowed the Nutrition Department, Food Services operations to remain within their financial and FTE budget.  The implementation of a room service program for patients was executed with no increase in FTE's, which is not typical in the healthcare food service industry.  The organization has absorbed additional work activities in their move to the new wing of the CC hospital due to its geographic size and layout, also with no additional FTE's.  The Nutrition Department was also able to move three clinical health technicians back into clinical care with no additional FTE's.  This was all accomplished through continual process improvements and technology, such as moving to a new computer system, which interfaces with the hospitals patient information, and utilizing motorized equipment to deliver trays to the furthest parts of the hospital wing.

Currently, all positions in the Food Service Operations are occupied by government employees with a vast knowledge base of the Clinical Center and its unique operations.  The continuity of the long time staff members assists in providing a sense of comfort and familiarity to the patients.  The Food Service operations function as a one stop, team oriented, all point food service reliable resource.

The MEO Team was able to decrease total FTE by 6.7 and reduce grade-levels of current staff based upon the complexity of the assignments identified in the RD, interviews, and data collected.

Any change in the scope or amount of workload in the current organization would pose many problems due to already reduced staffing numbers over the years.

#### Weaknesses of the Current Organization Structure

In the course of its organizational analysis, the MEO Team identified several limitations in the Food Services staffing.  Based upon the data collected, the RD, interviews, observations and a thorough review of the position descriptions, several overlaps in duties were identified.  Other areas of concern pertained to the series and grades of the current staff as well as the number of staff designated in each area.  In evaluating the current Office of Personnel Management classification policy and guidance, it has been determined that some of the current positions are not appropriately classified and unjustifiably over- graded.  Therefore, the MEO team has authorized the changes in position series and classification as well as a decrease in the grade levels of the current staff to correspond with the complexity of the tasks and work assignments.

#### Supervisor to Employee Ratio

The MEO staffing with 3.723 Supervisors has a ratio of Supervisor to employee at 11.9 to 1.  Currently the ratio of Supervisor to employee is 13.8 to 1.

Supervisors assist management in the operation of the Food Services operations.  Currently, the Supervisors develop and directly execute performance plans, develops employee schedules and staff assignments, recognizes exceptional performance; recommends disciplinary action.  The Supervisors perform other administrative and personnel duties as well as the tasks stated in the RD.

The Supervisors are not given specific employees to Supervise or a set amount to supervise but share in the process.  Performance plans are performed with information that is provided from all the Supervisors as well as feedback from management.

The Supervisors in the MEO will continue to carry out the duties and tasks that the present organization performs.

#### MEO and Continuing Governmental Activities (CGA) Separation

As introduced conceptually earlier in this report, the analysis of the current organization must consider those functions that are identified as Inherently Governmental (IG) and which will be performed by the Continuing Government Activity (CGA) and, as such, will not be part of the competitive process.  OMB Circular A-76 defines these types of functions, some of which are performed in the NIH CC Nutrition Department.  These CGA responsibilities specifically involve performing review and development of policy and procedure, budgetary responsibilities, and Quality Assurance (QA). Other IG supervisory tasks not part of the RD are performed by the Nutrition Department Chief.  These include CGA responsibilities such as approval of policies, interpretation of policy and clarification, direction and decisions on policies including Food Services needs and approval of design and project funds in addition to initiation of management analyses and IG employment issues.  In general, the CGA will consist of those tasks and functions that are IG or core to NIH, CC operations and therefore non-contractible.

The OMB Circular A-76 Quality Assurance (QA) requirement, including those positions that will oversee the performance of the Service Provider whether it is the Government MEO or a private sector contractor, should also be designated to the Project Manager (PM) including the QA requirements.

Therefore, NIH, CC management will appoint selected individuals within the CC Nutrition Department and outside the MEO Team to perform purely QA functions and apportion the remainder to those positions in the MEO dedicated to performing CGA.  The methodology for apportioned costing of positions that perform both CGA and MEO work will be reflected in the final staffing crosswalk attached as Technical Exhibit 2-001.

### Analysis of Staffing Requirements

#### Grade Structure

The grade distribution of the workforce can be an obstacle to cost-effective performance and successful competition with civilian contracting firms.  It is also mandatory that the grade distribution of the workforce should be commensurate with the work it performs.  Achieving such a balance is often difficult in a Federal organization.  Attrition due to turnover also tends to create frequent vacancies at lower-graded employees.

Additionally, in the Federal Government, supervisors and directors may over-grade new positions in order to ensure hiring of “quality” personnel, ultimately over-grading existing positions to retain experienced personnel.  Finally, a contributing factor, under the Federal classification and compensation system, a worker may be awarded the higher of two grades if he regularly performs even five (5) to ten (10) percent of his work effort at the more highly graded level.  It is therefore incumbent upon management to concentrate the more complex assignments among a limited number of workers to avoid unreasonable escalation of grades for a larger population of the workforce.

Having a grade distribution that is skewed towards the upper grades causes the organization to use highly skilled and paid workers to perform tasks that would likely be executed by intermediate or assistant-level personnel in a private sector organization.  This is a significant drawback when competing in the A-76 environment.  In the instance of the Nutrition Department, Food Services operations, the current grades are disproportionately stable and not proportioned towards the ultimate skill and task goal.

After meticulous analysis performed by the MEO Team, results show it to be more cost effective for the Nutrition Department, Food Services operations to reduce the grade levels of the majority of the positions.  In order to fulfill the vision and mission of the CC Nutrition department the higher graded positions are not needed to serve the specific needs of the organization based on the work assignments in the RD.  The functions of the Food Services operations can be performed by staff at lower grades and still maintain the high standards of services that the Food Services operations has been performing in the past.

Based upon the position descriptions, employee interviews and management discussions it is established that there are redundancies and an overlap in the position functions of the cook assistants, food service workers, and POS workers.  Office of Personnel Management (OPM) classification standards support eliminating the Cook Assistant positions and POS positions and replacing all the positions with the Food Service Worker WG 3-4 and Cook WG-4 positions to perform some of the functions stated in the RD.

The current position descriptions for the Food Services Assistant, GS-1603-5/6 have been evaluated and determined to be appropriately graded at the GS-5/6 level.  It was also determined that the current position descriptions for the Food Services Assistant, GS-1603-7 and GS-1603-8 would combine the higher level duties to support a Food Services Leader at the GS-7.  The outcome resulted in the abolishment of the Food Services Assistant, GS-1603-8 position. The GS-8 level Health Technician (Dietetics) position was also downgraded to a GS-5 position as the complexity of assignments were also found to be appropriate at a lower grade level (based on OPM classification standards).  The current positions of Cook, WG-7404-4, 6 and 8 were reviewed.  It was determined that the work did not fully meet the criteria established by the Cook classification standards to support a WG-7404-8, but instead a WG-7404-6.  Therefore, the MEO confirmed that the highest level of work necessary in carrying out the Cook duties was at the WG-7404-6.  For recruitment purposes, the MEO resulted in the support of Cook positions at the WG-7404-4 and 6 levels The current position of Cook Supervisor, WS-7404-8, was re-evaluated and determined to be supportable at the WS-7404-5.  Due to the elimination of WG-7404-8 cooks, the highest level of work supervised was at the full performance level of WG-7404-6, which impacted the current classification of the position. All functions of the current operational structure can be achieved by positions at lower grades and at the same expectation level as discovered in assessing classification standards for the appropriate positions needed for the Food Services operations.

As noted in section 2.2.2.1 above, the MEO will eliminate 2.04 vacant FTE positions to make the MEO more cost competitive.  The savings to the Nutrition Department, Food Services operations will be approximately $367,000 for the base year from elimination of some vacancies and reducing the grade-levels.

#### Series Classification

The Office of Personnel Management (OPM) uses the Position-Classification Standards to describe series and grade information.  Therefore the MEO Team, with support and guidance from the Human Resources Advisor (HRA), analyzed each draft of the MEO Position descriptions and tasks stated within the RD and verified and certified that the positions were appropriately assigned the correct series and grade to perform the work.

Based on OPM classification standards the 1603 series, Food Service Assistant positions have been changed to a GS-640 series Health Technician. The Health Technician Series, GS-640 covers positions involving nonprofessional work of a technical, specialized, or support nature in the field of health or medicine when the work is of such generalized, specialized, or miscellaneous nature that there is no other more appropriate series.  The purpose of assigning this series was based on a more accurate reflection of the duties supported where the incumbent is providing support to dietitians to ensure patients are receiving the correct nutrient values to their therapeutic or modified diets.

The current position of Health Technician (Dietetics), GS-640-8, was reviewed and should be appropriately assigned to the Food Services Assistant Series, GS-1603.  The rational for determining the Food Services Assistant Series as the appropriate series was based on two factors: (1) organizational mission and/or function and (2) recruitment source.   The subject position is providing support to the Office of the Chief, Nutrition Department, and is responsible for procuring, receiving and accounting for all food and non-food items essential to the mission of the organization.  The Food Services Assistant Series, GS-1603, covers work that involves maintaining records related to food safety inspections; collecting data for the budget of service operations; ordering supplies for food services; and recording information on equipment replacement schedules.  Based on the facts identified above, the position is appropriately assigned to the Food Services Series, GS-1603.

OPM classification standards support the elimination of the Nutrition Service Assistant (POS), 303 series as this particular series refers to positions that primarily provide clerical support (there was no justification to maintain this series based on the RD assignments).  The Nutrition Service 303 positions and Cook Assistant, 7404 positions were eliminated and replaced by the Food Service Worker 7408-3/4 series and Cook 7404-04 series. The current positions of Food Service Workers, WG-7408-3/4 are accurately classified and did not result in a change in current classification. The three (3) Food Service Worker-Leaders at the WL-7408-04 series were eliminated as they were determined by the MEO Team as redundant positions.

In accordance with OPM standards and under the guidance of the HRA, position series, grade structure, and classification of the current positions were modified to appropriately fit the tasks and assignments outlined in the RD document. Employee interviews, evaluations of the current position descriptions and the data gathered from the MEO Team were also considered in the final decision making process.   The MEO crosswalk in TE-2-001 illustrates the specific modifications to both grade and series changes.

### Analysis of Workload Data

The MEO Team took various approaches to determine the FTE requirement for the Food Services MEO, including gathering technical estimates for task times and conducting brainstorming sessions and multiple interviews with the employees and the Management staff.  The data gathered by the MEO Team through its interviews was critical to accomplishing the workload analysis and correctly sizing the MEO organization.

Beginning with the RD defined workload, the MEO Team gathered data to determine the number of FTE required for the MEO to perform the RD work.  Gathering technical estimates for task durations involved several steps.  Initial durational times would serve as a basis of discussions for gathering more in-depth task durations.  A few interviews were conducted where durational times were difficult to substantiate and to try and capture the appropriate estimated time.  When varied task times occurred, an averaging and weighting of tasks times was performed based on reasonability, reliability, and compatibility with the RD task and other data.  This system and analysis obtained reasonably reliable estimates for average durations and level of effort to accomplish a task.

In all cases, the final technical estimates used in the study were validated by the Nutrition Department, Food Services operations.  The next step was to calculate the FTE required for the performance of RD work.  OMB Circular No. A-76 mandates the use of 1776 hours as the available productive hours per full-time employee, accounting for holidays, annual and sick leave, and general training and meetings.  Dividing the total hours calculated by 1776 results in an estimated FTE for the MEO to perform the required RD work.

The resulting analysis (displayed in Technical 2-002) shows that approximately 51.683 FTE are required to perform the work required by the RD.  An additional .795 FTE is designated for Program Lead / Metabolic Kitchen a responsibility that is a requirement in the RD document.  Based upon this analysis the MEO will staff 49.188 FTE to account for estimated time variances and re-work processes.  A matrix showing how the current organizational positions crosswalk to the proposed MEO staffing, is represented in Technical Exhibit 2-001.  It must be emphasized that FTE workload calculations are merely one step in the formulation of the staffing, and the MEO Team used this data as it iteratively considered the development of position descriptions, alignment of work tasks, shift assignments and other factors.  This information is used in conjunction with the experience and expertise of the team to ultimately decide the proper staffing mix, grade level, and distribution.

During interviews, the question “What isn’t getting done?” was asked.  The Management team was confident that they were accomplishing the overall mission and goals of the Nutrition Department, Food Services operations and could continue to do so in the future with the MEO efficiencies and changes noted in this report.

### Analysis of Facilities, Equipment, and Materials and Supplies

#### Facilities

The facilities are adequate to perform the work of the RD and therefore any changes for the MEO will not be considered as an efficiency gain for the Food Services Organization.

#### Equipment

In the past two years, new equipment and minor renovations were made to accommodate the demanding room service operation.  Currently, the equipment used by the current organization is adequate for the work required in the RD.

#### Automated Information Systems and Software

The current organization has experienced recurring technology process improvements.   The organization has upgraded to a new computer system, which interfaces with the hospitals patient information.  The use of motorized equipment to deliver trays to distant wings in the hospital has assisted in reducing travel time.

It is estimated that additional new technology will be implemented in the future, including touch-screen monitors in the call center.  The touch screen monitors are expected to increase productivity and decrease the time it takes to receive an order.  Also, the execution of a new phone system in the call center will assist in tracking productivity and better serve patients with a minimum amount of delay.

#### Materials and Supplies

Materials and supplies currently being utilized by the Food services Organization will continue to be funded by the government, and therefore this area is not a candidate for large savings.

### Analysis of Processes

Throughout the CC Nutrition Department, Food Service section the MEO Team identified few processes that could be readily improved to either save resources, improve levels of service, or both not already outlined above.

## Proposed MEO

The paragraphs below describe the concept behind the development of the MEO; the general findings of the study that impact MEO development, the functional alignment of the MEO organization; and finally, the staffing plan describing types, number and grades required to perform the work required by the RD.

### MEO Development Concept

The development of the MEO involves the incorporation of a variety of concepts that must be integrated to ultimately create an organization that NIH CC Nutrition Department accepts as consistent with NIH’s mission and strategic goals and yet remains competitive for the A-76 cost comparison process.  Basic concepts employed by the MEO Team included:

- Eliminate Team Leaders.

- Eliminate overtime hours.

- Match staffing (series, grades and numbers) to the complexity and volume of work.

- Eliminate unneeded or redundant processes.

- Adopt a contractor’s cost perspective as appropriate.

The MEO Team realizes that Government and private sector organizations operate differently and that there are differences in the risk associated with developing a proposal in the A-76 environment.  With this in mind, the MEO Team has developed an MEO which is practical, feasible, and performs the required work in accordance with applicable NIH directives utilizing sound management practices while attempting to balance the competitiveness of the organization and the risk inherent in that process.

### General Findings

Based on the analysis and observations, the general findings of this study that impact the development of the MEO are as follows:

- The CC Nutrition Department has 3.60 FTE that were vacant but was still performing mission work to the quantity and quality required by the RD (in part by overtime hours).

- The CC Nutrition Department currently has three (3) Food Service Worker-Leader positions, which can be converted to Food Service Worker, positions and perform the same work more cost efficiently.

- The CC Nutrition Department currently has six (6) Cooks and three (3) Metabolic Cooks, which can be converted to nine (9), Cook positions cross-trained to cover both the Main Kitchen and the Metabolic Kitchen.

- The CC Nutrition Department Call Center currently has 7.3 FTE (five full-time positions and five part-time positions) to cover the Call Center hours of operation, which can be reduced to 6.1 FTE, based on schedule re-alignment.

- The CC Nutrition Department Point of Service workers and Cook Assistants/Control Center workers can be converted into Food Service Workers.

- Some of the RD work/tasks being performed by the current organization appear to be able to be performed by employees of a different (lower) grade.

- The grade level of most positions exceeds the RD work difficulty/complexity requirements.

- The CC Nutrition Department operates as a fairly lean organization.  The Department has lost a significant number of FTE (approximately 30%) while workload remained the same or increased within the last ten years.

- Quantitative and value-added efficiencies can be realized through vacant position elimination, rescheduling, and re-grading of most current positions.

### MEO Functional Organization

#### General

There were several proposed efficiency and structural options for MEO consideration. All of the proposed options were considered in the development of the MEO.  The primary focus of the MEO Team was to create an organizational structure that facilitated flexibility for the current organization and limited disruption to the overall Department at NIH.  Efficiencies identified by the MEO are both readily applicable and consist of the least intrusive means to obtain the most efficient organization for cost comparison purposes given the constraints of the current environment.

#### Functions and Alignment

The MEO Team processed all of the information gathered with a particular focus on structure and staffing that would represent the most readily available efficiencies while minimizing disruption to the Nutrition Department.  The MEO Team determined that facilities, functions, and programs should remain the same as the current organization and that structure and staffing should be changed.

Based on information gathered during interviews, and from workload, position, and scheduling analysis, the MEO Team chose to eliminate a few positions and FTE, re-classify several positions, and downgrade several others.  The WS-7404-07 Kitchen Supervisors, which originally accounted for 3.4 FTE, were determined to be at a higher-level grade than the RD work difficulty/complexity.  The MEO therefore decided to downgrade the Kitchen Supervisors to WS-7404-05’s at 3.28 FTE’s.  In addition, the three (3) Food Service Worker-Leaders were determined by the MEO Team as redundant positions.  The MEO Team decided to eliminate these three positions and combine the remaining workload with the Food Service Workers (see analysis below).

The MEO Team analyzed the Call Center staff and schedules and determined that 6.1 FTE would be sufficient to cover the workload and hours of operation instead of the current 7.3 FTE (a savings of 1.2 FTE).  The 1.0 FTE GS-0303-08 Program Assistant in the Call Center was eliminated with a 0.2 FTE GS-1603-05 Food Service Assistant since the workload didn’t support their time.  Furthermore, the remaining 6.1 FTE in the Call Center were changed to 1.6 FTE Part-Time GS-640-05 Health Technicians, 3.5 FTE Full-Time GS-640-06 Health Technicians, and 1.0 FTE GS-640-07 Health Technician-Leader.

The Nutrition Department Point of Service (POS) staff (currently 6.0 FTE GS-0303-05/06 Nutrition Service Assistants) was determined to be graded at a much higher level than the RD difficulty/complexity.  A function and classification analysis of the POS staff resulted in a position reclassification and downgrade to WG-7408-03/04 Food Service Workers.  Additionally, the POS staff didn’t need to be considered a separate working group and were therefore combined with all the other Food Service Workers.  The same reasoning was determined for the 8.0 FTE WG-7404-04 Cooking Assistants.  The MEO Team combined a total of 34.1 FTE’s from Food Service Worker-Leaders (mentioned above), Nutrition Service Assistants (POS staff), Cooking Assistants, and existing Food Service Workers and determined the proper classification and staffing of these positions (based also on workload analysis and requirements) should be:

- Food Service Workers – WG-7408-03: Total of 22.06 FTE’s

- Food Service Workers – WG-7408-04:  Total of 8.0 FTE’s

- Cooks – WG-7404-04:  Total of 2.0 FTE’s

The net difference in FTE’s realized through this analysis was a 2.04 FTE reduction.

The CC Nutrition Department currently has six (6) WG-7404-08 Cooks in the Main Kitchen and three (3) WG-7408-08 Metabolic Cooks in the Metabolic Kitchen for a total of 9.0 FTE.  The MEO Team determined that the 9.0 FTE is correct to account for the workload and hours of operation, however, a classification analysis determined the grades to be higher than the RD difficulty/complexity.  Furthermore, there was no logical reason to separate the Main Kitchen from the Metabolic Kitchen from an organizational structure standpoint.  The MEO team therefore downgraded and combined the Cooks into one position called a WG-7408-06 Cook increasing efficiencies by cross-training both the Main Kitchen Cooks and the Metabolic Kitchen Cooks who can assist in either kitchen during each Kitchen’s respective peak times.

The MEO Team also analyzed the 1.0 FTE GS-640-08 Health Technician (Dietetics) and determined the position needed to be reclassified to a GS-1603-05 Food Services Assistant.  Furthermore, the workload of this position didn’t support a full FTE, but rather 0.8 of and FTE (realizing a 0.2 FTE savings).

Overall staffing in the Clinical Center Nutrition Department was reduced from 55.243 FTE to 51.683 FTE.  Refer to the Crosswalk for a detailed look at staffing changes.  The MEO Functional Organization is depicted in TE- 2-001.

- FIGURE X – MEO FUNCTIONAL ORGANIZATION

Administrative Officer

Food Services, Chief

Clinical Nutrition Services,

Chief

Dietitian Informaticist

Production

Dietitian

Dietetic Internship Director

Metabolic Kitchen

Supervisory Metabolic Dietitian

Clinical Research & Metabolic Dietitians

Clinical Health Technicians

Supervisors

Call Center Health Technicians

Food Service Workers

Procurement Technician

Cooks

Program Support Assistant

Administrative Assistant

Dietetic Interns

Department Chief

### MEO Staffing

#### General Approach

The staffing for the MEO is based on the quantitative analysis conducted tempered with experience and operational considerations provided by a variety of individuals including the Director, MEO Team members, the Human Resources Advisor and, ultimately NIH.  There is no single answer for how a MEO should be constructed.  The blending of the quantitative methodologies and the qualitative elements is both an art and science and factually dependent for each study conducted.  The paragraphs below briefly summarize how MEO positions were developed.  Table 2 below shows the proposed MEO Staffing Plan for the Clinical Center Nutrition Department.

Table 2 – Proposed MEO Staffing Plan

| Position | Series & Grade | FTE |
| --- | --- | --- |
| Manager – Food Services Section Chief | Title 42 CRS | 0.108 |
| Manager – Supervisory Metabolic Dietitian | Commissioned Corps | 0.083 |
| Manager – Production Dietitian | Title 42 CRS | 0.096 |
| Manager – Dietitian Informaticist | Title 42 CRS | 0.156 |
| Program Lead/Metabolic Dietitian | Commissioned Corps | 0.795 |
| Supervisor | WS-7404-05 | 3.280 |
| Food Services Assistant | GS-1603-05 | 0.800 |
| Health Technician | GS-0640-07 | 1.000 |
| Health Technician | GS-0640-06 | 3.500 |
| Health Technician | GS-0640-05 | 1.600 |
| Cook | WG-7404-06 | 9.000 |
| Cook | WG-7404-04 | 2.000 |
| Food Service Worker | WG-7408-04 | 8.000 |
| Food Service Worker | WG-7408-03 | 18.77 |
| TOTAL |  | 49.188 |

#### Functional Discussions

##### Project Management

The Food Services Section Chief will function as the PM and verify that the specific work requirements and standards including QA are met.  These duties will be to ensure Quality Assurance (QA) Program requirements are met, and to oversee performance of the Service Provider whether it is the Government MEO or a private sector Service Provider.

Some MEO positions will be divided between Continuing Government Activity (CGA) and MEO responsibilities as well.  These responsibilities are designated to the Title 42 and Commission Corp positions.

The Title 42 Manager – Food Services Chief position will perform CGA including QA and will act as the approval authority for development, contract monitoring, training and other project management directed in the contract in addition to approval of policies, interpretation of policy and clarification, direction and decisions on policies including NIH needs and approval of design and project funds in addition to initiation of management analyses and IG employment issues noted in section 2.2.2.4 of this report.

Fractional times devoted to MEO and CGA duties are listed in Technical Exhibit 2-001 in the last two (2) columns as MEO/CGA fractional FTE allocations.  For A-76 purposes however, only the fractional FTE performing RD required tasks will be reflected in the Agency Cost Estimate.

##### Operations

The MEO staffing has 6.055 fewer positions than the current organization, and is comprised of a substantially different mix of positions and grades.  The MEO Team considered two (2) major factors in reducing the number of positions.  First, the workload analysis and time per workload occurrences could not justify the current organizational staffing levels.  Second, the hours of operations required a less than full reduction in the number of positions in order to staff enough personnel to cover the food service hours.

The grade of the proposed MEO positions was driven by the descriptions of work and programs in the RD and information provided by the employees and MEO Team members.  The blending of this information into the MEO position descriptions (PDs) will result in some reclassification of PD’s.

##### Operations Support

The Clinical Center Nutrition Department positions are still able to accomplish the original duties with minimal burden.  This will continue for MEO purposes.

#### MEO Positions – Brief Descriptions

Position Description Titles (GS levels)

See attached documents Technical Exhibit 2-003

#### Current to MEO Staffing Comparison

Technical Exhibit 2-001, MEO Staffing Crosswalk, provides a complete list of the positions included in the study, positions eliminated, positions added, and the final MEO staffing.

TECHNICAL EXHIBIT 2-001

MEO Staffing Crosswalk

See Attached.

TECHNICAL EXHIBIT 2-002

MEO Workload Analysis

See Attached.

Food Services

# Quality Control Plan

Chapter 3. Quality Control Plan	3-1

3.1 Overview	3-2

3.2 Purpose	3-2

3.3 Responsibility	3-2

3.4 Record Keeping	3-2

3.5 Annual Evaluation Instructions	3-2

3.6 Completing the Annual Evaluation Report	3-2

3.7 Completing the Letter of Certification	3-3

3.8 Evaluation Score	3-3

| Technical Exhibit Number | Title |
| --- | --- |
| Technical Exhibit 3-001 | Annual Evaluation Report |
| Technical Exhibit 3-002 | Comments/ Justification Form |
| Technical Exhibit 3-003 | Letter of Certification |
| Technical Exhibit 3-004 | QA Requirements Matrix |

## Overview

In accordance with the New OMB Circular NO. A-76 (revised May 29, 2003), Attachment B, paragraph E. 4. (2) Regardless of the selected Service Provider, after implementing a performance decision, The NIH CC Nutrition Department shall implement the Quality Assurance Surveillance Plan (QASP). The QASP used in the 2005 NIH A-76 studies is a matrix document that outlines the tasks, workload, performance standards, and surveillance method for each task. This QASP Instruction document provides procedures for systematic surveillance of the provided services to ensure accordance with the requirements of the RD.

## Purpose

These instructions are being used to provide quality assurance surveillance for the Government MEO, which won the A-76, streamlined competition, under the Revised A-76 Circular.  For clarity of language, the group performing the services will be referred to as the in-house MEO.  This document seeks to guide users, in a step-by-step manner, through the basic implementation, record keeping, and annual evaluation needed to assure that the in-house MEO’s performance is evaluated and meets the requirements outlined in the RD.

## Responsibility

NIH is responsible for implementing the QASP for the fiscal year (FY) 2006 A-76 Studies. This responsibility is further delegated below:

- The Contract Officer (CO) of the Office of the Director (OD) will monitor, provide oversight, conduct evaluations, and maintain records to implement the QASP for each study.

- The Quality Assurance Evaluator (QAE) will conduct the annual evaluations for their functional area.

- The Project Officer will validate the annual evaluation.

## Record Keeping

Record keeping is vital to the quality assurance surveillance process because the records serve as supporting documentation for subjective evaluations.  The level of documentation has focused on annual reports to support the evaluation and performance of the in-house MEO.  Continuous excellent performance will allow a continuation of a normal level of documentation, as outlined in these instructions.  In the same manner, performance that does not meet performance standards may require additional levels of inspection and documentation as directed by the CO.

## Annual Evaluation Instructions

At the end of each fiscal year, the Project Officer will complete the Annual Evaluation Report: Technical Exhibit 3-001.  Prepare the Comments and Justification form: Technical Exhibit 3-002, as necessary.  Submit the completed reports and form to the Office of the Director no later than (Date) of the following fiscal year.  The submission will also include a Letter of Certification: Technical Exhibit 3-003.

## Completing the Annual Evaluation Report

For each task listed in the left hand column:

- Assign points to each task based on its relative importance to meeting the requirements in the RD. The total number of points shall add to 100.

- Describe the evaluation method.  Evaluation methods may include different types of surveillance activities and analysis including, but not limited to direct observations, reconciliation reports, statistical analysis, and customer feedback.

- Indicate if performance met the performance standards.  The performance standards for each task are contained in Technical Exhibit 3-001: QA Requirements Matrix.

#### If performance has failed to meet the performance standards (i.e., a check mark in the “No” column), then a written justification must be entered on the Comments/Justification Form.

#### The written justification should include, but not be limited to, a detailed explanation of why the in-house MEO failed to meet the performance standard, any corrective action plan to correct the problem, and what will be done to meet the standard in the future.

- Sign and date the form.

- Provide to the Project Officer for approval.

- The Project Officer signs and dates the form and provides to the Office of the Director.

## Completing the Letter of Certification

- Sign and date the letter.

- Provide to the Project Officer (PO) for approval.

- The Project Officer signs and dates the letter and provides it to the Office of the Director.

## Evaluation Score

The CO will review the Evaluation Report and Comments/Justification Form and provide to the Project Officer a written evaluation of the fiscal year performance, as well as any additional requirements that are necessary to meet established performance standards.

Technical Exhibit 3-001

Department of Health & Human Services

National Institutes of Health

[OD Address]

Office of the Director

ANNUAL EVALUATION REPORT

FY: 2006

| TASK NUMBER | TASK | POINTS (Must add to 100) | EVALUATION METHOD | Met Performance Standards Yes; NO. |
| --- | --- | --- | --- | --- |
| 5.1 FOOD SERVICES GENERAL INFORMATION |  |  |  |  |  |
| 5.1.1 Work Management and Control |  |  |  |  |  |
| 5.1.1.5 | Event Drills |  | 100% Inspection |  |  |
| 5.1.1.6 | Computerized Kitchen Monitoring System |  | Random Sampling |  |  |
| 5.1.1.7 | Occurrence Reports |  | 100% Inspection |  |  |
| 5.1.1.8 | General Sanitation and Sanitation Standards |  | Random Sampling |  |  |
| 5.1.1.9 | Tugger and Pallet Jack Maintenance |  | Random Sampling |  |  |
| 5.1.2 General Food Service Requirements |  |  |  |  |  |
| 5.1.2.1 | Equipment Cleaning and Sanitizing |  | Random Sampling |  |  |
| 5.1.2.2 | Food Service Kitchen Refrigerator/Freezer Temperatures |  | Random Sampling |  |  |
| 5.1.2.3 | Patient Unit Refrigerator/Freezer Temperatures |  | Random Sampling |  |  |
| 5.1.2.4 | Dishwashing Services |  | Random Sampling |  |  |
| 5.1.2.5 | Refuse Removal |  | Random Sampling |  |  |
| 5.1.3 Procurement, Delivery and Receipt |  |  |  |  |  |
| 5.1.3.1 | Inventory, Research and Ordering |  | Random Sampling |  |  |
| 5.1.3.2 | Receive and Record Store Room Materials |  | Planned Sampling |  |  |
| 5.1.3.3 | Requisition of Store Room Materials |  | Random Sampling |  |  |
| 5.1.3.4 | Issuance of Store Room Materials |  | Random Sampling |  |  |
| 5.1.3.5 | Store Room Security |  | Random Sampling |  |  |
| 5.1.3.6 | Budget and Reconciliation |  | 100% Inspection |  |  |
| 5.1.3.7 | Printer Maintenance |  | Random Sampling |  |  |
| 5.2 NUTRITION CALL CENTER |  |  |  |  |  |
| 5.2.1 Meal Requests and Food Order Processing |  |  |  |  |  |
| 5.2.1.1 | Behavioral Health Processing |  | Random Sampling |  |  |
| 5.2.1.2 | Room Service Processing |  | Customer (Patient) Survey |  |  |
| 5.2.1.3 | Bag Meal Requests |  | N/A |  |  |
| 5.2.1.4 | Nourishment / Snack Requests |  | Random Sampling |  |  |
| 5.2.1.5 | Tube Feedings |  | Random Sampling |  |  |
| 5.2.1.6 | Emergency / Immediate Requests |  | Random Sampling |  |  |
| 5.2.1.7 | Nutritional Floor Stock |  | N/A |  |  |
| 5.2.1.8 | Behavioral Health Picnic Processing |  | Random Sampling |  |  |
| 5.2.1.9 | Dental Soft Trays |  | N/A |  |  |
| 5.2.2 Menu Administration |  |  |  |  |  |
| 5.2.2.1 | Behavioral Health Menu Administration and Delivery |  | Random Sampling |  |  |
| 5.2.2.2 | Menu Replication and Stocking |  | N/A |  |  |
| 5.2.2.3 | Menu Update and Maintenance |  | N/A |  |  |
| 5.2.2.4 | Menu and Patient Request Translation |  | Random Sampling |  |  |
| 5.2.3 Interpret and Process Patient Nutritional Data |  |  |  |  |  |
| 5.2.3.1 | Patient Status |  | N/A |  |  |
| 5.2.3.2 | Determine Current Patient Diet Orders |  | Random Sampling |  |  |
| 5.2.4 Perform CBORD Nutrition and Food Service Computer System Data Entry |  |  |  |  |  |
| 5.2.4.1 | Diet Order Revisions and Changes |  | Random Sampling |  |  |
| 5.2.4.2 | Patient Admissions and Discharges |  | Random Sampling |  |  |
| 5.2.5 Problem Resolution for Patient Food Service |  |  |  |  |  |
| 5.2.5.2 | System Information Changes and Updates |  | N/A |  |  |
| 5.2.6 Problem Resolution of CBORD and CRIS Downtime |  |  |  |  |  |
| 5.2.6.1 | Computer System Troubleshooting and Resolution |  | N/A |  |  |
| 5.2.6.2 | Computer System Application Downtime Menu Order Processing |  | N/A |  |  |
| 5.2.7 Generate Reports for Hospital Patients According to Clinical Condition Concerning Food Service |  |  |  |  |  |
| 5.2.7.1 | Missed Meal Reports |  | N/A |  |  |
| 5.2.7.2 | Nourishment Reports |  | Random Sampling |  |  |
| 5.2.7.3 | Scheduled Room Service Delivery Report |  | N/A |  |  |
| 5.2.7.4 | Advanced Ticket Diet Order Report |  | Random Sampling |  |  |
| 5.2.7.5 | Census Report with Notes |  | Random Sampling |  |  |
| 5.2.7.6 | Selections Report |  | N/A |  |  |
| 5.3 MAIN KITCHEN |  |  |  |  |  |
| 5.3.1 Hot and Cold Food Production |  |  |  |  |  |
| 5.3.1.1 | Food Preparation |  | Random Sampling and Customer (Patient) Survey |  |  |
| 5.3.1.2 | Tray Assembly |  | Random Sampling |  |  |
| 5.3.1.3 | Temperature Logs |  | Random Sampling |  |  |
| 5.3.2 Room Service and Behavioral Health Units |  |  |  |  |  |
| 5.3.2.1 | Tray Delivery – Room Service |  | Random Sampling and Customer (Patient) Survey |  |  |
| 5.3.2.2 | Tray Delivery – Behavioral Health Units |  | Random Sampling |  |  |
| 5.3.2.3 | Tray Removal from Patient Rooms and Areas |  | Random Sampling |  |  |
| 5.3.2.4 | Tray Removal from Behavioral Health Units |  | Random Sampling |  |  |
| 5.3.3 Prepare Specialized Foods and Therapeutic Projects |  |  |  |  |  |
| 5.3.3.1 | Celebratory Functions and Catering |  | Planned Sampling |  |  |
| 5.3.3.2 | Special Food / Snack Requests |  | Random Sampling |  |  |
| 5.3.3.3 | Family Lodge Assistance |  | Random Sampling |  |  |
| 5.3.4 Prepare First Floor Continental Breakfast for Phlebotomy Patients |  |  |  |  |  |
| 5.3.4.1 | Continental Breakfast Preparation and Delivery |  | Planned Sampling |  |  |
| 5.3.4.2 | Continental Breakfast Clean-Up and Pick-Up |  | Planned Sampling |  |  |
| 5.3.5 Assemble and Deliver Nutrition Floor Stock |  |  |  |  |  |
| 5.3.5.1 | Patient Care Unit Nourishment Stock |  | Random Sampling |  |  |
| 5.3.5.2 | Quality Check |  | N/A |  |  |
| 5.3.6 Assemble and Deliver Bag Meals |  |  |  |  |  |
| 5.3.6.1 | Order Receipt and Meal Preparation |  | Random Sampling |  |  |
| 5.3.6.2 | Bag Meal Delivery |  | Random Sampling |  |  |
| 5.3.7 Prepare and Deliver Nourishments/Snacks/Supplements |  |  |  |  |  |
| 5.3.7.1 | Receive, Prepare / Assemble and Deliver Patient Nutrition Requests |  | Random Sampling |  |  |
| 5.4 METABOLIC KITCHEN |  |  |  |  |  |
| 5.4.1 Perform Inventory Control of Food/Food Supplies |  |  |  |  |  |
| 5.4.1.1 | Identification of Menu Items |  | N/A |  |  |
| 5.4.1.2 | Special Requests |  | N/A |  |  |
| 5.4.1.3 | Metabolic Kitchen Weekly Inventory |  | N/A |  |  |
| 5.4.2 Store Metabolic Kitchen Food/Food Supplies |  |  |  |  |  |
| 5.4.2.1 | Metabolic Kitchen Store Room Maintenance |  | Random Sampling |  |  |
| 5.4.3 Request Metabolic Kitchen Food Preparation |  |  |  |  |  |
| 5.4.3.1 | Protocol Meal Preparation |  | Random Sampling |  |  |
| 5.4.3.2 | Protocol Meal Verification |  | N/A |  |  |
| 5.4.3.3 | Protocol Meal Communication |  | N/A |  |  |
| 5.4.4 Assemble, Deliver, and Pick Up Protocol Food |  |  |  |  |  |
| 5.4.4.1 | Assemble Meals |  | N/A |  |  |
| 5.4.4.2 | Tray Delivery and Pick Up |  | Random Sampling |  |  |
| 5.4.5 Process Refused Food |  |  |  |  |  |
| 5.4.5.1 | Weigh In and Process Refused Food |  | Random Sampling |  |  |
| 5.4.5.2 | Nourishment Replacement |  | N/A |  |  |
| 5.4.6 Metabolic Enteral Formula Orders |  |  |  |  |  |
| 5.4.6.1 | Verification of Formula Orders and Dietitian Communication |  | N/A |  |  |
| 5.4.6.2 | Process Diluted or Mixed Enteral Formula |  | Random Sampling |  |  |
| 5.4.6.3 | Process Refused Formula |  | Random Sampling |  |  |
| 5.4.7 Develop, Standardize and Test Recipes |  |  |  |  |  |
| 5.4.7.1 | Recipe Development |  | N/A |  |  |
| 5.4.7.2 | Recipe Taste Test |  | N/A |  |  |
| 5.4.8 Promote Patients’ Compliance with Research Diets |  |  |  |  |  |
| 5.4.8.1 | Metabolic Food Education |  | N/A |  |  |

Quality Assurance Evaluator Signature:__________________  Date:_________________

Project Officer Signature:					       Date:_________________

TECHNICAL EXHIBIT 3-002

Department of Health & Human Services

National Institutes of Health

[OD Address]

Office of the Director

COMMENTS / JUSTIFICATION FORM

---------------------------------------

FY: 2006

| Task No. / Criteria Statement | Comment / Justification |
| --- | --- |

TECHNICAL EXHIBIT 3-003

Department of Health & Human Services

National Institutes of Health

[OD Address]

Office of the Director

LETTER OF CERTIFICATION

DATE:

TO:   		      Contracting Officer

Office of the Director

FROM:	      (Project Officer)

SUBJECT:           Annual Evaluation Report Letter of Certification for -------------------------

I have approved the FY 2006 Annual Evaluation Report.  I have completed the Comments /Justification Form and have developed a Corrective Action Plan for those activities that do not meet performance standards as established in the final Requirements Document (RD).

We are continuing to provide services that were the subject of the competitive sourcing review and have maintained the workload level that was assumed in the study.  Furthermore, I certify that we are continually performing in accordance with the scope, technical standards and personnel requirements as specified in the RD.  I have notified the Contracting Officer of any changed conditions in my services, in accordance with the Letter of Obligation.

_____________________________________         ____________________

Project Officer   				Date

_____________________________________          ____________________

Contracting Officer 				Date

TECHNICAL EXHIBIT 3-004

Requirements matrix

| PWS NUMBER | TASK DESCRIPTION | PERFORMANCE INDICATOR | ALP |
| --- | --- | --- | --- |
| 5.1 FOOD SERVICES GENERAL INFORMATION |  |  |  |
| 5.1.1 Work Management and Control |  |  |  |
| 5.1.1.1 | Meal Service Hours of Operation | No Standard | N/A |
| 5.1.1.2 | Internship Support | No Standard | N/A |
| 5.1.1.3 | Communication Devices | No Standard | N/A |
| 5.1.1.4 | Personnel Interfaces | No Standard | N/A |
| 5.1.1.5 | Event Drills | Timeliness Standard: Acceptable performance requires that the Service Provider prepare and submit input and recommendations, regarding the event drill, by the timeframe specified by the Project Officer 99% of the time. | TS: 1% |
| 5.1.1.6 | Computerized Kitchen Monitoring System | Timeliness Standard: Acceptable performance requires that the Service Provider respond and take corrective action within two hours of receiving an alert 99% of the time. | TS: 1% |
| 5.1.1.7 | Occurrence Reports | Quality Standard: Acceptable performance requires that the Service Provider receive no more than 15 validated occurrence reports per month 80% of the time. Timeliness Standard: Acceptable performance requires that the Service Provider gather all necessary information and prepare an accurate response for the Project Officer within the given timeframe 90% of the time. | QS: 20% TS: 10% |
| 5.1.1.8 | General Sanitation and Sanitation Standards | Quality Standard: - Acceptable performance requires that the Service Provider accurately complete the Sanitation Solution Log (Exhibit 5 in the BTL) 85% of the time. - Acceptable performance shall require that all of kitchen pots and pans are cleaned, sanitized and properly put away by the end of the work day 98% of the time. - Acceptable performance requires that the Service Provider shall score in compliance with the policy, 99% of the time. Timeliness Standard: Acceptable performance also requires that the Service Provider correct any issues discovered by the identified policy timeframe 90% of the time. Acceptable performance also requires that the Service Provider submit the written response to the Project Officer within 3 workdays. | QS: - 15% - 2% - 1% TS: 10% |
| 5.1.1.9 | Tugger and Pallet Jack Maintenance | Quality Standard: Acceptable performance requires that the Service Provider perform tugger and pallet jack maintenance and complete the daily Tugger logs 99.9% of the time. | QS: .1% |
| 5.1.2 General Food Service Requirements |  |  |  |
| 5.1.2.1 | Equipment Cleaning and Sanitizing | Quality Standard: Acceptable performance requires that the Service Provider accurately utilize the Kitchen Equipment List (Technical Exhibit 5.1-001) to ensure cleanliness 97% of the time. Timeliness Standard: - Acceptable performance requires that the Service Provider properly cleans and sanitizes kitchen equipment by the end of the workday 99% of the time. | QS: 3% TS: 1% |
| 5.1.2.2 | Food Service Kitchen Refrigerator/Freezer Temperatures | Quality Standard: Acceptable performance requires that the Service Provider contact the necessary personnel to resolve issues and situations 98% of the time. Timeliness Standard: Acceptable performance requires that the Service Provider contact the necessary personnel within 15 minutes once the Rees System has notified and received a response from the Service Provider 99% of the time. | QS: 2% TS: 1% |
| 5.1.2.3 | Patient Unit Refrigerator/Freezer Temperatures | Quality Standard: Acceptable performance requires that the Service Provider contact the necessary personnel to resolve issues and situations 98% of the time Timeliness Standard: Acceptable performance requires that the Service Provider contact the necessary personnel within 15 minutes after initial corrective action has been attempted 99% of the time. | QS: 2% TS: 1% |
| 5.1.2.4 | Dishwashing Services | Quality Standard: - Acceptable performance requires that the Service Provider accurately and completely log the dishwashing machine temperature 98% of the time. - Acceptable performance requires that the Service Provider take corrective action within five minutes to rectify the temperature 99.9% of the time. - Acceptable performance requires that the Service Provider completely and accurately record the pot wash machine, cleaning solution, and three compartment sink temperature log 98% of the time. Timeliness Standard: Acceptable performance requires that the Service Provider, during each meal time, ensure the temperature meets all food service regulations 99% of the time. | QS: - 2% - .1% - 2% TS: 1% |
| 5.1.2.5 | Refuse Removal | Quality Standard: Acceptable performance requires that the Service Provider remove refuse so that the kitchen areas do not resonant the odor of spoiled food or create an unsanitary issue that could cause contamination to patient food 99% of the time. | QS: 1% |
| 5.1.3 Procurement, Delivery and Receipt |  |  |  |
| 5.1.3.1 | Inventory, Research and Ordering | Quality Standard: Acceptable performance requires that the Service Provider perform an accurate and complete inventory to ensure that the store room maintains the necessary levels and is not depleted of a needed item causing delay to food preparation and delivery time 90% of the time. | QS: 10% |
| 5.1.3.2 | Receive and Record Store Room Materials | Quality Standard: Acceptable performance requires that the Service Provider reject all non-acceptable food, as determined by HACCP, so that the storeroom does not contain outdated or spoiled food 98% of the time. | QS: 2% |
| 5.1.3.3 | Requisition of Store Room Materials | Quality Standard: Acceptable performance requires that the Service Provider prepare requisitions accurately and completely within two business days 90% of the time. | QS: 10% |
| 5.1.3.4 | Issuance of Store Room Materials | Quality Standard: Acceptable performance requires that the Service Provider issue the correctly requested food or fluid item 99.9% of the time. Timeliness Standard: Acceptable performance requires that the Service Provider issue foods, formulas, and non-food supplies by the requested time or for planned meals/nourishments/snacks, issued in time to prepare and deliver the request by the standard delivery time 98% of the time. | QS: .1% TS: 2% |
| 5.1.3.5 | Store Room Security | Quality Standard: Acceptable performance requires that the Service Provider completely and accurately log the store room security information on a daily basis 95% of the time. | QS: 5% |
| 5.1.3.6 | Budget and Reconciliation | Timeliness Standard: Acceptable performance requires that the Service Provider reconcile the credit card statement by the 13th of the month 99.9% of the time. | TS: .1% |
| 5.1.3.7 | Printer Maintenance | Timeliness Standard: Acceptable performance requires that the Service Provider stock printers with supplies (i.e., paper, toner cartridges) as needed 95% of the time. | TS: 5% |
| 5.2 Nutrition Call Center |  |  |  |
| 5.2.1 Meal Requests and Food Order Processing |  |  |  |
| 5.2.1.1 | Behavioral Health Processing | Quality Standard: Acceptable performance requires that the Service Provider enter a tray for all behavioral health in-house patients for each meal with the appropriate stamps 99% of the time. | QS: 1% |
| 5.2.1.2 | Room Service Processing | Quality Standard: Acceptable performance requires that the average monthly score on the Patient Satisfaction Survey be rated as Fair or above 99.9% of the time for the courtesy of the person taking the order of the received responses from the Patient Satisfaction Survey. | QS: .1% |
| 5.2.1.3 | Bag Meal Requests | No Standard | N/A |
| 5.2.1.4 | Nourishment / Snack Requests | Quality Standard: Acceptable performance requires that the Service Provider enter the nourishment / snack request accurately on a room service ticket or a CBORD requisition 97% of the time. | QS: 3% |
| 5.2.1.5 | Tube Feedings | Timeliness Standard: Acceptable performance requires that the Service Provider review, process, and take appropriate action regarding CRIS order requisitions within 15 minutes of receipt 80% of the time. | TS: 20% |
| 5.2.1.6 | Emergency / Immediate Requests | Timeliness Standard: Acceptable performance requires that the Service Provider review, process, and take appropriate action regarding CRIS order requisitions within 15 minutes of receipt 80% of the time. | TS: 20% |
| 5.2.1.7 | Nutritional Floor Stock | No Standard | N/A |
| 5.2.1.8 | Behavioral Health Picnic Processing | Quality Standard: Acceptable performance requires that the Service Provider accurately enter behavioral health picnic requests on a weekly basis 99% of the time. | QS: 1% |
| 5.2.1.9 | Dental Soft Trays | No Standard | N/A |
| 5.2.2 Menu Administration |  |  |  |
| 5.2.2.1 | Behavioral Health Menu Administration and Delivery | Quality Standard: Acceptable performance requires that the Service Provider accurately reflect the patient’s name, location and meal on the menu and send to the correct unit 99.9% of the time. | QS: .1% |
| 5.2.2.2 | Menu Replication and Stocking | No Standard | N/A |
| 5.2.2.3 | Menu Update and Maintenance | No Standard | N/A |
| 5.2.2.4 | Menu and Patient Request Translation | Quality Standard: Acceptable performance requires that the Service Provider translate all menus for non-English speaking patients’ requests correctly 80% of the time. | QS: 20% |
| 5.2.3 Interpret and Process Patient Nutritional Data |  |  |  |
| 5.2.3.1 | Patient Status | No Standard | N/A |
| 5.2.3.2 | Determine Current Patient Diet Orders | Timeliness Standard: Acceptable performance requires that the Service Provider review, process, and take appropriate action regarding CRIS order requisitions within 15 minutes of receipt, 80% of the time. | TS: 20% |
| 5.2.4 Perform CBORD Nutrition and Food Service Computer System Data Entry |  |  |  |
| 5.2.4.1 | Diet Order Revisions and Changes | Timeliness Standard: Acceptable performance requires that the Service Provider review, process, and take appropriate action regarding CRIS order requisitions within 15 minutes of receipt, 80% of the time. | TS: 20% |
| 5.2.4.2 | Patient Admissions and Discharges | Timeliness Standard: - Acceptable performance requires that the Service Provider review, process, and take appropriate action regarding CRIS order requisitions within 15 minutes of receipt 80% of the time. - Acceptable performance requires that the Service Provider accurately determine patients that need discharging and complete in the CBORD card file weekly 95% of the time. | TS: 20% TS: 5% |
| 5.2.5 Problem Resolution for Patient Food Service |  |  |  |
| 5.2.5.2 | System Information Changes and Updates | No Standard | N/A |
| 5.2.6 Problem Resolution of CBORD and CRIS Downtime |  |  |  |
| 5.2.6.1 | Computer System Troubleshooting and Resolution | No Standard | N/A |
| 5.2.6.2 | Computer System Application Downtime Menu Order Processing | No Standard | N/A |
| 5.2.7 Generate Reports for Hospital Patients According to Clinical Condition Concerning Food Service |  |  |  |
| 5.2.7.1 | Missed Meal Reports | No Standard | N/A |
| 5.2.7.2 | Nourishment Reports | Quality Standard: Acceptable performance requires that the Service Provider review the accuracy of the date and meal daily 99% of the time. | QS: 1% |
| 5.2.7.3 | Scheduled Room Service Delivery Report | No Standard | N/A |
| 5.2.7.4 | Advanced Ticket Diet Order Report | Quality Standard: Acceptable performance requires that the Service Provider accurately edits the meal ticket in compliancy with the new diet order 99% of the time. | QS: 1% |
| 5.2.7.5 | Census Report with Notes | Quality Standard: Acceptable performance requires that the Service Provider accurately reflect new diet orders on meal tickets 99.95 % of the time. | QS: .05% |
| 5.2.7.6 | Selections Report | No Standard | N/A |
| 5.3 MAIN KITCHEN |  |  |  |
| 5.3.1 Hot and Cold Food Production |  |  |  |
| 5.3.1.1 | Food Preparation | Quality Standard: - Acceptable performance requires that the Service Provider prepare the requested meal accurately following established food safety procedures to eliminate the potential of food born illness and inadvertent allergy contamination 99% of the time. - Acceptable performance requires that the Service Provider ensure that the prepared food falls within the correct temperature range as defined by the FDA Food Code 99% of the time. | QS: - 1% - 1% |
| 5.3.1.2 | Tray Assembly | Quality Standard: Acceptable performance requires that the Service Provider shall assemble trays that are correct 90% of the time. | QS: 10% |
| 5.3.1.3 | Temperature Logs | Quality Standard: - Acceptable performance requires that the Service Provider ensure time standards are met and temperature readings are performed to ensure that the food is properly cooked and held to temperatures that fall within the HACCP guidelines 99.9% of the time. | QS: - .1% |
| 5.3.2 Room Service and Behavioral Health Units |  |  |  |
| 5.3.2.1 | Tray Delivery – Room Service | Quality Standard: - Acceptable performance requires that the Service Provider deliver all patient trays to the room within 45 minutes of receiving the room service request 85% of the time. - Acceptable performance requires that the average monthly scores on the Patient Satisfaction Survey be rated as Fair or above 99.9% of the time for the quality of service, flavor and taste of food, appearance of the meal, meal temperature, courtesy of the person delivering the food, courtesy of the person taking your order, timeliness of the meals, and accuracy of the tray. | QS: - 15% - .1% |
| 5.3.2.2 | Tray Delivery – Behavioral Health Units | Quality Standard: - Acceptable performance requires that the Service Provider deliver all patient trays to the designated dining location within the Behavioral Health Unit by 7:45 a.m. for breakfast, by 11:45 a.m. for lunch, and by 4:45 p.m. for dinner 90% of the time. - Acceptable performance requires that the average monthly scores on the Patient Satisfaction Survey be rated as Fair or above 99.9% of the time for the quality of service, flavor and taste of food, appearance of the meal, and meal temperature. | QS: 10% QS: .1% |
| 5.3.2.3 | Tray Removal from Patient Rooms and Areas | Quality Standard: Acceptable performance requires that the Service Provider remove and return all trays to the kitchen to ensure sufficient trays, flatware and dishware are available for the next meal 90% of the time. | QS: 10% |
| 5.3.2.4 | Tray Removal from Behavioral Health Units | Quality Standard: Acceptable performance requires that the Service Provider collect and return all trays to the kitchen by the end of the workday 95% of the time, unless trays are unavailable for pick up. | QS: 5% |
| 5.3.3 Prepare Specialized Foods and Therapeutic Projects |  |  |  |
| 5.3.3.1 | Celebratory Functions and Catering | Quality Standard: Acceptable performance requires that the Service Provider prepare the meal as agreed upon 97% of the time. Timeliness Standard: Acceptable performance requires that the Service Provider deliver the meal to the correct location by the time requested 97% of the time. | QS: 3% TS: 3% |
| 5.3.3.2 | Special Food / Snack Requests | Quality Standard: Acceptable performance requires that the Service Provider accurately prepare the request 85% of the time. Timeliness Standard: Acceptable performance requires that the Service Provider deliver the available special snacks and food by the requested time 97% of the time. | QS: 15% TS: 3% |
| 5.3.3.3 | Family Lodge Assistance | Quality Standard: Acceptable performance requires that the Service Provider provide available food and food service supplies to the Family Lodge by the delivery date 90% of the time. | QS: 10% |
| 5.3.4 Prepare First Floor Continental Breakfast for Phlebotomy Patients |  |  |  |
| 5.3.4.1 | Continental Breakfast Preparation and Delivery | Quality Standard: Acceptable performance requires that the Service Provider prepare and deliver foods and food service supplies to the requested location between 7:00 a.m. -7:15 a.m. Monday – Friday 90% of the time. | QS: 10% |
| 5.3.4.2 | Continental Breakfast Clean-Up and Pick-Up | Timeliness Standard: Acceptable performance requires that the Service Provider pick up the food and food materials between 9:00 a.m. – 9:15 a.m. Monday – Friday 90% of the time. | TS: 10% |
| 5.3.5 Assemble and Deliver Nutrition Floor Stock |  |  |  |
| 5.3.5.1 | Patient Care Unit Nourishment Stock | Quality Standard: - Acceptable performance requires that the Service Provider stock Patient Care Unit refrigerators with in-stock / available items daily and pantries weekly so that the items meet established par levels 95% of the time right after restocking. - Acceptable performance also requires that the Service Provider ensure that no expired food remains in the pantry or refrigerator 99% of the time. | QS: - 5% - 1% |
| 5.3.5.2 | Quality Check | ( Standard provided in 5.3.5.1) | N/A |
| 5.3.6 Assemble and Deliver Bag Meals |  |  |  |
| 5.3.6.1 | Order Receipt and Meal Preparation | Quality Standard: Acceptable performance requires that the Service Provider accurately prepare and label the requested meal 99% of the time. | QS: 1% |
| 5.3.6.2 | Bag Meal Delivery | Timeliness Standard: Acceptable performance requires that the Service Provider deliver the bag meals by 10:30 a.m. for breakfast, by 1:00 p.m. for lunch, and by 8:00 p.m. for dinner 85% of the time. | QS: 15% |
| 5.3.7 Prepare and Deliver Nourishments/Snacks/Supplements |  |  |  |
| 5.3.7.1 | Receive, Prepare / Assemble and Deliver Patient Nutrition Requests | Quality Standard: Acceptable performance requires that the Service Provider deliver planned snacks by 10:00 a.m. for the morning snack, by 2:00 p.m. for the afternoon snack, and by 8:00 p.m. for the evening snack 85% of the time. Timeliness Standard: Acceptable performance also requires that the Service Provider deliver unplanned nourishments or snacks requests within 45 minutes of the received request 85% of the time. | QS: 15% TS: 15% |
| 5.4 METABOLIC KITCHEN |  |  |  |
| 5.4.1 Perform Inventory Control of Food/Food Supplies |  |  |  |
| 5.4.1.1 | Identification of Menu Items | No Standard | N/A |
| 5.4.1.2 | Special Requests | No Standard | N/A |
| 5.4.1.3 | Metabolic Kitchen Weekly Inventory | Quality Standard: - Acceptable performance requires that the Service Provider perform an accurate and complete inventory 90% of the time. - Acceptable performance requires that the Service Provider prepare CBORD requisitions and purchase orders accurately and completely 90% of the time. | QS: - 10% - 10% |
| 5.4.2 Store Metabolic Kitchen Food/Food Supplies |  |  |  |
| 5.4.2.1 | Metabolic Kitchen Store Room Maintenance | Quality Standard: Acceptable Performance requires that the Service Provider ensure that all food and formulas are dated with expiration dates 90% of the time and not used past their expiration dates 99.9% of the time. Timeliness Standard: Acceptable performance requires that the Service Provider remove outdated items from the pantries or refrigerators upon expiration 99% of the time. | QS: - 10% - .1% TS: 1% |
| 5.4.3 Request Metabolic Kitchen Food Preparation |  |  |  |
| 5.4.3.1 | Protocol Meal Preparation | Quality Standard: - Acceptable performance requires that the Service Provider use the exact ingredients required by the protocol recipe including the exact product and brand names 99.9% of the time. - Acceptable performance requires that the Service Provider shall accurately weigh food within 2% of the stated weight 80% of the time, within 5% of the stated weight 90% of the time, and within 10% of the stated weight 99.9% of the time. The weight of the food shall be document accurately and legibly 99.9% of the time. Timeliness Standard: Acceptable performance requires that the Service Provider serve metabolic meals, snacks, and formulas within 15 minutes of the requested delivery time 99% of the time. | QS: - .1% - 20% - 10% - .1% - .1% TS: 1% |
| 5.4.3.2 | Protocol Meal Verification | No Standard (included in 5.4.3.1) | N/A |
| 5.4.3.3 | Protocol Meal Communication | No Standard | N/A |
| 5.4.4 Assemble, Deliver, and Pick Up Protocol Food |  |  |  |
| 5.4.4.1 | Assemble Meals | No Standard | N/A |
| 5.4.4.2 | Tray Delivery and Pick Up | Quality Standard: Acceptable performance requires that the Service Provider accurately deliver and pick up patient meal trays, snack and nourishment containers to the correct requesting patient or nursing unit requestor 99% of the time. Timeliness Standard: Acceptable performance requires that the Service Provider deliver the tray to the correct patient as directed by the protocol schedule or within 15 minutes of the patient’s request 99% of the time. | QS: 1% TS: 1% |
| 5.4.5 Process Refused Food |  |  |  |
| 5.4.5.1 | Weigh In and Process Refused Food | Quality Standard: Acceptable performance requires that the Service Provider shall accurately re-weigh food within 2% of the stated weight 80% of the time, within 5% of the stated weight 90% of the time, and within 10% of the stated weight 99.9% of the time. The weight of the food shall be documented accurately and legibly 99.9% of the time. Timeliness Standard: Acceptable performance requires that the Service Provider re-weigh the food within one hour of receipt 80% of the time, and within the same day 99.9% of the time. | QS: - 20% - 10% - .1% - .1% TS: - 20% - .1% |
| 5.4.5.2 | Nourishment Replacement | No Standard | N/A |
| 5.4.6 Metabolic Enteral Formula Orders |  |  |  |
| 5.4.6.1 | Verification of Formula Orders and Dietitian Communication | No Standard | N/A |
| 5.4.6.2 | Process Diluted or Mixed Enteral Formula | Quality Standard: - Acceptable performance requires that the Service Provider shall ensure all foods; liquid and powered formulas are labeled with expiration dates and monitored. All opened and prepared items must have labeled expiration date recorded on the packaging 99.9% of the time. - Acceptable performance requires that prepare the requested formula using the exact product and brand names, and amount 99.9% of the time. - Acceptable performance requires that ingredients are stored at the proper temperature. 99.9% of the time. Timeliness Standard: Acceptable performance requires that the Service Provider prepare replacement formula 99% of the time within one hour of the request. | QS: - .1% - .1% - .1% TS: 1% |
| 5.4.6.3 | Process Refused Formula | Quality Standard: Acceptable performance requires that the Service Provider weigh the food and document findings accurately and legibly 99.9% of the time. Timeliness Standard: Acceptable performance requires that the Service Provider weigh the formula within one hour of receipt 80% of the time, and within the same day 99.9% of the time. | QS: .1% TS: - 20% - .1% |
| 5.4.7 Develop, Standardize and Test Recipes |  |  |  |
| 5.4.7.1 | Recipe Development | No Standard | N/A |
| 5.4.7.2 | Recipe Taste Test | No Standard |  |
| 5.4.8 Promote Patients’ Compliance with Research Diets |  |  |  |
| 5.4.8.1 | Metabolic Food Education | No Standard | N/A |
| 5.5 CONTINGENCY PLANNING |  |  |  |
| 5.5.1 Continuity of Operations Planning |  |  |  |
| 5.5.1.1 | Contingency Plan Development | No Standard at this time | N/A |
| 5.5.1.2 | Food Service Delivery | No Standard at this time | N/A |

Food Services

# Continuing Government Activity (CGA)

Chapter 4. Continuing Government Activity (CGA)	4-1

4.1 General	4-2

4.2 CGA Staffing Calculations	4-2

## General

As indicated in Chapter 2, the CGA will perform two (2) categories of tasks and functions: (1) those that are inherently governmental or which the RD Team has declared core to the Food Services operations, and (2) the OMB Circular A-76 “Post Competition Accountability” or Quality Assurance (QA) requirements.  CGA performance should include all of the tasks and functions performed by the current organization that are not included in the RD as well as the Circular A-76 QA function as defined by the Quality Assurance Surveillance Plan (QASP).  The Project Officer will oversee the performance of the Service Provider whether it is the Government MEO or a private sector Service Provider.

## CGA Staffing CALCULATIONS

Table 4-1 – Continuing Government Activity

| Position Title | Series/Grade | FTE |
| --- | --- | --- |
| Manager – Food Services Section Chief | Title 42 CRS | 0.096 |
| Manager – Supervisory Metabolic Dietitian | Commissioned Corps | 0.917 |
| Manager – Production Dietitian | Title 42 CRS | 0.844 |
| Manager – Dietitian Informaticist | Title 42 CRS | 0.892 |
| FTE Total |  | 2.749 |

Food Services

# Phase-In Plan

Chapter 5. Phase-In Plan	5-1

5.1 General	5-2

5.2 Assumptions, References and Affected Organizations	5-2

5.3 Pre-Performance Decision Activities	5-2

5.4 Post-Performance Decision Activities	5-3

5.5 Utilities and Any Other Services And Costs To Be Transferred	5-6

5.6 Indicators Of Successful Transition	5-6

Technical Exhibits

| Technical Exhibit Number | Title |
| --- | --- |
| Technical Exhibit 5-001 | Food Services Government Provided Training |
| Technical Exhibit 5-002 | Integrated Phase-In Timeline |

## General

This Chapter details a Phase-In Plan to replace the incumbent Service Provider with the MEO, even if the agency is the incumbent Service Provider.  Accordingly, this chapter does not specifically address the actions required to replace the incumbent provider with a private sector contractor, although many of the actions required may be similar.

During phase-in, the CC Nutrition Department, Food Services shall continue to provide quality service to its customers.  This Plan requires significant and well-coordinated efforts.  The following Phase-In Plan shall serve as the means by which successful implementation occurs.

The objective of the Phase-In Plan is to chart a course from the current organization to the future Government-operated MEO as it takes over the mission and functions of the areas that have been under study.

## Assumptions, References and Affected Organizations

### References

- The Food Services Requirements Document.

- The Food Services Quality Control Plan.

- The Food services Quality Assurance Surveillance Plan (QASP).

- The food Services Performance Work Statement.

- The Food services Bidders Technical Library.

### Affected Organizations

The NIH, CC Nutrition Department Food Services is the designated function under study and is directly affected.

## Pre-Performance Decision Activities

Planning for a transition may begin when the MEO has been completed and the performance decision has been officially announced as a Government decision.  During the time between the completion of the MEO and the announcement of the performance decision, the Office of Human Resources is primarily planning the efforts associated with personnel actions.  During the same planning period, training requirements and resources should be identified and plans for training may begin.

### Phase-In Team

To expedite the transition process, the Agency Tender Official (ATO), the NIH Office of the Director (OD), point of contact (POC), and the current Project Officer or designee shall establish a Phase-In Team tasked with implementing the MEO while simultaneously mitigating any adverse impact on the customers.  The Phase-In Team, under the direction of the current NIH OD POC, will address two (2) major functional areas: Administrative/HR and Technical/Logistical.  The Phase-In Team will thus include two (2) sub-teams to address these functional areas.  One (1) sub-team will consist of personnel from the Human Resources Division.  The other sub-team will include technical personnel from specified areas within NIH knowledgeable of CC Nutrition Department Food Services.

Each sub-team of the Phase-In Team will operate under a separate group leader.  The ATO and the Project officer or designee may chair or serve on these sub-teams.  The Administrative/HR sub-team will appoint members as necessary and address all personnel transition issues.  The Technical/Logistical sub-team will be comprised of Subject Matter Experts (SME) and technical personnel from within NIH who will assist in transitioning to an MEO or Private Service Provider based upon the outcome of the competition as well as training and other technical requirements.

### Phase-In Team Duties

During the planning period, the Phase-In Team will:

- Counsel and brief employees on transition.  This includes change management and providing employees with the solid understanding of duties and responsibilities working in an MEO.

- Identify any issues that may be related to the restructuring of the organization.

- Share new job descriptions and performance standards.

- Schedule and conduct inventory of accountable property.

- Schedule and provide procedures for the transfer or disposal of any equipment, material, or facilities if a private sector Service Provider is selected.

- Handle security issues with facility access (for private sector Service Providers).

## Post-Performance Decision Activities

Once the cost comparison has been conducted and the performance decision is announced as Government performance, two (2) major parallel actions are initiated – personnel related actions to create the MEO and to perform the Continuing Government Activities (CGA) logistics actions identified in the MEO.

### Personnel Actions

The Human Resources Division will execute actions necessary to allow the current organization to be structured to the new MEO and perform CGA.

#### Planning for Implementing the MEO

The implementation of the MEO and performance of the CGA should begin immediately following notification of the award decision.  The fractional FTE for the MEO and CGA positions are identified in Technical Exhibit 2-001 MEO Staffing Crosswalk.  Preliminary planning for the transition to the MEO may begin anytime prior to this date.  The Phase-In Team should move the current organization to the MEO structure including CGA responsibilities as soon as practical.  Specifically:

- During the time between the completion of the MEO and the announcement of the award, the Phase-In Team is primarily planning the efforts associated with personnel actions and any training/retraining if necessary.

- During the planning phase, any new training/retraining requirements or opportunities should be identified, but should not begin until the first day of the MEO implementation.  The objective of these training/retraining efforts is aimed at the new MEO personnel if required.

- Plans for any security checks and clearances for any new MEO employees and the attendant documentation must be formulated with implementation to be completed prior to initiation of execution of the RD tasks by the MEO.

- Fulfill all union bargaining obligations as appropriate.

### Technical/Logistics Actions

A Technical/Logistics sub-team headed by the ATO/Director will be established to ensure that all actions supporting the MEO implementation are coordinated with the Human Resources Team.

#### Technical/Logistical Transition Sub-Team Duties

After the award has been made, this Technical/Logistics sub-team will:

- Establish operating procedures for conducting business during the transition period before the MEO is fully operational.

- Schedule/coordinate any required training for MEO and CGA employees.

- Determine workload and scheduling of personnel to meet workload demands.

- Ensure all performance standards and productivity is maintained throughout the transition phase.

- Coordinate the orderly disposition of any excess Government facilities, material or equipment that will not to be used by the MEO.

- Coordinate the transfer of accountable property between incumbent and new Hand Receipt Holders as required.

- Ensure any modifications and/or relocations are completed.

#### Training

The Phase-In Team Leaders are responsible for planning, executing and coordinating any training required for MEO employees and the Director.  During the phase-in of the MEO, the Technical/Logistical sub-team will review the MEO position descriptions and MEO staffing to decide which positions may need training.  Possible formal training courses MEO personnel might need to attend include:

- CBORD training.

- New employee NIH CC orientation.

- CC Nutrition Department orientation.

- Kitchen equipment training.

- Pneumatic tube training.

- Disability awareness training.

- Harassment training.

- Motorized pallet jack/tugger training.

- Protection of human research subjects training.

- EEO training.

- Diversity appreciation and communication training.

- Customer service training.

- Ergonomics (slips, trips, falls) training.

- Age specific competency training.

- Infection control training.

- Patient confidentiality and privacy training.

- Government ethics training.

- Computer security awareness training.

- Patient safety training.

- Fire safety training-area specific.

- Emergency procedures.

- Hazard communication training.

- Material safety data sheet/PPE training.

While formal training is important, informal training is in conjunction also a useful and cost effective manner to ensure personnel can complete their tasks within the performance standards defined in the RD.    TE-5001 provides a more comprehensive description of the government provided training.

#### Transfer of Accountable Property

The Phase-In Team lead shall designate an individual or individuals to act as Property Managers on the Technical/Logistical sub-team and assist in transitioning accountable property is required.  The Technical/Logistical sub-team will create a schedule for this transition of property and will verify that all property transfers are completed by the effective date of MEO implementation.

### Letter of Obligation

Pursuant to OMB Circular A-76, in the case of a Government Performance Decision, the Agency must execute a Letter of Obligation with an official responsible for the MEO performing the work in the RD.  The Circular specifies that the “Contracting Officer” have cognizance for this action.  Typically, “official responsible for performing the work” is the Agency Tender Official or the PO identified and placed by the Contracting Officer.

The Letter of Obligation is a formal agreement between the MEO and the agency regarding the performance of work studied and competed.  It advises the MEO of the government’s performance expectations and how that performance will be monitored.  It also makes the MEO aware of OMB Circular A-76, Attachment B, Section E, which clearly defines the Post Competition Accountability requirements that are applicable to the MEO and the ramifications pertaining thereto for failure to perform.  Execution of this agreement is a critical step in the final phase of MEO implementation.

### Timeline

An integrated Phase-In Timeline is presented in Technical Exhibit 5-001.  This timeline includes the major milestones necessary to transition to the MEO.  Specialized training of personnel, are independent and are shown only in their relationship to the overall timing.

## Utilities and Any Other Services And Costs To Be Transferred

Any changes with regard to the use of utilities, to include changing any accounts or payment requirements, or for any other cost transference, should be performed, as appropriate, in the event of the award being won by the MEO or a Private Service Provider.  In addition, the Phase-In Team shall:

- Ensure the timely reassignment of telephone numbers and LAN access to the MEO.

- Ensure the telephone number changes are incorporated in the next scheduled change to the NIH directory.

## Indicators Of Successful Transition

The following indicators will serve as measures of how well the current organization transitioned to the MEO:

- Was any initial disruption of the performance-based work output kept to a minimum and eliminated within a reasonable period of time?

- Has the installation of the MEO and their initiation of RD tasks been implemented on schedule?

- Is the MEO cost at or below the ACE?

- Customer Feedback:

- Has an initial, baseline customer satisfaction survey been conducted?

- Has an “after-MEO implementation” customer survey been conducted?

- Has customer satisfaction, at the end of the transition period, been maintained, degraded, or improved?

- Is the quality level of work at the acceptable quality level designated in the RD Quality and Timeliness Standards?

- Is the work output volume at the level designated in the RD (assuming customer demand is at those levels)?  Has an output surge capability been planned or demonstrated?

- Has the MEO been fully complied with?

- Technical Exhibit 5-001 Food Services Government –Provided Training

| Training | Frequency | Documentation | Schedule | Staff To Attend |
| --- | --- | --- | --- | --- |
| New Employee NIH CC Orientation - Patient Confidentiality - Ethics - Diversity Appreciation & Communication - Patient Safety - Emergency Procedures - Customer Service - Infection Control - Universal Precautions | Once | Check List | Start of Employment | All Service Provider Staff |
| Nutrition Department Orientation | Once | Check List | Start of Employment | Train the Trainer * (That one staff would then train the rest of the Service Provider Employees) |
| Kitchen Equipment Training | Once | Check List | Start of Employment | Train the Trainer (That one staff would then train the rest of the Service Provider Employees utilizing the equipment) |
| CBORD Training | Once | Competency Assessment | Start of Employment | Train the Trainer (That one staff would then train the rest of the Service Provider Employees utilizing CBORD) |
| Pneumatic Tube Training | Once | Sign Review Statement | Start of Employment | Train the Trainer (That one staff would then train the rest of the Service Provider Employees utilizing the tube system) |
| Disability Awareness Training | Once | Certificate | Start of Employment | All Service Provider Staff |
| Harassment Training | Once | Certificate | Start of Employment | All Service Provider Staff |
| Motorized Pallet Jack / Tugger Training | Once | Certificate | Start of Employment | All Service Provider Staff Working with the Pallet Jack and Tugger |
| EEO Training | Once | Certificate | Start of Employment | All Service Provider Staff |
| Diversity Appreciation and Communication Training | Every 3 Years | Certificate | Start of Employment – then every 3 years | All Service Provider Staff |
| Customer Service Training | Every 3 Years | Performance | Start of Employment – then every 3 years | All Service Provider Staff |
| Ergonomics (Slips, Trips, Falls) Training | Annual | Certificate | Once within the Calendar Year | All Service Provider Staff |
| Age Specific Competency Training | Annual | Certificate | Once within the Calendar Year | Designated Service Provider Staff |
| Infection Control Training | Annual | Certificate | Once within the Calendar Year | All Service Provider Staff |
| Patient Confidentiality and Privacy | Annual | Certificate | Once within the Calendar Year | All Service Provider Staff |
| Government Ethics Training | Annual | Certificate | Once within the Calendar Year | All Service Provider Staff |
| Computer Security Awareness Training | Annual | Certificate | Once within the Calendar Year | All Service Provider Staff |
| Patient Safety Training | Annual | Certificate | Once within the Calendar Year | All Service Provider Staff |
| Fire Safety Training – Area Specific | Annual | Certificate | Once within the Calendar Year | All Service Provider Staff |
| Emergency Procedures Training | Annual | Certificate | Once within the Calendar Year | All Service Provider Staff |
| Hazard Communications Training | Annual | Certificate | Once within the Calendar Year | All Service Provider Staff |
| Material Safety Data Sheet / PPE Training | Annual | Certificate | Once within the Calendar Year | Train the Trainer (That one staff would then train the rest of the Service Provider Employees working in the kitchen) |
| NIH Specific/metabolic Diets - Metabolic Kitchen | At start of the contract and when new diets or protocols take effect | Check List | As Needed | Train the Trainer (That one staff would then train the rest of the Service Provider Employees) |
| Clinical Research Information System (CRIS) – Clinical Center Training | Once | Check List | Start of Employment | All Service Provider Staff that utilize CRIS |
| Clinical Research Information System (CRIS) – Nutrition Specific Training | As Needed – when new diets take effect | Check List | Start of Employment; As Needed | Train the Trainer (That one staff would then train the rest of the Service Provider Employees utilizing CRIS) |
| Therapeutic Nutrition Specific to NIH diets and protocol diets | Once | Check List | Start of Employment | Train the trainer (That one staff would then train the rest of the Service Provider Employees) |

Train the Trainer Sessions – These are sessions in which one staff would attend the Government provided training and then return and train the appropriate staff.

NOTE:  Initial trainings will be provided by the Government; however, recurring training sessions shall be provided by the Service Provider.

- Technical Exhibit 5-002 Integrated Phase-In Timeline

| - Date | - Event |
| --- | --- |
| - D-Day | - Decision Day (D-Day) |
| - D-Day | - Establish the Phase-In Team and sub-teams |
| - D-Day | - Conduct Preliminary Phase-In Planning |
| - D-Day + 2 | - Notify Employees of performance decision |
| - D-Day + 2 | - Announce Decision via FedBizOpps |
| - D-Day + 3 | - Commence Transition Period |
| - D-Day + 3 | - Develop Letter of Obligation |
| - D-Day + 5 | - Review MEO and Analyze Impact (Management) |
| - D-Day + 9 | - Sign Letter of Obligation |
| - D-Day + 31 | - Begin Formal Phase-In of MEO/CGA |
| - D-Day + Performance Period | - Ensure all performance standards and productivity are maintained throughout transition phase |
| - D-Day + | - Begin training/re-training for Government MEO |
| - D-Day + | - Conduct/obtain training for QA positions in CGA |
| - D-Day + | - Conduct orientation/cross-training for IG/Retained Tasks |
| - D-Day + | - Implement QASP oversight by CGA |
| - D-Day + 50-60 | - Implement MEO |

# Agency Cost Estimate

While an integral part of the MEO, the Agency Cost Estimate is an entirely severable document that must be kept sealed until the time of the cost comparison.  It is therefore not embedded within the text of this document, but is referenced for continuity and completeness of the MEO documentation.

Attachments and Technical Exhibits

Department Chief

Program Support Asst.

Administrative Asst.

Administrative Officer

Production Dietician

Dietician Internship Director

Metabolic Kitchen

Supervisory Metabolic Dietician

Metabolic Dietician

Food Services, Chief

Clinical Nutrition Services

Chief

Current

ATTACHMENT 1

Current