| World Trade Organization |  |
| --- | --- |
|  | WT/COMTD/AFT/W/6 16 June 2008 |
|  | (08-2815) |
| Committee on Trade and Development Aid for Trade |  |

2008 Aid-for-Trade Roadmap

Objectives:

- Increase developing country ownership of Aid for Trade.

- Shift emphasis to monitoring implementation - with a focus on country, regional and sectoral priorities.

- Launch work programme to develop performance indicators and to strengthen self evaluations.

Strategy:

Global Monitoring

- Assess results of the first year of monitoring.

- Update donor and (especially) partner-country questionnaires.

- Explore ways of increasing partner-country involvement (including by streamlining surveys and improving incentives).

- Examine how TPRs could be further adapted to Aid-for-Trade monitoring, building on existing work.

- Identify a cluster of indicators to benchmark progress in building trade capacity.

- Hold an Expert Symposium on Evaluation.

- Work with the OECD to implement an Aid-for-Trade "knowledge network" – i.e., using information technologies to establish contact points, highlight activities, share best practices, etc.

National and Sub-regional Reviews

- Take the initiative to the "next level" by holding a series of selected National and Sub-Regional Aid-for-Trade Reviews in Africa, Latin America and the Caribbean, and Asia and the Pacific.  These Reviews would be focused, technical, and results-oriented, with the aim of assisting in advancing – and then monitoring – the implementation of concrete national and sub-regional strategies. The broad objective would be to showcase how Aid-for-Trade strategies can progress – and are progressing – and to create incentives for others to follow suit.

- Work with countries, donors, regional banks, and other key stakeholders to identify ready and eligible "first generation" Review candidates (e.g., having an Aid-for-Trade plan, coordinating structure, completed needs assessments, identified priorities, etc.).

- Convene national and sub-regional reviews – co-hosted by the participating national government and/or REC together with the Regional Aid-for-Trade Support Network (as recommended by the regional reviews) – with the aim of:

  - assessing and improving national/regional plans (and coordinating structures)

  - identifying binding constraints and key priorities

  - agreeing on the roadmap for implementation (including timetables, institutional mandates, and financial requirements).

- Use OECD/WTO self-assessments as "living documents" to develop actionable plans, monitor progress, and encourage mutual accountability.

- Report on progress to periodic meetings of the CTD.

- Profile results at the next Global Review – to monitor progress and encourage "peer" review and incentives.

Regional Aid for Trade Networks

- Encourage early establishment of Regional Aid-for-Trade Networks – comprised of key stakeholders (RDBs, OECD, World Bank, UN economic commissions, WTO, lead donors, etc.) – as recommended by last year's regional reviews, to assist countries and sub-regions in identifying priorities, drawing up plans and mobilizing resources.

Global Review

- Hold next Global Review in Spring/Summer 2009 to provide political guidance, momentum and the "big picture" on implementation and evaluation.

Committee for Trade and Development

- Consult the CTD in the development and implementation of the 2008 roadmap.  Report regularly on progress and results.

__________

As approved by Members at the Committee on Trade and Development meeting of 25 February 2008.