## Weekly Update
No. | Weekly Update Report Data (sheet 1 of 2) Version 1.0
| Agency Name: | Department of the Interior
| Week Start Date: | 2009-02-23
| Submitter Name: | Mary Pletcher
| Submitter Contact Info: | 202-208-6851/mary_pletcher@ios.doi.gov
| Program Source/ Treasury Account Symbol: Agency Code | Program Source/Treasury Account Symbol: Account Code | Program Source/Treasury Account Symbol; Sub-Account Code (OPTIONAL) | Total Appropriation | Total Obligations | Total Disbursements
1 | 14 | 1108 |  | 125000000 | 0
2 | 14 | 1112 |  | 180000000 | 0
3 | 14 | 681 |  | 1000000000 | 0
4 | 14 | 803 |  | 140000000 | 0
5 | 14 | 1610 |  | 165000000 | 0
6 | 14 | 1613 |  | 115000000 | 0
7 | 14 | 1035 |  | 146000000 | 0
8 | 14 | 5541 |  | 15000000 | 0
9 | 14 | 1041 |  | 589000000 | 0
10 | 14 | 2101 |  | 40000000 | 0
11 | 14 | 2302 |  | 450000000 | 0
12 | 14 | 2629 |  | 10000000 | 0
13 | 14 | 101 |  | 15000000 | 0
14 | 14 | 1126 |  | 15000000 | 0
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98

## Major Activities
Weekly Update Report Data (sheet 2 of 2)
No. | Short bulleted list of the major actions taken to date | Short bulleted list of the major planned actions
1 | Secretary issued press release and held press conference. | DOI Recovery Lead, Chris Henderson, will be in place.
2 | Established link to recovery.gov from DOI web site. | Finalize apportionment of recovery funds.
3 | Stood up a DOI recovery webpage. | Bureaus to complete development of initial project lists.
4 | Requested apportionment of recovery funds from OMB. | Secretary to conduct reviews of initial project lists.
5 | Established internal DOI reporting portal on OMB MAX site. | Perform detailed reviews of initial project lists.
6 | Established Recovery Governance Board. | Continue Workgroup efforts to develop DOI policy, procedures and guidance on Recovery Act implementation.
7 | Established Recovery Task Force (TF) (TF reports to Board) | Continue development of General Agency Plan.
8 | Issued initial project identification and selection guidance. | Complete initial acquisition strategy.
9 | Secretary met with each bureau to review implementation strategies. | Complete draft risk management plan.
10 | Met with OMB regarding use of Section 638 contracts. | Submit first weekly update report.
11 | Started development of General Agency Plan required to Congress on March 18 for the Interior, Environment and Related Agencies Programs.
12 | Established 8 Task Force Workgroups (Reporting, Performance, Communications, Project Approval, Administration, Risk Management, Youth Outreach, and Acquisition Strategy)
13 | Established Bureau-level oversight boards.
14 | Indian Affairs met with interested Tribal representatives to discuss the ARRA and its implications.
15 | Indian Affairs met with Navajo Nation Department of Education to plan execution of education construction projects.
16 | Indian Affairs sent consultation letters to tribes with projects that may be included in the Construction program.
17 | Indian Affairs met with Department of Justice to discuss coordinated approach to addressing Detention Center program and projects.
18
19
20
21
22
23
24
25
26
27
28
29