## Weekly Update
No. | Weekly Update Report Data (sheet 1 of 2) Version 1.1
| Agency Name: | Social Security Administration
| Week End Date: | 2009-03-13
| Submitter Name: | Mark Silvestri
| Submitter Contact Info: | 410-965-0017 Mark.silvestri@ssa.gov
| Program Source/ Treasury Account Symbol: Agency Code | Program Source/Treasury Account Symbol: Account Code | Program Source/Treasury Account Symbol; Sub-Account Code (OPTIONAL) | Program Description (Account Title) | Total Appropriation | Total Obligations | Total Disbursements
1 | 28 | 418 | 09/11 | Economic Recovery Payments (ERP)-Recovery Act | 13250000000 | 0
2 | 28 | 417 | 09/11 | Administrative Expenses - Recovery Act/ERP | 90000000 | 1760610 | 1760610
3 | 28 | 417 | X | Administrative Expenses - Recovery Act/NSC | 500000000 | 0
4 | 28 | 417 | 09/10 | Administrative Expenses - Recovery Act/Workloads | 500000000 | 0
5 | 28 | 403 | 09/12 | Office of the Inspector General - Recovery Act | 2000000 | 4269 | 4269
6 | 28 | 400 | 2009 | OIG Annual Appropriation | 98127000 | 9151 | 9151
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98

## Major Activities
Weekly Update Report Data (sheet 2 of 2)
No. | Short bulleted list of the major actions taken to date | Short bulleted list of the major planned actions
1 | General Recovery Act Implementation | General Recovery Act Implementation
2 | Responded to OMB on BDR 09-12, Discretionary Outlay Rates and Mandatory Estimates for ARRA. | Working with OMB to interpret Recovery Act implementation guidance.
3 | Responded to OMB on BDR 09-11, Inventory of ARRA TAFSs. | Working with GSA to develop a template for contract reporting on web page.
4 | Met with Office of the Inspector General on how they intend to conduct audits and evaluations of our awarding, disbursing, and monitoring of ARRA funds to determine whether safeguards exist for funds to be used for their intended purpose. | Setting up RSS feed from the SSA.gov/recovery page. Waiting for OMB/GSA additional guidance on establishing Atom 1.0 feeds.
5 | Combined SSA reports with Office of the Inspector General weekly reports. | Developing Agency and Program draft plans due to OMB April 10.
6 | Reported to OMB that SSA does not have any systems that will collect information from ARRA recipients.
7
8
9
10
11 | One-Time Economic Recovery Payments (ERP) | One-Time Economic Recovery Payments (ERP)
12 | Awarded a printing contracts for the ERP advance informational mailer. | Preparing One-Time ERP leaflets in both Spanish and English for field offices.
13 | Provided test files to vendors for printing. | Developing an interagency testing schedule with Treasury for payments
14 | Received Catalog of Federal Domestic Assistance number from GSA. | Sending an advance informational mailer in late April to those who will receive the one-time ERP
15 |  | Preparing required systems lifecycle documents for software design and development.
16
17
18
19 | Replace the National Computer Center (NCC) | Replace the National Computer Center (NCC)
20 |  | Meeting regularly with GSA to define roles in the reporting process.
21 |  | Working with GSA to establish general project timeline with key milestones and target dates.
22 |  | Working with GSA reviewing proposals from three potential construction management firms (from GSA’s existing term contract schedule) to develop the program of requirements. The GSA/SSA source selection board is meeting and GSA anticipates an award date in ealry April.
23
24 | Additional Disability and Retirement Workloads | Additional Disability and Retirement Workloads
25 | Distributed overtime workyears. | Gearing up to hire additional staff starting April 1.
26 | Distributed hiring authority. | Working with States for hiring exemptions on State Disability Determination Services hires.
Planning to post job announcements competitively through OPM's USAJOBS website starting March 2009. Posted disability positions are primarily for case technicians, decision writers and some clerical positions. Posted regional positions are primarily front line positions, teleservice operations and processing centers. All positions are geographically disbursed throughout the United States.
Established coding for new hires to identify them as ARRA hires for tracking purposes.
| Office of the Inspector General | Office of the Inspector General
Met with the Government Accountability Office (GAO) to discuss Recovery Act oversight. The meeting was held to ensure no duplication of effort when performing oversight of Recovery Act funds.
27 | Held entrance conference with SSA senior management to discuss how OIG will provide oversight of Agency awarding, disbursing, and monitoring of Recovery Act funds to determine whether safeguards exist for funds to be used for intended purposes. The OIG will issue separate notices when it begins each specific review to inform SSA of the objective of each review.
28 | Held entrance conference with SSA management and staff to discuss OIG oversight of review of SSA's controls and procedures for administering the $250 one-time payments to eligible Social Security and Supplemental Security Income recipients.
29 | Participated in a teleconference with Office of Management and Budget representatives to clarify OIG's reporting requirements under the Recovery Act.