## Weekly Update
No. | Weekly Update Report Data (sheet 1 of 2) Version 1.1
| Agency Name: | National Science Foundation
| Week End Date: | 2009-03-27
| Submitter Name: | Dr. Marrett
| Submitter Contact Info: | 703-292-8001
| Program Source/ Treasury Account Symbol: Agency Code | Program Source/Treasury Account Symbol: Account Code | Program Source/Treasury Account Symbol; Sub-Account Code (OPTIONAL) | Program Description (Account Title) | Total Appropriation | Total Obligations | Total Disbursements
1 | 49 | 101 |  | Research and Related Activities | 2500000000 | 0 | 0
2 | 49 | 107 |  | Education and Human Resources | 100000000 | 0 | 0
3 | 49 | 552 |  | Major Research and Equipment and Facilities Construction | 400000000 | 0 | 0
4 | 49 | 301 |  | Office of the Inspector General | 2000000 | 0 | 0
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98

## Major Activities
Weekly Update Report Data (sheet 2 of 2)
No. | Short bulleted list of the major actions taken to date | Short bulleted list of the major planned actions
1 | Feb. 13th: Dr. Cora B. Marrett has been designated as NSF’s Senior Accountable Official for American Recovery and Reinvestment Act of 2009. | NSF is preparing a Current Plan to send to Congressional Appropriators as required by the Act.
2 | Feb 20th: Unique Treasury appropriation fund symbols (TAFS) have been established to distinguish Recovery Act spending from other spending. | NSF is working to ensure all stimulus funds are separate from non-Recovery Act funds in financial, grant writing, contract writing, and reporting systems.
3 | Feb. 20th: NSF submitted apportionment requests totaling $3 Billion to OMB on Friday | NSF is identifying opportunities to streamline data collection and help alleviate the reporting burden on recipients of Recovery Act funds.
4 | Feb. 24th: NSF agrees that it will not be necessary to enter into interagency agreements in order to execute the terms of the Recovery Act.
5 | Feb. 25th: NSF’s Recovery Act Home page has been created at http://nsf.gov/recovery/
6 | Mar. 16th: NSF received CFDA number for Recovery Act Funding
7 | March 18: NSF issued Important Notice 131 to presidents of universities and colleges and heads of other NSF awardee organizations to communicate key elements of NSF's implementation of the Recovery Act.
8 | March 18: Dr. Arden L. Bement and Dr. Cora B. Marrett issued a staff memorandum to communicate the key elements of NSF's implementation of the Recovery Act and to transmit NSF's policies and procedures document for implementing the Recovery Act.
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29