## Weekly Update
Weekly Update Report Data (sheet 1 of 2) Version 1.1
Agency Name: | Transportation
Week End Date: | 2009-03-07
Submitter Name: | Lana Hurdle
Submitter Contact Info: | 202-366-9191
Program Source/ Treasury Account Symbol: Agency Code | Program Source/Treasury Account Symbol: Account Code | Program Source/Treasury Account Symbol; Sub-Account Code (OPTIONAL) | Program Description (Account Title) | Total Appropriation | Total Obligations | Total Disbursements
69 | 0106 | 2009/2011 | Supp Disc Grants for Natl Surface Transport System, Recovery Act | 1500000000 | 0 | 0
69 | 0131 | 2009/2013 | Salaries and Expenses, Recovery Act | 20000000 | 0 | 0
69 | 0504 | 2009/2010 | Highway Infrastructure Investment, Recovery Act | 27460000000 | 364546243.05 | 0
69 | 0504 | 2009/2012 | Highway Infrastructure Investment, Recovery Act | 40000000 | 0 | 0
69 | 0718 | 2009/2012 | Capital Assistance for High Speed Rail Corridors, Recovery Act | 7980000000 | 0 | 0
69 | 0718 | 2009/2014 | Capital Assistance for High Speed Rail Corridors, Recovery Act | 20000000 | 0 | 0
69 | 0724 | 2009/2010 | Capital Grants to the National Railroad Passenger Corporation, Recovery Act | 1295000000 | 0 | 0
69 | 0724 | 2009/2013 | Capital Grants to the National Railroad Passenger Corporation, Recovery Act | 5000000 | 0 | 0
69 | 1101 | 2009/2010 | Transit Capital Assistance, Recovery Act | 6850700000 | 0 | 0
69 | 1101 | 2009/2012 | Transit Capital Assistance, Recovery Act | 49300000 | 0 | 0
69 | 1102 | 2009/2010 | Fixed Guideway Infrastructure Investment, Recovery Act | 742500000 | 0 | 0
69 | 1102 | 2009/2012 | Fixed Guideway Infrastructure Investment, Recovery Act | 7500000 | 0 | 0
69 | 1133 | 2009/2010 | Capital Investment Grants, Recovery Act | 742500000 | 0 | 0
69 | 1133 | 2009/2012 | Capital Investment Grants, Recovery Act | 7500000 | 0 | 0
69 | 1304 | 2009/2010 | Facilities and Equipment, Recovery Act | 200000000 | 0 | 0
69 | 1306 | 2009/2010 | Grants-in-aid for Airports, Recovery Act | 1100000000 | 0 | 0
69 | 1749 | 2009/2010 | Operations and Training, Recovery Act | 2000000 | 0 | 0
69 | 1771 | 2009/2010 | Assistance to Small Shipyards, Recovery Act | 98000000 | 0 | 0

## Major Activities
Weekly Update Report Data (sheet 2 of 2)
No. | Short bulleted list of the major actions taken to date | Short bulleted list of the major planned actions
1 | In total, $34.1 billion of Transportation’s $48.1 billion in ARRA funds were released to the states only two weeks after the President signed the ARRA. | During the week of March 9th, DOT will continue to conduct public outreach sessions.
2 | On March 3, the Federal Aviation Administration (FAA) issued final implementation guidance to FAA Field staff and external customers. FAA has posted guidance and FAQs on FAA website with links to DOT Recovery site and Recovery.gov. | The week of March 9th, DOT plans to draft guidance on reporting direct and indirect jobs and job-years pursuant to ARRA section 1201.
3 | On March 5, FAA conducted the first of several public outreach sessions on grants funded under the Airport Improvement Program. | In early March, the Airport Improvement Grant (AIP) program office plans to announce first allocation of funding.
4 | FAA has completed the site list for the following Facilities & Equipment (F&E) projects: power systems (70 sites), air traffic control tower/terminal radar (3 new towers in Wilkes-Barre, PA; Palm Springs, CA; and Oakland, CA). In addition, 18 air route traffic control centers are being modernized and 670 sites will receive improvements to their navigation/landing facilities. | By March 13th, MARAD to complete development of FAQs for Small Shipyard Grant Program that will be posted at www.dot.gov/recovery.
5 | On March 3rd, DOT provided comments to OMB on draft Guidance on jobs reporting, noting need to account for special requirements of ARRA section 1201. | The week of March 9th FHWA will allocate the remaining $0.9 billion in funding to other programs.
6 | DOT has completed development of a system to provide unprecedented tracking capability for recommendations made by OIG/GAO relating to DOT action on ARRA. System includes a Management Dashboard on DOT's internal Transportation Investment Generating Economic Recovery (TIGER) web site. | By the end of March, FHWA will finalize risk management plan for implementation and oversight of ARRA projects and funding.
7 | DOT is participating in the Government-wide Grants Executive Board meetings to discuss alternatives to Grants.gov for processing grants under the Recovery Act. | On March 9th, Secretary LaHood will address attendees at the American Public Transportation Association (APTA) Legislative Conference in Washington, DC. His remarks will be focused on the American Recovery and Reinvestment Act (ARRA).
8 | On March 2nd, the Federal Highway Administration (FHWA) met the 21 day requirement by issuing apportionments totaling $26.6 billion to states - 8 days earlier than required by law. | FTA will publish grant application guidance for transit program recipients the week of March 9th.
9 | DOT developed a help-desk email for procurement and financial assistance questions that will be posted on the DOT Recovery web-site. | FTA will publish Federal Register Notice in March soliciting applicants for the New Starts, Tribal Transit and Transit Greenhouse Gas and Energy Reduction programs.
10 | FHWA provided extensive guidance on certification requirements and has received section 1511 certifications from 31 states. | FTA will send to the Federal Register a notice on Capital Investment Grants for publication immediately upon OST/OMB concurrence of allocations.
11 | As of March 5th, FHWA has authorized projects in 11 states totaling $365 million in obligations. Construction began on the first recovery-act funded project, the resurfacing of a 1.1 mile stretch of Route 650 in Montgomery County, Maryland. | Amtrak capital grant agreement will be executed on March 13th at an event at Union Station.
12 | On March 5th FHWA circulated to OST and OMB for review and clearance draft guidance to grant recipients for reporting monthly on the status of projects and on employment generated. | By March 13th, FRA to finalize draft of selection criteria for high-speed rail and intercity passenger rail grant programs.
13 | On March 4th, FHWA distributed a memo to division offices to identify risks associated with delivering the ARRA in each state and to develop a plan for managing those risks. | By March 20th, FRA to conduct outreach to freight railroads for high-speed rail grant programs.
14 | On March 5, 2009 the Federal Transit Administration (FTA) published the Federal Register Notice with final public transportation allocations and grant program information apportionments to urbanized and non-urban areas and states.
15 | On March 5, 2009 Vice President Joe Biden joined Secretary LaHood and local elected officials at Miami International Airport for a tour of the Miami Intermodal Center (MIC). Remarks during the event focused on how President Obama's economic recovery package will impact transportation projects.
16 | On March 3rd, FRA held a kickoff meeting with Amtrak to review Amtrak's list of projects for the $850 million of capital grant funding for non-security related projects.
17 | On March 5th, MARAD posted the Small Shipyard Grants notice on Grants.gov.
18 | On March 5th, FRA developed implementation plan for high-speed rail and intercity passenger rail grant programs and posted to FRA website.
19 | The week of March 2nd, FRA reviewed proposals for program management support for high-speed rail and intercity passenger rail grant programs.
20
21
22
23
24
25
26
27
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101