## Weekly Update
No. | Weekly Update Report Data (sheet 1 of 2) Version 1.1
| Agency Name: | Transportation
| Week End Date: | 2009-03-20
| Submitter Name: | Lana Hurdle
| Submitter Contact Info: | 202-366-9191
| Program Source/ Treasury Account Symbol: Agency Code | Program Source/Treasury Account Symbol: Account Code | Program Source/Treasury Account Symbol; Sub-Account Code (OPTIONAL) | Program Description (Account Title) | Total Appropriation | Total Obligations | Total Disbursements
1 | 69 | 0106 | 2009/2011 | Supp Disc Grants for Natl Surface Transport System, Recovery Act | 1500000000 | 0 | 0
2 | 69 | 0131 | 2009/2013 | Salaries and Expenses, Recovery Act | 20000000 | 0 | 0
3 | 69 | 0504 | 2009/2010 | Highway Infrastructure Investment, Recovery Act | 27460000000 | 2385848452.39 | 1630907.07
4 | 69 | 0504 | 2009/2012 | Highway Infrastructure Investment, Recovery Act | 40000000 | 11609.49 | 1174.9
5 | 69 | 0718 | 2009/2012 | Capital Assistance for High Speed Rail Corridors, Recovery Act | 7980000000 | 0 | 0
6 | 69 | 0718 | 2009/2014 | Capital Assistance for High Speed Rail Corridors, Recovery Act | 20000000 | 0 | 0
7 | 69 | 0724 | 2009/2010 | Capital Grants to the National Railroad Passenger Corporation, Recovery Act | 1295000000 | 1288536000 | 0
8 | 69 | 0724 | 2009/2013 | Capital Grants to the National Railroad Passenger Corporation, Recovery Act | 5000000 | 5000000 | 0
9 | 69 | 1101 | 2009/2010 | Transit Capital Assistance, Recovery Act | 6850700000 | 41194697 | 0
10 | 69 | 1101 | 2009/2012 | Transit Capital Assistance, Recovery Act | 49300000 | 0 | 0
11 | 69 | 1102 | 2009/2010 | Fixed Guideway Infrastructure Investment, Recovery Act | 742500000 | 0 | 0
12 | 69 | 1102 | 2009/2012 | Fixed Guideway Infrastructure Investment, Recovery Act | 7500000 | 0 | 0
13 | 69 | 1133 | 2009/2010 | Capital Investment Grants, Recovery Act | 742500000 | 0 | 0
14 | 69 | 1133 | 2009/2012 | Capital Investment Grants, Recovery Act | 7500000 | 0 | 0
15 | 69 | 1304 | 2009/2010 | Facilities and Equipment, Recovery Act | 200000000 | 0 | 0
16 | 69 | 1306 | 2009/2010 | Grants-in-aid for Airports, Recovery Act | 1100000000 | 0 | 0
17 | 69 | 1749 | 2009/2010 | Operations and Training, Recovery Act | 2000000 | 0 | 0
18 | 69 | 1771 | 2009/2010 | Assistance to Small Shipyards, Recovery Act | 98000000 | 0 | 0
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98

## Major Activities
Weekly Update Report Data (sheet 2 of 2) | Weekly Update Report Data (sheet 2 of 2)
| Short bulleted list of the major actions taken to date | Short bulleted list of the major planned actions
| On March 19th, FRA executed the Grant Agreement with Amtrak. Amtrak has now obligated $1.3 billion and approved projects totaling more than $938 million. | FRA will continue to work on strategic plan for high-speed rail.
| On March 13th, FRA selected a program management support contractor for high-speed rail and intercity passenger rail grant programs, and began work. | FAA will continue to work closely with proposed grant recipients to ensure their solicitations for airport construction bids are made in timely manner so that FAA can meet the June 17 deadline to award 50 percent of the total airport grant funding.
| As of March 19, FAA has identified $913 million worth of specific Recovery Act airport projects (83 percent of the total funding). Of that amount, $618 million has been forwarded to the Department, and $181 million has been through Congressional notification. After the three-day Congressional notification period, the Department can announce tentative funding of the projects, at which point airport sponsors will be able to solicit bids for construction. Sponsors will then submit their grant applications to FAA based on the bids received. | FAA anticipates contract award to engineering firm for 18 modernization projects at en route air traffic control facilities will be made in the near future.
| On March 18th, FAA conducted a public outreach session with 400 attendees at the FAA Airports Northwest Mountain Annual conference in Seattle, WA. | On March 25th, Secretary LaHood will address the FAA International Aviation Forum in Washington DC on the ARRA.
| The Federal Transit Administration (FTA) has awarded three grants totaling $41.2 million dollars for public transportation capital needs in rural areas of Kentucky, Missouri and Maine. The Kentucky grant will be used to purchase 206 vehicles including trolleys, intercity buses and vans; 48 bus passenger shelters; and other miscellaneous capital items. The Missouri DOT will use their grant to purchase approximately 319 vehicles (including modified vans, minivans and minibuses). The Maine DOT will use their grant to construct a new passenger ferry. | FTA will soon finalize its ARRA risk management plan to ensure the effective and efficient use of transit-related funds
| FTA has an additional 23 grants (totaling $189 million) that have been sent to Department of Labor certification and are pending. The pending grants will fund public projects in urbanized areas; such as rail improvements and the purchase of new clean-fuel buses. | FTA is beginning to prepare for events related to the allocation of New Starts/Small Starts funding that will occur in the near future.
| FTA submitted notices soliciting proposals for two ARRA competitive programs: Energy Reduction Savings Program and Tribal Transit Program to the Federal Register for publication. | Week of March 23rd, FHWA will allocate Refuge Road funds for repairing Fish and Wildlife Service roads.
| On March 19th, Secretary LaHood joined Vice President Biden, and Senator Klobuchar (D-MN) in the Middle Class Task Force (MCTF) town hall meeting at the New Flyer Bus Company in St. Cloud, Minnesota. The event showcased how ARRA’s transit investment can sustain and maintain jobs for middle class families. | FHWA will finalize risk management plan for implementation and oversight of ARRA projects and funding
| As of Friday, March 20th, FHWA had obligated $2.4 billion in highway projects. By Monday, March 23rd, a total of $2.9 billion had been obligated in 33 states on nearly 800 projects. | The week of March 30th, Office of Federal Lands Highway to host ARRA reporting requirements presentation with representatives from National Park Service, Fish and Wildlife Service, Forest Service, Bureau of Land Management, and Department of Defense
| FHWA issued reporting guidance to States, and conducted presentation on ARRA requirements at National League of Cities Conference, and hosted ARRA implementation webcast for local agencies attended by over 400 people. | In early April FHWA will initiate allocation of Indian Reservation Road funds and Park Road and Parkway funds.
| FHWA staff met with White House ARRA Implementation Workgroup for Indian Tribes | DOT’s Accountability Executive Board is working with the Office of Inspector General’s (OIG) on their report titled, “American Recovery and Reinvestment Act of 2009: Oversight Challenges Facing the Department of Transportation. The report focuses on 10 challenges within 3 overall categories - grantee oversight, ARRA accountability requirements, and combating fraud waste and abuse.
| FHWA sent letters to CEOs of State DOTs regarding increased oversight by FHWA and the States of ARRA projects | OST is finalizing guidance and criteria for $1.5 billion OST discretionary grant program.
| DOT has received the majority of the 1201 certifications from the States and are reviewing them to ensure they are complete. | OST is finalizing plan with the Small Business Administration to develop a joint Disadvantaged Business Enterprise bonding assistance program and obtain the Secretary’s approval.
| DOT has established a Grants Executive Board that is focused on risk management for both Recovery Act financial assistance instruments and other DOT financial assistance instruments. | Continue planning for the Secretary's April 14th Recovery Tour.
| DOT's Accounting Staff consulted with other Federal agencies on ways to minimize risk and based on these consultations developed risk template. OMB has included this template in the government wide guidance on ARRA. DOT has distributed the risk template to Operating Administrations for them to complete in the next 2 weeks. | The week of March 25th, MARAD expects to submit a Notice to the Federal Register providing guidance to Small Shipyard applicants to expedite the agency's NEPA analysis.
DOT will review completed risk templates and conduct training on risk management with goal to develop a gap analysis to identify internal control weaknesses for all Operating Administrations.