## Weekly Update
No. | Weekly Update Report Data (sheet 1 of 2) Version 1.0
| Agency Name: | Department of Homeland Security
| Week Start Date: | 2009-03-03
| Submitter Name: | Brian DeVallance
| Submitter Contact Info: | brian.devallance@dhs.gov 202-447-3971
| Program Source/ Treasury Account Symbol: Agency Code | Program Source/Treasury Account Symbol: Account Code | Program Source/Treasury Account Symbol; Sub-Account Code (OPTIONAL) | Total Appropriation | Total Obligations | Total Disbursements
1 | 70 | 118 |  | 200000000 | 0 | 0
2 | 70 | 201 |  | 5000000 | 0 | 0
3 | 70 | 534 |  | 160000000 | 0 | 0
4 | 70 | 536 |  | 100000000 | 0 | 0
5 | 70 | 535 |  | 420000000 | 0 | 0
6 | 70 | 546 |  | 20000000 | 0 | 0
7 | 70 | 556 |  | 1000000000 | 0 | 0
8 | 70 | 617 |  | 98000000 | 0 | 0
9 | 70 | 618 |  | 142000000 | 0 | 0
10 | 70 | 563 |  | 300000000 | 0 | 0
11 | 70 | 567 |  | 210000000 | 0 | 0
12 | 70 | 708 |  | 100000000 | 0 | 0
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98

## Major Activities
Weekly Update Report Data (sheet 2 of 2)
No. | Short bulleted list of the major actions taken to date | Short bulleted list of the major planned actions
1 | All DHS funds are apportioned. | TSA - Negotiate with airports on OTAs after spend plan is approved.
2 | TSA - Hiring plans are in place. | OIG - Will assess DHS components implementation/exp plans
3 | USCG: | ICE - Anticipate award of contracts July/August 2009
4 | - Completion of the Mobile Bridge Const project bid package | FEMA:
5 | - Planning documentation and outlay projections completed on | - Will issue grant guidance June/July 2009
6 | 7 of 8 shore infrastructure projects | - Receipt and review of grant applications July/August 2009
7 | - Analysis, planning, and preliminary engineering design | - Grants will be awarded September/December 2009
8 | documentation completed on vessel projects. | - Emergency Food & Shelter:
9 |  | - Complete Congressional notifications of award 3/31/09
10 |  | - Issue funding document to National Board 3/31/09
11 |  | USCG:
12 |  | - Bid solicitation advertisements for the Mobile Bridge and
13 |  | Elgin, Joliet, and Eastern Railway Co. Bridge project.
14 |  | - Continue planning documentation for final shore
15 |  | infrastructure project.
16 |  | - Continue engineering design documentation for vessel projects.
17 |  | CBP:
18 |  | - Ports of Entry - Plans to issue Request for Proposal (RFP)
19 |  | by 5/30/09 and award project by 8/17/09.
20 |  | - SBInet - Initiate procurement and deployment of near-term
21 |  | existing technology, June/July 2009.
22 |  | - Non-intrusive inspection systems - Estimated contract
23 |  | award 5/29/2009.
24 |  | USM:
25 |  | - Will transfer funds to GSA via reimbursable agreement in
26 |  | the third quarter 2009.
27
28
29