## Weekly Update
No. | Weekly Update Report Data (sheet 1 of 2) Version 1.1
| Agency Name: | Department of Homeland Security
| Week End Date: | 2009-03-20
| Submitter Name: | Brian DeVallance
| Submitter Contact Info: | brian.devallance@dhs.gov 202-447-3971
| Program Source/ Treasury Account Symbol: Agency Code | Program Source/Treasury Account Symbol: Account Code | Program Source/Treasury Account Symbol; Sub-Account Code (OPTIONAL) | Program Description (Account Title) | Total Appropriation | Total Obligations | Total Disbursements
1 | 70 | 118 |  | Office of the Under Secretary for Management, Recovery Act | 200000000
2 | 70 | 201 |  | Operating Expenses, Recovery Act | 5000000
3 | 70 | 534 |  | Salaries and Expenses, Customs and Border Protection, Recovery Act | 160000000
4 | 70 | 536 |  | Border Security Fencing, Infrastructure and Technology, Recovery Act | 100000000
5 | 70 | 535 |  | Construction, Customs and Border Protection, Recovery Act | 420000000 | 2325000
6 | 70 | 546 |  | Automation Modernizaton, Immigration and Customs Enforcement, Recovery Act | 20000000
7 | 70 | 556 |  | Aviation Security, Recovery Act | 1000000000
8 | 70 | 617 |  | Acquisition, Construction, and Improvements, Recovery Act | 98000000
9 | 70 | 618 |  | Alteration of Bridges, Recovery Act | 142000000
10 | 70 | 563 |  | State and Local Programs, Recovery Act | 300000000
11 | 70 | 567 |  | Firefighter Assistance Grants, Recovery Act | 210000000
12 | 70 | 708 |  | Emergency Food and Shelter, Recovery Act | 100000000
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98

## Major Activities
Weekly Update Report Data (sheet 2 of 2)
No. | Short bulleted list of the major actions taken to date | Short bulleted list of the major planned actions
1 | All DHS funds are apportioned. | TSA - Negotiate with airports on OTAs after spend plan is approved.
2 | TSA: | ICE - Develop a project plan.
| - Hiring Plans are in place. | ICE - Continue development of procurement packages for P25 Upgrade.
3 | - Press release issued with TSA checked baggage screening projects listed. | FEMA:
4 | - Issued conditional letters to airports indicating project consideration. | - Will issue grant guidance June/July 2009
5 | - Submitted spend plan for DHS review on 3/13/09. | - Receipt and review of grant applications July/August 2009
6 | USCG: | - Grants will be awarded September/December 2009
7 | - Bid Documents of Mobile Bridge and EJ&E Bridge are completed | - Emergency Food & Shelter:
8 | - Planning documentation and outlay projections completed on | - Complete Congressional notifications of award March 27, 2009
9 | 7 of 8 shore infrastructure projects | - Award funds to the National Board of the Emergency Food and
10 | - Analysis, planning, and preliminary engineering design | Program March 31, 2009.
11 | documentation completed on vessel projects. | USCG:
12 | CBP: | - Bid solicitation advertisements for the Mobile Bridge and
13 | - Funding has been allocated to the program offices. | Elgin, Joliet, and Eastern Railway Co. Bridge project.
14 | - Tactical Communications - obtained Border Patrol, Air & Marine, and Field Operation's | - Continue planning documentation for final shore
15 | concurrence of ARRA Spend Plan in support of Land Mobile Radio (LMR) Modernization projects. | infrastructure project.
16 | USM - Submitted expenditure plan to GSA for review | - Continue engineering design documentation for vessel projects.
17 | ICE: | CBP:
18 | - Submitted expenditure plan to DHS on 03/17/09. | - Ports of Entry - Plans to issue multiple Request for Proposal (RFP)
19 | - Collecting operations requirements and user needs for Boston and Denver Regions | by 6/25/09 for multiple design/build project contract award by 8/16/09.
20 | - Identifying the number of repeaters required for P25 upgrades in the Boston and Denver Regions. | - SBInet - Initiate procurement and deployment of near-term
21 | - Identifying the site survey, design, staging, installation, testing, and optimization services ICE requires. | existing technology, June/July 2009.
22 | - Identifying the services, support, and equipment required. | - Non-intrusive inspection (NII) systems - Estimated contract
23 | - Identifying labor resources required to develop the procurement packages. | award 5/29/2009 for the first of approx. 5 or 6 awards. All awards
24 | OIG: | should be completed in the 4th quarter of FY 09.
25 | - Notified components of spending plan audits. | - Tactical Communications - Estimated contract award July 2009;
26 | - Drafted advisory report based on previous audit work identifying risks the Department should address | Initiate procurement & conduct radio site construction activities.
27 | in its Agency Recovery Plan and open recommendations for which implementation should be | Scheduled to meet with the CBP Executive Steering Committee on
| in its Agency Recovery Plan and open recommendations for which implementation should be | April 7th to review and discuss ARRA spend plans.
28 | expedited to achieve Recovery Act goals. | USM:
- Will transfer funds to GSA via reimbursable agreement in
the third quarter 2009.
OIG:
- Determine if components have developed practical and comprehensive
plans to expend the funds for the individual programs and initiatives.
- Conduct audits to determine the efficacy of the Department's
execution of ARRA initiatives, including evaluating procurement
processes and deployment of new equipment and assets.
- Determine if components have adequate processes and internal
controls over their programs.
- Conduct audits to evaluate the controls over data reliability for
information reported to Recovery.gov to ensure DHS is meeting
the transparency requirements of ARRA.
- Scheduling and/or conducting entrance conferences.
29