## Weekly Update
No. | Weekly Update Report Data (sheet 1 of 2) Version 1.1
| Agency Name: | Social Security Administration
| Week End Date: | 2009-04-03
| Submitter Name: | Mark Silvestri
| Submitter Contact Info: | 410-965-0017
| Program Source/ Treasury Account Symbol: Agency Code | Program Source/Treasury Account Symbol: Account Code | Program Source/Treasury Account Symbol; Sub-Account Code (OPTIONAL) | Program Description (Account Title) | Total Appropriation | Total Obligations | Total Disbursements
1 | 28 | 418 | 09/11 | Economic Recovery Payments (ERP)-Recovery Act | 13250000000 | 0 | 0
2 | 28 | 417 | 09/11 | Administrative Expenses - Recovery Act/ERP | 90000000 | 3598867 | 2977916
3 | 28 | 417 | X | Administrative Expenses - Recovery Act/NSC | 500000000 | 0 | 0
4 | 28 | 417 | 09/10 | Administrative Expenses - Recovery Act/Workloads | 500000000 | 0 | 0
5 | 28 | 403 | 09/12 | Office of Inspector General Recovery Act | 2000000 | 33550 | 21240
6 | 28 | 400 | 2009 | OIG Annual Appropriation | 98127000 | 13324 | 11836
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98

## Major Activities
Weekly Update Report Data (sheet 2 of 2)
No. | Short bulleted list of the major actions taken to date | Short bulleted list of the major planned actions
1 | General Recovery Act Implementation | General Recovery Act Implementation
2 | Received GSA approval of Really Simple Syndication (RSS) feed which is a family of web feed formats used to publish frequently updated works such as blog entries, news headlines, audio and video in a standardized format. | Continuing to work with OMB to interpret Recovery Act implementation guidance.
3 | Held a conference call with OMB on March 30th to review and discuss the draft Disability and Retirement Workload plan. | Working with OMB to provide specific guidance on recipient reporting and systems requirements.
4 |  | Setting up Atom 1.0 feed from the SSA.gov/recovery page.
5 |  | Planning to submit to OMB drafts of the Agency-wide Recovery Act Plan and three Program Plans by April 10th.
6
| One-Time Economic Recovery Payments (ERP) | One-Time Economic Recovery Payments (ERP)
7 | Refined validation schedule with the Treasury and Railroad Retirement Board. | Sending an advance informational mailer in late April to those who will receive the one-time ERP.
8 | Completed changes and validated Debt Management System for the OASDI ERP selection and payment process. | Preparing required systems lifecycle documents for software design and development.
9 | Completed validation of the ERP selection and notice file for SSI beneficiaries. | Developing a plan for reviewing production notices.
10 |  | Scheduling a call with VA, RRB, FMS and OMB to discuss ERP risk assessment and interagency coordination.
11 |  | Processing the ERP notices to selected SSI recipients and OASDI beneficiaries.
12 |  | Creating the mailing list for the ERP informational notice and delivering to contractor to print and mail.
13
| Replace the National Computer Center (NCC) | Replace the National Computer Center (NCC)
| Awarded the construction management contract on April 1, 2009. | Continuing meetings with GSA to define roles in the reporting process.
14 | Completed development of the site selection criteria by the GSA/SSA project team. | Working with GSA to establish general project timeline with key milestones and target dates.
15 |  | Preparing the program of requirements, a comprehensive project plan and assisting with site evaluation from a technical standpoint.
16
17 | Additional Disability and Retirement Workloads | Additional Disability and Retirement Workloads
| Continued to make hiring selections for Operations and Disability Determination Services. | Continuing to work with States for hiring exemptions on State Disability Determination Services hires.
18 | Held a conference call with OMB on March 30th and received feedback on the draft disability and retirement workload plan. | Working with CIO and Systems to finalize plans for IT spending.
| Office of the Inspector General | Office of the Inspector General
| Issued start notices for reviews of SSA's plans and actions to hire staff in various components using Recovery Act funds. | We will review and comment on SSA's Agency-wide and program specific plans within the next couple of weeks.
We will issue a start notice shortly for a review of SSA's plans and actions to conduct health information technology research and activities to facilitate the adoption of electronic medical records in disability claims. SSA's research and activities will be at least partially funded using Recovery Act funds.
19
20
21
22
23
24
25
26
27
28
29