## Weekly Update
No. | Weekly Update Report Data (sheet 1 of 2) Version 1.0
| Agency Name: | US Small Business Administration
| Week Start Date: | 2009-02-23
| Submitter Name: | Darryl Hairston
| Submitter Contact Info: | 202-205-1942
| Program Source/ Treasury Account Symbol: Agency Code | Program Source/Treasury Account Symbol: Account Code | Program Source/Treasury Account Symbol; Sub-Account Code (OPTIONAL) | Total Appropriation | Total Obligations | Total Disbursements
1 | 73 | 101 |  | 69000000 | 0 | 0
2 | 73 | 201 |  | 10000000 | 0 | 0
3 | 73 | 4268 |  | 15000000 | 0 | 0
4 | 73 | 1156 |  | 636000000 | 0 | 0
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98

## Major Activities
Weekly Update Report Data (sheet 2 of 2)
No. | Short bulleted list of the major actions taken to date | Short bulleted list of the major planned actions
1 | Established Recovery Act oversight/steering committee | Develop consolidated list of key decisions to be made
2 | Formed project teams and assigned team leaders for programs | Determine scope of IT Infrastructure & System Reqrmts
3 | Developed framework to manage each project | Test system changes to accommodate Recovery Act prgms
4 | Created dedicated SharePoint site for document control | Develop programmatic spending plan
5 | Established unique Treasury Appropriation Fund Symbols | Draft risk management plan
6 | Created dedicated page on www.sba.gov for Rec. Act efforts | Host GAO entrance conference
7 | Issued one press release about SBA's Recovery Act programs | Draft communications plan for Recovery Act programs
8 | Distributed talking points to field offices & partners for Prgms | Issue notices regarding prgm changes in response to Act
9 | Distributed sample remarks about Recovery Act prgms to field | Issue press releases about SBA program changes
10 | SBA field offices created community action plans for Rec. Act | Finalize video for SBA employess about Recovery Act
11 | Trained SBA's Answer Desk staff on SBA's Recovery Act prgms | Draft fact sheets on SBA's Recovery Act programs
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29